Georgian Patriarchate and UNICEF Joint Action Plan 2017

| Activities | Timeframe | Comments |
| --- | --- | --- |
| Setting up a coordinating body |  |  |
| Creation of a working group to oversee the elaboration of joint activities and their implementation | January 2017 | Following the signing of the MoU, UNICEF will develop the terms of reference of this working group and share them with GOG for comments UNICEF believes that this working group should meet regularly in order to monitor and evaluate the implementation of the joint work-plan |
| Awareness raising |  |  |
| Elaboration of joint messages for awareness raising matters and of dissemination strategies | February – March 2017 | As agreed during in 2016, these messages will focus on the following issues: violence against children, rights of children living with disabilities, maternal and child health |
| Organisation of round-tables at eparchy level to present, discuss and possibly refine messages and dissemination strategies | March – April 2017 | The number of and the location of these round-tables will be decided based on the GOG recommendations |
| Conduct awareness raising activities | April – December 2017 |  |
| Advocacy |  |  |
| Elaboration of a joint advocacy strategy and plans notably as regards to the strengthening of the child protection system in Georgia | February – March 2017 | The advocacy will aim at improving the accessibility and the quality of existing social services and at reinforcing the social work framework |
| Implementation of the joint advocacy strategy | April – December 2017 |  |
| Technical support |  |  |
| Elaboration of a “technical support” plan from UNICEF to the GOG as regards to existing family support services | February – March 2017 | UNICEF foresees this technical support particularly as regards to existing services for children with disabilities such as day care centres |
| Implementation of the “technical support plan” | April – December 2017 |  |