Neolab: visit date July 7, 2015  9-10 am

Visited by: Kiren Mitruka, MD     CDC, Atlanta

General comments

- Overall going well, including data entry into STOP-C.

- No delays in STOP-C data entry because it is being done by specific staff (not physicians).

- No lines or delays because all care, including testing done by appointment

Progress/status since initial capacity assessment:

- Moving to larger facility in September

- Still no fibroscan- referring patients out

- Patient booklet developed for record keeping of care (initially only for PWID- but will be implemented in all patients)

- Infection control training: all clinicians get it abroad- there is no national level certification

- Safe injection practice: contract with waste disposal company

- Harm reduction program: referred

- Added 1 more part time ID physicians: now 4 ID and 2 internal medicine

- At present – reached full patient capacity

| Challenges | Ways to correct |
| --- | --- |
| No standard recommendations for IFN-based versus sparing regimen | Clarify in indications in the treatment guidelines |
| State program for HIV testing only available at one center, so patients at other centers not getting testing | Expand state program to other providers |

What is going well:

- Have own database for M& E—earliest cohort – 8 weeks of treatment have RVR (low RNA) showing good adherence and effective treatment