Minutes of Discussion for the Consultative Committee Meeting

Japanese Grant Aid for the Economic and Social Development Programme

to the Government of Georgia FY2020

The Government of Japan has extended Grant Aid for the Economic and Social Development Programme to the Government of Georgia in accordance with the Exchange of Notes and the Agreed Minutes on Procedural Details signed on 22 July 2020.

This will be signed after the committee meeting

The Consultative Committee Meeting is held online between the signatories, the Government of Japan and the Government of Georgia, attended by Crown Agents Japan Limited (CA) in their capacity as advisor to the committee. The Consultative Committee hereby confirm that the attachments hereto (** pages) are a true and accurate record of the agreed actions and related issues necessary for the opportune implementation of the programme and in witness thereof they attach there signatures hereto.

These Consultative Committee Meeting Minutes shall be held in confidence and any changes or modification to them will be carried out in writing and shall require the agreement of all the signatories.

**** 2020

| (name) (title) (office) The Government of Georgia |  | (name) (title) (office) The Government of Georgia |
| --- | --- | --- |
| (name) (title) Embassy of Japan in Georgia |  | Ritsuko Yonemichi Senior Director SCS Division, Operations Department Crown Agents Japan Limited |

Attachment

1. Programme outline

Grant Value : JPY300,000,000

Exchange of Notes (E/N) : 22 July 2020

Banking Arrangement: 24 August 2020

Agent Agreement (AA) :10 September 2020

2. Grant Allocation

| End-User | Amount |
| --- | --- |
| Goods and Services | JPY 282,000,000 |
| Agent Fee (1-5 items 6%)* | JPY 18,000,000 |
| Total | JPY 300,000,000 |

*Crown Agents Fee; as per Appendix B of the Agent Agreement.

3. Consignee and End-user:

The Consignee is be Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs.

The End-user is Ministry of LELP Emergency Situations Coordination and Urgent Assistance Center who will be responsible for the operation and maintenance of the equipment procured.

4. Items requested

Item list received by the Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs is as follows:

| Item | Quantity | Referential model | Referential unit price (JPY) | Referential Exteded price (JPY) |
| --- | --- | --- | --- | --- |
| Defibrillator | 110 | TEC-5621 | 2,300,000 | 253,000,000 |
| Electrocardiograph | 155 | FX-8400 | 520,000 | 80,600,000 |
| Freight, insurance, other service cost and supplier’s margin |  |  |  | 40,032,000 |
|  |  |  |  | 373,632,000 |

Total value based on the referential price exceeds the budget and quantities may need to be adjusted before bidding process.

5. Eligibility of the participants in the Quotation Process

Contracts for purchase of products and/or services shall be placed with Japanese firms and the currency of Contract shall be Japanese Yen. The criteria of the participation are as follows:

(1) Japanese nationals

・ Bidders shall be Japanese nationals (Japanese physical persons or juridical persons controlled by Japanese physical persons).

・ Bidders shall be Japanese companies incorporated and registered under Japan Law with their headquarters in Japan.

・ The majority of bidders’ capital with voting rights shall be owned by Japanese nationals and majority of board members are Japanese physical persons.

・ Bidders shall not fall under any of the items of Article 26, paragraph 1 of the Foreign Exchange and Foreign Trade Act (Gaikokukawase-oyobi-Gaikokuboeki-Ho, Law No.228 of 1949, Japan).

(2) Bidders must have over 5 years of business experiences and more than 5 track records of delivering medical equipment on an ODA or commercial basis.

(3) Bidders’ current account balance shall not be deficit for 3 consecutive years and bidders shall not be insolvent.

(4) Bidders shall not be under the measures of the Government of Japan and the Japan International Cooperation Agency.

3. Procurement process

- Request for Quotation (RFQ)

- The General Procurement Notice (GPN) was posted in the Japan Times and on CA website where Japanese firms will register to participate in the RFQ.

- CA shall issue Request for Quotation (RFQ) only to the registered Japanese firms.

- The eligible source country shall be not limited as per the E/N. However, in order to shorten the quotation process, reference models shall be mentioned in the RFQ. In order to ensure the quality of the Goods, other criteria such as approval under Pharmaceutical and Medical Device Act of Japan.

- Evaluation

-	CA will evaluate offers technically and financially to establish the most advantageous offer. The Delivery period and completion period for services shall have the first priority in the evaluation. However, the offered price and budget are also considered.

- Approval of Certificate of Eligible Procurement (CEP) and Proforma Invoice (PI) and Contract Award

-  CA will send a document called Certificate of Eligible Procurement (CEP) and Proforma Invoice (PI) to the Recipient Government to explain the evaluation result and to recommend the winning firm.

-  Recipient Government needs to sign the PI which is the authorisation document, and enables CA to award a contract to the winning firm. After the receipt of the signed PI, CA will award a contract to the winning firm.

- The Recipient Government is expected to sign PI within 3 working days after the receipt of PI from CA.

- Ordering

-	Once the Contract is placed, the End-User will receive a copy of the Contract for their records.

-	Estimated Time of Arrival (ETA) will be provided to the End-User once shipping details become clear.

-	Shipping documents will be sent directly to the Consignee and the End-User by the Contractor.

- Responsibility of the Recipient Government

- Import Duty and Customs Duties Exemption: Pursuant to the E/N and Agreed Minutes on Procedural Details (A/M) the Recipient Government/End-User will be responsible for arranging tax exemption. Any demurrage caused by the delay of the Recipient Government/End-User’s responsibility such as tax exemption shall be covered by the Recipient Government.

- Preparation of the sites: It is the Recipient Government's responsibility to complete site preparation before the arrival of the Goods. As per the E/N, it is the responsibility of the Recipient Government to ensure that the procured items be maintained and used properly and effectively.

- Medical devices registration – Crown Agents kindly request Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs to advise the requirement of medical devices registration of the procured items in your country and to facilitate the registration procedures, if necessary.

- Delivery and Associated Services

- The delivery term will be Incoterms CIP named-destination (End-User’s premise) additionally including off-loading and customs clearance. The Contractor shall be responsible for arrangement and cost for transportation until final delivery point, off-loading, insurance, pre-shipment inspection, customs clearance.

- However, the risk and title of the goods is to pass to the Consignee at the point the goods were loaded onto the first principal means of transport. Shipping docuements such as Bill of Lading (B/L), Air Waybill (AWB) or Combined Transport Bill of Lading would consign the Goods to the Consignee and ownership would be theirs.

- Associated services such as assembly, installation, commissioning, and maintenance and/or operational training requested by the End-User, as included in the Contract shall be provided by the local agent of the Contractor.

- Delivery sits: Training Center of the LELP Emergency Situations Coordination and Urgent Assistance Center. Address: D. Agmashenebeli Alley, 12 Km.

- Keeping the Recipient Government/End-User updated

Throughout the procurement work, CA will keep the Recipient Government/End-User updated on the progress and submit reports regularly.

- Hand-over ceremony (To be discussed between two governments)

A hand-over ceremony may be arranged by the Recipient Government/End-User and the Embassy of Japan.

- Final report

Crown Agents will submit to the two Governments a Final Report including all RFQs, contracts and record of payments of the grant funds.

5. Expected procurement schedule As attached