Scope of Work

Advisor of the Minister - DRG Working Group member should:

- Participate in  elaboration of transition strategic plan

- Develop cost weights and base rate estimation methodology

- Analyze the vertical programs in the light of DRG implementation

- Conduct simulations for alternative DRG cost weights and base rate  scenarios

- Calculate the cost weights, base rate and DRG tariffs

- Participation in development of DRG implementation communication plan

მინისტრის მრჩეველი - ვალდებულია:

- მონაწილეობა მიიღოს გარდამავალი სტრატეგიული გეგმის შემუშავებაში;

- შეიმუშავოს ხარჯების შეწონვის კოეფიციენტები და საბაზისო შეფასების მეთოდოლოგია

- გააკეთოს ვერტიკალური პროგრამების  ანალიზი, DRG-ის განხორციელების თვალსაზრისით/გათვალისწინებით

- მოახდინოს  სიმულაცია DRG- ის ხარჯების შეწონვისა  და საბაზისო კოეფიციენტების ალტერნატიული სცენარების სიმულაცია

- გამოითვალოს ხარჯების შეწონვა, საბაზისო განაკვეთი და DRG ტარიფები

- მონაწილეობა მიიღოს DRG- ის განხორციელების საკომუნიკაციო გეგმის შემუშავებაში

Worker of health policy division - DRG Working Group member should:

- Participate in DRG license acceptance process (grouper, software)

- Participate in  elaboration of transition strategic plan

- Coordinate elaboration of DRG working group members job descriptions

- Analyze the legal framework to identify needed changes in legislation to implement the DRG system

- Prepare the legal documents needed for implementing the DRG system

- Participate in development cost weights and base rate estimation methodology

- Participate in Analyze the vertical programs in the light of DRG implementation

- Participate in simulations for alternative DRG cost weights and base rate  scenarios

- Participate in Calculation the cost weights, base rate and DRG tariffs

- Coordinate of  the DRG reimbursement policy  development

- Participate in simulations for DRG reimbursement policy scenarios

- Participate in Grouping the data, analyze and provide feedback about grouping results to providers

- Participate in development of performance indicators and principles for regular monitoring of providers and reporting by using DRGs

- Participation in development of DRG implementation communication plan

Worker of SSA UHC department - DRG Working Group member should:

- Participate in  elaboration of transition strategic plan

- Participate in IT system analyses and adaptation process

- Participate in revision and update ICD-10 and NCSP

- Participate in revision and improvement the coding guidelines for ICD-10 and NCSP

- Participate in development the external clinical coding audits

- Participate in revision and improvement the SSA claims management process

- Participate in development cost weights and base rate estimation methodology

- Participate in Analyze the vertical programs in the light of DRG implementation

- Participate in simulations for alternative DRG cost weights and base rate  scenarios

- Participate in Calculation the cost weights, base rate and DRG tariffs

- Participate of  the DRG reimbursement policy  development

- Participate in simulations for DRG reimbursement policy scenarios

- Coordinate in grouping the data, analyze and provide feedback about grouping results to providers

- Participate in development of performance indicators and principles for regular monitoring of providers and reporting by using DRGs

- Coordinate capacity building work for all stakeholders

- Participation in development of DRG implementation communication plan

Worker of SSA IT department - DRG Working Group member should:

- Participate in  elaboration of transition strategic plan

- Analyze  (pros and cons of alternative business processes) adaptation of the DRG grouper to the SSA’s IT system

- Adapt the SSA IT system to accommodate the grouper software

- Participate in revision and improvement the SSA claims management process

- Participate in simulations for alternative DRG cost weights and base rate  scenarios

- Participate in Calculation the cost weights, base rate and DRG tariffs

- Participate in simulations for DRG reimbursement policy scenarios

- Participate in Grouping the data, analyze and provide feedback about grouping results to providers

- Participate in capacity building works for all stakeholders

Worker of NCDC&PH - DRG Working Group member should:

- Participate in  elaboration of transition strategic plan

- Participate in revision and update ICD-10 and NCSP

- Participate in revision and improvement the coding guidelines for ICD-10 and NCSP

- Participate in development the external clinical coding audits

- Participate in capacity building works for all stakeholders

- Expected Outputs

- DRG License has been accepted

- DRG implementation and transition strategy has developed

- IT systems is prepared for DRG implementation

- ICD and NSCP are updated, coding guidance is improved and the external clinical coding audits has developed

- Regulation needed for implementation of DRG system is developed

- DRG tariff setting methodology has developed

- Reimbursement policy has developed

- Monitoring and reporting system has developed

- Capacity building for all Stakeholders has finalized

- DRG implementation communication plan is developed

- Timeframe

- 2018-2019

- Qualifications/Expertise:

The DRG group member(s) needs to have the following experience:

- Experience in clinical field

- Experience in Health Program development

- Experience in health finance field

- Experience in health legislation field

- Experience in IT technologies

- Reporting arrangements

The DRG group member(s) will work under the coordination of the Deputy Minister of Labor, Health and Social Affairs