National Environment and Health Action Plan NEHAP-2)

and 2017-2021  National Strategy

- Content

Table of Contents

Abbreviations

Introduction

1Current situation

1.1  Legislative Framework Anaysis

1.2. Major Challenges and Problems

2.	Strategy Goal, Objectives, Vision and Basic Principles

3.	Strategic Tasks and Interventions

3.1.       Strategic Objective№1:

3.2.	Strategic Objective №2

3.3.	Strategic Objective №3:

3.4.	Strategic Objective №4:

3.5.	Strategic Objective№5.

3.6.	Strategic Objective №6:

3.7.	Strategic Objective №7:

4.	Stragegy Implementation Timeframe and Responsible Institutions

5.	Potential Risks Occuring In the Course of or Resultin From Strategy Implementation Process

6.	Strategy Monitoring and Evaluation Mechanisms

7.	National Environment and Health Action Plan Funding

Annex 1. Performance Indicators for the National Action Plan of the Environmental Health, 2017-2021

Annex 2. Strategy Implementation Action Plan 2017-2021

Abbreviations

Figures and Tables

Abbreviations

| UNECE | United Nations Economic Commission for Europe |
| --- | --- |
| EU | European Union |
| WHO | World Health Organization |
| UNICEF | United Nations Children’s Fund |
| NCDC | National Center for Disease Control & Public Health |
| JMP | Joint Monitoring Programme |
| DALY | Disability-Adjusted Life Year |
| WHO ECEH Bonn office | World Health Organization European Center for Environment and Health in Bonn, Germany |
| TAIEX | Technical Assistance and Information Exchange instrument of the European Commission |
| Twinning | European Union instrument for institutional cooperation between Public Administrations of EU Member States and of beneficiary or partner countries |
| MoLHSA | Ministry of Labour Health and Social Affairs of Georgia |
| GNERC | Georgian National Energy and Water Supply Regulatory Commission |
| MoENR | Ministry of Environment and Natural Resources of Georgia |
| MoESD | Ministry of Economy and Sustainable Development of Georgia |
| MoA | Ministry of Agriculture of Georgia |
| MoRDI | Ministry of Regional Development and Infrastructure of Georgia |
| MoES | Ministry of Education and Science of Georgia |
| MoF | Ministry of Finances of Georgia |
| MoSYA | Ministry of Sport and Youth Affairs of Georgia |
| TM | Tbilisi Municipality |
| MoIA | Ministry of Internal Affairs of Georgia |
| MoFA | Ministry of Foreign Affairs of Georgia |
| MoD | Ministry of Defense of Georgia |
| MTO | Mid term objective |
| RIDP’s | ### Refugees and internally displaced persons |
| CLRTAP | Convention on Long-Range Transboundary Air Pollution |
| CBRNEP | National Strategy for Chemical, Biological, Radiological and Nuclear Threat Reduction |
| FCTC | Framework Convention on Tobacco Control |
| UNFCCC | United Nations Framework Convention on Climate Change |
| SAICM | Strategic Approach to International Chemicals Management |
| UBA | German Federal Environment Agency |
| UK | United Kingdom |
| UNSCEAR | United Nations Scientific Committee on the Effects of Atomic Radiation |

- introduction

In the era of modern civilization, environment is one of the  most important factors directly affecting public health, increasing burden of disease and causing latent harm to body, still remaining  the global-scale topical problem in the 21st century agenda. Policy documents and guidelines adopted by WHO articulate modern approaches and principles designed to establish safe environment. In addition, primary responsibility has been placed on environmental and health care sectors for elaboration and implementation of health and environmental policy and its management mechanisms that provide for ecologically sustainable development as well as effective monitoring and prevention of adverse health impacts of environmental factors.

Georgia assumed a commitment at the second European Conference on Environment and Health held under the auspices of WHO Regional Office for Europe, and in 2001 elaborated the National Environmental Hygiene Action Plan of Georgia - Environment and Health, approved by Ordinance # 326 of the President of Georgia of 24 March 2003.

Since 2003, fundamental changes and reforms have been carried out in the country; the realities with regard to institutional structure of executive branch and civil society development have changed. In view of large-scale fight against corruption, the old system of control and surveillance was denied.

In 2005-2007, radical reform with full abolition of State Sanitary Surveillance System was implemented. In 2007, the Georgian “Sanitary Code” was declared invalid in pursuance of the Law of Georgia on Public Health. Surveillance, controlling and permissive powers within the competence of the Sanitary Surveillance Service were completely withdrawn without establishing alternative structures and therefore they were no longer reflected in the new legislation.

All the stakeholders (representatives of ministries, agencies, research institutions and non-governmental organizations, subject matter experts) took part in the activities of National Working Group (NWG), established to organize the process of National Environment and Health Action Plan (NEHAP 2) elaboration, supported by experts from WHO European Centre for Environment and Health (ECEH), located in Bonn.

Thus, this NEHAP-2 represents the outcome of cooperation between all stakeholders of environmental health interventions and WHO ECEH international experts.

This National Strategy Plan outlines the country’s current modalities of establishment and preservation of safe environment, defines priorities of the next phase (2017-2021), substantiates necessity of using domestic resources as well as emphasizes the need for quality control improvement and multidisciplinary approaches that will enable achievement of the United Nations Sustainable Development  Goal 3  "Ensure healthy lives and promote well-being for all at all ages."

The National Environmental and Health Action Plan is conceptually and strategically linked with "Health 2020" and the United Nations' 2030 Sustainable Development Goals. Additionally, the National Strategy pays due regard to WHO European Region recommendations designed to ensure safe environment, prevent environmental releated diseases and reduce impact of risk factors.

# overview of current situation

## legislative framework analysis

This National Strategy is based on Association Agreement between Georgia and the EU, which came into force on July 1, 2016, including a Deep and Comprehensive Free Trade Area Agreement (AA / DCFTA). AA / DCFTA significantly enhances political association and economic integration between Georgia and the EU, reflecting deep bilateral commitments based on common values ​​and interests of democracy, rule of law, human rights, fundamental freedoms, good governance, market economy and sustainable development. In addition, the Agreement obliges Georgia to harmonize legislation and implement reforms in the main areas of the Agenda such as safety policy, economic revival and growth, trade, transport and energy, public health, environmental protection and social development.

Full-scale analysis of country’s existing legislative framework and its subsequent improvement are important for implementation of National Environment and Health Action Plan (NEHAP-2).  NEHAP is based on the following laws:

- Constitution of Georgia;

- The Law of Georgia on Health Care;

- The Law of Georgia on Public Health;

- The Law of Georgia on the State Budget of 2016;

- The Law of Georgia on Environmental Protection;

- The Waste Management Code;

- The Law of Georgia on Water;

- The Law of Georgia on Air Protection;

- The Law of Georgia on Soil Protection;

- The Law of Georgia on Pesticides and Agrochemicals;

- The Law of Georgia on Licenses and Permits;

- The Catalog of pesticides permitted for use in Georgia;

- The Labor Code of Georgia;

- The Law of Georgia on Civil Security;

- Georgian legislation concerning hazardous chemical substances. Might be divided into two stages: before and after 2003;

- The Law of Georgia - Product Safety and Free Movement Code;

- PRTR- National Pollutant Release and Transfer Register;

- National Chemical, Biological, Radiological and Nuclear (CBRN) Threat Reduction Strategy;

- Sanitary-hygienic norms, technical regulations, various sectoral strategies as well as public health standards and recommendations developed to ensure safe environment.

Provisions of Constitution of Georgia, which envisage support of equal social and economic development (Article 26, paragraph 6), juvenile and youth physical education and engagement in sports (Article 34) as well as the right to live in safe environment and the right to ensure healthy environment (Article 37, Paragraphs 3, 4).

According to Constitution of Georgia (Article 37. paragraphs 3.4.5) "Everyone shell have the right to live in healthy environment, enjoy the natural and cultural surroundings. Everyone shall be obliged to care for natural and cultural environment. With the view of ensuring safe environment, in accordance with ecological and economic interests of society, with due regard to the interests of the current and future generations, the state shall guarantee the protection of environment and the rational use of nature. Everyone shall have the right to receive a complete, objective and timely information as to a state of environment."

The Law of Georgia on Health Care considers Public health care as system of state obligations aimed to protect, maintain and restore person's physical and mental health, prevent and control the diseases, study their prevalence, promote healthy lifestyle practices and safe environment (Article 3, paragraph u1).

The Law of Georgia on Public Health aims to promote public health and healthy lifestyle practices; ensure safe environment   promote reproductive health care and prevent the spread of noncommunicable diseases (NCDs) (Article 1). The law defines the rights and obligations of the population and legal entities in public health domain. According to the Law, the Ministry of Labor, Health and Social Affairs develops quality quality standards, public health guidelines and technical regulations designed to ensure safe environment.

The Law of Georgia on the State Budget of 2016 emphasizes that ongoing surveillance over health condition of population will be continued to ensure disease prevention and preparedness for public health threats.

The Law of Georgia on Environmental Protection is a basic law regulating legal relations between physical and legal persons as well as state institutions in the field of environmental protection and use of natural resources.

The Law of Georgia -Waste Management Code establishes legal framework for waste management sector and aims to protect environment and human health through prevention or reduction of waste generation and its adverse impacts, creation of efficient waste management mechanisms, mitigation of harm caused by resource consumption and more efficient use of resources.

The Law of Georgia on Licenses and Permits regulates the organized activity or action concerning indefinite circle of persons, characterized by increased danger for human life or health, covering especially important state or public interests or related to use of state resources. In addition, this Law regulates the area regulated by license and permit, defines list of the types of licenses and permits, stipulates the rules of issuance of license and permit, their amendment and cancellation.

The Law of Georgia on Water regulates all types of water protection from deterioration and pollution. Every resident of Georgia is obliged to ensure rational and sustainable use and conservation of water and prevent its pollution, littering and depletion.

The Law of Georgia on Air Protection regulates protection of    ambient   air    from   dangerous technogenic impacts in the territory of Georgia. The Law defines types of the harmful anthropogenic impacts on ambient air; pollution of ambient  air with harmful factors; limitations of concentrations of harmful substances in ambient  air; monitoring system for ambient air and etc.

The Law of Georgia on Soil Protection is intended for protection of soil from erosion processes, pollution and littering, secondary swamping and salting as well as prevention of  soil losses due to opencast mining of fossil minerals and building materials  and wrongful anthropogenic activities. On the basis of requirements of the Law, norms and standards of harmful substances’ permissible concentrations in the soil are approved for the purposes of ensuring human health and preservation of flora and fauna.

The Catalog of pesticides permitted for use in Georgia is maintained (in accordance with FAO "International Code of Conduct on the Distribution and Use of Pesticides" and EEC 91/114 Directive) by Pesticides and Agrochemicals Department of National Food Agency. The catalog is updated and refilled on a yearly basis. It is available on the following web portal:

http://nfa.gov.ge/?sec_id=130&lang_id=GEO The catalog contains data on 254 active ingredients and 682 formulations.

The Labor Code of Georgia establishes general principles, requirements and standards for safe and healthy working environment. The Code (Article 35. Right to a Safe and Healthy Working Environment) determines obligations of the employer:

- The employer is obliged to provide the employee with a working environment that is maximally safe for the life and health of the employee.

- Within a reasonable term, the employer is obliged to provide the employee with available full, objective, and clear information on all the factors that affect the employee’s life and health or the safety of the natural environment.

The Law of Georgia on Pesticides and Agrochemicals

Regulates the relations generated during governmental control of effective use and safe application of agricultural chemicals and biological agents as well as development, registration, manufacturing, labeling, packaging, marketing, storage, transportation, use, decontamination, disposal information exchange, advertising and export-import of pesticides and agrochemicals.

Georgian legislation concerning hazardous chemical substances. Might be divided into two stages: before and after 2003

Prior to 2003, Georgian legislation reflected the approaches and norm setting conditions remaining from the Soviet era, which were imperfect and did not pay due regard to results and conclusions of modern research. Since 2003, along with general liberalization of legislation, legislative norms have become liberal with respect to issues such as production, use and utilization of harmful chemical substances. The aforementioned circumstances negatively affected governmental approaches to the protection of human life, health and economic interests. However, in that period, an attempt (unfortunately, inefficient) was made to meet international requirements and obligations.

In Georgia, legislation on hazardous chemical substances the was liberalized in the simplest manner,  namely - through abolition of legislative acts. The following laws were abolished:

1. The Law on Licensing of Activities in the Field of Production of Agrochemicals, Trade with Agrochemicals, Laboratory Activities in the Field of Agro-chemistry and Soil Protection and Detecting the Quality of Agrochemicals and on Issuance of Import and Export Permits for Agrochemicals;

2. The Law of Georgia on Hazardous Chemicals.

In fact, these laws were not adequate to international requirements, but it was possible to improve them. At the same time, Georgia had become a party of a number of international conventions and treaties, assuming significant responsibilities, including those related with dangerous chemical substances.

Applicable National and International Normative Documents, Conventions on Chemical Substances Management as well as Obligations taken in pursuance of Vienna, Paris, Basel, Stockholm, Rotterdam, and Parma Declarations.

Law of Georgia on Civil Security regulates the field of "Rule of establishing and operating a uniform Emergency Situations Management System as well as the rights and duties of its subjects." Unified Response System is created: "The Unified System encompasses emergency management at political, operational and tactical levels".

The Law of Georgia - Product Safety and Free Movement Code aims to preserve human life, health, property and environment, as well as introduce risk-based analise    inspection system etc.

In order to fulfill the terms and conditions of Association Agreement, regulatory acts and policy documents for public health sector as well as relevant technical regulations and normative acts are being gradually developed.

Existing legislative framework does not ensure nether physical persons’ health or public health protection nor fulfillment of requirements of signed by Georgia international treaties and agreements related with ensuring safe environment.

1.2 Major challenges and problems

1.2.1 Global environmental burden of disease

Globally, scrutiny of ecological factors has revealed modern challenges: to which extent is it possible to prevent cases of death, diseases and disabilities through reduction of people's exposure to ecological risks. In 2016, WHO released the new assessment "Preventing disease through healthy environments. Global assessment of the burden of disease from environmental risks". Core message of new global assessment is that premature death and diseases can be prevented through ensuring healthy environment and reducing impacts of risk factors.

Interrelation between environmental conditions and diseases was analyzed on the basis of available data; according to expert conclusions, adverse impacts of ecological threats and risks on global health, include more than 100 types of diseases and damages. Analysis showed that 23% of global mortality (26% of child mortality up to 5 years) is caused by modified environmental factors. Stroke, ischemic disease, diarrhea and tumor are at the top of the disease list.

Along with development of countries, there is a significant shift in environmental risk factors and the share of NCDs, including malignant tumors, increases. It is noteworthy that developing countries have relatively heavier burden of disease of environment-related unintentional injuries  and road traffic injuries; The average amount of healthy years of life lost is 2 times higher than the same indicator of developed countries and significantly varies depending on their development level.

From 2002 to 2012, health impacts of environmental risk factors were slightly mitigated and the global mortality rate decreased from 13.3 to 12.6 millions per year. Similarly, global-scale total mortality rate decreased from 57.0 to 55.6 millions. In the same period, the mortality attributable to environmental factors also slightly decreased from 23.3% to 22.7%.

Diagram 1.

Trend of environment-related deaths the groups of diseases, 2002-2012

2002                              2012

Injuries

2002                              2012

Total

2002                              2012

Noncommunicable diseases

2002                              2012

Infectious, parasitic, neonatal and foodborne diseases

Globally, between 2002 and 2012, the major changes in environmental burden of disease were observed in the following categories, namely – mortality rate and burden of disease significantly decreased for contagious, neonatal and nutrition categories; mortality rate of NCDs increased, partly due to aging of population.

Diagram 2. Systemic analysis of correlation between environmental diseases proportions

Infectious, parasitic, neonatal and foodborne diseases

NCDs

Injuries

Observed in 2002 -2012 reduction of the burden of infectious, parasitic, newborns and food-born diseases and increase of NCD burden were related to awareness of association between exposure and diseases as well as acquisition of strong evidences. It should be noted that availability of safe water and sanitary conditions (in both relative and absolute terms) was improved (WHO & UNICEF, 2014), reducing risk of transmissible diseases. In the same time period, the number of people using clean fuel for preparing food slightly increased, and the number of people using solid fuels remained unchanged. In recent years, slight decrease of ambient air quality was observed in many low and middle income countries around the world (Who, 2014cc). Enhanced impacts of air pollution lead to augmentation of NCDs and respiratory infections for the children under 5 years.

1.2.2 Major environmental health challenges and problems of in Georgia

From 1921 to 1991, the environmental health system in Georgia was a part of unified Soviet system; planning, health care organization, control and almost all resources were allocated from the centralized.  Sanitary and epidemiological (oversight and performing functions) service, responsible for ensuring sanitary and epidemiological welfare, was a separately operating entity. Since the country gained state independence, necessity of fundamental reorganization as well as establishing and formation of  the principally new model became evident over time.

Accordingly, the Georgian Sanitary Code was declared invalid in pursuance of the Law of Georgia on Public Health in 2007. After abolition of State Sanitary Surveillance Inspection in 2005-2007, until 2012 environmental and health issues were directed towards the Noncommunicable Diseases Department of the National Center and in 2013 the Environmental Health Division was established.

Currently, assessment of environmental risk factors’ impact on human health does not take place due to lack of inadequate laboratory capabilities, methodologies as well as human and financial resources. Nowadays, provision of safe environment is a problem of immense complexity.

No  surveillance, control, monitoring and analysis of environmental diseases in line with internationally recognized indicators, delivery of information to common information system, as well as assessment and monitoring of environmental quality norms for public buildings and living environment is performed in the country.

In Georgia,  overview and assessment of environmental health situation was  performed in 2011

In 2011, with financial support of the EU Delegation to Georgia, within the framework of activities carried out by the Georgian National Projects Implementation Center, in cooperation with the LEPL  L. Sakvarelidze National Center for Disease Control and Public Health, the NGO - Center for Strategic Research and Development of Georgia conducted Environmental Health Situation Analysis - the first or initial stage of National Environmental Health Action Plan (NEHAP) elaboration.

The following steps were taken to assess the environmental burden of disease:

1. Review and analysis of reference literature was performed;

2. The list was compiled for the diseases / disease groups,  burden of disease of which is partially or completely determined by harmful exposure to environmental factors;

3. On the basis of  reference literature review performed by experts, as well as expert evaluation, the attributable fraction of environmental burden of disease was defined with 95% confidence interval through correlation of experts’ and WHO data with average indicator of environmental burden of disease for the diseases / disease groups, such as  disability-adjusted life years (DALYs) and mortality ratio;

4. An overview of environmental health indicators was carried out and samples of passports of indicators were formed.

In Georgia, situation with environmental burden of disease  is unsatisfactory; It is estimated that 17% of total burden of disease in the country is caused by adverse environmental impacts.

According to WHO Registry for 2004 -  "Country profiles of Environmental Burden of Disease", high burden of cardiovascular, lung cancer and other localization cancer, asthma and chronic obstructive pulmonary disease is observed in Georgia.

Table 1. Share of adverse environmental impacts in the burden of disease by some groups diseases (DALYs/ 1000 capita, per year, all ages), Georgia 2004)

| Diseases | Georgia | Worldwide range |
| --- | --- | --- |
| Respiratory infections | 1.9 | 0.1-71 |
| Cardiovascular diseases | 7.9 | 1.4-14 |
| Lung obstructive diseases | 0.5 | 0.0-4.5 |
| Asthma | 0.6 | 0.3-2.8 |
| Lung cancer | 0.9 | 0.0-2.6 |
| Other malignant tumors | 1.5 | 0.0-4.1 |
| Neuro-psychological disorders | 2.3 | 1.4- 3.0 |
| Musculoskeletal diseases | 1.3 | 0.5-1.5 |
| Road traffic injuries | 0.7 | 0.3-15 |
| Other unintentional injuries | 1.4 | 0.0-7.5 |

This data significantly exceeds the indicators of any disease for developed countries. It is noteworthy that it is approximate, since validation of cause-and-effect relationship is quite difficult for many diseases. Moreover, it should be taken into account that for a number of reasons, no ecological epidemiologic research, designed to obtain relevant evidences and determine dynamics of environmental diseases, has been conducted in Georgia over recent years.  Evaluation was performed based on routine statistics of epidemiological surveillance.

In 2016, spread tendencies of the most prevalent NCDs - cancer, cardiovascular diseases, chronic respiratory diseases, diabetes and traumatism was analyzed. The analysis was based on medical statistical data for 2015.

### Cardiovascular diseases are the main cause of death in the world. Cardiovascular morbidity and mortality still remain the problems to be tackled  for Georgia. Prevalence and incidence of circulatory system diseases are characterized by tendency of growth in the country.

Distribution   of  circulatory system diseases, Georgia, 2003-2015

Prevalence

Incidence

The country’s hypertension distribution characteristics are especially high, indicating its priority importance.

According to the International Agency for Research on Cancer, globally 14.1 million new cases of cancer are diagnosed each year, 8 million out of which are registered in developing countries. The number of deaths caused by oncologic diseases reaches annual number of 8.2 million (approximately 22,000 deaths per day).

Since 2015, Georgia has established a population-based Cancer Registry; the data gathered within its scope significantly changed previous picture of cancer. 9598  new cancer cases were reported in 2015, almost doubling the cases registered in previous years.

New cases of all types cancer, Georgia, 2006-2015

Cancers of five locations are the most common among women: breast, thyroid gland, colorectal, cervical and uterine corpus cancer. Cancers of five locations are the most common among men: tracheal / bronchial / lung, prostatic, urinary bladder, colorectal and laryngeal cancer.

Incidence rates of cancers of all locations per 100,000 men is 240, and 100,000 women is  275.

Distribution of all location new cancer cases is as follows: First stage: 20%; Second stage: 20%; Third stage: 23%; Fourth stage: 28%; and unknown: 9%.

age-standardized incidence                                                    age-standardized mortality

Georgia,                           Registry, 2015

Latvia                litva               Belarus              Russia           Azerbaijan         Armenia          Georgia

Chronic respiratory diseases are among the major challenges to global public health, causing one sixth of death cases. Similar to many countries around the world, the incidence of respiratory diseases in Georgia is characterized by the tendency of growth, primarily related to ambient air pollution and tobacco use trends.

Disease incidence rate   of respiratory system in general populations and children, 2000 - 2015

Incidence in children

Incidence

On the background of the respiratory system diseases, the incidence of bronchial asthma and status asthmaticus increases; the major part of the structure of chronic obstructive pulmonary disease accounted for chronic and unspecified bronchitis.

Prevalence rate per 100,000 capita was 565.7, incidence rate equaled 245.9. In 2015, chronic obstructive pulmonary diseases accounted for 70.1% of chronic lower respiratory tract diseases group.

Traumatism is an important, growing problem for  public health sector. According to WHO data, different types of injuries and violence result in 14,000 deaths per day and   more than 5 million deaths per year, which accounts for 9% of global burden of mortality and is 1.7 times more than total lethality caused by HIV, tuberculosis and Malaria. Trauma is the leading cause of death in 5-29 age category.

In Georgia, body injury is the fourth cause of death. Road traffic trauma is among the leading constituent parts of general injury structure. The high rate of deaths and injuries resulting from road accidents poses a serious problem to Georgia. As a result of road traffic accidents, hundreds of people die each year and thousands of people suffer from injuries of various severity. The road traffic accidents mortality rate in Georgia has increased by 41.2% in 2015.

Dynamics of road traffic accidents, injuries and mortality Georgia, 2008-201517

Despite multiple steps taken in this direction, a number of legislative amendments implemented and regulations changed, WHO data suggests that Georgia is among the top 12 countries in terms of road traffic accident morbidity. However, it should be noted that considering the data of 2009, this indicator has slightly improved - Georgia shifted from 9th to 12th place).

2. Strategy goal, tasks, vision and basic principles,

Vision

Reduce and prevent the burden of Environmentally-Related Diseases reduction of people's exposure to ecological risks

Goal

Provide for improvements through coordinated actions and ecologically sustainable development to attain Sustainable Development  Goals concerning  environmental quality and healthy lives.

Objective

Effective use of financial resources through strengthening coordination and cooperation between different sectors to ensure sustainable development and human health improvement.

Basic Principles and Approaches

1. Cover all the stages of life cycle.

2. Human rights protection.

3. Equality and justice.

4. Pursue integrated policies to co-ordinate goals and activities between environmental and health sectors

- Gradually develop of integrated information system for health and environmental sectors, designed to assess health impacts of environmental risk factors and pollution. Elaborate environmental health indicators and comprehensive assessment of environmental quality.

Develop a Joint Methodology and Analysis System to assess health impacts of environment. Public health services determine relevant measures and develop joint programs to minimize environmental risk factors.

5. Ensure sustainable development - a form of economic growth ensuring short-term, medium-term and, most importantly, long-term public welfare; according to it, current needs are to be met without endangering the future generations, with due consideration of public health and environmental issues.

6. Solidarity – creation of equal conditions, especially - when developing special measures for vulnerable and disadvantaged groups.

7. Subsidiarity - principle implies deconcentration and decentralization of powers as well as exercise of power at the lower level of governance, which is closer to people and quite familiar with local needs.

8. Participation principle - implies publicity of planning, decision making, implementation and monitoring process as well as involvement of citizens, stakeholders, organizations and various social groups in this process.

9. National action, International Cooperation

10. Multi-sectoral approach.

# 3.  Strategic objectives and Interventions

- Ensure public health through improvement of access to safe and sustainable water supply and sanitation. Ensure access of each child to safe water supply and sanitation by2021.

- Improved children accessibility to healthy and safe environments and settings of daily life, promoting their increased physical activity by 2021

- The impact of ambient and indoor air pollution on human health assessed and implemented measures to reduce the harmful effects

- Prevention of morbidity caused by exposure to chemical substances.

- Integration of health issues in climate change adaptation and mitigation policies.

- Improving Governance of existing "Environment and Health “System in Georgia.

- Reduced risks from physical agents of the environment by 2021.

Strategic  Objective 1.  Ensure public health through improvement of access to safe and sustainable water supply and sanitation. Ensure access of each child to safe water supply and sanitation by2021.

Rationale

Development of modern society largely depends on the quantity and quality of water resources. Water helps people to improve their health and well-being, and universal access to safe drinking water is one of the basic human rights.

It is unacceptable that millions of people in the WHO European Region still have no access to safe drinking water, sanitation and hygiene conditions. In particular, out of 912 million people living in the WHO Europe Region, more than 62 million people had  no access to adequate sanitation conditions and 14 million did not use quality drinking water sources by 2015. Despite the fact that access has increased over the last decades, there have been significant differences between villages and cities, especially in the Caucasus and Central Asia, where less than 40% of the rural population is provided with water through central water supply systems. Universal and equal access to safe water, sanitation and hygiene conditions remains the main priority.

Environmental and health problems caused by pollution of water and soil with pharmaceutical waste are increasingly important. Antimicrobial waste can contribute to the development of antimicrobial resistance (AMR), which constitutes a significant public health problem.

The Protocol on Water and Health, adopted at the London Conference in 1999, remains the main instrument in the WHO European Region designed to contribute to Sustainable Development Goal 6  "Ensure availability and sustainable management of water and sanitation for all". It offers governments international platforms to promote and develop guidelines as well as plan for the ways of achieving Sustainable Development Goal 6.

The overall goal of the WHO for European Region is to provide universal, equal and sustainable access to safe drinking water, sanitation and hygienic conditions for all, via the following means:

A. Ensure quantity and quality of fresh water resources as well as sufficient amount of safe drinking water, especially in regions with water shortage, high level of its use and competition, caused and accelerated climate change.

B. Fulfilment of  Parma Commitments.  In particular, ensure public health through improving access to safe drinking water and sanitation.

In Parma Declaration, the Ministers of Environmental Protection and Health have expressed their wish to provide access to safe drinking water and adequate sanitary conditions for each child at home, in preschool institutions, schools, medical facilities and recreational water use areas as well as improve hygienic behaviors of children by 2020.

Achievements and challenges

Water quality and resources management is one of the most complex areas of the Association Agreement between Georgia and the EU, including Deep and Comprehensive Free Trade Area (AA / DCFTA), as it relates to many issues. Due to the large number of the water sector stakeholders, elaboration of some parts of the new legislation requires involvement of meny stakeholders. In particular, the requirements of the Drinking Water Directive (98/83 / EC) requirements are to be introduced. According to "Water Quality and Resource Management Road Map", 27 activities are identified, twelve out of which apply to elaboration of the new legislation, nine - to policy documents development and six - to research and planning. Despite the recent intense rehabilitation and construction of water supply and sanitation infrastructure and water quality improvement work. The issue of drinking water supply to the country's population as well as educational and boarding institution remains currently central as   most of the populated areas, water pipelines and distribution networks still require replacement, capital and / or current repairs etc., which is evidenced by the ongoing projects in this field. The situation is also aggravated by irrational expenditure of drinking water and quite common practices of its inappropriate use.

WHO / UNICEF Joint Monitoring Programme (JMP) for Water Supply and Sanitation provides information on progress in achieving the Millennium Development Goal (MDG) relating to water supply and sanitation and provides support for  country-level improvement of monitoring process as well as effective management and planning.

Table 1: Progress in access to drinking water and sanitation (JMP,WHO and UNICEF 2015)

ა) Use of drinking water sources   (percentage of population)

*  According to the JMP (WHO and UNICEF, 2015), “improved” drinking-water sources are defined as those that, by the nature of their construction, are protected from outside contamination, particularly faecal matter, and include the following supply technologies: household connection, public standpipe, borehole, protected dug well, protected spring, rainwater collection.

ბ) Used  Improved sanitary facilities (percentage of population)

* According to the JMP (WHO and UNICEF, 2012), “improved” sanitation facilities are defined as those that hygienically separate human excreta from human contact. The following technologies are included: flush toilet, piped sewer system, septic tank, flush/pour flush to pit latrine, ventilated improved pit latrine, pit latrine with slab and composting toilet.

Despite the fact that Georgia is the signatory to the first international agreement - Protocol on Water and Health,  the country has not yet ratified it.

The Law of Georgia on Public Health defines responsibilities related to water management in the country and is allocates them to various state agencies. The National Food Agency of the Ministry of Agriculture of Georgia has developed annual state control plans and state programs for monitoring laboratory research, in the framework of which state control and monitoring of drinking water quality and safety is exercised.

It should be noted that according to the data of LEPL National Food Agency, in 2014-2015 level of bacteriological contamination of potable water in the country remained unchanged and accounted for 23.0 %  and 19.1% of taken samples.

| Assessment of drinking water quality across the country | 2014 | 2015 |
| --- | --- | --- |
| The number of samples tested on E. coli | 842 | 701 |
| did not compliance to drinking water technical regulations by E. Coli | 194 | 134 |
| Noncompliance % | 23,0% | 19,1% |

The situation with supply of drinking water to rural population and local small-scale water supply systems is similar, as evidenced by the findings of “Situation assessment of small scale water supply systems in the Dusheti and Marneuli districts of Georgia” project supported by the WHO ECEH and UBA in 2011-2013. It has practically revealed the problems that impede improvement of existing systems and supply of improved quality of drinking water to the population. In addition, quite often these water pipes have no sanitary protection zones. No country-scale inventory and passportization of water supply systems (including small scale water supply) have been performed in recent years, non-existent sanitary protection zones (unsatisfactory sanitary and technical conditions of the abstraction facilities and distribution networks of the small-scale water supply systems).  In most small scale supplies, drinking-water is not disinfected (i.e. chlorinated), and in places where chlorination facilities are in place, the existing practices are inadequate. The issue of subordination and ownership of small-scale water supply systems is practically unregulated.

The NCDC has implemented and coordinated the process of the UN-Water Global Analysis and Assessment of Sanitation and Drinking-Water -GLAAS ( 2013/2014, 2016/2017) in Georgia . Situation with provision of public schools’ students with drinking water and proper sanitary conditions is also unsatisfactory, which is evidenced by the findings of research on drinking water supply and sanitary-hygienic conditions of the country’s 600 public schools, conducted by the National Agency for Educational and Scientific Infrastructure Development with financial and technical support of the United Nations Children's Fund (UNICEF) in 2013. It was found that situation in schools is currently inadequate in regard to all the main points of the International Standard of Drinking Water, Sanitation and Hygiene (WASH).

Due to above mentioned reasons, infectious diseases and outbreaks presumably  caused by water occurred in various populated areas of the country. Over the last five years, 14 outbreaks supposedly related to drinking water and encompassing 649 cases of disease, have been registered in the country.

According recent years’ statistics, the average rate  of annually registered cases of diseases which might possibly be transferred via drinking water, is still high. While 70% of registered diarrhea cases occur in children's age. The situation is unsatisfactory in the field of municipal wastewater treatment as well , since 75% of untreated and Insufficiently treated municipal wastewater is the main source of Surface water pollution in Georgia. Biological type treatment facilities are functioning only in 2 towns (Sachkhere and Batumi), whereas Tbilisi-Rustavi regional treatment facility provides only the initial mechanical treatment of wastewater. The owner of treatment facility (Georgian Water & Power) has an obligation to perform rehabilitation and modernization of treatment facilities until 2018.

Strategic interventions

#### Mid-term objective 1.1 National legislation and policy frameworks on protection of water resources, drinking-water supply and sanitation reviewed and updated by 2021.

#### Mid-term objective 1.2. Establishe effective surveillance systems for drinking  water quality and water-born diseases by 2018.

Mid-term objective 1.3 Ensure continuous supply of the population with drinking water meeting national and international requirements

Mid-term objective 1.4 Provision of population of the country with adequate sanitation by 2021

Mid-term objective 1.5 Improvement of drinking water, sanitation and hygiene (WASH) conditions in educational, health care and recreational facilities/sites and in RIDPs settlements.

Strategic Objective  2: Improved children accessibility to healthy and safe environments and settings of daily life, promoting their increased physical activity  by 2021

Rationale

In modern era, the environment is one of the most important factors directly affecting public health. Urbanization of cities, industrial capacity building, powerful network of public transport, introduction of new technologies, rapid pace of life and a other factors have a significant impact on the quality of environmental media (ambient air, water, soil, habitat) and public health, which gives generates a variety of complex anthropogenic problems.

The concept of "environment" primarily implies human habitat and includes physical, biological, social, cultural, and the other environmental factors, as well as related behaviors associated, affecting human health. 20-22% of the global world population morbidity and 23% of its mortality are caused by impacts of environmental factors.

Traumatism is a major problem for public health sector. Road traffic trauma is distinguished from other conditions of unintentional injuries category by increasing mortality rate, burden of which equals to the burden of disease for Malaria and tuberculosis. Nearly 3 400 people die every day on the roads of the world. Tens of millions of people get various types of body injuries, becoming disabled. The situation is particularly alarming in low and middle income countries – out of 1,3 million cases of annual traffic trauma, 80% occur in middle income countries. In the regional distribution of the WHO, rates of mortality due to road traffic accidents are  the highest for African region and the lowest - for European region. According to the WHO data, road traffic crashes are the leading cause of death among people aged between 15 and 29 years. Worldwide, only 28 countries have applicable legislation fully addressing five main risk factors (speed, driver under the influence of alcohol, safety belt, helmet and baby seat) which cause road traffic accidents.  Millennium Development Goals did not cover traffic safety. Hence, it was not a priority area for global regulations. Though, Sustainable Development Goals consider traffic safety as one of the most important issues. These Goals will become a basis for the International Development Agenda and supersede Millennium Development Goals.

Children, pedestrians, bicyclist and elderly people constitute the most vulnerable group of traffic users. High rate of deaths and injuries resulting from road accidents pose a serious problem to Georgia. Due to road traffic accidents, hundreds of people die and thousands of people suffer from injuries of various ceverity each year. Despite multiple steps taken in this direction, a number of legislative amendments implemented and regulations changed, according to WHO data, Georgia is among the top 10 high-risk countries in terms of road traffic accident morbidity.

Intervention "Active Movement to School" is designed to support school-aged children’s safe commuting to school by foot or bike. Such intervention requires provision of safe roads, sideways, "zebra crossings" and traffic lights in the vicinity of schools. Such interventions facilitate formation of sustainable infrastructure designed for promoting children's safe transportation and physical activity.

Facilitation of physical activity starting from school age upwards is important in terms of establishing a healthy lifestyle. Introduction of active lifestyle programs in schools is a key for children's ultimate involvement. The Health Care sector in conjunction with the Educational sector is ready to assume a leading role in cause of popularization of physical activity, although full involvement of population, including children, requires multidisciplinary efforts.

It should be noted that in Georgia many schools are located near the highways,  exposing students and school personnel to traffic emissions and impacts of constant noise and vibration. According to World Health Organization, a health promoting school "is one that constantly strengthens its capacity as a healthy setting for living, learning and working."

Achievements and challenges

(a) Currently, absence of reliable organizational structures and lack of qualified personnel are the key inhibiting factors for planning and implementation of measures designed to introduce improvements in the process of ensuring healthy and safe environment in Georgia. The ability to solve existing problems and reveal new ones is significantly reduced due to insufficient of ineffective cooperation between different sectors, which is often caused by the lack of its sustainable mechanisms (such as absence of relevant article in the budget), or informal nature of cooperation. Above circumstances complicate cooperation and mobilization of resources for achieving common goals as well as timely collection/analysis of reliable and systemic data on the environmental and health indicators; monitoring of trends and detection of potential risks, provision of information to the population and proper allocation of the resources for response activities.

(b) Due to topicality of the issue, the National Strategy for Prevention and Control of Trauma and Violence and 5-year Action Plan have been developed on the initiative of the National Center for Disease Control and Public Health.

(c) In addition, National Road Safety Strategy and Action Plan have been developed by the Multi-sectoral Working Group with involvment of foreign experts, approval and implementation of which will significantly improve the country’s road safety conditions.

(d) In Georgia, similar to other medium and low income countries, one third of the road accidents cause injuries to the pedestrians, among which the children constiture the most vulnerable group.

(e) Obesity and excess weight are among the undesirable effects of low physical activity. According to the 2009 nutritional survey of Georgia, prevalence of excess weight and obesity was 19.9% for children aged 0-5 and 42.1% for non-pregnant women aged 15-49.

(f) According to the 2010 Research of NCDs Risk Factors, for the population aged 18 and older total prevalence of excess weight and obesity was 56%, while the prevalence of obesity accounted for 25%.

(g) One of the Global Targets of the WHO Global Action Plan for the Prevention and Control of Noncommunicable Diseases 2013-2020 is to Halt the Rise in Diabetes and Obesity. Considering this Target, the National Strategy and Action Plan for Obesity Prevention and Control were elaborated in the NCDC.

Strategic interventions

MTO 2.1 Relevant legislation harmonized according to the Association Agreement by  2020.

MTO 2.2. Increased proportion of schools and kindergartens equipped with (or with access to) adequate facilities for safe physical activity of children by x%…in 2020 as compared to 2016).

MTO 2.3. In comparison to 2016, increase share of schools with adjacent territories safe for children’s movement by 2020;

Strategic Objective 3: The impact of ambient and indoor air pollution on human health assessed and implemented measures to reduce the harmful effects

Rationale

According to the World Health Organization, air pollution is one of the major environmental health risks. By experts’ judgment, it causes 8 million premature deaths worldwide every year. Permanent exposure to dust particles increase the risk of cardiovascular and respiratory diseases as well as lung cancer. Besides, low concentration of pollutants in the air also causes undesirable health effects. Significant mitigation of polluted air impacts can be achieved via reduction of concentration of widespread air pollutants through fuel burning. These measures will also contribute to reduction of greenhouse gases concentration and climate changes caused by global warming.

According to World Health Organization reports, in cities with high levels of air pollution, the general mortality rate exceeds by 15-20% the similar indicators of the ones with relatively clean air. Ambient air dust affects health than more than any other air pollutant. Sulfates, nitrates, ammonia, sodium chloride, carbon, mineral dust and water are the components of solid dust particles composed of complex mixture of organic and inorganic substances’ hard and liquid particles suspended in the air. According to modern approaches, differentiation of solid dust particles by fractions depending on their aerodynamic diameter  is applied for their  health impact assessment and norm setting. Specifically, out of PM10 (particles with aerodynamic diameter <10 μm) and PM2.5 (particles with aerodynamic diameter <2.5 μm), the latters are considered the most dangerous for health due to their capacity of penetrating into the bronchia peripheral areas and hampering air exchange.

In Georgia, 21% of total burden of disease and 25% of deaths are caused by adverse environmental impacts (WHO, 2012). Children are particularly sensitive to environmental risks, therefore compared with adults, the burden of disease and mortality of this contingent are higher due to environmental impacts. In low and middle income countries of Europe, including Georgia, 14% of deaths and 30% of burden of disease of children aged under 5 are caused by adverse environmental impacts (WHO, 2004).

Achievements and challenges

Published in May 2016, WHO report - World Health Statistics 2016: Monitoring Health for the SDGs, sustainable development goal - the structure of which is based on Sustainable Development Goals, uses the latest indicators and their calculation methodologies. One of the chapters of the report is devoted to deaths caused by air pollution and the Sustainable Development Goal 3.9 – to significantly reduce the diseases and mortality caused by hazardous chemical substances as well as air, water and soil pollution and contamination by 2030. Indicator of above mentioned Goal (Indicator 3.9.1: Mortality rate attributed to indoor and ambient air pollution) - is calculated according to the new methodology, rankings of countries are presented by WHO regions. The attributed index (rate for Georgia)  is 292.3 is the highest within the European region as well as among the indexes of other WHO regions.

By macroeconomic and health indicators, Georgia does nor significantly differ from the majority of the middle-income countries of the European region, while ambient air pollution indicators do not exceed average European data. On the basis of the request of The Ministry of Labor, Health and Social Affairs, the Special Mission of the World Health Organization visited Georgia in July 2016. It held the meetings with the competent Governmental Authorities  of Georgia in order to study the current situation and latest data. By the end of September 2016, the World Health Organization published updated data on Georgia, according to which the mortality index attributed to ambient  and indoor air pollution was 204.9. Accordingly, Georgia moved from the 1st to the third place after Bosnia-Herzegovina and Bulgaria.

Pollution of ambient air in Georgia comes from transportation vehicles, energy sector, industrial facilities and agriculture sectors. However, the main pollutant in Georgia is the vehicle emission.

High level of vehicle emissions results from many factors, and for the purposes of their reduction the measures should be taken, such as:  gradual tightening of control for motor fuel quality and vehicle emissions; establishment of  admissible age limits for vehicles with its gradual reduction, traffic flow  management optimization, development of electric vehicles etc.

in Georgia,  high level of exposure resulting from use of solid fuel for the purposes of indoor cooking and heating is one of the key risk factors for health, especially for children and women. According to the data of WHO database (Public Health and Environment (PHE): Indoor air pollution/Population using solid fuels (%) 2013), Georgia's indicators are among the highest in the European region (84% of the rural population; 12% of urban population, National - 46%), significantly exceeding the Overall Regional Index (<5%), as well as the Global Index (41%) However, they correspond to the World Bank's medium  and low-income countries consumption level (56%). In parallel with the ongoing projects on the gas supply infrastructure development, in case of introduction of relevant indicators, through indoor survey designed for collection of state statistical data, it will be possible to assess the progress achieved towards the reduction of adverse impacts within Environmental and Public Health systems.  Georgia’s applicable air quality normative acts and the current monitoring system which do not provide for assessment of air pollution and its impacts on population health in accordance with the WHO recommended parameters, requires initiation of both relevant normative framework and revised monitoring system. Although in accordance Association Agreement with the European Union, air quality monitoring and management improvement measures have been elaborated within the framework of the Georgian Government’s Action Plan, they still require strengthening in terms of capacity building for Health Impact Assessment, which is one of the Goals of the National Action Plan.

Strategic interventions

MTO 3.1. - Relevant legislation harmonized according to the Association Agreement; CLRTAP and its last Protocol (Gothenburg Protocol) ratified.

MTO  3.2. - Air quality monitoring in major cities of Georgia (Tbilisi, Kutaisi, Rustavi, Batumi) carried out in accordance with  EU Air Quality Directive (2008/50/EC) by 2021.

MTO 3.3. Health-relevant information on population exposure to air pollution and its influence on health in major cities of Georgia (Tbilisi, Kutaisi, Rustavi, Batumi) ensured by 2020.

MTO 3.4. Health risks due to fuels combustion (wood, gas, kerosene, etc.) for heating and cooking in households and children’s educational institutions assessed by 2021.

MTO 3.5. Child care facilities, kindergartens, schools and public recreational settings are tobacco smoke-free by 2020.

MTO 3.6.  The Action Plan for reduction of ambient and indoor air pollution impact on children's health adopted for Tbilisi by 2020.

Strategic objective  4:  Prevention of morbidity caused by exposure to chemical substances

Rationale

According to WHO recommendations, chemical safety is achieved via implementation of all measures for chemical substances. It includes all (natural and synthetic) chemicals  as well as all the stages of exposure to chemical substances throughout their extraction, synthesis, industrial production, transportation and utilization. Despite the delay in manufacturing industry development, chemical substances management issues are highly topical,  requiring introduction of effective regulatory mechanism and  state agencies’ coordination scheme.

Achievements and challenges

Proceeding from the geopolitical location of Georgia, implications of the traffic corridor function place on Georgia additional responsibility to perform activities related to hazardous goods transportation in accordance with international trade regulations. At this stage of national development, management of chemical safety issues in conformity with European standards, being  some sort of indicator of the country's commitment to democracy and European values, should play significant role in pursuing the policy of consistent struggle against international terrorism.

in Georgia, the major shortcoming for chemical substances management is lack of required information resources. Due to complete disruption of information collection and sharing  systems, currently Georgia has no reliable information on the following:

- What hazardous chemical substances and in what quantities are produced or imported or transported within in the country;

- Where, in what value and through which technologies are the hazardous chemical substances used;

- To what extent are safety and labor conditions or environmental norms upheld;

- What hazardous wastes are generated in the country, in what value, where and how they are neutralized or allocated, whether environment is  protected from pollution or not;

- - What are the hazardous (harmful) chemicals deposited in the environment; What is their concentration in the air, water or soil;

- - What is the health impact of hazardous (harmful) substances (directly or through polluted environment or through food / drinking water).

- - There is no  poisoning information and advisory center.

- - No biological monitoring is carried out for priority pollutants (lead, mercury, cadmium, chromium, manganese)

- - No statistical information is collected on chronic intoxication, and acute one is based on medical history data.

Only the following are registered in Georgia:

- Pesticides and agrochemicals - In the pursuance of FAO " International Code of Conduct on the Distribution and Use of Pesticides" and EEC 91/114 Directive requirements (The Catalog of pesticides permitted for use in Georgia has been compiled).

- Disinfectants - Registration procedures need further improvement (the list of registered disinfectants available on the NCDC web-site).

In addition, currently Georgia lacks the following:

- Modern methodologies for chemical impact risk assessment and management;

- Qualified professional staff..

- The country does not have laboratories for chemical-toxicological acute and chronic intoxication diagnostics;

- No quality control and proper labeling   of goods, toys, consumer commodities, cosmetic perfumes, and indoor chemistry is performed.

- There is no comprehensive database on hazardous chemical substances consistent with the international requirements (Safety data sheet).

- Chemical substances classification and labeling GHS and CLP system, intended to ensure availability to information on hazardous physical and toxic, in order to improve environmental and health protection during treatment, transportation and use of chemical substances.

- The requirements of SAICM are not fully implemented. Georgian system of selective authorization of chemical substances for circulation is to be approximated to European REACH (Regulation, Evaluation, Authorization and Restriction of Chemicals) system (REACH Regulation - (EC) No 1907/2006) or its Its simplified analogue, taking into consideration transitional state of Georgia's capabilities and economy). The 1992 United Nations Rio de Janeiro Conference defined chemical substances sustainable use principles; in particular – requiring to establis the national system for safe use of chemical substances, which have not yet been introduced in Georgia.

It is also crucial to introduce WHO recommendations and methodologies on the chemical substances impact risk assessment in the country.

Besides fulfilling the commitments undertaken by the Association Agreement, the National CBRN Threat Reduction Strategy approved by the Ordinance No164 of the Government of Georgia in 2014, identified common challenges in the CBRN security field. In addition, determination of goals and priorities designed for the prevention of CBRN are the basis for gradual improvement of chemical substances management in Georgia.

Strategic interventions:

MTO 4.1 Harmonization of the relevant legislation in line with the Association Agreement (AA) (REACH, CLP, IHR) and other relevant legal multilateral environmental international treaties by 2020 (implemented Globally Harmonized System of Classification, Labelling and Packaging of Chemicals (GHS), Minamata Convention on mercury ratified by 2020).

MTO 4.2 Elaboration of legislative and operational framework for collecting and sharing information on hazardous chemical substances by 2018.

MTO 4.3 Risk to children from exposures to hazardous chemical substances in schools and kindergartens assessed and reduced by 2020.

MTO 4.4 The National Program for Elimination of Asbestos Related Diseases developed by 2019.

MTO 4.5 Risk of exposure to hazardous chemical in rural areas assessed and reduced by 2020.

Strategic task 5: Integration of health issues in climate change adaptation and mitigation policies.

Rationale:

The climate change phenomenon has become known since the 70s of the 20th century, when tendency for marked increase in the global average annual temperature and frequent climatic disasters were observed. Climatic changes significantly impact health, social and environmental factors such as clean air, safe drinking water, sufficient food and safe housing. Unlike any other period of global climate change throughout the human history, the modern change, caused by human activity, is associated with intensive industrialization. The most important anthropogenic factor is the increase in atmospheric carbon dioxide levels associated with natural fuel, ozone hole, agriculture and forest felling.

Climate change is clearly reflected on human health. In this context, adaptation of population to climate change plays an important role. In many cases, adaptation process is very difficult. Climate change results in enlargement of geographical area of spread of diseases. According to the WHO data, three major characteristics, including heat waves, natural disasters and altered infectious background of climate change have particular health impacts,.

Exposure to extremely high temperature during several days directly affect human health – not only resulting in onset of certain diseases and aggravation of existing pathologies, but even possibly causing death. According to experts, high atmospheric temperatures negatively affect cardiovascular and respiratory systems, particularly in elderly and chronic patients. In addition to direct influence, extremely high temperatures exert indirect influence on human health: under high ambient temperature conditions, concentrations of ground ozone and other air pollutants get altered, triggering  onset of  cardiovascular and respiratory system diseases.

The number of climate change attributable natural disasters has been tripled since the 60s of the last century. Consequently, the damage inflicted by natural disasters (the number of injuries and deaths, as well as frequency of the diseases occurring due to extreme natural phenomena) has enhanced.. For example, floods cause disruption of the sanitary system, consequently triggering outbreaks of infectious diseases.

Climate change is also considered as a factor contributing to increase of frequency of infectious pathologies, especially water-borne and transmitted infections. Air temperature and humidity have a considerable influence on the life cycle of insect vectors (e.g. Malaria carrier). In case of establishing favorable to the insect climate conditions (high temperature and humidity), infectious pathology easily spreads out. Climate change may prolong season of transmissible diseases and/or change their geographical area.

It is assumed that with rise of temperature, the number of diseases such as Malaria, West Nile Fever, viral hemorrhagic infections will significantly increase; in addition, rise of chronic diseases such as asthma, cardiovascular diseases and etc will occur.

Extremely high temperatures directly increase the mortality rates of cardiovascular and respiratory diseases, especially in elderly people. Sea level rise and extreme weather disasters cause damage to accommodation buildings, medical facilities and other essential services.

Health impacts of climate change can only be estimated. Nevertheless, WHO claims that in 2030-2050, climate change will result in more than 250,000 deaths annually. Out of these, 38,000 cases with elderly people will be caused by exposure to thermal waves, 48,000 cases - by diarrhea and 60,000 cases – by Malaria; insufficient nutrition is expected to result in 95,000 newborn deaths.

Detection and quantitative assessment of climate change health impacts is essential for public health protection as well as for elaboration of national and international policies.

Achievements and challenges

in Georgia, the signs of climate change have been observed since the 60s of the 20th century. The picture varies for different regions of the country. Georgia’s Second National Communication (SNC) to The United Nations Framework Convention on Climate Change (UNFCCC) describes trends of change in  the climatic parameters for two periods - 1955-1970 and 1990-2005.

In Western Georgia, between first and second periods the mean temperature increased by 0,20C and the annual precipitation decreased by 27 mm; in Eastern Georgia, the mean annual temperature increased by 0,30C and annual precipitation increased by 41 mm.

In Tbilisi, in addition to general trend of climate change characteristic for Eastern Georgia, particularly severe impacts of climate change are observed, caused by urbanization, "island effect" resulting from thermal waves (under high temperature conditions, heat is absorbed by asphalt and buildings, causes the city to "glow" and maintain the heat even after the sunset).

It is noteworthy that climate change is not yet reflected in the dynamic of water-born and transmitted infections. Over the recent years, decrease in cases of Malaria, leishmaniasis, Crimean-Congo Hemorrhagic Fever and other insect-born diseases has been observed.

In 2012-2013, ICRC Georgia carried out the pilot study on thermal waves, which led to the development of the National Thermal Wave Action Plan.

It is important for Georgia, in accordance with the decision of the WHO 61st Assembly held in 2008  (To protect health of the population from the harmful effects of climate change, develop and implement an Action Plan for WHO member states), to elaborate the Action Plan, taking into consideration the following priority directions:

- Promote health systems to strengthen and enhance their capabilities of assessment and monitoring of health vulnerabilities.

- Determine climate change attributable risks and health impacts in order to protect human health and first of all, the most vulnerable groups of the population.

- Develop and implement relevant strategies and actions.

- Spread and share knowledge and good practices

Strategic interventions:

MTO 5.1 Evaluate  vulnerability to climate change, health impacts and adaptation (health care aspects) including assessment of existing and anticipated risks related to health impacts of climate change.

MTO 5.2 Develop National Health Care Adaptation Strategy and Action Plan, among them, for medical facilities;

MTO 5.3 Harmonize the legislation with regard to the requirements of the UNFCCC Convention and assessment of health outcomes.

MTO 5.4 Health care facilities reduce the share of greenhouse gas emissions X%  in national emissions by 2020 (from 2017), including introduction of renewable energy use in several hospitals within the framework of the pilot project.

Strategic task 6: Improvement of the existing Environmental Health System management in Georgia.

Rationale:

Administrative reorganization carried out in the Ministry of Labor, Health and Social Affairs during 2004-2012 negatively affected the development of environmental and health policy. International experience demonstrates that economic development further increases pressure on environmental and natural resources and makes it is difficult to provide for safe environment unless timely and appropriate measures are taken. Almost all the issues of the National Action Plan are of cross-sectoral nature. Without coordinated actions of Health Care sector, various ministries and local self-governmental structures, it will be impossible to implement individual measures and consequently achieve the goals set by the Action Plan.

Achievements and challenges:

Taking into consideration the above, for the purpose of developing, strengthening and improving the current Environment and Health management system, the Ministry of Labor, Health and Social Affairs of Georgia applied to EU Delegation to Georgia for assistance and in 2013, with support of the TAIEX, visit of  TAIEX Expert Mission was held in NCDC, aiming to assist Georgia in providing safe environment and Health system. The report ofTAIEX Expert Mission provide the review of current situation in the Environment and Health sector as well as general and concrete recommendations consistent with the commitments assumed by Georgia through  Association Agreement. TAIEX Expert Mission's findings highlight the following problems:

- Absence of legislative framework.

- Absence and/or ineffectiveness of control measures to be applied by competent authorities as legislation enforcement tools.

- Lack of institutional structures.

- Insufficient coordination between the institutions.

- Lack of staff.

- Insufficiently trained staff (due to frequent changes in personnel).

- Insufficient technical infrastructure, equipment, consumables, fuel, etc. for operative activities.

- Lack of information and absence of database, due to non-existence of relevant legislative framework to provide such information.

- Lack of appropriate skills and knowledge regarding environmental and health issues.

The TAIEX Experts Mission report outlines recommendations and priority measures. After the TAIEX Expert Mission, a project proposal for the EC Twining project  "Strengthening the Environment and Health System in Georgia" was elaborated. On the basis of twining project selection criteria, Consortium of Italy, Poland and UK was selected out of EU countries. Twining Project implementation began in 2017. After its completion, the new environmental and health system, similar to relevant EU services and capable of addressing   modern challenges, will be established.

For the purposes of management improvement, special attention is paid to adequate expertise and governance and continuous professional development of the staff, since the country lacks qualified personnel and no uniform system approach is applied in this sphere.

It should be noted that the Law of Georgia on “Public Health” envisages the necessity of regulating the professional training and education of labor/human resources in the field of public health. The Ministry of Labor, Health and Social Affairs of Georgia is authorized to define the list of public health specialties and their respective competences. Unfortunately, above mentioned list has not been defined yet. Its absence to some extent prevents from developing public health specialties in accordance with the Western model, determining terms of reference  for  relevant specialties, forming undergraduate and postgraduate education system in line with the principles of European and / or American ones, which in turn hinders development of  labor market  In the field of public health, one of the component parts  of which is environmental health.

In the light of the above, one of the matters of great importance for public health in general and particularly – for environmental health is ensuring due attention to the issues of professional training and education by  Government of Georgia, as well as relevant institutions, academia and NGOs. Short-term and long-term bachelor’s and master’s degree programmes as well as vocational training programmes  for environmental health specialists should be expanded in a number of the country’s  universities. Topical workshops, seminars and conferences should be organized with participation of local and international experts. Elaboration of training/scientific programs based on up-to-date requirements as well as development of existing ones will contribute to the continuous professional development. In addition, market conjuncture should be constantly monitored and outcomes reflected in academic programs and educational process. Implementation of NEHAP  is a matter of great importance. The NCDC will annually prepare the Performance Report on National Environment and Health Action Plan and Strategy. Another issue is separation of powers, roles and responsibilities between different agencies and institutional strengthening to ensure safe environment.

Special importance is given to Georgia's involvement in the European Environment and Health process.

Strategic interventions:

MTO 6.1 Institutional strengthening of the existing Environment and Health System.

MTO 6.2 Implementation of National Environment and Health Action Plan

Strategic task 7: Reduce the impacts of physical agents  of the environment by 2021

Rationale:

Human habitat is characterized by the variety of physical factors which have a significant impact on the health of population (noise, vibration, electromagnetic radiation, Radon,, irradiation in the course of  medical diagnostics and treatment). Among the measures taken for improvement of population’s health and reduction of morbidity,  special significance is assigned to establishing principles and fulfillment of specific tasks necessary for the prevention of physical factors characterized by health impacts.

Achievements and challenges:

Currently, no assessment of exposure to physical factors of living and working environment is performed in Georgia, therefore there is no database. Individual researchs  of the noise and vibration exclusively on the basis of the citizens' statements is conducted by the National Environmental Agency. Such individual researchs  do not allow for the situation assessment. Therefore, a separate budgeted, targeted program should be worked out for the purposes of proactive detection of morbidity and initiation of preventive measures, to assess the impacts of various physical factors with significant health effects.

Due to abolition of State Sanitary Surveillance Service, urban planning requirements are not fulfilled any more, development master plans for the cities have not yet been drawn up, recreational and green areas of different purposes have been reduced. Repeal of the Decree No. 234/n of 6 October 2003 of the Minister of  Labor, Health and Social Affairs of Georgia "On Approval of Sanitary Protection Zones (SPZs) and Sanitary Classification of Enterprises, Buildings and Other Facilities", resulted in occurrence of residential and mixed-purpose zones in  industrial zones, in the immediate vicinity of polluting enterprises, without consideration of sanitary protection zones which were canceled under the current legislation. It is important to have the operational materials on environmental situation monitoring concerning noise, electromagnetic emissions and radiation (Radon) background in different districts of Tbilisi and other cities. The location, safety and amenities of the school area are essential for  students’ health protection. Environmental safety of school is determined not only by its amenities and proper maintenance, but also by influence of adjacent areas, buildings and facilities, depending on their functional load (schools located in the vicinity of transport corridors, bus depots, industrial enterprises, abandoned facilities, landfills, burial sites, military bases, construction sites, etc.).

In consequence of 2007 reform, responsibility for nuclear and radiation safety was transferred to the Ministry of Environment and Natural Resources Protection. Radioactive Waste Management System was established in 2014-2015. The LEPL Nuclear and Radiation Safety Agency, concurrently excercising a function of radioactive waste state management, has been established. Radioactive waste storage and radioactive waste burial site were placed under the management  of the Agency for the purpose of establishing the unified radioactive waste management system. In addition, the Agency concurrently executes the function of state regulation of nuclear and radiation activities . The Governmental Ordinance on  approval of the Technical Regulation on Radiation Safety Standards and Basic Requirements for Handling Sources of Ionizing Radiation has been adopted. Also, Technical Regulation on Individual Monitoring and Control Procedure, establishing the essential requirements for working with the source of ionizing radiation  .

According to the UNSCEAR  the share of medical radiation exposure in the population’s radiation exposure dose account for 40-50%. Countywide, in view of the quality of X-ray equipment in as well as the age of X-ray equipment used in the regions, radiation exposure of the population is sharply rising, entailing the necessity of providing medical radiation safety in the country, regular monitoring of the radiographic and radiological equipment's technical consition and raising patient safety regarding  radiation safety issues etc.

Over the years in the aftermath of Chernobyl accident, Georgia has been conducting assessment of  environmental pollution level in terms of radionuclide contamination of food, water and air, which allowed for assessment of environmental radiation contamination. Such assessment has not been held since the abolition of State Sanitary Surveillance Inspection.

Strategic Interventions:

Medium-term goal 7.1 Reduce health impact of noise by 2021.

Medium-term goal 7.2 Reduce health impact of anthropogenic  ionizing radiation by 2021

Medium-term goal 7.3 Reduce impact of Radon on population.

Medium-term goal 7.4 Reduce impact of ultraviolet radiation reduction by 2021.

Medium-term goal 7.5 Reduce health impact of electromagnetic fields by 2021.

Medium-term goal 7.6  Education / training and preparedness of the population for emergency situations caused by natural disasters such as earthquakes, floods and other extreme weather events as well as technogenic disasters.

4. Strategy implementation timeframe and responsible institutions

The list of activities within the framework of each task and strategic intervention is given in Annex No.2, which also provides information about the institutions responsible for implementation and their partner organizations.

Responsibility for effective implementation of the National Environment and Health Action Plan and the Strategy will be divided among various Governmental institutions and agencies, considering their mandates and competencies. The list below comprises the key agencies that will guide, coordinate and oversee implementation of the Strategic Plan:

●National Environment and Health Action Plan and the Strategy Coordination Council, which is the advisory body of the Ministry of Labor, Health and Social Affairs of Georgia which, on the basis of analysis of environment  attributable morbidity and mortality data as well as assessment and analysis of the country’s relevant services capabilities, elaborates recommendations for intensification of prevention and control of environment  attributable diseases in order to determine national policies and priorities of state programs;

● The Ministry of Labor, Health and Social Affairs of Georgia, responsible for organizing health care services in general as well as developing and implementing the national policy and regulations for environmental health sector;

● NCDC under the state control of the MoLHSA of Georgia, one of the priority directions of which is reduction of environment attributable morbidity and mortality.  It also exercises  the function of Secretariat of the Environmental Health Coordination Council.

One of the main principles of the National Strategic Plan is close cooperation between the state and international sectors and multicultural approaches. Due to multifaceted nature of environmental risk factors attributed diseases, without intersective approach, progress in terms of unimaginable their prevention and management is unimaginable.

Therefore,  along with  the Health sector, the MoLHSA, the MoENR, the MoES, the MoF, the MoSYA, the MoIA, the MoA, the MoRDI, the MoESD and Tbilisi City Hall are among the partner organizations responsible for Strategy implementation.

5. Potential risks occuring in the course of / resulting from strategy implementation process

In the course of implementation of the Strategy, certain financial and social risks that may impede achievement of results defined by the Strategic Plan, should be taken into consideration.

The financial risk of Strategy implementation is caused by the lack of donor funding in the area of diseases attributable to environmental risk factors which requires gradual but substantial increase in state financing to cover financial needs defined by the Strategy.

It is necessary to include prevention and control programs of diseases attributable to environmental risk factors in the National Development Goals. It is necessary to recognize the priority of mobilization of adequate, predictable and sustainable resources in order to apply the national efforts (with allocation of local budget) designed to prevent and control diseases attributable to environmental risk factors.

Solution to the problem of lack of resources requires balanced approach to mobilizing of internal resources and working upon  the donor organizations.

6. Strategy monitoring and evaluation mechanisms

Regular monitoring and evaluation through appropriate mechanisms will be carried out for providing timely detection and response to progress and challenges in the course of  the NEHAP and the Strategy implementation.

The MoLHSA monitors the implementation of the strategy through NCDC. Strategic Plan Monitoring and Evaluation Indicators are given in Annex No. 2. Assessment of 2017-2021 and implementation of the National Strategic Plan 2017-2021  will be carried out in accordance with the fulfillment of planned indicator values provided in above mentioned Annex. For the purpose of determining the data for individual indicators of the Monitoring and Evaluation Framework, it is planned to introduce the Annual Reporting Format. Indicators of environment attributable diseases, elaboration of which has already started, will be used along with  obtainment of statistical information and research and evaluation activities. Indicators attributable to mortality and its causes, are generated by the GEOSTAT, will also be used. Based on the above sources of data,  the Strategic Plan indicators’ data will be generated with relevant frequency. The NCDC is accountable to NEHAP and the Strategy Coordination Council and the MoLHSA for collecting, validating, analyzing and reporting information on indicators.

The NCDC will prepare annually the report on the implementation of the NEHAP and the Strategy, which will be submitted to the MoLHSA.

Key performance indicators (KPIs)  and Goals by 2021 (Baseline - 2015).

Improvement of environmental quality in the country, reduction of environment attributed  burden of disease and ensuring safe environment for the population require implementation of integrated intersectoral policies.

Environmental adverse impacts and professional risk factors such as pollution of drinking/recreational water resources and ambient/indoor air, ozone, dust, substances and allergens emitted through fuel combustion, carcinogens, exposure to ionizing and nonionizing radiation, noise, vibration, uncontrolled use of agrochemicals and pesticides can cause increase in environment attributed  burden of disease at all stages of life cycle. Accordingly, coordinated action of different agencies, implementation of integrated policies and assessment of progress via Key Performance Indicators ("KPIs) is required to prevent and avoid diseases. The Key Performance Indicators demonstrate the extent of cost-effectiveness and benefits of providing safe environment. In some cases, indicators might have a note  “Data absent, to be defined." Due to absence of baseline data in the country, progress can not be evaluated. There is a need to achieve common consensus on the main conceptual issues between relevant government agencies, which is feasible in case of submission of requests by the authorities. it may be necessary to develop additional implementation guidelines as well as plan/implement certain activities and researchs/evaluations.

Key performance indicators (KPIs)

Strategic task 1

- Progress report in compliance with the requirements of EU Association Agreement; national legislation on drinking water and sanitation harmonized with the EU legislation; laws and subordinate acts adopted and published

- The Protocol on Water and Health ratified by 2021

- The Protocol on Water and Health - Priority National Goals, indictors and estimated deadlines approved and published by 2019

- The % of urban population provided with access to improved centralized water supply sources, compared to 2015 (96%)

- The % of rural population provided with access to improved centralized water supply sources, compared to 2015 (62%)

- The % of the population that will benefit from improved sewage systems, compared to 2015 (86%)

- The % of rural population provided with access to improved centralized water supply sources, compared to 2015 (62%)

- Situational analysis of existing drinking water quality surveillance system is published

- The single database of drinking water quality is functional and regularly updated

- Drinking water quality assessment laboratories are identified and findings of the survey are entered into the single database of drinking water quality

- Water Supply and Sewage Systems Inventory Report

- The measures for water supply modernization and improvement are identified and established deadlines for implementation are approved and published

- Number of water supply companies implementing WHO WSP recommendation

- The % of the drinking water treatment infrastructure producing standard-compliant drinking water (for 2015 “Data absent, to be defined") to be increased by X% by 2021

- The % of the drinking water treatment infrastructure with standard-compliant treatment technology (2015 “Data absent, to be defined") to be increased by X% by 2021

- Drinking water quality noncomplince across the country in terms of მიხედვით  E.coli (19.1% in 2015)   to be reduced by 5% by the year 2019 and by 10% by the year 2021

- Incidence of drinking water-born  diarrheal diseases (2015 “Data absent, to be defined") to be decreased by X% by 2021

- The measures for modernization and improvement of sewage systems are defined and the established deadlines are approved and published

- The  number of buildings and structures connected to the sewage system to be increased (2015 “Data absent, to be defined") by 10% by the year 2021

- The  number of wastewater treatment facilities across the country (2015 “Data absent, to be defined") by 10% by the year 2021

- The % of standard-compliant wastewater quality samples (2015 “Data absent, to be defined") to be increased by X% by the year 2021

- The % of educational and boarding institutions using improved water supply sources, compared to2015 (86% -2015)

- The % of educational and boarding institutions providing for decontamination of  unimproved drinking water sources (unprotected well, unprotected spring), compared to 2015 (8%)

- The % of medical facilities using improved water supply sources, compared to 2015 (2015 “Data absent, to be defined")

- The % of RIDP settlements using improved water supply sources, compared to 2015 (2015 “Data absent, to be defined")

- The % of educational and boarding institutions using improved sanitation systems, compared to 2015 (70% -2015).

- The % of medical facilities using improved sanitation systems, compared to 2015 (2015 “Data absent, to be defined")

- The % of RIDP settlements using improved sanitation systems, compared to 2015 (2015 “Data absent, to be defined")

- Swimming Pools Water Quality Monitoring Report, with reference to the web site

- The number of identified recreational-bathing sites and water quality monitoring results, with reference to the web site

Strategic task 2.

Medium-term goal 2.1. In accordance with the Association Agreement, relevant harmonization of legislation in the area of Children’  Safety by 2020. (2016 “ Not prepared, to be prepared by 2020").

– Indicator: The number of laws and subordinate acts in compliance with the EU Directives.

Medium-term goal 2..2. By the year 2020, increase, share of schools and kindergartens ensuring availability of safe physical activities by X% compared to 2016 (2016 “Data absent, to be increased by X% by the year 2020")

– Indicator: Number of schools and kindergartens with adequate equipment for safe physical activity.

Medium-term goal 2.3. In comparison to 2016,  increase share of schools with  adjacent territories safe for children’s movement By 2020; (2016 “Data absent, to be increased by X% by the year 2020")

Indicator: 1. Mortality rate of children under 0-14 years due to road traffic accidents

2.  Indicator of traumatism attributed to road traffic accidents in children under 0-14 years, including pedestrians and bike users

Strategic task 3

- The number of enacted laws and subordinate acts on air quality management, harmonized with EU legislation in accordance with the requirements of the Association Agreement;

- The number of laws and subordinate acts harmonized with the Protocol of the Gottborough Convention on Long-Range Transboundary Air Pollution;

- Fraction of deaths attributable to ambient and indoor air pollution (according to SDG indicator);

- Proportional share of the population with access to clean energy and technology;

- Average annual indicator of solid dust particles (PM10, PM2.5) concentration in the air for the cities of Georgia.

- Number of Georgian cities covered by air quality monitoring network;

  - The spatial distribution and characteristics of the monitoring stations comply with the EU Directive;

  - The list of observable pollutants corresponds to the complies with EU Directive;

  - The functional organogram of the monitoring network is available for stakeholders;

- Total number of air quality monitoring stations;

  - Number of operational monitoring stations in the country;

  - The number of monitoring stations with PM10 and PM2.5 measurement

  - The number of personnel who has undergone instuction / training;

  - Proportional share of monitoring stations (%) where the Quality Control (QA / QC) System is introduced;

  - The number of stations that meet quality criteria.

- Information about the average annual concentrations of PM10, PM2.5, NO2 and O3  in four cities (Tbilisi, Kutaisi, Rustavi, Batumi) is available for the population;

- The number of Georgian cities where information about ambient air quality and its health impacts is available for the population;

- The number of Georgian cities where the health risks attributable to air pollution are assessed;

  - Methodologies are tested and approved;

  - Quantity of media outlets (magazines, television or radio stations, web-pages) through which the population is informed about air quality of quality of each city on a daily basis;

  - The number of cities for which the Health Impact Assessment (HIA) has been performed and completed;

  - Assessment of deaths attributable to ambient air pollution for selected cities (Tbilisi, Kutaisi, Rustavi, Batumi).

- The number of indicators of health risk attributable to burning of the fuel (firewood, gas, kerosene, etc.) used for cooking and heating in the households and children's educational and boarding institutions (Determined with definitions and formulated with methodologies); (განსაზღვრული დეფინიციებით და ფორმულირებული მეთოდოლოგიებით);

- Elaboration of document(s) on methodology/methodologies of assessment of health risk attributable to burning of the fuel (firewood, gas, kerosene, etc.) used for cooking and heating in the households and children's educational and boarding institutions.

  - Number of selected indicators (Determined with definitions and formulated with methodologies);

  - Document on risk assessment methodology/methodologies;

  - Document on risk assessment data processing, analysis and reporting methods;

  - The number of children's educational and boarding institutions for which the evaluation have been carried out

  - The number of children covered by the study of households

  - % of population which uses each type of fuel for cooking and heating.

- Percentage of child care institutions, kindergartens, schools and public places that fully meet legislation requirements and are free from tobacco;

  - Requisites of the adopted legal act;

  - Percentage of persons with adequate knowledge about tobacco’s harmful effects;

  - Tobacco consumption level / frequency in institutions subject to prohibition.

- Requisites for the Ordinance of the Government of Georgia on Approval of the National Plan for Reduction of Impact of Ambient and Indoor Air Pollution on Children's Health;

- The number of activities carried out by responsible agencies eenvisaged by the National Plan for Reduction of Impact of Ambient and Indoor Air Pollution on Children's Health.

  - The number of relevant normative acts harmonized with the EU legislation;

  - Requisites of the Ordinance of the Government of Georgia on Approval of the National Plan;

  - The number of responsible agencies reports on the performed works.

Strategic task 4.

- The management of hazardous chemical substances has been improved (the Law on Chemical Substances Management is enacted; powers are separated; the National Chemical Substances Management Body is functioning; GHS/CLP implementation under the Association Agreement is underway; rules for chemical substances classification and attribution to  toxicity and hazard classes; requirements for packing, marking and labeling; the form of fact sheet on chemical substances safe handling; other subordinate acts).

- Approximation of system of selective authorization of chemical substances for circulation to  REACH  is being carried out  (2021)

- Sectoral legislation on Mercury is published and enacted.

- Consumer rights in Georgia are protected through harmonization with EU legislation and securing consumer products by 2021:

- Requirements of  Directive 2001/95/EC of the European Parliament and of the Council of 3 December 2001 on general product safety are  enacted and quality monitoring is carried out.

- European recommendation for child consumer products safety „Child Product Safety Guide - Potentially dangerous products“ is enacted  and quality monitoring is carried out.

- Directive 2009/48/EC of the European Parliament and of the Council of 18 June 2009 on the safety of toys) is enacted  and quality monitoring  is carried out.

- Safer cosmetics for Europeans  Regulation (EC) No 1223/2009 on cosmetic products is enacted  and quality monitoring is carried out.

- Directive EC No648/2004 on Household Chemical Products is enacted  and quality monitoring is carried out.

- Legislative amendments on "Prohibition of use of lead in paints" are enacted and quality monitoring is carried out.

- The National “Standard on emissions of hazardous chemical substances for furniture and construction materials” is enacted and the quality monitoring is carried out.

- Directive on biocides Regulation (EC) No 528/2012 and DIRECTIVE 98/8/EC is enacted and Register is periodically updated.

- Directive on Pyrotechnics Placement on the Consumer Market 2007/23/EC   is enacted  and monitoring is carried out.

- Legislative amendments are enacted to introduce primary and secondary special packaging (difficult-to-remove caps, labeling) and to prevent children's poisoning with medications and other items containing hazardous chemical substances.

- Assessment report is published (indicating web site) to establish chemical safety system and a relevant system for monitoring of chemical substances in circulation in the territory of the country.

- The requirements of international medico-sanitary regulations (IHR-requirement) on emergency situations caused by chemical substances are incorporated into the national legislation

- Periodically updatable Action Framework (register) is elaborated and for the purpose of collecting and sharing information on hazardous chemical substances,  legislative amendments are enacted to ensure sustainability of the system.

- Access to existing toxicological-chemical laboratories and mapping are ensured,  To prevent, detect, respond and eliminate spread of massive non-communicable diseases and poisonings in the population.

- Number of schools and gardens, the indoor air pollution with hazardous chemical substances of which  is monitored,  annually increases by 10% (2015--0%).

- The National Program of Elimination of Asbestos Diseases is being implemented.

- The national capabilities are established to evaluate the risk attributable to compbine impacts chemical substances in accordance with WHO methodology.

- Information Consulting Center for Poisoning Control and Toxicology is functioning.

- Construction of burial sites for toxic industrial waste and unrecyclable toxic industrial waste generated on the territory of the country is initiated.

Strategic task 5 .

- The final report, which analyzes the current and expected risks of vulnerability to climate change, is approved and published;

- The Public Health Policy and Programs required to reduce the climeate change attributable health risks are elaborated;

- National Reports on Vulnerability, Impact and Adaptation to Climate Change (Midterm and Final) are approved;

- National Strategy and Action Plan for Health Care Adaptation to Climate Change are published;

- Report on analysis of deaths resulting from high temperature impacts is published;

- Report on Detailed Analysis of Health System Energy Efficiency is developed and published;

- Manuals on energy efficiency and climate change (posters, booklets) are elaborated and published, Health Care personnel are trained.

Strategic objective  6.

1.  The Environment and Health System is established and institutionally strengthened  by 2020.

2. Environment and Health Information System is set up by 2018, the environment and health indicators are developed with respect to SDG.

3. Annual report on implementation of the National Environment and Health Action Plan.

4. The number of trained medical personnel (methodological assistance is provided and turnings are organized according to Medical Institutions Waste Management Code "Developing new technical regulations for medical waste management").

5. To evaluate physical factors of the environment, access to the existing laboratory capacitiesand mapping is provided.

6. The "Transport, Environment and Health" National Action Plan is developed by 2018.

Strategic Task 7.

  - Percentage of schools and buildings where noise levels are monitored.

  - Evaluation of noise impacts in buildings where children spend most of the time; planning  and implementation of  measures designed to minimize noise impacts

  - Measures on city planning and improvement of the infrastructure, designed to reduce noise impacts.

  - Report on measures for reduction of the impacts of ionizing radiation related to medical activity  (indicating the web site).

  - Preparedness and response plan for the nuclear and radiation accidents and elimination of accident consequences, 2021

  - Report on radiation monitoring and interventions for reduction of Radon health impacts, map / mapping, indicating web site.

  - Annual Report on preventive measures related to Radon.

  - Annual Report of measures for reduction of the impacts of ultraviolet radiation on the population, indicating web site.

  - Legislation developed / enacted to reduce the impact of electromagnetic fields, approved Action Plan to reduce electromagnetic fields generated by all possible sources.

  - Annual Report of measures for education/training and readiness of the population for emergency situations caused by natural disasters such as earthquakes, floods and other extreme weather events as well as technogenic disasters (information supplied by mass media).

- Funding of  the environment attributed diseases prevention and control measures

Due to high morbidity and mortality rates, environment attributed diseases constitute significant financial and public burden for the country’s Health Care system. Budget calculations for the activities of the National Strategy were carried out in view of epidemiological situation, the planned coverage indicators and potential of the service. The cost of the unit is based on the existing prices, depending on local inflation and international price trends.

The amount of money required to finance environment attributed diseases prevention and control measures in 2017-2021 in annex2.

Annex 1. Performance Indicators for the National Action Plan of the Environmental Health, 2017-2021

Strategic  Objective 1.  Ensure public health through improvement of access to safe and sustainable water supply and sanitation. Ensure access of each child to safe water supply and sanitation by2021.

|  | Activity | Assessment Indicator for Implementation of a Plan |  | Baseline Data (2016/2015) |  | Tatget Data (2021) |  | Terms of Implementation |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | 2017 Implemented Activities |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  |
| #### MTO 1.1 National legislation and policy frameworks on protection of water resources, drinking-water supply and sanitation reviewed and updated by 2021 Note: Once the Protocol on Water and Heath is ratified, MTO 1,1 including below specified activities, becomes a national target under the provisions of the Protocol |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.1 | Revision of existing legislation, regarding water resources, drinking water quality and sanitations, that require harmonization with international requirements. |  | The number of laws considered |  | Should be determined |  | Approved |  |  |  | Performed |  | P |  | P |  |  |
| 1.1.2 | Making changes in the national policy for drinking water quality and sanitation and regulatory normative documents accordint to the recommendation of the WHO |  | Number of legislative amendments and / or newly adopted docuements, laws and norms on the water quality, supervision, reporting and riska management |  | No data /or incomplete data |  | All sectoral laws and sub-legislative norms are considered |  | P |  | P |  | P |  |  |  |  |
| 1.1.3 | Harmonization of national legislation and adoption of new water law in accordance with the European Union Association Agreement |  | Evaluation Report for the Harmonization Process and Progress |  | Work in progress, Working version for the draft law on "Water Resource Management" is ready |  | Approved, Published |  |  |  | P |  | P |  |  |  |  |
| 1.1.4 | Ratification of the protocol "Water and Health" |  | Ratification Status |  | Work in progress, the ratification process is initiated, the Georgian version is ready |  | Ratified |  |  |  |  |  |  |  |  |  | P |
| 1.1.5 | Elaboration and adoption of National priority tergets, indicators and implementation timelines according to the protocol provisions |  | Priority National Goals, Indicators and Estimated Deadlines are approved by the Government Priority national targets, indicators and implementation timelines are approved by the government |  | Work in progress |  | Approved, Published |  | P |  | P |  |  |  |  |  |  |
| MOT- 1.2. Establishe effective surveillance systems for drinking water quality and water-born diseases by 2017-2021 Note: Once the Protocol on Water and Heath is ratified, MTO 1. 2, including below specified activities, becomes a national target under the provisions of the Protocol. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1 | Conduct baseline analysis of the quality of surveillance system of drinking water and implement necessary interventions for its improvement | Situational analysis is conducted, measures are outlined |  | incomplete data |  | Approved, Published |  |  |  | P |  |  |  |  |  |  |  |
| 1.2.2 | Conduct baseline analysis of the surveillance system for waterborne diseases and implement necessary interventions for its improvement | Situational analysis is conducted, measures are outlined |  | Work in progress |  | Approved, Published |  |  |  | P |  |  |  |  |  | P |  |
| 1.2.3 | Conduct state routine monitoring on the quality of drinking water and creation of the unified database | The unified database on drinking water quality is created, functioning and regularly updated Drinking water quality assessment laboratories are established and included in the unified database for v water quality |  | Data are incomplete on the national level |  | Unified database has been developed and updated periodically |  |  |  |  |  | P |  |  |  |  |  |
| MTO 1.3 Ensure continuous supply of the population with drinking water meeting national and international requirements Note: Once the Protocol on Water and Heath is ratified, MTO 1.3 including below specified activities, becomes a national target under the provisions of the Protocol. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.1 | Inventory of urban and rural water supply systems | An inventory has been conducted. % number of population, having access to "improved" and "non improved" water supply systems |  | The data on is incomplete at the national level, 100% of population has access to improved water supply in 2015 |  | Complete database / inventory database at national level |  |  |  | P |  |  |  |  |  |  |  |
| 1.3.2 | Determination of the rehabilitation, modernization and improvement needs for urban and rural water supply systems, for ensuring safe drinking water supply | The improvement and modernization measures for water supply systems are defined and execution terms are specified Old water preparation technologies are replaced gradually |  | Data is incomplete at the national level |  | Rehabilitation, modernization and improvement plan are approved |  |  |  |  |  | P |  |  |  |  |  |
| 1.3.3 | Preparation of gradual-introduction plan of inclusion/implementation of WSP approaches in the urban and rural water supply systems | WSP approaches" introduction is reflected in the national drinking water regulations, the supportive programs are planned, WSP is implemented, gradual introduction plan is developed |  | Data is incomplete at the national level |  | WSP approaches are introduced in 10% of water supply systems of big cities, regions and villages |  |  |  |  |  | P |  | P |  | P |  |
| 1.3.4 | Conduct education and capacity building programmes for staff involved in urban and rural water supply systems | Educational program is prepared and training cycle is functioning The staff is retrained |  | Data is incomplete at the national level |  | Employees in water sypply systems of large cities and regions have been trained in qualification upgrading courses |  |  |  | P |  |  |  |  |  |  |  |
| 1.3.5 | Implementation of awareness raising campaigns for population and providing timely and objective information regarding drinking water quality. Raise awareness of population regarding prevention of contamination of bathing waters | Number of measures conducted for water resources' protection, water hygiene and prevention of water borne diseases. Population has access to drinking water quality information |  | Data is incomplete at the national level |  | Website, where the information is available |  | P |  | P |  | P |  | P |  | P |  |
| MTO 1.4 Provision of population of the country with adequate sanitation Note: Once the Protocol on Water and Heath is ratified, MTO 1.4 including below specified activities, becomes a national target under the provisions of the Protocol. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4.1 | Inventory of the sewage / sanitation systems of the cities and villages | An inventory has been conducted % number of population, which have access to "improved" and "non improved" sanitary and sewage sites |  | Data is incomplete at the national level 2015 totally 86% improved 13% non improved |  | Complete database / inventory database at the national level |  |  |  |  |  |  |  |  |  | P |  |
| 1.4.2 | Develop complex measures for improving the state of sewage / sanitation systems in urban and rural areas to protect water resources' pollution from sewage wastewater | Improvement and modernization measures for sewage / sanitation systems are defined and the deadlines for execution are specified Old technologies of sewage / sanitary systems are replaced gradually |  | Data is incomplete at the national level |  | Rehabilitation and improvement plan is approved |  |  |  |  |  |  |  |  |  | P |  |
| MTO 1.5 Improvement of drinking water, sanitation and hygiene (WASH) conditions in educational, health care and recreational facilities/sites and in RIDPs settlements Note: Once the Protocol on Water and Heath is ratified, MTO 1.5, including below specified activities, becomes a national target under the provisions of the Protocol. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5.1 | Planning and implementing of priority mesures in educational facilities fo improvement of WASH condition | The availability has been improved by implementing priority measures on safe water and sanitation Continuous supervision has improved hygienic conditions |  | Centralized water supply system is 70%. Main supplies of drinking water in 4% of urban and 12% rural schools are non improved supplies |  | 100% of schools in rural and urban area should use the improved water supply systems |  |  |  |  |  | P |  |  |  |  |  |
| 1.5.2 | Planning priority measures in Health care facilities for improvement WASH conditions | The availability has been improved by implementing priority measures on safe water and sanitation Continuous supervision has improved hygienic conditions |  | Data is incomplete at the national level |  | 100% of Health care facilities in rural and urban area should use the improved water supply systems |  |  |  | P |  |  |  |  |  |  |  |
| 1.5.3 | Undertake baseline assessment and plan and prioritize activities in RIDPs settlements for impruvement of WASH | The availability has been improved by implementing priority measures on safe water and sanitation Continuous supervision has improved hygienic conditions |  | Data is incomplete at the national level |  | 100% of RIDPs settlements in rural and urban area should use the improved water supply systems |  |  |  |  |  |  |  | P |  |  |  |
| 1.5.4 | Developing the monitoring system for the water quality in swimming pools | Responsibilities are defined Report is available |  | Data is incomplete at the national level |  | All the data are available at the website |  |  |  |  |  | P |  |  |  |  |  |
| 1.5.5 | Identify recreational/bathing areas and monitor their water quality | Responsibilities are defined Report is available |  | Data is incomplete at the national level |  | All the data are available at the website |  |  |  |  |  | P |  |  |  |  |  |

Strategic Objective  2: Improved children accessibility to healthy and safe environments and settings of daily life, promoting their increased physical activity  by 2021

|  | Activity | Assessment Indicator for Implementation of a Plan | Baseline Data (2016/2015) | Target Data (2021) | Terms of Implementation |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 2017 Implemented Activities | 2018 | 2019 | 2020 | 2021 |
| MTO 2.1 Relevant legislation harmonized according to the Association Agreement by 2021 |  |  |  |  |  |  |  |  |  |
| 2.1.1 | Identification of relevant legislation in the field of child safety and its relevant harmonization | Assessment report for the harmonization process and progress | A working version of the Law on Sport and Physical Education has already been prepared, which is in compliance with the Association Agreement | Harmonization is implemented |  |  |  |  | P |
| MTO 2.2. Increased proportion of schools and kindergartens equipped with (or with access to) adequate facilities for safe physical activity of children by x%…in 2020 as compared to 2016) |  |  |  |  |  |  |  |  |  |
| 2.2.1 | Introduction of adequate objects and equipment definitions to ensure safe physical activity | Report on definition is prepared | National standards and relevant requirements for safe sports establishments are created by the MoSYA which does not concern institutions in the education structure | Definition is prepared and introduced |  |  |  | P |  |
| 2.2.2 | Advocate national programs in schools and kindergardens for ensuring safe physical activity | National program is prepared | Work in progress | National program is prepared, introduction is going on |  | P | P | P | P |
| 2.2.3 | Increase availability of physical activitiues outside the school institutions | Existance of sports stadiums and squares for the physical activity of children | Non-equal availability | Existence of recently open sports clubs and squares |  | P | P | P | P |
| 2.2.4 | Preparation and dissemination of educational materials, fliers for the purpose to promote physical activity | Prepared materials | The process for preparing materials and providing social networks with it, are in progress | Increased awareness of the importance of the physical activity |  | P | P | P | P |
| MTO 2.3. In comparison to 2016, increase share of schools with adjacent territories safe for children’s movement by 2020 |  |  |  |  |  |  |  |  |  |
| 2.3.1 | Advocate the infrastructure (zebra crossings, traffic lights, speed restriction hills) to ensure safe movement of children on the surrounding areas of schools | Zebra crossings, traffic lights and speed restriction hills are ensured at the surrounding areas of the schools | Zebra crossings, traffic lights and speed restriction hills aren't at the surrounding areas of all schools | Recently created zebra crossings, traffic lights and speed restriction hills |  |  | P | P | P |
| 2.3.2 | Preparation of educational material for promoting safe movement of children and pilot implementation in selected schools | Materials are prepared regarding pilot implementation | Materials prepared and placed on NCDC website | Materials are prepared and implemented in a pilot manner |  | P | P | P | P |

Strategic Objective 3: The impact of ambient and indoor air pollution on human health assessed and implemented measures to reduce the harmful effects

|  | Activity | Assessment Indicator for Implementation of a Plan | Baseline Data (2016/2015) | Target Data (2021) | Terms of Implementation |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 2017 Implemented Activities | 2018 | 2019 | 2020 | 2021 |
| MTO 3.1. - Relevant legislation harmonized according to the Association Agreement; CLRTAP and its last Protocol (Gothenburg Protocol) ratified |  |  |  |  |  |  |  |  |  |
| 3.1.1 | Relevant legislation harmonized according to the Association Agreement; CLRTAP and its last Protocol (Gothenburg Protocol) ratified | Protocol of 1999 on reduction of acidification, eutrophication and ground-level ozone, protocol on heavy metals and protocol on persistent organic pollutants are ratified | Protocols of the convention on long-range transboundary air pollution aren't ratified | All three protocols are ratified according to the UN Reporting System |  |  | P |  |  |
| 3.1.2. | Harmonization of the national legislation in line with the requirements considered under Association agreement and according to the implemenatation road map | Number of harmonized laws and subordinate acts | Determined by the harmonization process and the progress report | Current legislation and subordinate acts have been updated and new acts are enacted |  | P |  |  |  |
| MTO 3.2. - Air quality monitoring in major cities of Georgia (Tbilisi, Kutaisi, Rustavi, Batumi) carried out in accordance with EU Air Quality Directive (2008/50/EC) by 2021 |  |  |  |  |  |  |  |  |  |
| 3.2.1 | Designing National Air Quality Monitoring Network reflecting population exposure to air pollution in accordance with Georgian legislation and international recommendations | - The spatial distribution of the monitoring stations and features complies with the EU Directive - the list of observable pollutants complies with the EU Directive - The functional organogram of the monitoring network is available for interested individuals | The Air Quality Monitoring Network does not meet the requirements of the EU Directive (2008/50 / EC) | Report of the Ministry of Environment and Natural Resources Protection of Georgia regarding the design of national monitoring network |  |  |  |  | P |
| 3.2.2. | Procurement and installation of AQ monitoring equipment and laboratory infrastructure | - Number of operational monitoring stations on the territory of the country; - The number of monitoring stations conducting PM10 and PM2.5 measurements | The national control / management (NAQMN) system for monitoring the air quality is not created | Monitoring stations are installed in accordance with the air quality monitoring national control / management (NAQMN) system and reflects the exposure of the population. |  |  |  |  | P |
| 3.2.3 | Provision of the training for the monitoring network staff | Number of personnel who has undergone training | Monitoring network staff needs the training | All personnel of the monitoring stations and laboratory have undergone training |  |  |  |  | P |
| 3.2.4. | Establishment of the Quality Assurance / Quality Control (QA/QC) system | Proportional share (%) of monitoring stations, where the quality control (QA / QC) system is introduced | Quality assurance and quality control (QA / QC) system is not introduced | The quality assurance and quality control (QA / QC) system is introduced in accordance with the EU Directive (2008/50 / EC) |  | P |  |  |  |
| 3.2.5. | The monitoring system operates: collecting and processing air quality data | The number of stations that meet quality criteria | The stations' evaluation is not going on in compliance with quality criteria | The PM10, PM2.5, NO2, O3 data regarding concentrations conforms to quality standards |  | P |  |  |  |
| MTO 3.3. Health-relevant information on population exposure to air pollution and its influence on health in major cities of Georgia (Tbilisi, Kutaisi, Rustavi, Batumi) ensured by 2020; |  |  |  |  |  |  |  |  |  |
| 3.3.1. | Determining the format of information on population exposure to air pollution and its influence on health | Methodology is tested and approved | Methodology for the population exposure to air pollution and impacts on health condition isn't approved | - The system for population awareness regarding the air quality is introduced - Health risk assessment methodology is determined and approved - Data users are trained and prepared for analyzing and interpreting data |  | P |  |  |  |
| 3.3.2 | Health-relevant information on ambient air quality , in major cities of Georgia (Tbilisi, Kutaisi, Rustavi, Batumi) made available to the public | Quantity of media means (magazines, television or radio stations, web-pages) through which the population is informed, on a daily basis, about air quality of each city | Information, regarding the air pollution, population exposure and impacts on health condition, isn't available | Data regarding the concentrations in atmospheric air according to the baseline indicators (PM10, PM2.5, NO2, O3) of air quality are available for population in selected cities |  |  | P | P | P |
| 3.3.3 | Assessing impact on health of exposure to air pollution in major cities of Georgia (Tbilisi, Kutaisi, Rustavi, Batumi | - The number of cities for which the assessment of health impact (HIA) is conducted and completed - Mortality associated with atmospheric air pollution in 4 cities -SDG 3.9.1. is calculated | The assessment report on air quality management policy has not been published | Assessment report, oriented to air quality management policy, is published |  |  | P | P |  |
| MTO 3.4. Health risks due to fuels combustion (wood, gas, kerosene, etc.) for heating and cooking in households and children’s educational institutions assessed by 2021. |  |  |  |  |  |  |  |  |  |
| 3.4.1. | Selection of the health risk assessment indicators and creation of their passports, related to fuels combustion (wood, gas, kerosene, etc.) for heating and cooking in households and children’s educational institutions | Number of selected indicators (with the defined definitions and formulated methodologies) 2. Document regarding risk assessment methodology (ies) | Methodology is not defined, the assessment process isn't going on | 1. Indicators are selected according to WHO ENHIS and SDG; 3. The methodology of health impact assessment (HIA) is defined in accordance with the WHO recommendations |  |  |  | P |  |
| 3.4.2. | Determining the methodology of health risk assessment related to fuels combustion (wood, gas, kerosene, etc.) for heating and cooking in households and children’s educational institutions | Document, regarding the processing, analyzing and report preparation of risk assessment data is developed and published | Methodology is not defined, the assessment process isn't going on | Risk assessment data processing, analyzing and reporting methods are defined |  |  |  | P |  |
| 3.4.3. | Determining the methodology of data processing, analysis and report preparation for health risk assessment related to fuels combustion (wood, gas, kerosene, etc.) for heating and cooking in households and children’s educational institutions | 1. The number of children's educational-care institutions for which the assessment is conducted 2. The number of children that were covered in the study of households 3. % number of population which use each type of fuel for food preparation and heating SD+G 7.1.2. | Risk assessment system isn't implemented | Risk assessment system is implemented and functioning |  |  |  |  | P |
| MTO 3.5. Child care facilities, kindergartens, schools and public recreational settings are tobacco smoke-free by 2020 |  |  |  |  |  |  |  |  |  |
| 3.5.1 | Introduction of total ban of smoking in public places | Requisites of adopted legal act(s) | Monitoring process isn't going on | Tobacco consumption is prohibited by law in public places | P |  |  |  |  |
| 3.5.2. | Support of the effective and relevant education, awareness raising and sensitization in accordance with the 12th article of FCTC | Percentage share of persons with adequate knowledge regarding tobacco harmful influence | No training is conducted, low sensitization | Heads of child care institutions, kindergardens, schools and other public institutions are trained on the issues related to tobacco harmful effects and sensitization is increased |  | P | P | P |  |
| 3.5.3. | National survey on tobacco smoking in child care facilities, kindergartens, schools and public facilities | Tobacco consumption level / frequency in institutions under prohibition | National research has not been conducted | Information on the prohibition of tobacco consumption is available and prohibition is enforced |  |  |  |  | P |
| MTO 3.6. The Action Plan for reduction of ambient and indoor air pollution impact on children's health adopted for Tbilisi by 2020 |  |  |  |  |  |  |  |  |  |
| 3.6.1 | Harmonization of the normative basis for reduction of children exposure to outdoor and indoor air pollution with EU legislation | The number of relevant normative acts harmonized with the EU legislation | The existing normative base is to be revised, the new normative acts are to be developed | 1. An inventory of a normative base has been conducted; 2. Revision of the normative acts and elaboration of new acts are completed |  |  |  |  | P |
| 3.6.2. | Preparation of the National action plan to reduce children exposure to outdoor and indoor air pollution and its agreement with the competent state institutions | The project of a plan and the letter of agreement | National plan for reduction of outdoor and indoor air pollution impacts on children’s' health isn't elaborated | 1. The plan is prepared and agreed with all the competent public agencies 2. The plan is reviewed and the proposals from public organizations are taken into account |  |  |  |  | P |
| 3.6.3 | Endorsement and implementation reporting of the National action plan to reduce children exposure to outdoor and indoor air pollution | - Requisites of the resolution of the government of Georgia on approval of a plan - Number of the reports of responsible agencies, on the performed works | National plan for reduction of outdoor and indoor air pollution impacts on children’s' health isn't approved | 1. The plan has been approved 2. Responsible agencies provide reporting regarding measures taken with defined regular intervals |  |  |  |  | P |

Strategic objective  4:  Prevention of morbidity caused by exposure to chemical substances

|  | Activity | Assessment Indicator for Implementation of a Plan | Baseline Data (2016/2015) | Tatget Data (2021) | Terms of Implementation |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 2017 Implemented Activities | 2018 | 2019 | 2020 | 2021 |
| MTO 4.1 Harmonization of the relevant legislation in line with the Association Agreement (AA) (REACH, CLP, IHR) and other relevant legal multilateral environmental international treaties by 2020 (implemented Globally Harmonized System of Classification, Labelling and Packaging of Chemicals (GHS), Minamata Convention on mercury ratified by 2020). |  |  |  |  |  |  |  |  |  |
| 4.1.1 | Elaboration of the Law on chemicals management | Harmonization process and progress evaluation report | The Agreement process has begun with donor organizations | Approved, published |  |  | P |  |  |
| 4.1.2 | draft law / by-law on classification, labelling and packaging of Chemicals | Harmonization process and progress evaluation report | JSC N. Makhviladze Labour, Medicine and Ecological Institute started work on the aforementioned issue | Approved, published |  |  | P |  |  |
| 4.1.3 | Development of the national standard on the emissions of hazardous chemical substances, for the furniture and construction materials 2020 | Harmonization process and progress evaluation report | No information | Approved, published |  |  |  |  |  |
| 4.1.4 | Harmonize national legislation, in line with the Association Agreement; approximate national legislation to registration, Evaluation and Authorisation of Chemicals REACH | Georgian system of selective authorization of chemical substances for circulation is approximated to (REACH Regulation - (EC) No 1907/2006) system or its simplified analogue | No information | Approved, published, enacted |  |  | P |  |  |
| 4.1.5 | Harmonization of EU legislation and introduction of the production safety directive in general for ensuing safety of consumer products. Directive 2001/95 / EC of the European Parliament and the Council of 3 December 2001 on general product safety | act is published | Requires perfection | Subordinate normative act has been adopted by the goverment and published in an official journal |  |  | P |  |  |
| 4.1.6 | Harmonization of the EU legislation and introduction of European recommendations for general child consumer products safety to ensure consumer products safety „Child Product Safety Guide- Potentially dangerous products“http://www.childsafetyeurope.org/publications/info/product-safety-guide.pdf | Working version of subordinate act is published | No data | The subordinate normative act is adopted by the Government and published in the official journal |  |  | P |  |  |
| 4.1.7 | Harmonization of the EU legislation and introduction of European Directives on childrens' toys to ensure consumer products safety (Directive 2009/48/EC of the European Parliament and of the Council of 18 June 2009 on the safety of toys). (Directive 2009/48/EC of the European Parliament and of the Council of 18 June 2009 on the safety of toys). | Working version of subordinate act is published | No data | The subordinate normative act is adopted by the Government and published in the official journal |  | P |  |  |  |
| 4.1.8 | Introduce primary and secondary special packaging (hard to remove lid, labelling) for drugs,other preparations which contain hazardous chemicals, such as household cleaning products, household use pesticides etc in order to prevent poisoning | Working version of subordinate act is published | No data | The subordinate normative act is adopted by the Government and published in the official journal |  | P |  |  |  |
| 4.1.9 | Harmonization of the EU legislation and introduction of European Directives on cosmetic-perfume products safety to ensure consumer products safety Safer cosmetics for Europeans Regulation (EC) No 1223/2009 on cosmetic products | Working version of subordinate act is published | No data | The subordinate normative act is adopted by the Government and published in the official journal |  |  | P |  |  |
| 4.1.10 | Harmonization of the EU legislation and introduction of Directives on the household chemical products to ensure consumer products safety (Regulation (EC) No648/2004 | Working version of subordinate act is published | No data | The subordinate normative act is adopted by the Government and published in the official journal |  | P |  |  |  |
| 4.1.11 | "Prohibition of use of leads in paints" according to WHO recommendations to ensure consumer products safety | Working version of subordinate act is published | No data | The subordinate normative act is adopted by the Government and published in the official journal |  | P |  |  |  |
| 4.12 | Harmonization of EU legislation and introduction of Directives on biocides to ensure consumer products safety Regulation (EC) No 528/2012,DIRECTIVE 98/8/EC | Working version of subordinate act is published | No data | The subordinate normative act is adopted by the Government and published in the official journal |  | P |  |  |  |
| 4.1.13 | Harmonization of EU legislation and introduction of Euro-Directives on placement of pyrotechnics in the consumer market to ensure consumer products safety Directive 2007/23/EC | Working version of subordinate act is published | No data | The subordinate normative act is adopted by the Government and published in the official journal |  | P |  |  |  |
| 4.1.14 | Assessment of capabilities, formation of chemical safety system and creation of a relevant system for monitoring chemicals in circulation on the territory of the country. | The competent body is mentioned CLP (1272/2008/EC) According to the requirements | Work in progress | The subordinate normative act is adopted by the Government and published in the official journal |  | P |  |  |  |
| 4.1.15 | Involvement and implementation of IHR-requirements of international Health regulations in the national legislation, for controlling emergency situations caused by chemical substances | National legislation reflects IHR-requirement requirements | Work in progress | The subordinate normative act is adopted by the Government and published in the official journal |  | P |  |  |  |
| 4.1.16 | Promote the implementation of the Minamata Convention on Mercury | Action plan in relation to mercury is published | Work in progress | Legislation is published in the Legislative Herald |  | P |  |  |  |
| 4.1.17 | Elaboration of legislation on mercury (sectoral legislation amendments related to mercury) | Legislation regarding mercury is published | Work in progress | Legislation is published in the Legislative Herald |  | P |  |  |  |
| MTO 4.2 Elaboration of legislative and operational framework for collecting and sharing information on hazardous chemical substances by 2018 |  |  |  |  |  |  |  |  |  |
| 4.2.1 | Create a model of a chemical register and its operational framework for collection and information sharing on hazardous chemicals in Georgia | Register of hazardous chemical substances is developed | Working version of register is approved | Action frame is elaborated, agreed, enacted | P |  |  |  |  |
| 4.2.2 | Developproposals for the legislation revision to ensure sustainability of functioning of an operational framework | The package of legislative amendments has been developed for the sustainability of the register | Preparation of working version | The legislative amendments were reflected in the national legislation | P |  |  |  |  |
| MTO 4. 3 Risk to children from exposures to hazardous chemical substances in schools and kindergartens assessed and reduced by 2020 |  |  |  |  |  |  |  |  |  |
| 4.3.1 | Develop and implement a system for monitoring and control of indoor air pollution with hazardous chemicals in schools and kindergarten | Monitoring and control system is developing | 0%, No data | The number of schools and kindergartens is increasing by 10% annually, which is monitored, 2020 |  | ??? |  |  |  |
| 4.3.2 | Create national capacities for assessment of risk of combined exposure to multiple chemicals accordance with WHO methodology | National capabilities have been created to evaluate the risk of combined impact of some chemical substances | No data | Methodology has been developed, the number of experts with relevant preparation (trainings) |  | P |  |  |  |
| MTO 4.4 The National Program for Elimination of Asbestos Related Diseases developed by 2019 |  |  |  |  |  |  |  |  |  |
| 4.4.1 | Development of asbestos national profile in accordance with WHO recommendations (identification of the needs / deficiencies). | The number of people who are at the risk of occupational health because of the impact of asbestos, are analyzed | Working versions is developed | Government resolution on approvals of asbestos national profile |  |  |  |  |  |
| 4.4.2 | Development of the national program for elimination of asbestos-related diseases | Working version of the national program for elimination of asbestos-related diseases are agreed between agencies | Outstanding issue | Approved and enacted |  |  |  |  |  |
| MTO 4.5 Risk of exposure to hazardous chemical in rural areas assessed and reduced by 2020 |  |  |  |  |  |  |  |  |  |
| 4.5.1 | Proper management of pesticides and other agricultural chemicals for farmers, inclusion the component on educational and preventive measures | % number of farmers who have trained on educational program | No data | Implemented educational programs |  | ?? |  |  |  |
| 4.5.2 | Registration of the agrochemicals and their waste and improvement of the management | The working version of the agrochemicals and their waste registers has been developed | ? No data | Registration is developed, approved, published, updated periodically |  | ??? |  |  |  |
| 4.5.3 | Create poison control and toxicology (information) center (PoisonCenter) in line with WHO requirements | Center is established and functioning | No information | Annual report of the information consulting center (Poisoning Center) for poisoning-control and toxicology |  |  |  |  |  |
| 4.5.4 | Mapping of existing toxicology-chemistry laboratories and ensuring accessibility for the purpose to prevent, detect, provide readiness, respond and liquidate the mass non-comunicable diseases and poisoning in population | Laboratory confirmation of poisoning is possible | No information | Number of confirmed diagnoses according to the annual report of the consulting center (poisoning center) for poisoning-control and toxicology | P |  |  |  |  |
| 4.5.5 | Construction of the disposal landfill for the industrial toxic wastes, which are generated in the territory of the country | The government's resolution regarding polygon construction has been developed and approved | Outstanding issue | Construction of the polygon is in progress | ??????? |  |  |  |  |

Strategic objective  5. Integration of health issues in climate change adaptation and mitigation policies

|  | Activity | Assessment Indicator for Implementation of a Plan | Baseline Data (2016/2015) | Target Data (2021) | Terms of Implementation |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 2017 Implemented Activities | 2018 | 2019 | 2020 | 2021 |
| MTO 5.1 Evaluate vulnerability to climate change, health impacts and adaptation (health care aspects) including assessment of existing and anticipated risks related to health impacts of climate change |  |  |  |  |  |  |  |  |  |
| 5.1.1 | Assessment of current and future risks of climate change on population health • Frame and scope the assessment • define the geographical region and health outcomes of interest; • identify the questions to be addressed and steps to be included • identify the policy context for the assessment • establish a project team and management plan • establish a stakeholder process • develop a communications plan | The final project of the report, which analyzes the existing and expected risks of vulnerability to climate change, has been developed and approved | Outstanding issue | Report is published |  | P |  |  |  |
| 5.1.2 | Conducting the vulnerability and adaptation assessment. • Establishing baseline conditions on human health risks of climate change, determining current capacity of public health policies and programmes for addressing these risks | Determination of the public health policies and programs needed to reduce the risks of climate current change impacts on human health • Climate-sensitive health care risks • Vulnerable population groups and regions risks - • Existing capabilities of the other sectors of health care for reduction of risks | Outstanding issue | Report is approved and published |  | P |  |  |  |
| 5.1.3 | Conducting health impact assessment by: • projected future health risks and impacts under climate change, including the most vulnerable populations and regions, which will be determined for the coming decade • estimating the additional burden of adverse health outcomes due to climate change | Definition of additional programs for the public-health and health-care policies to identify the current and expected health risks, and identification of the resources needed to overcome potential barriers during implementation | Outstanding issue | National health care reports (interim and final) of the vulnerability to climate change, impact and adaptation is approved |  |  |  | P |  |
| 5.1.4 | Estimate the costs of action and of inaction to protect health | Assessment of the activity costs and health-care costs of inactivity. |  | Expenses in USD currency and their share in relation to GDB |  |  | P |  |  |
| 5.1.5 | Capacity building of national experts based on international experience and provision of project management team with technical means | Preparation of the experts and provision of project management group with technical means | Outstanding issue | Number of trained experts Number of technical means |  | P |  |  |  |
| MTO 5.2 Develop National Health Care Adaptation Strategy and Action Plan, among them, for medical facilities |  |  |  |  |  |  |  |  |  |
| 5.2.1 | Elaboration of NationalHealth Climate Change Adaptation Strategy - To create vision - Describe the size and the nature of the problem - Identify effective interventions - Develop the strategies and priorities - Create a Strategy Action Plan | National Adaptation Strategy has been developed and includes all necessary public health-care activities | Outstanding issue | The final draft is approved and published |  |  | P |  |  |
| 5.2.2 | Elaboration of an Heat-Health action plan for medical institutions | Impact of hit waves on the health has been reduced | Outstanding issue | Reports of deaths analysis results due to high temperature impacts |  | P |  |  |  |
| MTO 5.3 Harmonize the legislation with regard to the requirements of the UNFCCC Convention and assessment of health outcomes |  |  |  |  |  |  |  |  |  |
| 5.3.1 | Inventory of health-care legislation and identification of those acts that require change | All sectors, laws and subordinate acts are defined |  | Number of identified sectors and legislative acts |  |  | P |  |  |
| 5.3.2 | Harmonization of health-care legislation with the association agreement and convention | New legislative acts have been developed |  | Number of acts are harmonized and adapted |  | P |  |  |  |
| MTO 5.4 Health care facilities reduce the share of greenhouse gas emissions X% in national emissions by 2020 (from 2017), including introduction of renewable energy use in several hospitals within the framework of the pilot project. |  |  |  |  |  |  |  |  |  |
| 5.4.1 | Determination of the share of greenhouse-gas emissions from the medical institutions, in the country's general emissions | Distribution of medical institutions' greenhouse-gas emissions | Outstanding issue | The volume and percentage of greenhouse-gas emissions from the health sector |  | ?? |  |  |  |
| 5.4.2 | Detailed analysis of energy efficiency in the health system | Recommendations for the use of energy efficient buildings and renewable energy resources in the hospitals |  | The final draft of the report on analysis and recommendations has been developed |  |  | P |  |  |
| 5.4.3 | Assessment of hospital safety | Assessment of the security and stability of the buildings, with taking into account the requirements of energy efficiency |  | The number and percentage amount of the hospitals has been assessed |  |  | P | P |  |
| 5.4.4 | Introduction of the use of the renewable energy, within the frameworks of the pilot project, in several hospitals | Reduction of the share of hit-gas emissions from hospitals at municipal level | Outstanding issue | Evaluation of greenhouse gas emissions reduction after 6 months after installation of energy-efficient buildings and renewable energy sources |  |  |  | P |  |
| 5.4.5 | Increase awareness of healthcare personnel in energy-efficiency issues | Reduction of greenhouse-waves emissions Reduction of the annual costs of the hospital on heating and electricity | Outstanding issue | The manual has been developed The health-care personnel is trained Posters and booklets are published |  |  | P | P | P |

Strategic Objective 6. Improving Governance of existing "Environment and Health “System in Georgia

|  | Activity | Assessment Indicator for Implementation of a Plan | Baseline Data (2016/2015) | Target Data (2021) | Terms of Implementation |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 2017 Implemented Activities | 2018 | 2019 | 2020 | 2021 |
| Task 6 . 1 Institutional Strengthening of the Existing Environment and Health System |  |  |  |  |  |  |  |  |  |
| 6.1.1 | Gap Assessment of the Existing Environmental Health System, Mapping of functions of all stakeholders versus EH challenges | Shortcomings and needs are identified | Outstanding issue | Report is available | P |  |  |  |  |
| 6.1.2. | The environmental and health information system is set up 2018, environmental and health indicators are developed in relation to SDG | Environmental and health indicators are developed in relation to SDG. | 5 indicators | The environment and health information system is updating with 15 indicators |  | P |  |  |  |
| 6.1.3 | The existing system/structure of the environmental health is in compliance with the similar system /structure operating in the EU | All sectoral laws and subordinate normatives have been reviewed The responsibilities are defined and agreed between different agencies | Outstanding issue | Annual reports |  | P |  |  |  |
| MTO 6.2 Implementation of National Environment and Health Action Plan |  |  |  |  |  |  |  |  |  |
| 6.2.1 | The NEHAP inter-agency coordination group has been created and operates for 2017. | The framework and format of the relationship is established | Work in progress |  |  | P |  |  |  |
| 6.2.2 | Strengthening human resources for implementation of NEHAP in Georgia | Masters and Doctoral Programs Planning / Implementation in the field of environmental health, Qualification upgrading courses for acting socialists | Work in progress, data should be specified, it is incomplete | 100% of acting specialist have undergone the training |  | P |  |  |  |
| 6.2.3 | Mapping of proper laboratory capabilities, provide for/ensure availability | Detailed and reliable information on laboratories was prepared, the existing laboratories are assigned responsibilities It was planned to establish new laboratories To eliminate the gaps | Outstanding issue | 1. The assessment of needs has been completed. 2. 50% of needs that will be covered by existing laboratories. 3. % of gaps is assessed, which will be covered by a new laboratory |  | P |  |  |  |
| 6.2.4 | "Development of New Technical Regulations for Medical Waste Management" in accordace with the waste management code, methodological assistance and organization of trainings for medical institutions 2017-18yy. | The training materials have been developed and retraining of the medical personnel is underway | Work in progress | 100% of the staff, which is responsible for the management of medical wastes, has been retrained | P |  |  |  |  |
| 6.2.5 | Development of the national action plan "Transport, Environment and Health", 2018 | Action plan is approved | Outstanding issue | The results / report of the action plan execution monitoring |  | P | P |  |  |

Strategic Objective  7: Reduce the impacts of physical agents  of the environment by 2021

|  | Activity | Assessment Indicator for Implementation of a Plan | Baseline Data (2016/2015) | Target Data (2021) | Terms of Implementation |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 2017 Implemented Activities | 2018 | 2019 | 2020 | 2021 |
| MTO 7.1 Reduce health impact of noise by 2021 |  |  |  |  |  |  |  |  |  |
| 7.1.1 | Monitor noise and exposure to noise in public bildings where childrenspend time, planning and implementing measures to reduce noise exposure | % number of schools and kindergardens, where the noise impact has been reduced by 2021 | No data | % number of schools and kindergartens where the monitoring has been conducted, 2021 |  |  |  | P | P |
| 7.1.2 | Improvement of urban and infrastructure planning for reduction of noise impact | The report of the measures taken: 1. Assessment of the needs in Tbilisi and other large cities for improving noise level control, monitoring and supervision system; number of identified locations where the monitoring is conducted; noise impact map in Tbilisi, Kutaisi, Batumi and Rustavi. The number of low noise zones is shown. 2. Organizational and technical measures are developed and implemented for noise reduction - Organization of traffic flow; restriction / prohibition of the movement of heavy trucks on weekends and night hours - Speed reduction - A special asphalt that does not create noise - Building of sound-barrier and anti-noise walls - Greening plans for cities and districts. | Work in progress | Noise impact map and assessment of the impact risk on population health in Tbilisi, Kutaisi, Batumi and Rustavi. | ??????? |  |  |  |  |
| MTO 7.2 Reduce health impact of anthropogenic ionizing radiation by 2021 |  |  |  |  |  |  |  |  |  |
| 7.2.1. | The review and update of the security system related to medical activities, 2020 | Study programs include labor safety issues during radiation procedures | Work in progress | Monitoring report for the individual doses is available |  |  |  | P |  |
| 7.2.2. | Readiness and responsive actions for prevention of nuclear and radiation accident, as well as post-accident consequences | Training of the personnel, working at ionizing sources, has been conducted | Work in progress | 100% readiness of the personnel, working at ionizing radiation, for nuclear and radiation accidents |  |  |  | P |  |
| MTO 7.3 Reduce impact of Radon on population |  |  |  |  |  |  |  |  |  |
| 7.3.1 | Implementation of radiation monitoring in underground buildings On the basis of geological prediction in the country | Preparation of a map on radon monitoring results | Outstanding issue | % number of kindergardens, schools, hospitals and underground structures, where the planning and implementation of the construction works have been conducted, for the reduction of radon impact | ????? |  |  |  |  |
| 7.3.2 | Raising of awareness of the population and stakeholders, regarding preventive measures related to radon. | Number of developed / prepared information materials and activities The share of the population, in informational events | Outstanding issue | The population is periodically provided with information. The website shows educational materials |  |  |  | P | P |
| 7.3.3 | Implementation of interventions in the building with high radon concentrations. | % number of structures, where construction works have been conducted for the reduction of radon impacts. | Outstanding issue | The report on the conducted measures and the planned activities, shown with stages | ???? |  |  |  |  |
| MTO 7.4 Reduce impact of ultraviolet radiation reduction by 2021 |  |  |  |  |  |  |  |  |  |
| 7.4.1 | Informing population, school personnel and parents regarding harmful effects of excessive ultraviolet irradiation and preventive measures. | Training materials have been developed and reflected in educational programs, awareness campaigns were conducted | Work in progress. The population is informed during the summer period | Information is available for the population, TV-programs, etc. |  |  |  | P | P |
| MTO 7.5 Reduce health impact of electromagnetic fields by 2021 |  |  |  |  |  |  |  |  |  |
| 7.5.1 | Elaboration / enactment and execution of the legislation for reduction of impact of electromagnetic fields; meeting safety norms with respect to all possible sources | The action plan is approved for reduction of electromagnetic fields generated by all possible sources | Outstanding issue | The existing monitoring and risk assessment system has been improved |  | P | P | P |  |
| MTO 7.6 Education / training and preparedness of the population for emergency situations caused by natural disasters such as earthquakes, floods and other extreme weather events as well as technogenic disasters |  |  |  |  |  |  |  |  |  |
| 7.6.1 | Conducting training and practical applications, where the needs for children, adolescents and pregnant women will be considered, for the prepadnes in emergency situations and providing adequate response | Report of measures, to be conducted annually, with showing the website (information supplied by the mass media). | Work in progress Information is periodically distributed | The relevant information is available for the population |  | P |  |  |  |

Annex 2. Strategy Implementation Action Plan 2017-2021

Vision

Reduce and avoid the burden of disease associated with the environment, on the basis of reduction of human exposure to the ecological risks

Goal

Improve the quality of the environment and human health, on the basis of coordinated actions and ecologically sustainable development, for achieving Sustainable Development Goals

| Tasks | Activity | Expected Result | Responsible Agency | Partner Organization | Budget on an annual basis |  |  |  |  | Funding Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Implemented activities in 2017 (GEL) | 2018 (GEL) | 2019 (GEL) | 2020 (GEL) | 2021 (GEL) |  |
| Task 1. Ensuring public health through improving access to safe water and sanitation, ensuring access, for every child, to safe water and sanitation, 2021 |  |  |  |  |  |  |  |  |  |  |
| 1.1 National legislation and policy frameworks on protection of water resources, drinking-water supply and sanitation reviewed and updated by 2021 | 1.1.1 Revision of existing legislation, regarding water resources, drinking water quality and sanitations, that require harmonization with international requirements | All sectoral laws and subordinate norms have been reviewed | MOLHSA , MOA, NCDC | MoENR |  | 10 000 | 10 000 |  |  | State budget Twining Ge22 |
|  | 1.1.2. Making changes in the national policy for drinking water quality and sanitation and regulatory normative documents accordint to the recommendation of the WHO | The preventive control is introduced for drinking water and sanitation risks in recreation zones, according to WHO recommendation | MOA, MOLHSA NCDC | All stakeholders |  |  | 10 000 |  |  | State budget Twining Ge22 WHO expert support |
|  | 1.1.3 Harmonization of national legislation and adoption of new water law in accordance with the European Union Association Agreement | Final Draft Law in place (March, 2017) | MOE | All stakeholders |  | 30 000 |  |  |  | Donor support will be needed for Regulatory Impact Assessment -- RIA |
|  | 1.1.4. Ratification of the protocol "Water and Health" | Ratification status, provision of the Secretariat with information and approvale of the coordination council | Georgian government |  | Outstanding issue |  |  |  |  |  |
|  | 1.1.5. Elaboration and adoption of National priority targets, indicators and implementation timelines according to the protocol provisions | Priority national goals, indicators and estimated deadlines are approved by the government | Georgian government |  |  | 10 000 |  |  |  | State budget Twining Ge22 WHO expert support |
| Task 1.2 1.2. Establishe effective surveillance systems for drinking water quality and water-born diseases by 2017-2021 | 1.2.1 Conduct baseline analysis of the quality of surveillance system of drinking water and implement necessary interventions for its improvement | The current state supervision system is reviewed and concrete measures are set | MOLHSA NCDC |  |  | 10 day international Experts 23 000 |  |  |  | Donor support will be Needed State budget Twining Ge22 |
|  | 1.2.2. Conduct baseline analysis of the surveillance system for waterborne diseases and implement necessary interventions for its improvement | The current state supervision system is reviewed and concrete measures are set | MOLHSA NCDC |  |  | 5000 |  |  | 5000 | State budget |
|  | 1.2.3. Conduct state routine monitoring on the quality of drinking water and creation of the unified database | An unified database on drinking water quality has been developed, functioning and is updating regularly. | GNERC | All stakeholders |  |  | 70 000 |  |  | State budget Twining Ge22 WHO expert support Donor support will be needed |
| 1.3 Ensure continuous supply of the population with drinking water meeting national and international requirements | 1.3.1. Inventory of urban and rural water supply systems | The report of the inventory of water supply is published | MORDI | MOLHSA MOE Local self-government |  |  | -- |  |  | Donor support will be Needed MICS survey UNICEF |
|  | 1.3.2. Determination of the rehabilitation, modernization and improvement needs for urban and rural water supply systems, for ensuring safe drinking water supply | Enhancing access to safe water and adequate sanitary conditions | MORDI | MOLHSA MOE Local self-government |  |  | 100 000 |  |  | Donor support will be needed |
|  | 1.3.3 Preparation of gradual-introduction plan of inclusion/implementation of WSP approaches in the urban and rural water supply systems | Improvement of drinking water quality | MORDI MOLHSA | WHO Local self-government |  |  | 30 000 |  |  | Donor support will be needed WHO expert support |
|  | 1.3.4. Conduct education and capacity building programmes for staff involved in urban and rural water supply systems | Implementation of a permanently-acting training cycle, professional retraining of the employees preparing drinking water throughout the country | MORDI |  |  | 12 regions 30 000 |  |  |  | State budget Twining Ge22 WHO expert support Donor support will be needed |
|  | 1.3.5. Implementation of awareness raising campaigns for population and providing timely and objective information regarding drinking water quality. Raise awareness of population regarding prevention of contamination of bathing waters | Prevention of waterborne diseases, increase awareness of the population | MOLHSA NCDC |  | 10 000 | 10 000 | 10 000 | 10 000 | 10 000 | State budget |
| 1.4 Provision of population of the country with adequate sanitation | 1.4.1 Inventory of the sewage / sanitation systems of the urban and rural area | The inventory report of sewage systems is published, the number of the population, having access to "improved" and "non-improved" sanitary / sewage facilities, will be defined | MORDI | NCDC Local self-government |  |  |  |  |  | Donor support will be Needed MICS survey UNICEF |
|  | 1.4.2. Develop complex measures for improving the state of sewage / sanitation systems in urban and rural areas to protect water resources' pollution from sewage wastewater | Improvement and modernization measures of sewage systems are defined | Georgian government | All stakeholders |  |  | 30 day international Experts 70 000 |  |  | Donor support is required |
| 1.5 Improvement of drinking water, sanitation and hygiene (WASH) conditions in educational, health care and recreational facilities/sites and in RIDPs settlements | 1.5.1. Planning of priority mesures in educational facilities fo improvement of WASH condition | Improvement of access to continuous safe drinking water and adequate sanitation, Improvement activities of hygienic conditions is going on with constant supervision Accessibility has been significantly increased on safe water and sanitation with implementing priority measures Continuous supervision has improved hygienic conditions | MES MOLHSA NCDC | MORDI |  |  | 10000 |  |  | UNICEF WASH survey |
|  | 1.5.2. Planning priority measures in Health care facilities for improvement WASH conditions | Improvement of access to continuous safe drinking water and adequate sanitation, Improvement activities of hygienic conditions is going on with constant supervision Accessibility has been significantly increased on safe water and sanitation with implementing priority measures Continuous supervision has improved hygienic conditions | MOLHSA NCDC |  |  | 5000 |  |  |  | State budget |
|  | 1.5.3. Undertake baseline assessment and plan and prioritize activities in RIDPs settlements for improvement of WASH | Improvement of access to continuous safe drinking water and adequate sanitation, Improvement activities of hygienic conditions is going on with constant supervision Accessibility has been significantly increased on safe water and sanitation with implementing priority measures Continuous supervision has improved hygienic conditions | MRA MOLHSA , NCDC | Local self-government |  |  |  | 30000 |  | Donor support is required IOM National survey |
|  | 1.5.4. Developing the monitoring system for the water quality in swimming pools | The structure of the monitoring system is available Responsibilities between agencies are defined A report is available online | MOLHSA |  |  |  | 10 day international Experts 23 000 |  |  | Donor support will be Needed State budget Twining Ge22 |
|  | 1.5.5. Identify recreational/bathing areas and monitor their water quality | The recreation and bathing areas are identified Seasonal monitoring of water quality is carried out Water quality assessment is carried out during unexpected short-term pollution. The list of permitted sanitary areas was created The information is available | MOE |  |  | 10 day international Experts 23 000 |  |  |  | Donor support will be Needed State budget Twining Ge22 |

| Tasks | Activity | Expected Result | Responsible Agency | Partner Organization | Budget on an annual basis |  |  |  |  | Funding Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Implemented activities in 2017 (GEL) | 2018 (GEL) | 2019 (GEL) | 2020 (GEL) | 2021 (GEL) |  |
| 2: Improved children accessibility to healthy and safe environments and settings of daily life, promoting their increased physical activity by 2021 |  |  |  |  |  |  |  |  |  |  |
| MTO 2.1 Relevant legislation harmonized according to the Association Agreement by 2021 | 2.1.1. Identification of relevant legislation in the field of child safety and its relevant harmonization | The law is identified and harmonized in child safety field | MOLHSA MES MORDI MOSYA |  |  |  |  | 10 000 | 10 000 | State budget, EU funds and other sources |
| MTO 2.2. Increased proportion of schools and kindergartens equipped with (or with access to) adequate facilities for safe physical activity of children by x%…in 2020 as compared to 2016) | 2.2.1. Introduction of adequate objects and equipment definitions to ensure safe physical activity | Safe exercise and play are provided in schools and kindergardens | MOLHSA MOE MORDI MES MOSYA Tbilisi City Hall |  |  |  | 10 000 |  |  | State budget, EU funds and other sources |
|  | 2.2.2. Advocate national programs in schools and kindergardens for ensuring safe physical activity | National programs are introduced in schools and kindergardens | MOLHSA , MES |  |  | 5000 | 5000 | 5000 | 5 000 | State budget |
|  | 2.2.3. Increase availability of physical activitiues outside the school institutions | New sports grounds and squares are open | MOLHSA , MES, MORDI Local self-government |  |  | 5000 | 5000 | 5000 | 5000 | State budget, EU funds and other sources |
|  | 2.2.4. Preparation and dissemination of educational materials, fliers for the purpose to promote physical activity | Materials arevprepared and disseminating | MES, MOLHSA , NCDC |  |  | 5000 | 5000 | 5000 | 5000 | State budget |
| MTO 2.3. In comparison to 2016, increase share of schools with adjacent territories safe for children’s movement by 2020 | 2.3.1. Advocate the infrastructure (zebra crossings, traffic lights, speed restriction hills) to ensure safe movement of children on the surrounding areas of schools | New zebra crossings, traffic lights are opened | MES, MOLHSA , NCDC |  |  |  | 10000 | 10000 | 10000 | State budget |
|  | 2.3.2. Preparation of educational material for promoting safe movement of children and pilot implementation in selected schools | Materials are prepared, pilot introduction is going on | MES, MOLHSA , NCDC |  |  |  |  |  |  | State budget |

| Tasks | Activity | Expected Result | Responsible Agency | Partner Organization | Budget on an annual basis |  |  |  |  | Funding Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Implemented activities in 2017 (GEL) | 2018 (GEL) | 2019 (GEL) | 2020 (GEL) | 2021 (GEL) |  |
| 3: The impact of ambient and indoor air pollution on human health assessed and implemented measures to reduce the harmful effects |  |  |  |  |  |  |  |  |  |  |
| 3.1. - Relevant legislation harmonized according to the Association Agreement; CLRTAP and its last Protocol (Gothenburg Protocol) ratified | 3.1.1 Relevant legislation harmonized according to the Association Agreement; CLRTAP and its last Protocol (Gothenburg Protocol) ratified | Protocol 1999 on reduction of acidification, eutrophication and ground-level ozone, protocol on heavy metals, and protocol on persistent organic pollutants are ratified | MoENR | Georgian Parliament MFA |  |  |  |  |  | Donor support will be Needed |
|  | 3.1.2. Harmonization of the national legislation in line with the requirements considered under Association agreement and according to the implemenatation road map | Current legislation and subordinate acts have been updated and new acts are enacted | MoENR | სშჯს MORDI, MOA, MFA | 10 day national experts 10 000 10 day international Experts 23 000 | 30 day international Experts 70 000 |  |  |  | minor donor support has been requested from EU - (the law shall set limit values for SO2, NO2, NOx, PM10, PM2,5, lead, benzene, CO, arsenic, cadmium, mercury, nickel and PAHs) |
| 3.2. - Air quality monitoring in major cities of Georgia (Tbilisi, Kutaisi, Rustavi, Batumi) carried out in accordance with EU Air Quality Directive (2008/50/EC) by 2021) | 3.2.1. Designing National Air Quality Monitoring Network reflecting population exposure to air pollution in accordance with Georgian legislation and international recommendations | 1. Spatial distribution of monitoring stations is supportive for reflecting the exposure of population to air pollution 2. Monitoring stations' indicators are defined and the list of observable pollutants is determined 3. The functional organogram of the monitoring network is defined | MoENR | MOLHSA ; Municipalities of big cities; |  |  |  |  | to be determined by donor, 30 day international Experts 70 000 | Support has been requested from EU and other potential donors but not confirmed |
|  | 3.2.2. Procurement and installation of AQ monitoring equipment and laboratory infrastructure | Monitoring stations are installed according to the national air quality monitoring national control / management (NAQMN) and reflects the exposure of the population (2017-2021) | MOE | Municipalities of relevant cities |  |  |  |  | open | Support has been requested from EU and other potential donors but not confirmed |
|  | 3.2.3. Provision of the training for the monitoring network staff | Personnel of the monitoring stations and laboratory have undergone education / training (2017) | MOE | Municipalities of relevant cities; |  |  |  |  | open | Support has been requested from EU and other potential donors but not confirmed |
|  | 3.2.4. Establishment of the Quality Assurance / Quality Control (QA/QC) system | Quality assurance and quality control (QA / QC) system is implemented in accordance with Euro-Directive (2008/50 / EC) (2017) | MOE | Organization responsible for operation of stations |  | 20 day national experts 20 000 20 day international Experts 66 000 |  |  |  | Support has been requested from EU and other potential donors but not confirmed |
|  | 3.2.5. The monitoring system operates: collecting and processing air quality data | PM10, PM2.5, NO2, O3 data conform to quality standards (2017-2021) | MOE | Monitoring network operator |  | 20 day national experts 20 000 20 day international Experts 66 000 |  |  |  | Support has been requested from EU and other potential donors but not confirmed |
| 3.3. Health-relevant information on population exposure to air pollution and its influence on health in major cities of Georgia (Tbilisi, Kutaisi, Rustavi, Batumi) ensured by 2020; | 3.3.1. Determining the format of information on population exposure to air pollution and its influence on health | 1. The system for informing population regarding air quality is introduced 2. The health-risk assessment methodology is defined and approved 3. Data users are trained and prepared for data analysis and interpretation | MOLHSA , NCDC | MOE |  | 10 000 |  |  |  | State budget |
|  | 3.3.2Health-relevant information on ambient air quality , in major cities of Georgia (Tbilisi, Kutaisi, Rustavi, Batumi) made available to the public | Data on concentrations in atmospheric air, in accordance with the air baseline indicators (PM10, PM2.5, NO2, O3) are available for the population, in selected towns | MOE | MOLHSA , Georgian National Academy of Sciencesmedia |  |  | 15 000 | 5000 | 5000 | State budget WHO expert support |
|  | 3.3.3 Assessing impact on health of exposure to air pollution in major cities of Georgia (Tbilisi, Kutaisi, Rustavi, Batumi ) | Assessment report, oriented on air quality management policy, has been prepared | MOLHSA NCDC |  |  |  | 10000 | 50000 |  | State budget WHO expert support |
| 3.4. Health risks due to fuels combustion (wood, gas, kerosene, etc.) for heating and cooking in households and children’s educational institutions assessed by 2021. | 3.4.1. Selection of the health risk assessment indicators and creation of their passports, related to fuels combustion (wood, gas, kerosene, etc.) for heating and cooking in households and children’s educational institutions | 1. Indicators are selected according to WHO ENHIS and SDG; 3. The methodology of health impact assessment (HIA) is defined in accordance with WHO recommendations. | MOLHSA NCDC | MOE MOES GEOSTAT |  |  |  | 20 day national experts 20 000 30 day international Experts 70 000 |  | Donor support will be Needed WHO expert support |
|  | 4.2. Determining the methodology of health risk assessment related to fuels combustion (wood, gas, kerosene, etc.) for heating and cooking in households and children’s educational institutions | Methods for risk assessment data processing, analysis and report preparation are defined | MOLHSA NCDC | MOE MOES GEOSTAT |  |  |  | 20 day national experts 20 000 20 day international Experts 66 000 |  | Donor support will be Needed WHO expert support |
|  | 4.3. Determining the methodology of data processing, analysis and report preparation for health risk assessment related to fuels combustion (wood, gas, kerosene, etc.) for heating and cooking in households and children’s educational institutions | The risk assessment system is introduced and functioning | GEOSTAT | MOE MOES |  |  |  | 20 day national experts 20 000 20 day international Experts 66 000 |  | Donor support will be Needed WHO expert support |
| 3.5. Child care facilities, kindergartens, schools and public recreational settings are tobacco smoke-free by 2020 | 5.1. Introduction of total ban of smoking in public places | Tobacco consumption in public places is prohibited by the law | GEO Government |  | completed |  |  |  |  | State budget |
|  | 5.2. Support of the effective and relevant education, awareness raising and sensitization in accordance with the 12th article of FCTC | Heads of child care institutions, kindergardens, schools and other public institutions are trained on the issues related to tobacco harmful effects and sensitization is increased | MOLHSA NCDC | MOES GEOSTAT |  | 38 000 | 38000 | 38000 |  | State budget |
|  | 5.3. National survey on tobacco smoking in child care facilities, kindergartens, schools and public facilities | Information on the prohibition of tobacco consumption is available and prohibition is enforced | MOLHSA NCDC | MOES GEOSTAT |  |  |  | 38000 |  | State budget |
| 3.6 The Action Plan for reduction of ambient and indoor air pollution impact on children's health adopted for Tbilisi by 2020 | 3.6.1. Harmonization of the normative basis for reduction of children exposure to outdoor and indoor air pollution with EU legislation | 1. An inventory of a normative base has been conducted; 2. Revision / review of the normative acts and the elaboration of new version is completed | MOLHSA | MOE MOES MESD MORDI |  |  |  |  | 35000 | Donor support will be Needed WHO expert support |
|  | 3.6.2. Preparation of the National action plan to reduce children exposure to outdoor and indoor air pollution and its agreement with the competent state institutions | 1. The plan is prepared and agreed with all the competent public authorities 2. The plan has been discussed and the proposals of public organizations are taken into account | MOE MOES MESD MORDI |  |  |  |  |  | 35000 | Donor support will be Needed WHO expert support |
|  | 3.6.3. Endorsement and implementation reporting of the National action plan to reduce children exposure to outdoor and indoor air pollution | 1. The plan has been approved 2. Responsible agencies provide reporting regarding measures taken with defined regular intervals | WHO UNICEF |  |  |  |  |  | 10000 |  |

| Tasks | Activity | Expected Result | Responsible Agency | Partner Organization | Budget on an annual basis |  |  |  |  | Funding Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Implemented activities in 2017 (GEL) | 2018 (GEL) | 2019(GEL) | 2020 (GEL) | 2021 (GEL) |  |
| 4: Prevention of morbidity caused by exposure to chemical substances |  |  |  |  |  |  |  |  |  |  |
| 4.1 Harmonization of the relevant legislation in line with the Association Agreement (AA) (REACH, CLP, IHR) and other relevant legal multilateral environmental international treaties by 2020 (implemented Globally Harmonized System of Classification, Labelling and Packaging of Chemicals (GHS), Minamata Convention on mercury ratified by 2020). | 4.1.1 Elaboration of the Law on chemicals management | The law is enacted | MoENR |  |  |  | to be determined by donor, 50-50 day for national international Experts |  |  | donor support has been requested (UNIDO, GEF); green light from GEF awaited |
|  | 4.1.2. draft law / by-law on classification, labelling and packaging of Chemicals | The implementation process is going on GHS / CLP, a form of information paper for safe handling of chemical substances, as well as other sub-legal normative acts | MOE MOLHSA | UNECE UNDP |  |  | to be determined by donor, 50-50 day for national international Experts |  |  | donor support has been requested (UNIDO, GEF); green light from GEF awaited |
|  | 4.1.3 Development of the national standard on the emissions of hazardous chemical substances, for the furniture and construction materials 2020 | Enacted | MOLHSA NCDC | MESD MOE |  |  | to be determined by donor, 10 day national experts 10 000 |  |  | Donor support will be Needed Twining GE22 |
|  | 4.1.4. Harmonize national legislation, in line with the Association Agreement; approximate national legislation to registration, Evaluation and Authorisation of Chemicals REACH | Introduction process of the approximate model with REACH is in progress, 2021 | MoLNSA NCDC | UNDPWHO |  |  | to be determined by donor |  |  | Donor support will be WHO expert support |
|  | 4.1.5. Harmonization of EU legislation and introduction of the production safety directive in general for ensuing safety of consumer products. Directive 2001/95 / EC of the European Parliament and the Council of 3 December 2001 on general product safety | Enacted, quality monitoring process is in progress | MOLHSA NCDC | MOE MESD |  |  | to be determined by donor, |  |  | Donor support will be Needed Twining GE22 |
|  | 4.1.6. Harmonization of the EU legislation and introduction of European recommendations for general child consumer products safety to ensure consumer products safety „Child Product Safety Guide- Potentially dangerous products“http://www.childsafetyeurope.org/publications/info/product-safety-guide.pdf | Enacted, quality monitoring process is in progress | MESD NCDC |  |  |  | 10 day national experts 10 000 to be determined by donor |  |  | Donor support will be Needed Twining GE22 |
|  | 4.1.7. Harmonization of the EU legislation and introduction of European Directives on childrens' toys to ensure consumer products safety (Directive 2009/48/EC of the European Parliament and of the Council of 18 June 2009 on the safety of toys). (Directive 2009/48/EC of the European Parliament and of the Council of 18 June 2009 on the safety of toys). | Enacted, quality monitoring process is in progress | MESD |  | to be determined by Georgian Governmen |  |  |  |  | State budget Twining GE22 |
|  | 4.1.8 Introduce primary and secondary special packaging (hard to remove lid, labelling) for drugs,other preparations which contain hazardous chemicals, such as household cleaning products, household use pesticides etc in order to prevent poisoning | Enacted, quality monitoring is in progress | MESD |  | to be determined by Georgian Governmen |  |  |  |  | State budget Twining GE22 UNICEF |
|  | 4.1.9. Harmonization of the EU legislation and introduction of European Directives on cosmetic-perfume products safety to ensure consumer products safety Safer cosmetics for Europeans Regulation (EC) No 1223/2009 on cosmetic products | Enacted, introduced | MOLHSA NCDC | WHO UNICEF |  |  | 10 day national experts 10 000 10 day international Experts 23 000 |  |  | State budget Twining GE22 |
|  | 4.1.10. Harmonization of the EU legislation and introduction of Directives on the household chemical products to ensure consumer products safety (Regulation (EC) No648/2004 | Enacted, quality monitoring process is in progress | MOLHSA NCDC | MoENR MESD |  |  | 10 day national experts 10 000 10 day international Experts 23 000 |  |  | Donor support will be Needed Twining GE22 WHO expert support |
|  | 4.1.11. "Prohibition of use of leads in paints" according to WHO recommendations to ensure consumer products safety | Enacted, quality monitoring process is in progress | MOLHSA NCDC | MoENR MESD |  |  | 5 day national experts 5 000 |  |  | Donor support will be Needed Twining GE22 WHO expert support |
|  | 4.1.12. Harmonization of EU legislation and introduction of Directives on biocides to ensure consumer products safety Regulation (EC) No 528/2012,DIRECTIVE 98/8/EC | Enacted, quality monitoring process is in progress | MOLHSA NCDC | MOE MESD MOF |  | to be determined by donor |  |  |  | donor support has been requested UBA/WHO |
|  | 4.1.13. Harmonization of EU legislation and introduction of Euro-Directives on placement of pyrotechnics in the consumer market to ensure consumer products safety Directive 2007/23/EC | Enacted, registration updating process is going on | MoIAMOLHSA NCDC | MOENR MESD |  | to be determined by donor 10 day national experts 10 000 10 day international Experts 23 000 |  |  |  | Donor support will be Needed Twining GE22 |
|  | 4.1.14. Assessment of capabilities, formation of chemical safety system and creation of a relevant system for monitoring chemicals in circulation on the territory of the country | Enacted, quality monitoring process is in progress | MOLHSA MIA | MOE MESD |  |  | to be determined by donor | National Survey |  | Donor support will be Needed |
|  | 4.1.15 Involvement and implementation of IHR-requirements of international medicine-sanitary rules in the national legislation, for controlling emergency situations caused by chemical substances | National legislation reflects IHR-requirement requirements) | MoLHSA NCDC |  |  | 10000 | to be determined by donor |  |  | State budjet Donor support will be Needed |
|  | 4.1.16. Promote the implementation of the Minamata Convention on Mercury | Mercury-related sectoral legislation is published and enacted | MOE | MOLHSA MOA MESD MOF | to be determined by donor |  |  |  |  | ongoing GEF / UNDP project funding (June 2017) |
|  | 4.1.17. Elaboration of legislation on mercury (sectoral legislation amendments related to mercury) | Mercury-related sectoral legislation is published and enacted | MOE | MOLHSA MOA MESD MOF |  |  |  |  |  | open, donor support will be required (likely to be requested from GEF / UNDP, UNEP….) |
| Task 4 MTO 4.2 Elaboration of legislative and operational framework for collecting and sharing information on hazardous chemical substances by 2018 | 4.2.1. Create a model of a chemical register and its operational framework for collection and information sharing on hazardous chemicals in Georgia) | Action Framework has been elaborated, national institutional capaibilities for the purpose of collecting and sharing information on chemical safety is developed | MOLHSA MOE | MOF MOA MESD WHO, UBA Germany |  |  |  |  |  | UBA Germany WHO ECEH |
|  | 4.2.2. Develop proposals for the legislation revision to ensure sustainability of functioning of an operational framework | The legislative amendments are enacted, sustainability is provided, the action framework meets to the needs of interested parties | MOLHSA MOE | MOF MOA MESD WHO, UBA Germany |  |  |  |  |  | UBA Germany WHO ECEH |
| 4.3 MTO 4. 3 Risk to children from exposures to hazardous chemical substances in schools and kindergartens assessed and reduced by 2020 | 4.3.1. Develop and implement a system for monitoring and control of indoor air pollution with hazardous chemicals in schools and kindergarten | The system is set up, the number of schools and kindergardens increases annually by 10% (2015 - 0%), in which the monitoring is provided on indoor air pollution from hazardous chemicals. | MOES MOLHSA | WHO UNICEF | open |  |  |  |  | Donor support will be Needed Twining GE22 WHO expert support |
|  | 4.3.2. Create national capacities for assessment of risk of combined exposure to multiple chemicals accordance with WHO methodology | Methodologies are tested and approved; experts, which can evaluate the risk of combined impact of several chemical substances, are trained | WHO MOLHSA |  | open |  |  |  |  | Donor support will be Needed WHO expert support |
| 4.4 4 The National Program for Elimination of Asbestos Related Diseases developed by 2019 | 4.4.1. Development of asbestos national profile in accordance with WHO recommendations (identification of the needs / deficiencies). | Needs / shortcomings are identified Resolution of the Government on asbestos national profile has been approved | MOLHSA | WHO MOE | open |  |  |  |  | Donor support will be Needed Twining GE22 WHO expert support |
|  | 4.4.2. Development of the national program for elimination of asbestos-related diseases | Implementation of the National Program of Elimination is underway | MOLHSA | WHO MOE | open |  |  |  |  | Donor support will be Needed Twining GE22 WHO expert support |
| 4.5. 4.5 Risk of exposure to hazardous chemical in rural areas assessed and reduced by 2020 | 4.5.1. Proper management of pesticides and other agricultural chemicals for farmers, inclusion the component on educational and preventive measures | Farmers are aware of the impact of agrochemical risks and health impacts | MOA | MOLHSA | open |  |  |  |  | Donor support will be Needed |
|  | 4.5.2. Registration of the agrochemicals and their waste and improvement of the management | Information is available on the volume of used agrochemicals, existing practices and unused agrochemicals | MOA | MOLHSA | open |  |  |  |  | Donor support will be Needed |
|  | 4.5.3. Create poison control and toxicology (information) center (Poison Center) in line with WHO requirements | The poison-control and toxicology information consultation center (Poisoning center) is functioning Acute and chronic poisonings caused by chemical substances are registered, diagnosis is defined, treatment is carried out and protection measures are developed | MOLHSA | WHO | open |  |  |  |  | Donor support will be Needed Twining GE22 WHO expert support |
|  | 4.5.4. Mapping of existing toxicology-chemistry laboratories and ensuring accessibility for the purpose to prevent, detect, provide readiness, respond and liquidate the mass non-comunicable diseases and poisoning in population | Laboratory confirmation of poisoning is possible, the number of confirmed diagnoses | MOLHSA | Accreditation Centre | 5000 |  |  |  |  | State budjet |
|  | 4.5.5. Construction of the disposal landfill for the industrial toxic wastes, which are generated in the territory of the country | Construction of a polygon has been initiated | Georgian government | MOE MOLHSA MOF MORDI MESD | open |  |  |  |  | State budjet Donor support will be Needed |

| Tasks | Activity | Expected Result | Responsible Agency | Partner Organization | Budget on an annual basis |  |  |  |  | Funding Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Implemented activities in 2017 (GEL) | 2018 (GEL) | 2019(GEL) | 2020 (GEL) | 2021 (GEL) |  |

| 5. Integration of health issues in climate change adaptation and mitigation policies |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5.1 Evaluate vulnerability to climate change, health impacts and adaptation (health care aspects) including assessment of existing and anticipated risks related to health impacts of climate change | 5.1. 1Assessment of current and future risks of climate change on population health • Frame and scope the assessment • define the geographical region and health outcomes of interest; • identify the questions to be addressed and steps to be included • identify the policy context for the assessment • establish a project team and management plan • establish a stakeholder process • develop a communications plan | To reduce the risk of climate change, determine priority activities, designed to provide the basis for the decisions on the future measures | MOLHSA | MOE |  | 20 day national experts 20 000 20 day international Experts 66 000 |  |  |  | Donor support will be Needed |
|  | 5.1.2. Conducting the vulnerability and adaptation assessment. • Establishing baseline conditions on human health risks of climate change, determining current capacity of public health policies and programmes for addressing these risks | Define risks of current climate changes' health impacts and the Public Health Care policies and programs designed for their reduction: . Risks of climate-sensitive health care outcomes . Risks of vulnerable population groups and regions . Health care and other sectors’ current risk reduction capabilities | MOLHSA |  |  | to be determined by donor 10 day national experts 10 000 10 day international Experts 23 000 |  |  |  | Donor support will be Needed |
|  | 5.1.3. Conducting health impact assessment by: • projected future health risks and impacts under climate change, including the most vulnerable populations and regions, which will be determined for the coming decade • estimating the additional burden of adverse health outcomes due to climate change | Additional Public Health and Health Protection policies and programs designed to identify current and expected health risks are defined and the resources needed to overcome the potential barriers to their implementation are identified | MOLHSA |  |  |  | to be determined by donor 10 day national experts 10 000 10 day international Experts 23 000 |  |  | Donor support will be Needed |
|  | 5.1.4. Estimate the costs of action and of inaction to protect health | The costs of actions and inactivity health costs are assessed | MOLHSA |  |  |  | 20 day national experts 20 000 20 day international Experts 66 000 |  |  | Donor support will be Needed |
|  | 5.1.5 Capacity building of national experts based on international experience and provision of project management team with technical means | Experts are prepared and the Project Management Team is provided with technical capabilities | MOLHSA |  | open |  |  |  |  | Donor support will be Needed |
| MTO 5.2 Develop National Health Care Adaptation Strategy and Action Plan, among them, for medical facilities | 5.2.1. Elaboration of NationalHealth Climate Change Adaptation Strategy - To create vision - Describe the size and the nature of the problem - Identify effective interventions - Develop the strategies and priorities - Create a Strategy Action Plan | National Adaptation Strategy has been developed and includes all necessary Public Health measures | MOLHSA | MOE |  |  | 20 day national experts 20 000 20 day international Experts 66 000 |  |  | Donor support will be Needed |
|  | 5.2.2 Elaboration of an Heat-Health action plan for medical institutions | Health impact of hit waves is reduced | MOLHSA |  |  | to be determined by donor 10 day national experts 10 000 10 day international Experts 23 000 |  |  |  | Donor support will be Needed |
| Task 5.3. Harmonize the legislation with regard to the requirements of the UNFCCC Convention and assessment of health outcomes | 5.3.1. Inventory of health-care legislation and identification of those acts that require change | Laws and subordinate acts are elaborated for all sectors | MOLHSA | MOE |  |  | 20 day national experts 20 000 20 day international Experts 66 000 |  |  | Donor support will be Needed |
|  | 5.3.2. Harmonization of health-care legislation with the association agreement and convention | New legislative acts are elaborated | MOLHSA | MOE |  | 10 day national experts 10 000 | to be determined by donor |  |  | Donor support will be Needed |
| MTO 5.4 Health care facilities reduce the share of greenhouse gas emissions X% in national emissions by 2020 (from 2017), including introduction of renewable energy use in several hospitals within the framework of the pilot project. | 5.4.1. Determination of the share of greenhouse-gas emissions from the medical institutions, in the country's general emissions | Distribution of greenhouse gas emissions of medical institutions | MOLHSA | MOE | open |  | 20 day national experts 20 000 20 day international Experts 66 000 |  |  | Donor support will be Needed |
|  | 5.4.2. Detailed analysis of energy efficiency in the health system | Recommendations for energy- efficient buildings and renewable energy resources in hospitals | MOLHSA | MOE |  |  | 20 day national experts 20 000 20 day international Experts 66 000 |  |  | Donor support will be Needed |
|  | 5.4.3 Assessment of hospital safety | Assess the security and stability of the buildings, taking into account the requirements of energy efficiency | MOLHSA | MOE |  |  | 20 day national experts 20 000 20 day international Experts 66 000 | 20 day national experts 20 000 20 day international Experts 66 000 |  | Donor support will be Needed |
|  | 5.4.4. Introduction of the use of the renewable energy, within the frameworks of the pilot project, in several hospitals | Reduction of the share of greenhouse gas emissions from hospitals at municipal level | MOLHSA | MOE |  |  |  |  | Pilot project for 4 hospitals 100 000 | Donor support will be Needed |
|  | 5.4.5. Increase awareness of healthcare personnel in energy-efficiency issues | Reduce annual costs heating and electricity of the hospitals | MOLHSA | MOE |  |  | 5000 | 5000 | 5000 | State budjet |

| Tasks | Activity | Expected Result | Responsible Agency | Partner Organization | Budget on an annual basis |  |  |  |  | Funding Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Implemented activities in 2017 (GEL) | 2018 (GEL) | 2019(GEL) | 2020 (GEL) | 2021 (GEL) |  |

| Task 6: 6. Improving Governance of existing "Environment and Health “System in Georgia |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task 6.1 . 1 Institutional Strengthening of the Existing Environment and Health System | 6.1.1 Gap Assessment of the Existing Environmental Health System, Mapping of functions of all stakeholders versus EH challenges. | The major shortcomings / gaps in the existing environmental and health system are identified, formalized procedures are developed, responsibilities separated | MOLHSA | MOE MOA MESD MOES | 20 day national experts 20 000 20 day international Experts 66 000 |  |  |  |  | Donor support will be Needed Twining GE22 |
|  | 6.1.2 The environmental and health information system is set up 2018, environmental and health indicators are developed in relation to SDG | The relationship framework and integrated policy between the Environmental and Health sectors are formed, information exchange is going on within the information system, Environment and Health indicators are developed in relation to SDG | MOLHSA | MOE |  | 20 day national experts 20 000 20 day international Experts 66 000 |  |  |  | Donor support will be Needed Twining GE22 WHO expert mission |
|  | 6.1.3. The existing system/structure of the environmental health is in compliance with the similar system /structure operating in the EU | An analogue of the European system is established, the role and responsibilities are clearly defined | MOLHSA NCDC | The European Commission Twinning Project |  | 20 day national experts 20 000 20 day international Experts 66 000 |  |  |  | Donor support will be Needed Twining GE22 WHO expert mission |
| Task 6.2 .2 Implementation of National Environment and Health Action Plan | 6.2.1. The NEHAP inter-agency coordination group has been created and operates for 2017 | The relationship framework of is created with involvement of all interested agencies | MOLHSA NCDC | All interested agencies | 10 day national experts 10 000 to be determined by donor | 10 day national experts 10 000 to be determined by donor |  |  |  | State budjet Donor support will be Needed Twining GE22 |
|  | 6.2.2. Strengthening human resources for implementation of NEHAP in Georgia | Number of trained professionals | MOLHSA NCDC | სგს WHO |  | 20 day national experts 20 000 20 day international Experts 66 000 |  |  |  | State budjet Donor support will be Needed Twining GE22 |
|  | 6.2.3 Mapping of proper laboratory capabilities, provide for/ensure availability | Detailed and reliable information on laboratories was prepared, the existing laboratories are assigned responsibilities It was planned to establish new laboratories To eliminate the gaps | MOLHSA NCDC |  |  | 5000 |  |  |  | State budjet |
|  | 6.2.5 Developthe new Technical Regulations for Medical Waste Management in accordance with the Waste Management Code, Methodological assistance and organization of tranings for medical institutions in 2017-18 | Medical staff has undergone training (methodological assistance is being conducted and organizers are organized) | MOLHSA NCDC |  | completed |  |  |  |  | State budjet |
|  | 6.2.6. Develop Transport, Environment and Health National Action Plan by 2019 | Approved and published | MOLHSA | All interested agencies |  | 20 day national experts 20 000 20 day international Experts 66 000 | 10 day national experts 10 000 10 day international Experts 23 000 |  |  | State budjet Donor support will be Needed Twining GE22 |

| Tasks | Activity | Expected Result | Responsible Agency | Partner Organization | Budget on an annual basis |  |  |  |  | Funding Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Implemented activities in 2017 (GEL) | 2018 (GEL) | 2019(GEL) | 2020 (GEL) | 2021 (GEL) |  |

| 7: Reduce the impacts of physical agents of the environment by 2021 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 7.1. Reduce health impact of noise by 2021 | 7.1.1. Monitor noise and exposure to noise in public buildings where children spend time, planning and implementing measures to reduce noise exposure. | Noise levels and impacts in buildings are estimated (schools, kindergartens) | MOES and MOLHSA , NCDC | All interested agencies |  |  |  | 10 day national experts 10 000 10 day international Experts 23 000 | 10 day national experts 10 000 10 day international Experts 23 000 | Donor support will be Needed Twining GE22 WHO expert mission |
|  | 7.1.2 Improvement of urban and infrastructure planning for reduction of noise impact | 1. The legislation revised and brought into conformity with WHO recommendations 2 The requirements are assessed. Noise level control, monitoring and surveillance system in Tbilisi and other major cities is set up according to WHO recommendations. 3. Organizational and technical measures are developed and implemented to minimize noise -Management of traffic flow, limitation / restriction of movement of heavy vehicles during weekends and night hours. - Reduction of speed Special asphalt which does not generate noise. - Construction of noise-suppressing and anti-noise walls; greenery planting in urban areas. | Georgian Government | Tbilisi City Hall, local self-government of cities and districts | open |  |  |  |  | Donor support will be Needed |
| 7.2 7.2 Reduce health impact of anthropogenic ionizing radiation by 2021 | 7.2.1. The review and update of the security system related to medical activities, 2020 | MOLHSA MOE | WHO |  |  |  |  | 10 day national experts 10 000 10 day international Experts 23 000 |  | Donor support will be Needed WHO expert mission |
|  | 7.2.2 Readiness and responsive actions for prevention of nuclear and radiation accident, as well as post-accident consequences | MOLHSA MIA | MOE |  |  |  |  | 10 day national experts 10 000 10 day international Experts 23 000 |  | State budjet Donor support will be Needed WHO expert mission |
| 7.3 Reduce exposure of population to Radon | 7.3.1 Based on the country’s geological projections, carry out radiation monitoring in underground structures | MOLHSA | Tbilisi City Hall, local self-government of cities and districts |  | open |  |  |  |  | Donor support will be Needed |
|  | 7.3.2 Raise awareness of population and stakeholders on preventive measures related to Radon. | MOLHSA NCDC |  |  |  |  |  | 5000 | 5000 | State budjet |
|  | 7.3.3 Carry out interventions in the buildings with high Radon concentrations . | Plan construction works to minimize Radon impacts | Tbilisi City Hall, local self-government of cities and districts |  |  | open |  |  |  | Donor support will be Needed |
| 7.4 7.4 Reduce impact of ultraviolet radiation reduction by 2021 | 7.4.1 Informing population, school personnel and parents regarding harmful effects of excessive ultraviolet irradiation and preventive measures. | Information materials are developed about the risks associated with ultraviolet radiation. Population has access to information on preventive measures | MOLHSA NCDC |  |  |  |  | 5000 | 5000 | Sate budjet |
| 7.5. 7.5 Reduce health impact of electromagnetic fields by 2021 | 7.5.1 Elaboration / enactment and execution of the legislation for reduction of impact of electromagnetic fields; meeting safety norms with respect to all possible sources | Improvement of existing monitoring and risk assessment system | MOLHSA | MOE |  | 10 day national experts 10 000 10 day international Experts 23 000 | 10 day national experts 10 000 10 day international Experts 23 000 | 10 day national experts 10 000 10 day international Experts 23 000 |  | State budjet Donor support will be Needed WHO expert missio |
| 7.6 MTO 7.6 Education / training and preparedness of the population for emergency situations caused by natural disasters such as earthquakes, floods and other extreme weather events as well as technogenic disasters | 7.6.1 Conducting training and practical applications, where the needs for children, adolescents and pregnant women will be considered, for the prepadnes in emergency situations and providing adequate response | Awareness raising companies, trainings, TV programs will be organized. Information will be reflected in curriculums. Availability of information will be ensured. | MES MOLHSA |  |  | 10 day national experts 10 000 10 day international Experts 23 000 |  |  |  | State budjet Donor support will be Needed |

http://apps.who.int/iris/bitstream/10665/204585/1/9789241565196_eng.pdf?ua=1

http://ncdc.ge/Category/Article/6620

http://www.who.int/quantifying_ehimpacts/national/countryprofile/georgia.pdf?ua=1

As of September 1, 2011 the Covenant was ratified by 160 countries. Georgia joined the Covenant in 1994. General comments No.15 to the UN International Covenant “On Economic, Social and Cultural Rights”1, adopted in 1966 at the UN General Assembly.

In 2010,  the 5th Ministerial Conference on Environment and Health was held in Parma, Italy.

http://water.gov.ge/geo/about-us/company

http://nfa.gov.ge/ge/

Situation assessment of small-scale water supply systems in Dusheti and Marneuli districts, Tbilisi, 2013.

http://www.ncdc.ge/uploads/publications/angarishebi/mciremasStabiani_wyalmomaragebis_sistemebi.pdf

http://www.who.int/water_sanitation_health/publications/glaas_report_2014/en/

Health protection - statistical reference  2014.

http://moe.gov.ge/index.php?lang_id=GEO&sec_id=119

Global status report on road safety 2015

Global status report on road safety 2015 http://www.who.int/violence_injury_prevention/road_safety_status/2015/GSRRS2015_Summary_EN_final2.pdf

Global status report on road safety 2013: supporting a decade of action.

Global status report on road safety 2013; http://www.who.int/violence_injury_prevention/road_safety_status/2013/en/

Report of the 2009 Georgia National Nutrition Survey. http://unicef.ge/uploads/Report_of_the_Georgia_National_Nutrition_Survey_2009_-_eng.pdf

Global Action Plan for Prevention and Control of Non-Communicable Diseases. http://www.who.int/nmh/events/ncd_action_plan

http://apps.who.int/gho/data/node.sdg.3-9-viz-1?lang=en

http://www.who.int/topics/chemical_safety/en/

Source: Ministry of Agriculture, results of  Drinking Water Quality State Surveillance