|  | Intervention logic | Benchmarks | Sources of Verification | Assumptions (External to project) |
| --- | --- | --- | --- | --- |
| Overall objective | To reduce poverty and enhance social cohesion in Georgia through the introduction of measures designed to stimulate employment, and to ensure synergy between the demands of the labour market and the skills and qualifications offered by the vocational education and training system. | - Reduction in numbers of citizens living on or below the poverty line - Reduction in numbers of unemployed - Increase in total active labour population | - EC Regular Report on progress by Georgia in implementation of the AA - GEOSTAT reports - MoLHSA Annual Reports |  |
| Project purpose | The project purpose is to strengthen the institutional and human resource capacities of the Employment Support Services of Georgia to deliver well-targeted, high-quality, gender-sensitive and cost-effective services to job seekers | - Enhanced management and administrative arrangements within the ESS - Institutional reorganisation has been completed - Operational guidelines for the full range of services offered by the ESS have been prepared and codified - Comprehensive quality assurance plan designed and implemented - Labour Market Information Management System (WorkNet Information System) upgraded and providing quantitative and qualitative data on current state of Georgian labour market - Staff are well-trained - ESS has developed the tools and techniques for preparing and delivering well-targeted and user-friendly communications and awareness raising campaigns | - EC Regular Reports on progress by Georgia in implementation of the AA - MoLHSA and ESS Annual Reports - Progress Reports delivered by the Partner Country in Twinning Project Evaluation reports - Satisfaction of job-seekers and employers with the quality and range of services provided by ESS | - Continued commitment to an interventionist labour market policy - MoLHSA continues to develop and implement coherent labour market policies, notably linked to active employment initiatives - Adequate budgetary resource allocation to the ESS permitting it to extend the range and quality of its services - Sufficient capacity within the ESS to absorb the assistance provided by Twinningpartner. |
| Mandatory results (Components) | COMPONENT 0 Visibility events and project management Mandatory result: Two project visibility events organised and high level of dissemination of information achieved | - 2 key visibility events organised: 1 Kick-off and 1 Final Conference - Information disseminated through various communication channels media - Visibility and promotional materials developed and disseminated | - Attendance of the list of participants - Media coverage report - Press clipping published - Quarterly report - Final report |  |

|  | COMPONENT 1 Mandatory result: Revision of the Georgian Legal Framework of equal opportunities legislation and related to employment in line with the EU acquis and in accordance with the provisions of Annex XXX of the Association Agreement | - Review of Georgian Equal Opportunities legislation related to employment and measure of concordance with EU Equal Opportunities legislation identified in Annexes of the Association Agreement - Drafting a Concordance Report and recommendations for harmonisation of the Georgian legislation related to employment with the EU Equal Opportunities Directives identified in Annexes of the Association Agreement - Support to legal drafting with regard to the Equal Opportunities legislation related to the employment service identified in the relevant Annexes of the Association Agreement - Gap analysis of the equal treatment and non-discrimination sections of the regulations for which the ESS has competence - Regulatory drafting support to the ESS in order to ensure compliance of the regulations for which it has competence with the revised Georgian Equal Opportunities legislation harmonised with EU Equal Opportunities legislation | - Official Journal of the Georgian Parliament(Indicator 1.1, 1.2 & 1.3) - EU Regular Reports on the implementation of the AA(Indicator 1.1, 1.2 & 1.3) - MoLHSA/ESS Regulations(Indicator 1.4 & 1.5) | - Adequate legal and regulatory drafting capacity within the MoLHSA and ESS - Continued commitment to an interventionist labour market policy - MoLHSA continues to develop and implement coherent labour market policies, notably linked to active employment initiatives - Adequate budgetary resource allocation to the ESS permitting it to extend the range and quality of its services - Sufficient capacity within the ESS to absorb the assistance provided by Twinning partner - Sufficient financial resources within the MoLHSA to develop the Labour Market Information System - Motivation of ESS/MoLHSA staff involved into the project implementation - Readiness of ESS/MoLHSA staff to incorporate new practices into work |
| --- | --- | --- | --- | --- |
|  | COMPONENT 2 Mandatory result: The structure and functions of the ESS have been revised to reflect it expanded role in the labour market management processes, the range and quality of services provided to job-seekers have been piloted and enhanced, the internal management and administrative processes have been clearly codified | 2.1Functional Review of the SSA/ESS 2.2 Support to drafting of an Institutional Reform Plan for the SSA/ESS 2.3 Support to the implementation of institutional reforms within the SSA/ESS 2.4Review and revision (if required) of the current procedures for registration of job-seekers and job opportunities 2.5Introduction of new services within the ESS 2.6Support to the further development of job-seeker counselling services 2.7Development of a Procedures Manual 2.8Development of a Quality Assurance Plan 2.9Study Visit to MSs to examine the range of services provided to job-seekers and employers through employment offices | - STEs reports - (Indicator2.1, 2.2, 2.3,2.4, 2.5, 2.6, 2.7& 2.8) - Functional Review document(Indicator 2.1) - Institutional reforms – ESS &MoLHSA Annual Reports (Indicator s 2.1, 2.2& 2.3 ) - Revised registration procedures - ESS & MoLHSA Annual Reports (Indicator 2.4) - Number of new services introduced - ESS & MoLHSA Annual Reports (Indicator 2.5) - Revised methodology for counselling services - ESS & MoLHSA Annual Reports (Indicator 2.6) - Procedures Manual(Indicator 2.7) - Quality Assurance Plan (Indicator 2.8) - Study visit report (Indicator 2.9) - Project reports |  |
|  | COMPONENT 3 Mandatory result: A comprehensive Labour Market Information Management System (WorkNet Information System) has been established and is fully operational | 3.1Review of the WorkNet Information System 3.2Elaboration of a Concept Paper for upgrading the WorkNet Information System 3.3Preparation of Terms of Reference/Technical Specifications for upgrading the WorkNet Information System 3.4 Development of methodology and tools for the preparation of monthly/quarterly and annual labour market reports 3.5 Study Visit to MSs to examine the collection, collation and analyses of Labour market data by the employment services | - STE report - (All indicators) - Concept Paper(Indicator 3.2) - Terms of Reference/Technical Specifications(Indicator 3.3) - Methodology and tools for labour market reports (Indicator 3.4) - Study visit report (Indicator 3.5) - Project reports |  |
|  | COMPONENT 4 Mandatory result: Modern human resource management techniques have been introduced, the staff have acquired the necessary skills and experience to provide high quality services to job-seekers, and an in-house training and retraining platform has been established | 4.1Review of current HRD policy 4.2Drafting of an HRD Manual 4.3Conduct Training Needs Analysis 4.4Development of Training Programme and Training Materials 4.5Conduct Formal and in-service trainings for the ESS staff 4.6 Development of the Training manual 4.7 Training/retraining platform (Train the trainers) | - STE reports - (All indicators) - Review Paper(Indicator 4.1) - HRD Manual(Indicator 4.2) - Training Needs Analysis (Indicator 4.3) - (Indicator 4.1 - Training programme and training materials (Indicator 4.4) - Feedback evaluation sheets (training) (Indicator4.5.) - Training Manual (Indicator 4.6) - ToT feedback evaluation sheets(Indicator 4.7) - Project reports |  |
|  | COMPONENT 5 Mandatory result: The ESS has acquired the necessary tools and materials to communicate effectively its range of services to clients and potential clients | 5.1Review of current communications policies and recommendations for upgrading 5.2Support to the establishment of a Communications Unit within the ESS 5.3 Elaboration of communications and awareness raising strategy and Action Plan 5.4Development and application of communications tools and materials 5.5. Study Visit to MSs to experience practical use of the promotion and marketing of services to job-seekers and employers | - STE report - (Indicator5.1) - Communications and Awareness Raising Strategy and Action plan (Indicator5.2) - Communications materials, updated website, awareness events (Indicator5.2 - Study visit report (Indicator 5.4) - Project reports |  |
| COMPONENT 0 | Activity 0.1. Project management including the Steering Committee meetings, monthly meetings and project visibility | - Min . 15 monthly meetings organised - 6 Quarterly SC meetings held | Attendance list of participants Attendance list of journalists Quarterly report | - The ESS assigns appropriately skilled and competent staff at all levels to act as counterparts to the RTA and his/her colleagues - The ESS releases members of staff to participate in Project activities (e.g. training workshops, study tours, communications actions) - The ESS ensures that the results of the project are fully integrated into the work routine of the ESS - The ESS provides access to all relevant legislation, regulations, policies, strategies and supporting documentation relevant to the Project - The ESS facilitates access to regional offices of the ESS, and to decision-makers at national, regional and local levels - The ESS provides suitable venues for training workshops/presentations/meetings held within the framework of the Project |
|  | Activity 0.2. Kick-off meeting and first SC meeting | - Kick-off meeting held - Press conference conducted - Visibility materials for the kick-off event published | Monthly reports Attendance list of participants Monthly minutes Quarterly reports Project final report |  |
|  | Activity 0.3 Closure Meeting – Final conference. | - 1 closing conference prepared and organised - Press conference conducted - Visibility materials for the kick-off event published | Attendance list of participants Quarterly reports Final report Monthly minutes Project final report |  |
| COMPONENT 1 | Activity 1.1. Review of Georgian Equal Opportunities legislation related to employment and measure of concordance with EU Equal Opportunities legislation identified in Annexes of the Association Agreement | A short-term legal/regulatory drafting expert conducted a review of Georgian Equal Opportunities legislation and related to employment in order to determine the measure of compliance with the EU Equal Opportunities Directives identified in Annexes of the Association Agreement. | Review report of Georgian Equal Opportunities legislation Project quarterly reports Mission reports Project final report |  |
|  | Activity 1.2 Drafting a Concordance Report and recommendations for harmonisation of the Georgian legislation related to employment with the EU Equal Opportunities Directives identified in Annexes of the Association Agreement; | - On the basis of the review (1.1), the short-term legal/regulatory drafting in a form of Concordance Report prepared. The Report will highlight where there are gaps in the legislation related to employment or where the current provisions are not aligned with the EU Equal Opportunities Directives identified in Annexes of the Association Agreement. - Complete set of recommendations for closing the gaps and ensuring harmonisation with the relevant EU Directives elaborated. | Concordance Report Recommendations as part of the Concordance report Project Quarterly reports Mission reports Project final report |  |
|  | Activity 1.3 Support to legal drafting with regard to the Equal Opportunities legislation related to the employment service identified in the relevant Annex XXX of the Association Agreement; | - Draft/Amendments to Georgian legislation to ensure that it is harmonised with Council Directives Nº2000/43/EC, Nº2000/78/EC, and Nº2006/54/EC related to the principles of equal treatment and non-discrimination in employment supporting services elaborated in accordance with the recommendations appended to the Concordance Report | Draft amendments to the GE law in compliance with relevant EU directives Project Quarterly reports Mission reports Attendance list of participants Project final report |  |
|  | Activity 1.4 Gap analysis of the equal treatment and non-discrimination sections of the regulations for which the ESS has competence; | - Gap Analysis to ensure that the regulations for which the ESS has competence are consistent with Georgian legislation that should be harmonised with Council Directives Nº2000/43/EC, Nº2000/78/EC, and Nº2006/54/EC related to the principles of equal treatment and non-discrimination in employment supporting services conducted. - Complete set of recommendations for revising the regulations in order to ensure compliance in EU law elaborated as part of Gap Analysis. | Gap Analysis document Set of recommendations Project Quarterly reports Mission reports Attendance list of participants Project final report |  |
|  | Activity 1.5 Regulatory drafting support to the ESS in order to ensure compliance of the regulations for which it has competence with the revised Georgian Equal Opportunities legislation harmonised with EU Equal Opportunities legislation | - Legal Revision elaborated for those regulations for which it ESS has competence ensuring that the revised regulations are consistent with Georgian legislation that should be harmonised with Council Directives Nº2000/43/EC, Nº2000/78/EC, and Nº2006/54/EC related to the principles of equal treatment and non-discrimination in employment supporting services | Legal Revision of those regulations for which it has competence ensuring that the revised regulations are consistent with Georgian legislation that should be harmonised with Council Directives Nº2000/43/EC, Nº2000/78/EC, and Nº2006/54/EC related to the principles of equal treatment and non-discrimination in employment supporting services Project Quarterly reports Mission reports Attendance list of participants Project final report |  |
| COMPONENT 2 | Activity 2.1. Undertake Functional Review of the SSA/ESS; | - Review the SSA’s/ESS’s Charter and Mission Statement conducted - Functional analysis of the management structure of the SSA/ESS, the range of services offered, and the distribution of tasks and staffing elaborated - Recommendations on management/administrative and operational changes, where necessary and appropriate elaborated | Review document Functional Analysis Report Project Quarterly reports Mission reports List of interviewed persons Project final report | - The ESS assigns appropriately skilled and competent staff at all levels to act as counterparts to the RTA and his/her colleagues - The ESS releases members of staff to participate in Project activities (e.g. training workshops, study tours, communications actions) - The ESS ensures that the results of the project are fully integrated into the work routine of the ESS - The ESS provides access to all relevant legislation, regulations, policies, strategies and supporting documentation relevant to the Project - The ESS facilitates access to regional offices of the ESS, and to decision-makers at national, regional and local levels - The ESS provides suitable venues for training workshops/presentations/meetings held within the framework of the Project |
|  | Activity 2.2. Support to drafting an Institutional Reform Plan for the SSA/ESS | - Institutional Reform Plan for the SSA/ESS prepared | Institutional Reform Plan Project Quarterly reports Mission reports Project final report |  |
|  | Activity 2.3. Support to the implementation of theInstitutional reform of the SSA/ESS | - Institutional Reform Plan implemented - Revisions to the ESS’s Charter, Mission Statement and Regulations, a redefinition of the range of services offered, and a scheme ensuring a more efficient distribution of tasks and staff implemented | Project Quarterly reports Mission reports Attendance list of participants Project final report |  |
|  | Activity 2.4. Review and revision (if required) of the current procedures for registration of job-seekers and job opportunities | - The STE will assist Review of the ESS operating procedures and methodologies for the registration of job-seekers and job opportunities including provision of matching services to clients to ensure that the current procedures allow for the profiling and tracking of job seekers and job opportunities conducted - Recommendations to the ESS for strengthening its registration procedures prepared | Review Report of the ESS operating procedures and methodologies for the registration of job-seekers and job opportunities Set of Recommendations Project Quarterly reports Mission reports Attendance list of participants Project final report |  |
|  | Activity 2.5. Introduction of new services within the ESS | - New services, as appropriate, introduced. - Guidelines, methodologies, and tools for each of the new services developed and introduced. | Guidelines, methodologies, and tools for each of the new services Project Quarterly reports Mission reports Project final report |  |
|  | Activity 2.6. Support to the further development of job-seeker counselling services | - Counselling services for job-seeker developed - Piloting of the enhanced counselling services done in at list 30% of the total ESS offices and revised according to the outcomes of the piloting. | Counselling services document Piloting Report Revision document of counselling services piloting Project Quarterly reports Mission reports List of participants in piloting Project final report |  |
|  | Activity 2.7. Development of a Procedures Manual | - Internal Procedures Manual for use by Head Office and Regional Office staff elaborated | Internal Procedures Manual Project Quarterly reports Mission reports Project final report |  |
|  | Activity 2.8. Development of a Quality Assurance Plan | - Quality Assurance Plan elaborated - Quality controls for use of the manual by Head Office and District Office staff installed | Quality Assurance Plan Report on results of the installation of Quality controls Project Quarterly reports Mission reports Attendance list of participants Project final report |  |
|  | Activity 2.9. Study Visit to MS to examine the range of services provided to job-seekers and employers through employment offices. | - 1 Study Visit focus upon the range of services provided to job-seekers and employers through employment offices for a min of 5 working days for min. 7 persons (including RTA Assistant/translator as a member of the group) organised | Project Quarterly reports Mission reports Attendance list of participants in the Study visit Project final report |  |
| COMPONENT 3 | Activity 3.1. Review of the WorkNet Information System | - Review of the WorkNet Information System to ensure that the WorkNet Information System is compatible with the wider Labour Market Information System being developed by the MoLHSA and to identify what methodologies and tools would be required to enable the ESS to develop a comprehensive overview of the current labour market, using the data gathered through the WorkNet Information System conducted | Review Report on WorkNet IT system Project Quarterly reports Mission reports Project final report |  |
|  | Activity 3.2. Elaboration of a Concept Paper for upgrading the WorkNet Information System | - Concept Paper developed, addressing three core areas: 1) Recommendations for refining the functionalities of the current WorkNet IT to ensure interoperability and interconnectivity with the wider Labour Market Information System; 2) upgrades in hardware and software; 3) approach, methodology, tools and templates to permit the ESS to develop monthly/quarterly and annual reports on the current state of the Georgian labour market | Concept Paper Project Quarterly reports Mission reports Attendance list of participants Project final report |  |
|  | Activity 3.3. Preparation of Terms of Reference/Technical Specifications for upgrading the WorkNet Information System | - Terms of Reference and Technical Specifications for the procurement of off-the-shelf or tailor-made software and hardware prepared | Terms of Reference and Technical Specifications document Project Quarterly reports Mission reports Project final report |  |
|  | Activity 3.4. Development of methodology and tools for the preparation of monthly and annual labour market reports | - Methodology, tools and templates developed which would permit the ESS to develop consolidated monthly/quarterly and annual reports on the current state of the Georgian labour market, and provide accurate data on supply and demand in the labour market, disaggregated by region/age/gender | Methodology document including tools and templates Project Quarterly reports Mission reports Project final report |  |
|  | Activity 3.5. Study Visit to MS to examine the collection, collation and analysis of labour market data by the employment services | 1 Study Visit focus upon the collection, collation and analysis of labour market data for a min of 5 working days for min 7 persons (including RTA assistant/interpreter) drawn from the MoLHSA and the ESS central and regional offices organised | Project Quarterly reports Mission reports Attendance list of participants in the Study visit Project final report |  |
| COMPONENT 4 | Activity 4.1. Review of current HRD policy | - Review of the current HRD policy with focus on the recruitment system, terms and conditions of employment, career development and promotions’ policy, in-service training, and performance appraisal conducted. - Revisions to the current HRD policy to the ESS management elaborated | Review Report on HRD Document containing revisions to the current HRD policy Project Quarterly reports Mission reports Project final report |  |
|  | Activity 4.2. Drafting of an HRD Manual | - HRD Manual which includes: a) transparent recruitment, b)career development and promotions procedures, c)standard contracts; templates and methodology for performance assessment, d) identifying standard induction and in-service training modules elaborated. | HRD Manual Project Quarterly reports Mission reports Attendance list of participants Project final report |  |
|  | Activity 4.3. Conduct Training Needs Analysis | - Training needs analysis (TNA) of the staff of the ESS (Headquarters and District Offices) elaborated | Training needs analysis document Project Quarterly reports Mission reports Project final report |  |
|  | Activity 4.4. Development of Training Programme and Training Materials | - Training Programme divided between formal and in-service training, and mentoring of senior management for the Headquarters and District staff prepared. - Training materials developed | Training Programme document Training materials Project Quarterly reports Mission reports Project final report |  |
|  | Activity 4.5. Conduct Formal and in-service trainings for the ESS staff | - Training programme implemented - 10 formal workshops for 1-2 days per each on different topics for 140 persons at least 75 hours of in-service training organised - Series of trainings in three main regional centres: Kakheti, Imereti and Ajara conducted. - in-service training to ESS Headquarters staff and mentoring the Director and Deputy Director conducted. | Project Quarterly reports Mission reports Attendance lists of participants at workshops Project final report |  |
|  | Activity 4.6. Development of the Training manual | - Training Manual elaborated including all training materials | Training Manual Project Quarterly reports Mission reports Project final report |  |
|  | Activity 4.7. Training/retraining platform (Train the trainers) | - Training of at least 5 trainers covering pedagogic methods, the design and implementation of induction training for new members of staff and the content of the Training Manual conducted | Project Quarterly reports Mission reports Attendance lists of participants at training Project final report |  |
| COMPONENT 5 | Activity 5.1. Review of current communications policies and recommendations for upgrading | - Review on current ESS communications policies and provisions to establish a dedicated communications unit conducted. - Assessment of the ESS’s communications needs elaborated - Recommendations for upgrading the approach, messages, target groups, and communications tools elaborated. | Review Report on ESS communication policies including Assessment of ESS needs Set of recommendations Project Quarterly reports Mission reports Project final report |  |
|  | Activity 5.2. Support to the establishment of a Communications Unit within the ESS | - Mission statement, functions and optimum staffing level of the communications unit prepared | Document Mission statement, functions and optimum staffing level of the communications unit Project Quarterly reports Mission reports Project final report |  |
|  | Activity 5.3. Elaboration of communications and awareness raising strategy and Action Plan | - Communication and Awareness Strategy and associated Action Plan elaborated. | Communication and Awareness Strategy Action Plan Project Quarterly reports Mission reports Project final report |  |
|  | Activity 5.4. Development and application of communications tools and materials | - Communications tools and materials developed focused on the establishment of consultative mechanisms with employers, the further development of the ESS’s interactive web-site, www.worknet.gov.ge ; elaboration of information materials for job-seekers and employers, and the organisation of promotional events | Communications tools and materials Project Quarterly reports Mission reports Project final report |  |
|  | Activity 5.5. Study Visit to MS to experience practical use of the promotion and marketing of services to job-seekers and employers | 1 Study Visit focus on the promotion and marketing of services to job-seekers and employers for a min of 5 working days for min 7 persons (including RTA assistant/interpreter) organised | Project Quarterly reports Mission reports Attendance list of participants in the Study visit Project final report |  |

Annex XXX of the AA titled Employment, social policy and equal opportunities, page, Official Journal, L261/p.601 of 30.8.2014