| Activities | Responsible persons | Due date | comments |
| --- | --- | --- | --- |
| 1st phase |  |  |  |
| - Analysis of adaptation of the DRG grouper to the SSA’s IT system (after the technical information about the grouper software has been received from grouper software provider). |  | April-July 2018 |  |
| - Adaptation of SSA’s IT system to the DRG grouper by making amendments/changes in the system to accommodate the grouper software |  |  |  |
| - To revise/change/modify business process according to DRG requirements |  |  | Consider advanced experiences to adapt to concrete requirements by using expert’s support |
| - Revise and update ICD-10 and NCSP |  | April-July 2018 | Latest version of codes are almost ready, but it is necessary to revise and make several amendments according to last version |
| - Revise and improve the coding guidelines for ICD-10 and NCSP |  | I stage – March-July 2018, then continuously | There are coding guidelines and presentations for ICD-10 and NCSP prepared by NCDC. There will be necessary to revise/modify them according to DRG grouper coding requirement |
| - Organize trainings of trainers for technical support/trainings of providers |  |  | Expert’s support is necessary |
| 2nd phase |  |  |  |
| - Develop the external clinical coding audits |  | I stage – March-August 2018, II stage – September –December 2018 | Elaborate external clinical coding audits how to use precisely as primary as secondary diagnoses, especially coding complicated and mixed cases to avoid/minimize doubtable/uncertain data |
| - Organize trainings/technical support to improve coding of diagnoses (primary and secondary) and Activities according to the agreed standards. |  | September-December 2018 | Analyze feedback from providers with help of experts |
| - Test IT solutions from the selected providers perspective |  | September-November 2018 |  |
| 3rd phase |  |  |  |
| - Develop cost weight for using “shadow funding” |  | September-November 2018 | Elaborate cost weights for “shadow funding” developing the weighs based on Georgian data and at the same time comparing it with foreign (available) data (using international expert’s support) |
| - Analyze the vertical programs in the light of DRG implementation |  |  | Consider need/advantage of integration some vertical programs and UHC program |
| - Conduct simulations for alternative DRG cost weights and base rate scenarios |  |  |  |
| - Calculate the cost weights, base rate and DRG tariffs |  |  |  |
| - Define different clinical areas for identifying reimbursement method for them |  |  | Consider the possibility to include in UHC DRG groups some clinical areas from vertical programs |
| - Identify certain field/cases for setting different reimbursement rules |  |  |  |
| - Define exemptions |  |  | Consider existing exemptions in UHC program adding and/or deducting some of them |
| - Analyze the legal framework, identify the needed changes in legislation |  | May-December 2018 | On the pilot stage no important legislative changes are necessary. |
| - Prepare the legal documents needed for implementing the DRG system |  |  |  |
| 4th phase |  |  |  |
| - Revise and improve the SSA claims management process according testing results |  | January-April 2019 | Analyze data comparing it with foreign similar findings with help of international experts |
| - Revise and improve the external clinical coding audits |  | January-April 2019 |  |
| - Simulations for the different DRG reimbursement policy scenarios |  | January-May 2019 |  |
| - Revise/modify/amend cost weight/DRG tariffs used for “shadow funding” and elaborate cost weigh/DRG tariffs for the actual reimbursement |  | September-November 2019 |  |