Communication plan to support DRG implementation

Objective(s)

- Build an environment for providers to participate and collaborate

- Raise awareness of the public and providers about ongoing changes

Target audience

- Hospitals

- doctors

- Managers

- IT persons

- private insurers

- beneficiaries

- politicians

- SSA and MOLHSA staff

- media

Key messages

Communication area:

- To inform target audience about DRG reform objectives

- To inform target audience about DRG reform implementation plan

- To inform target audience about progress during the DRG implementation process

- To inform target audience about some technical aspects of DRGs

| Target group | Key messages |
| --- | --- |
| Hospitals | Simplicity of reporting, more realistic prices, comparable statistics; well-organized information system; |
| Beneficiaries | Transparent service prices, less to pay… |
| Politicians | DRG - Cost containment, transparency and cost efficiency of expenses; |
| SSA and MOLHSA staff | Simplicity of planning, reporting, and monitoring |
| Media | DRG - Other health needs of vulnerable groups will be satisfied with savings costs |

Channels

Potential channels: website, social media, media release, briefing, seminar, email, radio, TV, Training,

Action plan

DRG implementation communication plan

| Communication area | Activity | Target audience | Responsible institution/person | Channel(s) of communication | Frequency | Due date | Budget | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| To inform target audience about DRG reform objectives | Organize meeting | Hospitals; private insurers beneficiaries, politicians, SSA and MOLHSA staff, Media | MoLHSA/SSA PR department | Meeting | Before the start of implementation | April 2018 |  |  |
|  | Preparation and printing of press release | Hospitals; private insurers beneficiaries, politicians, SSA and MOLHSA staff, Media | MoLHSA/SSA PR department/ Health care department | Meeting | Before the start of implementation | April 2018 |  |  |
|  | Prepare information for MoLHSA and SSA websites | Hospitals; private insurers beneficiaries, politicians, SSA and MOLHSA staff, Media | MoLHSA/SSA PR department/ Health care department | website | Before the start of implementation | April 2018 |  |  |
|  | Participation in medical programs in TV, Radio | Hospitals; private insurers beneficiaries, politicians, SSA and MOLHSA staff, Media | MoLHSA/SSA PR department/ Health care department | TV, radio | Before the start of implementation | April 2018 |  |  |
|  | Preparation and printing of Brochures | Hospitals; private insurers beneficiaries, politicians, SSA and MOLHSA staff, Media | MoLHSA/SSA PR department/ Health care department | Meeting/SSA branches | Before the start of implementation | April 2018 |  |  |
|  | Preparation of information for Facebook | Hospitals; private insurers beneficiaries, politicians, SSA and MOLHSA staff, Media | MoLHSA/SSA PR department/ Health care department | Social Media | Before the start of implementation | April 2018 |  |  |
|  | Prepare Infographics and Banners | Hospitals; private insurers beneficiaries, politicians, SSA and MOLHSA staff, Media | MoLHSA/SSA PR department/ Health care department/ SSA UHC department | Social Media; TV; | Before the start of implementation | April 2018 |  |  |
| To inform target audience about DRG reform implementation plan | Organize meeting | Hospitals; private insurers SSA and MOLHSA staff, politicians, Media | MoLHSA/SSA PR department/ Health care department | Meeting | Before the start of implementation | September, 2018 |  |  |
|  | Preparation and printing of press release | Hospitals; private insurers SSA and MOLHSA staff, politicians, Media | MoLHSA/SSA PR department/ Health care department | Meeting | Before the start of implementation | September, 2018 |  |  |
|  | Prepare information for MoLHSA and SSA websites | Hospitals; private insurers SSA and MOLHSA staff, politicians, Media | MoLHSA/SSA PR department/ Health care department | website | Before the start of implementation | September, 2018 |  |  |
|  | Participation in medical programs in TV, Radio | Hospitals; private insurers SSA and MOLHSA staff, politicians, Media | MoLHSA/SSA PR department/ Health care department | TV, radio | Before the start of implementation | September, 2018 |  |  |
| To inform target audience about some technical aspects of DRGs | Organize meeting | Hospitals; SSA and MOLHSA staff | MoLHSA/SSA PR department/ SSA UHC department | Meeting | If necessary | April, 2018 -November, 2019 |  |  |
|  | Prepare information for MoLHSA and SSA websites | Hospitals; SSA and MOLHSA staff | MoLHSA/SSA PR department/ SSA UHC department | website | If necessary |  |  |  |
|  | Organize Workshop | Hospitals; SSA and MOLHSA staff, media | MoLHSA/SSA PR department/ Health care department/ SSA UHC department | Workshop | Before the start of implementation | April, 2018 -November, 2019 |  |  |
|  | Prepare technical manuals | Hospitals; SSA and MOLHSA staff | MOLHSA;/SSA;PR department | Website; video-manual; Print version. | Before the start of implementation | April, 2018 -November, 2019 |  |  |
|  | Training for MOLHSA Hot Line | Hot line of MOLHSA | MOLHSA/SSA; PR department; SSA UHC department | Training; | Before the start of implementation | April, 2018 -November, 2019 |  |  |
| To inform target audience about progress during the DRG implementation process | Organize conference | Hospitals; private insurers beneficiaries, politicians, SSA and MOLHSA staff, Media | MoLHSA/SSA PR department/ Health care department/ SSA UHC department | Conference | End of Implementation | January, 2019 |  |  |
|  | Preparation and printing of press release | Hospitals; private insurers beneficiaries, politicians, SSA and MOLHSA staff, Media | MoLHSA/SSA PR department/ Health care department/ SSA UHC department | Meeting | End of Implementation | January, 2019 |  |  |
|  | Prepare progress information for MoLHSA and SSA websites | Hospitals; private insurers beneficiaries, politicians, SSA and MOLHSA staff, Media | MoLHSA/SSA PR department/ Health care department/ SSA UHC department | website | End of Implementation | January, 2019 |  |  |
|  | Preparation and printing of Scientific reports | Hospitals; private insurers politicians, SSA and MOLHSA staff | MoLHSA/SSA PR department/ Health care department/ SSA UHC department | Scientific journals | End of Implementation | January, 2019 |  |  |