Contracting Authority

# Eastern Partnership Integration and Cooperation (EaPIC) 2013

# “Capacity Building of the Employment Support Services (ESS) in Georgia”

# Twinning Contract

| # Name of Beneficiary: | # Social Services Agency under the Ministry of Labour, Health and Social Affairs of Georgia |
| --- | --- |

| # Dossier No | # GE/20 |
| --- | --- |

# (for official use only)

TWINNING CONTRACT

GE/20

The European Union, represented by the European Commission with its office at 38 Nino Chkheidze Street, 0102 Tbilisi, Georgia,  represented by Mr Janos Herman, Head of the European Union Delegation to Georgia  ("the Contracting Authority")

of the one part,

and

Regional Development Agency, Slovakia with its office at Vysoka 35, 811 06 Bratislava, Slovakia, ID (IČO): 36065781 and VAT (DIČ) No.: 2021686018 represented by Mrs. Luba Pavlovova, Director ("the Member State Partners" - MSPs),

of the other part,

(the "Parties")

have agreed as follows:

Special Conditions

Article 1 - Purpose

1.1    The purpose of this contract is the award of a Twinning grant, consisting of reimbursement of expenditures, by the Contracting Authority for the implementation of the Action entitled: “Capacity Building of the Employment Support Services (ESS) in Georgia“("the Action") described in annex A1.

1.2     The Member State Partners (MSPs) shall be awarded the Twinning grant on the terms and conditions set out in this Contract, which consists of these special conditions ("Special Conditions") and the annexes, which the MSP hereby declares it has noted and accepted.

1.3     The MSPs accepts the Twinning grant and undertakes to carry out the Action under its own responsibility.

1.4  	The final recipient of this operation is:  Social Services Agency under the Ministry of Labour, Health and Social Affairs of Georgia, 144 Tsereteli Ave, Tbilisi 0119, Georgia

Article 2 – Execution and Implementation period of the Action (legal and work plan duration)

2.1     The execution period of the contract (legal duration) shall enter into force upon the date of notification by the Contracting Authority of the contract signed by all parties. The execution period of the contract shall end 3 months after the implementation period of the Action as stipulated in art 2.2.

2.2     The implementation period of the Action shall take 18 months and shall begin on the date of the arrival of the Resident Twinning Adviser (RTA) to the beneficiary country. His arrival has to take place at the latest within one month following the notification of the Twinning contract.

Article 3 - Financing the Action

3.1   The total cost of the Action eligible for financing by the Contracting Authority is estimated

at1 100 000 EUR, as set out in Annex A3.

3.2   The Contracting Authority undertakes to finance a maximum of 1 100 000EUR. The final amount shall be established in accordance with Article 17 of Annex A2 except where annex A7 applies. The Action is co-financed as per Annex A3 by the Final Recipient of the Action.

Article 4 - Payment arrangements and technical and financial reporting

4.1	Payment shall be made in accordance with Article 15 of Annex A2 option no. 2, as set out in Article 15.1.

Initial pre-financing payment:						586 666,66 EUR

Further pre-financing payment(s):						403 333,34 EUR

(subject to the provisions of Annex A2)

Balance of the final amount of the Twinning contract

(subject to the provisions of Annex A2):					110 000 EUR

4.2	Technical and financial reports shall be produced in compliance with Articles 2 and, 15.1 and 15.3 of Annex A2, using the relevant twinning templates.

Financial section of these reports shall comply with the requirements defined in paragraphs 4, 5 and 6 of Article 15.7 of Annex 2 (requirements for a detailed breakdown of expenditure).

In addition to these reports, the Lead Member State Partner shall send additional interim reports in compliance with article 2.1 of Annex A2 on a quarterly basis. The specific reporting procedure shall follow the provisions spelled out in Annex A7 to this contract.

Article 5 - Contact addresses

5.1	Any communication relating to this contract shall be in writing, state the number and title of the Action and be sent to the following addresses:

For the Contracting Authority

Payment requests and attached reports, including requests for changes to bank account arrangements shall be sent to:

Contract, Finance and Audit Section

Delegation of the European Union to Georgia

38 Nino Chkheidze Street, 0102 Tbilisi

Georgia

Tel: + 995 32 2943763

E-mail: Delegation-Georgia-Finance@eeas.europa.eu

Copies of the documents referred to above, and correspondence of any other nature, should be sent to:

Mr. Roman Kakulia

Head of EU Assistance Coordination Department / Programme Administration Office (PAO) in Georgia

Office of the State Minister of Georgia for European and Euro-Atlantic Integration

7 Ingorokva Street, Tbilisi 0134

Georgia

Te: 995 32 2998914

E-mail: pao@eu-nato.gov.ge

Ms. Nino Kochishvili

Project Manager, Operations Section

Delegation of the European Union to Georgia

38 Nino Chkheidze Street, 0102 Tbilisi

Georgia

Tel: + 995 32 2943763

E-mail: Nino.Kochishvili@eeas.europa.eu

For the Lead Member State Partner

Regional Development Agency Senec Pezinok

Vysoka 35, 811 06 Bratislava,

Slovak Republic

Mrs. Luba Pavlovova

Director

Tel.: + 421 2 20 72 83 92 or + 421 903 77 36 74

Email: Lpavlovova@rrasenec-pezinok.sk

and

Mr. Branislav Ondrus

State Secretary/ MS Project Leader

Ministry of Labour, Social Affairs and Family of the Slovak Republic

Špitálska 4, 6, 8

816 43 Bratislava

Phone: +421 (0)2/ 2046 2713 or 2046 2723

E-mail: branislav.ondrus@employment.gov.sk

Secretariat of Mr Ondrus: Mrs. Dominika Beňušová and Mrs Tatiana Hinerová

For the Final Recipient of the Action

Ms. Tea Sturua

Project Leader

Head of Employment Programmes Department

Social Service Agency

Ministry of Labour, Health and Social Affairs of Georgia

144 Tsereteli ave

Tbilisi 0119,

Georgia

Mob: + 995 599 97 62 88

E-mail: tsturua@saesa.gov.ge

5.2	The expenditure verification referred to in Article 15.7 of Annex A2 will be carried out by

J&P, s.r.o.

Budkova 33

811 04 Bratislava

Slovak Republic

Tel: +421254640488

Fax: +421263811139

IČO: 313 940 94 (registration number)

IČ DIČ: 202 084 36 60 (tax number for VAT)

Article 6 - Annexes

6.1     The following documents are annexed to these Special Conditions and form an integral part of the contract:

Annex A1:          	Description of the Action (including Work Plan)

Annex A2:      	General Conditions applicable to European Union-financed grant contracts for external Actions

Annex A3:         	Budget for the Action (including co-financing part by the Final Recipient of the Action)

Annex A4:        	Contract-award procedures

Annex A5:         	Standard request for payment and financial identification form

Annex A6:        	Expenditure verification report

Annex A7:       	Special Financial Annex

Annex A8:		Mandates of Junior Project Partners (Hungary and Czech Republic)

Annex A9: 		CVs

6.2     In the event of conflict between the provisions of the present Special Conditions and any Annex thereto, the provisions of the Special Conditions shall take precedence. In the event of conflict between the provisions of Annex A2 and those of the other annexes, those of Annex A2 shall take precedence.

In case of discrepancies between Article 14 of Annex A2 and Annex A7, the latter shall prevail.

.

Article 7 - Other specific conditions applying to the Action

7.1     The General Conditions are supplemented by the following:

7.1.1 In annexes A2 to A7:

In case of consortium of Member State Partners, the Member State Partner signing the Twinning contract and leading the consortium is referred to as the Lead Member State Partner.

The term “Beneficiary(ies)” refers collectively to all Member State Partners (MSP), including the Lead Member State Partner.

The term “Coordinator” refers to the Lead Member State Partner.

When there is only one Member State Partner, the terms Beneficiary(ies) and Coordinator should both be understood as referring to the only Member State Partner.

7.1.2.	The Action is co-financed as per annex A3 by the Final Recipient of the Action.

7.1.3	In article 7.1 and 7.2 of annex A2, the term ’Beneficiary(ies)’ is replaced by ‘the Final Recipient of the Action’. Article 7.2 of Annex A2 applies also to any work done by the RTA(s) and other experts mobilised by the MSP(s) in the performance of their duties related to the implementation of the Action.

7.2	The following derogations from the General Conditions shall apply:

7.2.1	By derogation from article 9.4 of Annex A2, changes to the Twinning work plan and budget shall be governed by the procedure spelled out in Annex A7.

7.2.2	By derogation from Article 12.1 of Annex A2:

In case of failure by the Final Recipient of the Action to fulfil any of their obligations under the Twinning Contract, or for any other duly substantiated external reason, the MSP(s) may terminate the Twinning Contract by giving three months' notice in writing to the Final Recipient of the Action, after having informed the CA, the Commission Headquarters and the administrative office of the BC.

In case of failure by the MSP(s) to fulfil any of their obligations under the Twinning Contract, or for any other duly substantiated external reason, the Final Recipient of the Action may terminate the Twinning Contract by giving three months' notice in writing to the MSP(s), after agreement with the Commission Headquarters and after having informed the CA (where the Commission is not the CA) and the administrative office of the BC.

In case of failure by the MSP(s) or by the Final Recipient of the Action to fulfil any of their obligations under the Twinning Contract, or for any other duly substantiated external reason, the CA, after agreement with the Commission (where the Commission is not the Contracting Authority), may halt funding of the Action or terminate the Action by giving three/two months' notice in writing to the MSP(s) and the Final Beneficiary of the Action.

7.2.3.	By derogation from Articles 13.3 and 13.4 of Annex A2, the following procedure for settlement of disputes shall apply:

The Parties shall endeavour to settle amicably any dispute or complaint relating to the interpretation, application or fulfilment of this Twinning Contract, including its existence, validity or termination. In default of amicable settlement, any Party may refer the matter to arbitration in accordance with the Permanent Court of Arbitration Optional Rules for Arbitration Involving International Organisations and States in force at the date of this Agreement.

The language to be used in the arbitral proceedings shall be English, French or German. The appointing authority shall be the President of the Court of Justice of the European Union following a written request submitted by either Party. The Arbitrator’s decision shall be binding on all Parties and there shall be no appeal.

7.2.4	By derogation to Article 14.3 of Annex A2, eligible costs may also be constituted by unit costs (fee per day worked in the Beneficiary Country and per diems) and flat-rate financing (twinning management costs and 6% of salary and non-wage labour costs for the RTA), as defined in section 3.5 of Annex 7 and in the Common Twinning Manual.

7.2.5	By derogation to Article 14.4 of Annex A2, the first paragraph of Article 14.4 shall not apply.

7.2.6	By derogation to Article 14.5 of Annex A2, the total amount of financing on the basis of simplified costs options as defined in Article 7.2.4 above may exceed EUR 60 000.

7.2.7	Articles 14.6, 14.7 and 14.8 of Annex A2 shall not apply.

7.2.8	The last sentence of article 15.2 of Annex A2 (extension of the deadline for submission of the final report) shall not apply.

7.2.9	By derogation to Article 15.4 of Annex A2, the initial pre-financing payment shall be made within 30 days of the date of notification by the Contracting Authority of the contract signed by all parties.

7.2.10	The expenditure verification report of Article 15.7 of Annex A2 is only required for the final payment. The auditor is designated in accordance with the regulation prevailing for the MSP.

7.2.11	By derogation to Article 15.7 of Annex A2, a detailed breakdown of expenditure shall be submitted in support of each request for further pre-financing payment. This detailed breakdown of expenditure shall consist in the financial section of the narrative reports produced in compliance with Articles 2 and 15 of Annex A2, provided that this financial section complies with the requirements for a detailed breakdown of expenditure that are defined in paragraphs 4, 5 and 6 of Article 15.7 of Annex A2.

7.2.12	By derogation to Article 15.9 of Annex A2, costs incurred in other currencies are converted in Euro at the rate published by the Directorate General of the European Commission for Budget, at InforEuro (http://ec.europa.eu/budget/inforeuro/index.cfm) for the month in which the expenditure is incurred.

7.2.13	A Privacy statement is publicly available on the twinning website at the following address: http://ec.europa.eu/enlargement/pdf/financial_assistance/institution_building/privacy_statement_twinning_103994_en.pdf . The information contained therein applies to this Twinning contract.

7.2.14	All Twinning partners undertake to facilitate the organisation and conduct of the Twinning review Missions referred to in Article 9 of Annex A1 and described in the Common Twinning Manual.

7.2.15 The provisions of Article 7.1 and 7.2 of the General Conditions (annex A2) are supplemented by the following: all rights to any work done by RTAs in the performance of their duties become the property of the BC in question. The MSP and the Commission will be permitted to use the results of the work elsewhere by permission of the BC. Permission may only be refused where the proposed use is liable to prejudice the interests of the BC or the European Union, or where it is for commercial purposes.

Done at Tbilisi in four originals in the English language, one original being for the European Commission, one original being for the Contracting Authority (European Union Delegation to Georgia), one original being for the Member State Partner (RDA) and one original being for the Beneficiary Country Administration (Social Service Agency of the Ministry of Labour, Health and Social Affairs of Georgia).

For the Member State Partner                                                     For the Contracting Authority

Mrs Luba Pavlovova                                                                   Mr Janos Herman

Director 						         Head of Operation

Regional Development Agency Senec – Pezinok                       European Union Delegation

Bratislava Region                                                                        to Georgia

Slovak Republic

Signature	Signature

Date	Date

ANNEXES A: ANNEXES to the

Twinning CONTRACT

## ANNEX A1:		Description of the action (including the Work Plan)

## ANNEX A2:	General Conditions applicable to European Union-financed
grant contracts for external actions

## ANNEX A3:		Budget for the Action (breakdown of costs)

## ANNEX A4:		Contract Award Procedures

## ANNEX A5:		Standard request for payment and financial identification form

## ANNEX A6:		Terms of reference for an expenditure verification report

## ANNEX A7:		Special Financial Annex

ANNEX A8:		Mandate JP Hungary, Mandate JP Czech Republic

## ANNEX A 9:		CVs

# ANNEX A1
DESCRIPTION OF THE ACTION

TWINNING WORKPLAN

The Administration of Georgia, the Social Service Agency of the Ministry of Labour, Health and Social Affairs (hereinafter referred to as the BC) represented by MsTea Sturia, Head of Employment Programmes Department and the BC P r o j e c t   L e a d e r

of the one part,

And the Administration of the Slovak Republic, Regional Development Agency Senec - Pezinok (hereinafter referred to as the Member State) represented by Mrs. Luba Pavlovova, Director, who entrusts the implementation of the project to Mr. Branislav Ondrus, State Secretary and MS  P r o j e c t  L e a d e r

of the other part

HAVE AGREED THE FOLLOWING WORK PLAN WHICH THEY UNDERTAKE TO IMPLEMENT JOINTLY:

ARTICLE 1.	BACKGROUND

1. 1. BC policy developments in the sector

This twinning project is financed under the Sector Reform Contract, EVET (Employment and Vocational Education and Training). The EVET SRC, component 1, is aiming at complex support for stimulation of sustainable and inclusive socio-economic development through improved transition from training to employment. In this respect, this twinning project directly supports the implementation of component 1 of the EVET SRC. A chronology of main developments in the sector is provided below.

The previous Government pursued a laisser-faire employment policy. In 2006, the Government abolished the State Employment Services at central and local levels, closed the Employment Policy Department of the Ministry of Labour, Health and Social Affairs, and pursued a very liberal/flexible labour market policy. The policy proved largely unsuccessful and as a consequence unemployment rose sharply, peaking at 16.5% in 2008 and subsequently levelling out at the current rate of 15%.

The EU and Georgia recognise that the context of their relations has changed in a significant and positive way since the inception of the Eastern Partnership. The negotiations of an Association Agreement (hereinafter AA) began in 2010 and the Agreement was initialled on 29 November 2013. The AA negotiations were not a stand-alone exercise. EU assistance to Georgia is linked with the reform agenda as it emerges from the result of negotiations. Consequently, after completion of all necessary works and procedures, the AA was signed on 27th July 2014. This ambitious and pioneering Agreement represents a concrete way to exploit the dynamics in EU-Georgia relations, focusing on support to core reforms, on economic recovery and growth, governance and sector cooperation in areas such as, for example, energy, transport, environment protection, industrial and small and medium enterprise cooperation, social development and protection, equal rights, consumer protection, education, training and youth as well as cultural cooperation. The EU-Georgia cooperation is enhanced in some 28 key sector policy areas, among which the fields of employment, social policy and equal opportunities are of key importance.

In the areas of Employment, Social Policy and Equal Opportunities, the cooperation between EU and Georgia will be focused on:

- preparation for the implementation of the EU acquis in the area of health and safety at work, labour law and working conditions, and gender equality and anti-discrimination;

- develop a strategic approach to employment, aiming at more and better jobs with decent working conditions, better matching of skills and jobs in the labour market and promoting active labour market measures and efficient employment services;

- strengthen the capacities of the administration in charge of developing and implementing employment and social policies, notably employment services and social services, enhance the level of social protection, including through implementation of the universal health care including insurance programmes; and ensure the efficiency and financial sustainability of the social protection systems;

- encourage social dialogue through capacity-building of social partners.

In contrast the new Government has adopted a more interventionist approach. In June 2013, the Parliament adopted amendments to the Labour Code at the third and final reading, which entered into force in July. All International Labour Organization (ILO) standards-related provisions were properly adopted, which means that the Labour Code is now complying with ILO Conventions 87 and 98 in relation to collective bargaining and anti-discrimination. Provisions regarding fixed-term contracts were improve. The Ministry of Labour, Health and Social Affairs is working on the practical implementation of the amended Code.

New Employment Law, Migration Law, and Health and Safety Regulations are being drafted, and a Strategy and Action Plan (2013-2014) for the re-establishment of labour market institutions have been adopted. In addition, a Labour Market Strategy and an associated Action Plan (2013-2014) were adopted in August 2013, which target five key measures: establishment/improvement of the legal base; formation/development of the labour market infrastructure in order to enhance the range and quality of services available to job-seekers; improved labour market information, through the institutionalization of labour market analysis and the establishment/development of a labour market database; greater synergy between the needs of the labour market and the provisions of the Vocational Education and Training (VET) and continuing education systems; and supporting legal, temporary migration. The present Strategy was conceived as an interim document in order to guide immediate actions to tackle unemployment. Work has commenced on developing a long-term Strategy and Action Plan, which is expected to be ready by the third quarter of 2014.

The IMFhas estimated the unemployment rate in 2013 at 16.7 %, amongst the highest in the region. Over 50% of the unemployed have secondary education and 40 % are university graduates. The situation of young people (age 15-24) is also problematic as evidenced by the fact that about 30 % are not in education, training or employment. Geostat data also show wide gender disparities, with the activity rate for women estimated at 54 % (20 points less than men) and the employment rate at 48 % (15 points less). Georgia’s budget for 2013 provided for increased social spending to protect the most vulnerable groups, while continuing on the path of fiscal consolidation.

the Government initiated a number of structural/institutional changes to reinforce the ability of the MoLHSA to develop sound labour market policies and to strengthen the capacities of public institutions to deliver high quality services. In February 2013, the MoLHSA established a new Employment and Labour Policy Department. The Department comprises three Divisions: Labour Migration, Labour Relations and Social Partnership, and Employment Promotion. The Ministry has a total permanent staff complement of 238, and an additional 59 contractual employees. The Employment and Labour Policy Department has a complement of 20 employees. The Department acknowledges that it needs capacity building and technical assistance in order to develop the necessary analytical and policy-making skills in the areas of employment and labour market.

State policy is implemented through the Legal Entities of Public Law (LEPL), which are under the control of the Ministry. There are 7 LEPL under the control of the MoLHSA, of which 4 are responsible for implementing health policy, while 3 deal with social policy, including employment promotion policies.

During the recent months (e.g. in December 2014) a number of positive developments happened:

- Labour Market Strategy 2015-2018 was adopted by the Government of Georgia and the Action Plan

- Labour market information system - Implementing and Developing Concept 
and 2015-2018 Action Plan

- Continuous career planning and professional counselling Development concept and 2015-2018 Action Plan

- Ministry of Labour, Health and Social Affairs  has approved the SSA employment support services development and 2015-2018 Action Plan

The Labour Market Strategy 2015-2018 outlined in nowadays the labour market of Georgia is facing the following challenges:

- Low employment and high unemployment levels (according to the GeoStats the employment level of the population 15+ makes 56,6%, and unemployment level makes 14,6%).

- High index of informal employment and labour migration.

- High level of youth unemployment and large part of long time unemployed among unemployed population.

- Long-term structural unemployment, caused with derangement of the industrial and economical system as a result of disintegration of the Soviet Union;

- Incomplete application of labour resource certified with low involvement of persons, who have attained working age, in labour market.

- Nonexistence of reliable information about amount and structure of the labour force in the country, professional and territorial mobility, labour migration and immigration.

- Superfluity of low-paid and/or low-qualification jobs, which are basically concentrated on service, agrarian and trade sectors.

- Mismatching of the knowledge and skills of the labour resources existing in the country to requirements of the labour market, caused with shortage of information and/or irrelevance of these requirements.

- Obvious deficit of information about the structure of the current labour market, real and potential growth indicator of the requirement, caused with tangential information about labour market components and characteristics.

- Insufficient development of the employment support services – shortage of career planning and vocational consulting services, caused with lack of information about labour market.

- Imperfect coordination between education and vocational training and retraining policy on the one side and labour market requirements on the other side, caused with nonexistence of the labour market informational system.

The priority of the Government is to support to reduction of the unemployment level with implementation of active labour market policy – existence of information about labour market and institutionalization of analysis of the given information is vitally essential.

- Of immediate relevance to this Twinning project is the Social Services Agency (SSA), which is an LEPL subordinate to the Ministry. Responsibility for the provision of employment services has been allocated to the Social Services Agency. The SSA is regulated by Order of the Minister of Labour, Health and Social Affairs #190/n, June 27th 2007. Article 2 of the SSA’s Charter defines the Goals, Functions, Powers and Principles of the SSA as they relate specifically to labour market issues.

Recently, the a) intermediary service implementation rules and b) the general job seekers counselling handbook were approved by SSA.

By strengthening the institutional and human capacity of the Employment Support Services of Georgia Social and Economic Councils (ESS) to deliver well-targeted high-quality services which are gender-sensitive and cost-effective to job-seekers as well as to employers, this twinning project will contribute to reducing the poverty and enhancing social cohesion in Georgia. Thus project will take into account all new developments recently achieved (2014) in the sector and will result in putting efforts and designing and introducing tailor-made measures for stimulating employment while bringing synergy between labour markets needs and skills and qualifications offered by the Georgian vocational education and training system.

The project will also aim to empower ESS and MoLHSA and other relevant Georgian staff to become the effective and experienced for reaching project main objective and meeting obligations arising from the Association Agreement. Activities under this twinning project will be linked to any results already achieved within other relevant projects accomplished in Georgia or to any ongoing relevant actions.

In this respect, the project will support the ESS/MoLHSA to provide employment services in line with good EU practices and, at the same time, tailored to the Georgian realities and economic and social situation.

At the end, the implementation of activities designed within the project will contribute to reach the following mandatory results:

- Mandatory Result 1: Revision of the Georgian Legal Framework of equal opportunities legislation and related to employment in line with the EU acquis and in accordance with the provisions of Annex XXX of the Association Agreement (chapter 14, Employment, social policy and equal opportunities);

- Mandatory Result 2: The structure and functions of the ESS have been revised to reflect it expanded role in the labour market management processes, the range and quality of services provided to job-seekers have been piloted and enhanced,  the internal management and administrative processes have been clearly codified;

- Mandatory Result 3: A comprehensive Labour Market Information Management System (WorkNet Information System) has been established and fully operational;

- Mandatory Result 4:  Modern human resource management techniques have been introduced, the staff have acquired the necessary skills and experience to provide high quality services to job-seekers, and an in-house training and retraining platform has been established;

- Mandatory Result 5: The ESS has acquired the necessary tools and materials to communicate effectively its range of services to clients and potential clients

1. 2. Beneficiary institutions and other parties involved

Main beneficiaries:

The principal beneficiaries are:

- Employment Support Services (ESS), which forms a constituent part of the Social Service Agency and which is located in Tbilisi;

- Ministry of Labour, Health and Social Affairs of Georgia (MoLHSA)

- Employment Support Services (ESS) is an LEPL (Legal Entity of Public Law) and it is subordinated to the MoLHSA. Responsibility for the provision of employment services has been allocated to the Social Services Agency. The SSA is regulated by Order of the Minister of Labour, Health and Social Affairs #190/n, June 27th 2007. Article 2 of the SSA’s Charter defines the Goals, Functions, Powers and Principles of the SSA as they relate specifically to labour market issues:

- create and develop electronic system and data bases for registration of job-seekers and available (free) jobs;

- develop cooperation with employers, employers’ associations and private employment agencies in order to ensure efficiency of intermediary services in Georgian labour marker;

- promote and implement research on current and future tendencies of demand and supply of Georgian labour market;

- provide informative and consultative services to job seekers;

- organize, implement and/or participate in implementation of training/vocational education of job-seekers;

- implement state programme on employment;

- organize and/or participate in the organization of job fairs;

- develop international cooperation on employment issues

The Head Office of the SSA is located in Tbilisi and is complemented by 10 regional offices, 69 district offices.  There are 13 Departments within the Head Office, of which 7 are responsible for the provision of specific services. The SSA has a total staff complement of 1719 persons, of which 366 work at Head Office and 1353 in the regional and district offices. The statutes of the Social Service Agency have recently been amended to allocate the Agency a significant role in the coordination of the activities of the Employment Support Services (ESS) at national and district level, to host the Labour Market Information system, and to oversee implementation of labour market and employment policies. Specific responsibility for the management of labour market issues rests with the Employment Programmes’ Department, which is a constituent part of the SSA. The Head of the Department reports directly to the Minister of Labour, Health and Social Policy. The Department has a permanent staff complement of 18, of which 16 are currently employed and two posts are vacant. It also has access to a further 40 contract posts (i.e. non-permanent). At present, 16 of these posts are filled and the persons employed work within the Employment Programmes’ Department. The remaining posts (24) are provisionally assigned to the district offices. The posts will be advertised once there is greater clarity on the functions/range of services to be offered through the district offices.

The Employment Programmes’ Department is led by a Head and Deputy Head of Department and is divided into two Divisions: the Division for State Programmes in support of employment promotion and the Labour Market Management Information System Division. The former has 8 full-time members of staff, while the latter has 6 members of staff currently employed and two posts unfilled. The Department’s competencies are regulated by the general regulation governing the work of the SSA. The Department is presently represented by one member of staff in each of the 69 District Centres of the SSA. These sub-units are referred to as District Centres of Employment and are regulated through their own Charters. Collectively the Employment Programmes’ Department and the 69 District Centres of Employment are referred to as the Employment Support Services (ESS).Given that the ESS will now play a strategic role in the implementation of the Government’s Socio-Economic Development Strategy of Georgia, “Georgia 2020” and the MoLHSA’s Labour Market Strategy and Action Plan, and given that the ESS has limited experience of designing, delivering and monitoring support services to job-seekers, managing active labour market initiatives, or carrying out labour market diagnoses, support is urgently required in order to ensure the establishment of a comprehensive, efficient and effective Service.

Contact person for the ESS

Ms. Tea Sturua

Head of Employment Programmes Department/BC Project Leader

Social Service Agency

Ministry of Labour, Health and Social Affairs of Georgia

144 Ak.Tsereteli ave, Tbilisi 0119, Georgia

Mob: + 995 599 97 62 88

E-mail: tsturua@saesa.gov.ge

- The MoLHSA´s mission is to ensure sustainable development of human capital through elaborating and implementing effective national health and social policies and thus to create high quality, fare, and accessible social system for every citizen in the country through consequent implementation of reforms. The Ministry works in five basic directions to fulfil this mission:

1. Improving the health of the people of Georgia by guaranteeing universal access to a package of public health and priority basic health services available to the entire population regardless of place of residence or financial circumstances

2. Helping the population to protect themselves from the catastrophic financial effects of ill health by developing, and financing for the poor, an affordable, accessible, and acceptable basic health insurance product.

3.  Increasing the quality of public and private health services by developing appropriate regulations, including contracting, for controlling and monitoring the quality of health services and making information widely available on health care provider performance.

4. Strengthen the stewardship and governance function of the MoLHSA and affiliated organizations through an improved policy and regulatory framework and more effective management of the health sector.

5. Enable more effective use of health care resources by upgrading, restructuring and better integrating the health service delivery infrastructure, and creating an appropriately sized, trained and distributed health sector labour force.

Contact persons for MoLHSA

Ms. Elza Jgerenaia
Head of Department of Labour and Employment Policy

Ministry of Labour, Health and Social Affairs of Georgia
144 Ak. Tsereteli Ave., Tbilisi 0119

Georgia
Tel.: +99568 01 71 17 /+(995 32) 2 51 00 11 (ext.1507)

Email: akvernadze@moh.gov.ge

and

Mr Tengiz Abazadze

Deputy Head of SSA

Social Service Agency

Ministry of Labour, Health and Social Affairs

144 Ak. Tsereteli Ave., Tbilisi 0119

Georgia
Tel.: +99 591 050900

Email:  tabazadze@ssa.gov.ge

Other beneficiaries/Indirect stakeholders are:

- Ministry of Education and Science (MoES)

The Ministry of Education and Science of Georgia aims at establishing modern and innovative educational and scientific environment in close cooperation with civil society. The Ministry advocates freedom of choice, fair competition, equal opportunities, civil integrity, and respect for cultural identity. The Ministry promotes acquisition and development of knowledge and skills necessary for social success and self-realization.

Contact details:

Ministry of Education and Science (MoES)

Dimitri Uznadze N 52

0102 Tbilisi, Georgia

Tel: (995 32 2) 200 220

E-mail: pr@mes.gov.ge

Ministry of Finance (MoF)

Gorgasali Str 16,

Tbilisi 0114, Georgia

Tel.:+995 32 2 261 444

Ministry of Regional Development and Infrastructure (MoRDI)

Al.Kazbegi ave. 12

Tbilisi, Georgia

Tel: +995 32 2510649

e-mail: giorgi@mrdi.gov.ge

Ministry of Economy and Sustainable Development (MoESD)

Chanturia Str. 12

Tbilisi, 0108, Georgia

Tel: +(995 32) 299 11 11;  +(995 32) 299 11 05.
Fax: +(995 32) 292 15 34
E-mail: ministry@economy.ge

Ministry of Agriculture (MoAG)

6,Marshal Gelovani ave,

Tbilisi 0159; Georgia

Phone:  (+995  32) 237 66 89

(+995  32) 237 80 14

email: infomoa@moa.gov.ge

The cooperation mechanism will be set up for a smooth involvement and participation of all the nominated institutions into the relevant project activities.

As a general rule, the institutions and their staff (relevant ministries and other partner’s representatives’ staff) will be involved into the project implementation based on their competences, topic/s covered by concrete project activities and their role addressed to the project.

There are 2 cooperation levels to be operated during the project implementation – Steering Committee (SC) Meetings(management and monitoring level) and specialised working groups (operational level).

The nomination to the SC members will be done based on the Statute of the SC and the Rules of the SC Meetings. Implementation of the project activities will be conducted on the operational level based on the relevant working groups created for the particular issue. The nomination of the working groups members will be conducted based on the agreed procedures with the BC partner.

In addition to the above, during the first month of RTA arrival to the country, he will, together with ESS senior management, establish contacts with the Technical Assistance TA project within MoLHSA and MoES.

In line with the above-mentioned, the following formal settings will be operational and available: the EVET Council for coordination of the whole programme (organized on a quarter basis; the beneficiary Agency as well as the RTA and RTA-counterpart will be invited),  the SC for the TA service contract to be held on a quarter basis;  the RTA and RTA-counterpart as well as SSA Agency representative will be  participants of the latter). The SC for the Twinning project – in which the TL and Deputy TL of the TA service contract, could be invited. The already suggested specialized working groups will ensure the overall coordination at project operational level.

1. 3. Parallel or related projects in the field

This Twinning Project will be seen as continuation of few international initiatives in this field and will use the project’s outputs and results achieved. The project is a constituent part of the Employment and Vocational Education and Training Sector Reform Contract, being financed through EaPIC 2013. The actions to be implemented under this Twinning Contract will extend and reinforce the activities defined within the wider Sector Reform Contract and will complement the Technical Assistance project designed to strengthen the capacities of the Ministries of Labour, Health and Social Affairs and Education and Science. Together they will assist the Georgian authorities to address the issues described above.

To date there has been limited direct support provided to labour and employment issues, although the EU has provided and continues to provide substantial indirect support through Sector Reform Contracts targeted at Vocational Education and Training, the European Neighbourhood Programme on Agriculture and Rural Development (ENPARD) and Regional Development.

- In 2014, the ETF made an intervention to support the Ministry of Labour, Health and Social Affairs through the elaboration of policy guidelines and capacity building on how to implement the most effective and efficient training and retraining programmes for the unemployed in Georgia. Four international experts were working on topics of specific interest for the Georgian staff, i.e. LM monitoring and employer’s questionnaires, ALMP and unemployed peoples trainings, LMIS. Four workshops were held at the MoLHSA and SSA involving the staff of these institutions. LMIS Concept Note was prepared as well within the implementation of the above-mentioned actions.

- The International Organisation for Migration (IOM) was also intending to provide support in 2014 to the ESS to strengthen its work vis-à-vis the reintegration of returned nationals within the framework of the project: “Reinforcing the capacities of the Government of Georgia in border and migration management”.

- The World Bank is currently financing the Technical Assistance project to the MoLHSA on improving the matching of registered unemployed to training programmes. As a result of this intervention MOLHSA/SSA will be able to fine-tune the matching procedure to be developed by the consultancy. The team will develop guidelines and recommendations for a monitoring and evaluation (M&E) system. In the short-run, the M&E system will allow the MoLHSA/SSA to monitor and evaluate the effectiveness of the training; in the long-run, the M&E system will also include an assessment of the quality of the eventual job placement. The project started at the end of March 2014.The ISET Policy Institute (ISET-PI) was commissioned by the World Bank to assist the Social Service Authority (SSA) of Georgia to identify those qualifications offered by vocational and educational training (VET) institutions that should be promoted by the government. ISET-PI carried out an analysis in the municipalities of Gori, Kutaisi, Batumi and Rustavi. The applied criteria for evaluating qualifications were (a) the demand in the Georgian labour market, and (b) the willingness of job seekers to receive training in a field. They also decided to manage Recommendation System for job seekers.

There is presently no Sector Coordination Council for Employment issues and relationships between the Ministry of Labour, Health and Social Affairs and the donors are dealt with on a bilateral basis. There is however a tripartite council, involving the Ministry and the social partners, which meets regularly to discuss employment-related policies.

The outputs of the projects will be taken into account while implementing the activities within the project components.

ARTICLE 2.	ACQUIS - PROJECT FICHE FIELD OF COOPERATION WITH THE EU

Relevant Field of Cooperation with the EU

The twinning project will contribute to the implementation of commitments undertaken by the Georgian government arising from Association Agreement and its annexes, more specifically from chapter 14 related to the Employment, Social Policy and Equal Opportunities.

The project reflects the needs of the country and priorities set up in the EC document as of 27th March 2014 “Implementation of the European Neighbourhood Policy in Georgia Progress in 2013 and recommendations for action“. Moreover, the project is aiming directly at building the legislative and policy capacities for effective functioning of the labour market in the country while providing targeted, gender sensitive and cost-effective employment services to job-seekers and employers.

Therefore, the project is also aiming at strengthening the institutional capacity of ESS/MoLHSA on national, regional and local level to empower relevant staff to provide such services while taking into consideration EU good practices. In this respect the following EU acquis and standards will be implemented in national legislation within the upcoming period based on the Georgia priorities and respecting the current stage of works already done and taking into account the Commission’s recommendations.

The following Anti-discrimination and Gender Equality  directives which are in compliance with the Annex XXX of the AA will be covered by this twinning project:

- Council Directives 2000/43/EC, of 29 June 2000 implementing the principle of equal treatment between persons irrespective of racial or ethnic origin

- Council Directives 2000/78/EC of 27 November 2000 establishing a general framework for equal treatment in employment and occupation

- Council Directive 2006/54/EC of the European Parliament and of the Council of 5 July 2006 on the implementation of the principle of equal opportunities and equal treatment of men and women in matters of employment and occupation (recast)

- Council Directive 2004/113/EC of 13 December 2004 implementing the principle of equal treatment between men and women in the access to and supply of goods and services

- Council Directive 92/85/EEC of 19 October 1992 on the introduction of measures to encourage improvements in the safety and health at work of pregnant workers and workers who have recently given birth or are breastfeeding (tenth individual Directive within the meaning of Article 16(1) of Directive 89/391/EEC)

- Council Directive 79/7/EEC of 19 December 1978 on the progressive implementation of the principle of equal treatment for men and women in matters of social security

The following EU directives and secondary legislation relating to protection of young people at work could be also taken into consideration

- (31975L0117) Council Directive 75/117/ЕЕC of 10 February 1975 on the approximation of the laws of the Member States relating to the application of the principle of equal pay for men and women

- (31976L0207) Council Directive 76/207/ЕЕC of 9 February 1976 on the implementation of the principle of equal treatment for men and women as regards access to employment, vocational training and promotion, and working conditions

- (32002L0073)  Directive 2002/73/ЕC of the European Parliament and of the Council of 23 September 2002 amending Council Directive 76/207/ЕЕC on the implementation of the principle of equal treatment for men and women as regards access to employment, vocational training and promotion and working conditions (Text with EEA relevance)

- (32000Y0731(02)) Resolution of the Council and of the Ministers for Employment and Social Policy, meeting within the Council of 29 June 2000 on the balanced participation of women and men in family and working life

- 32010L0018 Council Directive 2010/18/EU of 8 March 2010 implementing the revised Framework Agreement on parental leave concluded by BUSINESSEUROPE, UEAPME, CEEP and ETUC and repealing Directive 96/34/EC

-		(31994L0033) Council Directive 94/33/EC of 22 June 1994 on the protection of young people at work

-	(31967H0125) 67/125/ЕEC:  Commission Recommendation of 31 January 1967 to the     Member States on the protection of young workers

-	(32000H0581) 2000/581/EC: Commission Recommendation of 15 September 2000 on the ratification of International Labour Organisation (ILO) Convention No 182 of 17 June 1999 concerning the prohibition and immediate action for the elimination of the worst forms of child labour( notified under document number C (2000)2674)

The list of the above-mentioned EU Directives will remain open for the project implementation period to enable inclusion of the new ones potentially adopted meanwhile.

ARTICLE 3.	MANDATORY RESULTS (OUTPUTS)

|  | Intervention logic | Benchmarks | Sources of Verification | Assumptions (External to project) |
| --- | --- | --- | --- | --- |
| Overall objective | To reduce poverty and enhance social cohesion in Georgia through the introduction of measures designed to stimulate employment, and to ensure synergy between the demands of the labour market and the skills and qualifications offered by the vocational education and training system. | - Reduction in numbers of citizens living on or below the poverty line - Reduction in numbers of unemployed - Increase in total active labour population | - EC Regular Report on progress by Georgia in implementation of the AA - GEOSTAT reports - MoLHSA Annual Reports |  |
| Project purpose | The project purpose is to strengthen the institutional and human resource capacities of the Employment Support Services of Georgia to deliver well-targeted, high-quality, gender-sensitive and cost-effective services to job seekers | - Enhanced management and administrative arrangements within the ESS - Institutional reorganisation has been completed - Operational guidelines for the full range of services offered by the ESS have been prepared and codified - Comprehensive quality assurance plan designed and implemented - Labour Market Information Management System (WorkNet Information System) upgraded and providing quantitative and qualitative data on current state of Georgian labour market - Staff are well-trained - ESS has developed the tools and techniques for preparing and delivering well-targeted and user-friendly communications and awareness raising campaigns | - EC Regular Reports on progress by Georgia in implementation of the AA - MoLHSA and ESS Annual Reports - Progress Reports delivered by the Partner Country in Twinning Project Evaluation reports - Satisfaction of job-seekers and employers with the quality and range of services provided by ESS | - Continued commitment to an interventionist labour market policy - MoLHSA continues to develop and implement coherent labour market policies, notably linked to active employment initiatives - Adequate budgetary resource allocation to the ESS permitting it to extend the range and quality of its services - Sufficient capacity within the ESS to absorb the assistance provided by Twinningpartner. |
| Mandatory results (Components) | COMPONENT 0 Visibility events and project management Mandatory result: Two project visibility events organised and high level of dissemination of information achieved | - 2 key visibility events organised: 1 Kick-off and 1 Final Conference - Information disseminated through various communication channels media - Visibility and promotional materials developed and disseminated | - Attendance of the list of participants - Media coverage report - Press clipping published - Quarterly report - Final report |  |

|  | COMPONENT 1 Mandatory result: Revision of the Georgian Legal Framework of equal opportunities legislation and related to employment in line with the EU acquis and in accordance with the provisions of Annex XXX of the Association Agreement | - Review of Georgian Equal Opportunities legislation related to employment and measure of concordance with EU Equal Opportunities legislation identified in Annexes of the Association Agreement - Drafting a Concordance Report and recommendations for harmonisation of the Georgian legislation related to employment with the EU Equal Opportunities Directives identified in Annexes of the Association Agreement - Support to legal drafting with regard to the Equal Opportunities legislation related to the employment service identified in the relevant Annexes of the Association Agreement - Gap analysis of the equal treatment and non-discrimination sections of the regulations for which the ESS has competence - Regulatory drafting support to the ESS in order to ensure compliance of the regulations for which it has competence with the revised Georgian Equal Opportunities legislation harmonised with EU Equal Opportunities legislation | - Official Journal of the Georgian Parliament(Indicator 1.1, 1.2 & 1.3) - EU Regular Reports on the implementation of the AA(Indicator 1.1, 1.2 & 1.3) - MoLHSA/ESS Regulations(Indicator 1.4 & 1.5) | - Adequate legal and regulatory drafting capacity within the MoLHSA and ESS - Continued commitment to an interventionist labour market policy - MoLHSA continues to develop and implement coherent labour market policies, notably linked to active employment initiatives - Adequate budgetary resource allocation to the ESS permitting it to extend the range and quality of its services - Sufficient capacity within the ESS to absorb the assistance provided by Twinning partner - Sufficient financial resources within the MoLHSA to develop the Labour Market Information System - Motivation of ESS/MoLHSA staff involved into the project implementation - Readiness of ESS/MoLHSA staff to incorporate new practices into work |
| --- | --- | --- | --- | --- |
|  | COMPONENT 2 Mandatory result: The structure and functions of the ESS have been revised to reflect it expanded role in the labour market management processes, the range and quality of services provided to job-seekers have been piloted and enhanced, the internal management and administrative processes have been clearly codified | 2.1Functional Review of the SSA/ESS 2.2 Support to drafting of an Institutional Reform Plan for the SSA/ESS 2.3 Support to the implementation of institutional reforms within the SSA/ESS 2.4Review and revision (if required) of the current procedures for registration of job-seekers and job opportunities 2.5Introduction of new services within the ESS 2.6Support to the further development of job-seeker counselling services 2.7Development of a Procedures Manual 2.8Development of a Quality Assurance Plan 2.9Study Visit to MSs to examine the range of services provided to job-seekers and employers through employment offices | - STEs reports - (Indicator2.1, 2.2, 2.3,2.4, 2.5, 2.6, 2.7& 2.8) - Functional Review document(Indicator 2.1) - Institutional reforms – ESS &MoLHSA Annual Reports (Indicator s 2.1, 2.2& 2.3 ) - Revised registration procedures - ESS & MoLHSA Annual Reports (Indicator 2.4) - Number of new services introduced - ESS & MoLHSA Annual Reports (Indicator 2.5) - Revised methodology for counselling services - ESS & MoLHSA Annual Reports (Indicator 2.6) - Procedures Manual(Indicator 2.7) - Quality Assurance Plan (Indicator 2.8) - Study visit report (Indicator 2.9) - Project reports |  |
|  | COMPONENT 3 Mandatory result: A comprehensive Labour Market Information Management System (WorkNet Information System) has been established and is fully operational | 3.1Review of the WorkNet Information System 3.2Elaboration of a Concept Paper for upgrading the WorkNet Information System 3.3Preparation of Terms of Reference/Technical Specifications for upgrading the WorkNet Information System 3.4 Development of methodology and tools for the preparation of monthly/quarterly and annual labour market reports 3.5 Study Visit to MSs to examine the collection, collation and analyses of Labour market data by the employment services | - STE report - (All indicators) - Concept Paper(Indicator 3.2) - Terms of Reference/Technical Specifications(Indicator 3.3) - Methodology and tools for labour market reports (Indicator 3.4) - Study visit report (Indicator 3.5) - Project reports |  |
|  | COMPONENT 4 Mandatory result: Modern human resource management techniques have been introduced, the staff have acquired the necessary skills and experience to provide high quality services to job-seekers, and an in-house training and retraining platform has been established | 4.1Review of current HRD policy 4.2Drafting of an HRD Manual 4.3Conduct Training Needs Analysis 4.4Development of Training Programme and Training Materials 4.5Conduct Formal and in-service trainings for the ESS staff 4.6 Development of the Training manual 4.7 Training/retraining platform (Train the trainers) | - STE reports - (All indicators) - Review Paper(Indicator 4.1) - HRD Manual(Indicator 4.2) - Training Needs Analysis (Indicator 4.3) - (Indicator 4.1 - Training programme and training materials (Indicator 4.4) - Feedback evaluation sheets (training) (Indicator4.5.) - Training Manual (Indicator 4.6) - ToT feedback evaluation sheets(Indicator 4.7) - Project reports |  |
|  | COMPONENT 5 Mandatory result: The ESS has acquired the necessary tools and materials to communicate effectively its range of services to clients and potential clients | 5.1Review of current communications policies and recommendations for upgrading 5.2Support to the establishment of a Communications Unit within the ESS 5.3 Elaboration of communications and awareness raising strategy and Action Plan 5.4Development and application of communications tools and materials 5.5. Study Visit to MSs to experience practical use of the promotion and marketing of services to job-seekers and employers | - STE report - (Indicator5.1) - Communications and Awareness Raising Strategy and Action plan (Indicator5.2) - Communications materials, updated website, awareness events (Indicator5.2 - Study visit report (Indicator 5.4) - Project reports |  |
| COMPONENT 0 | Activity 0.1. Project management including the Steering Committee meetings, monthly meetings and project visibility | - Min . 15 monthly meetings organised - 6 Quarterly SC meetings held | Attendance list of participants Attendance list of journalists Quarterly report | - The ESS assigns appropriately skilled and competent staff at all levels to act as counterparts to the RTA and his/her colleagues - The ESS releases members of staff to participate in Project activities (e.g. training workshops, study tours, communications actions) - The ESS ensures that the results of the project are fully integrated into the work routine of the ESS - The ESS provides access to all relevant legislation, regulations, policies, strategies and supporting documentation relevant to the Project - The ESS facilitates access to regional offices of the ESS, and to decision-makers at national, regional and local levels - The ESS provides suitable venues for training workshops/presentations/meetings held within the framework of the Project |
|  | Activity 0.2. Kick-off meeting and first SC meeting | - Kick-off meeting held - Press conference conducted - Visibility materials for the kick-off event published | Monthly reports Attendance list of participants Monthly minutes Quarterly reports Project final report |  |
|  | Activity 0.3 Closure Meeting – Final conference. | - 1 closing conference prepared and organised - Press conference conducted - Visibility materials for the kick-off event published | Attendance list of participants Quarterly reports Final report Monthly minutes Project final report |  |
| COMPONENT 1 | Activity 1.1. Review of Georgian Equal Opportunities legislation related to employment and measure of concordance with EU Equal Opportunities legislation identified in Annexes of the Association Agreement | A short-term legal/regulatory drafting expert conducted a review of Georgian Equal Opportunities legislation and related to employment in order to determine the measure of compliance with the EU Equal Opportunities Directives identified in Annexes of the Association Agreement. | Review report of Georgian Equal Opportunities legislation Project quarterly reports Mission reports Project final report |  |
|  | Activity 1.2 Drafting a Concordance Report and recommendations for harmonisation of the Georgian legislation related to employment with the EU Equal Opportunities Directives identified in Annexes of the Association Agreement; | - On the basis of the review (1.1), the short-term legal/regulatory drafting in a form of Concordance Report prepared. The Report will highlight where there are gaps in the legislation related to employment or where the current provisions are not aligned with the EU Equal Opportunities Directives identified in Annexes of the Association Agreement. - Complete set of recommendations for closing the gaps and ensuring harmonisation with the relevant EU Directives elaborated. | Concordance Report Recommendations as part of the Concordance report Project Quarterly reports Mission reports Project final report |  |
|  | Activity 1.3 Support to legal drafting with regard to the Equal Opportunities legislation related to the employment service identified in the relevant Annex XXX of the Association Agreement; | - Draft/Amendments to Georgian legislation to ensure that it is harmonised with Council Directives Nº2000/43/EC, Nº2000/78/EC, and Nº2006/54/EC related to the principles of equal treatment and non-discrimination in employment supporting services elaborated in accordance with the recommendations appended to the Concordance Report | Draft amendments to the GE law in compliance with relevant EU directives Project Quarterly reports Mission reports Attendance list of participants Project final report |  |
|  | Activity 1.4 Gap analysis of the equal treatment and non-discrimination sections of the regulations for which the ESS has competence; | - Gap Analysis to ensure that the regulations for which the ESS has competence are consistent with Georgian legislation that should be harmonised with Council Directives Nº2000/43/EC, Nº2000/78/EC, and Nº2006/54/EC related to the principles of equal treatment and non-discrimination in employment supporting services conducted. - Complete set of recommendations for revising the regulations in order to ensure compliance in EU law elaborated as part of Gap Analysis. | Gap Analysis document Set of recommendations Project Quarterly reports Mission reports Attendance list of participants Project final report |  |
|  | Activity 1.5 Regulatory drafting support to the ESS in order to ensure compliance of the regulations for which it has competence with the revised Georgian Equal Opportunities legislation harmonised with EU Equal Opportunities legislation | - Legal Revision elaborated for those regulations for which it ESS has competence ensuring that the revised regulations are consistent with Georgian legislation that should be harmonised with Council Directives Nº2000/43/EC, Nº2000/78/EC, and Nº2006/54/EC related to the principles of equal treatment and non-discrimination in employment supporting services | Legal Revision of those regulations for which it has competence ensuring that the revised regulations are consistent with Georgian legislation that should be harmonised with Council Directives Nº2000/43/EC, Nº2000/78/EC, and Nº2006/54/EC related to the principles of equal treatment and non-discrimination in employment supporting services Project Quarterly reports Mission reports Attendance list of participants Project final report |  |
| COMPONENT 2 | Activity 2.1. Undertake Functional Review of the SSA/ESS; | - Review the SSA’s/ESS’s Charter and Mission Statement conducted - Functional analysis of the management structure of the SSA/ESS, the range of services offered, and the distribution of tasks and staffing elaborated - Recommendations on management/administrative and operational changes, where necessary and appropriate elaborated | Review document Functional Analysis Report Project Quarterly reports Mission reports List of interviewed persons Project final report | - The ESS assigns appropriately skilled and competent staff at all levels to act as counterparts to the RTA and his/her colleagues - The ESS releases members of staff to participate in Project activities (e.g. training workshops, study tours, communications actions) - The ESS ensures that the results of the project are fully integrated into the work routine of the ESS - The ESS provides access to all relevant legislation, regulations, policies, strategies and supporting documentation relevant to the Project - The ESS facilitates access to regional offices of the ESS, and to decision-makers at national, regional and local levels - The ESS provides suitable venues for training workshops/presentations/meetings held within the framework of the Project |
|  | Activity 2.2. Support to drafting an Institutional Reform Plan for the SSA/ESS | - Institutional Reform Plan for the SSA/ESS prepared | Institutional Reform Plan Project Quarterly reports Mission reports Project final report |  |
|  | Activity 2.3. Support to the implementation of theInstitutional reform of the SSA/ESS | - Institutional Reform Plan implemented - Revisions to the ESS’s Charter, Mission Statement and Regulations, a redefinition of the range of services offered, and a scheme ensuring a more efficient distribution of tasks and staff implemented | Project Quarterly reports Mission reports Attendance list of participants Project final report |  |
|  | Activity 2.4. Review and revision (if required) of the current procedures for registration of job-seekers and job opportunities | - The STE will assist Review of the ESS operating procedures and methodologies for the registration of job-seekers and job opportunities including provision of matching services to clients to ensure that the current procedures allow for the profiling and tracking of job seekers and job opportunities conducted - Recommendations to the ESS for strengthening its registration procedures prepared | Review Report of the ESS operating procedures and methodologies for the registration of job-seekers and job opportunities Set of Recommendations Project Quarterly reports Mission reports Attendance list of participants Project final report |  |
|  | Activity 2.5. Introduction of new services within the ESS | - New services, as appropriate, introduced. - Guidelines, methodologies, and tools for each of the new services developed and introduced. | Guidelines, methodologies, and tools for each of the new services Project Quarterly reports Mission reports Project final report |  |
|  | Activity 2.6. Support to the further development of job-seeker counselling services | - Counselling services for job-seeker developed - Piloting of the enhanced counselling services done in at list 30% of the total ESS offices and revised according to the outcomes of the piloting. | Counselling services document Piloting Report Revision document of counselling services piloting Project Quarterly reports Mission reports List of participants in piloting Project final report |  |
|  | Activity 2.7. Development of a Procedures Manual | - Internal Procedures Manual for use by Head Office and Regional Office staff elaborated | Internal Procedures Manual Project Quarterly reports Mission reports Project final report |  |
|  | Activity 2.8. Development of a Quality Assurance Plan | - Quality Assurance Plan elaborated - Quality controls for use of the manual by Head Office and District Office staff installed | Quality Assurance Plan Report on results of the installation of Quality controls Project Quarterly reports Mission reports Attendance list of participants Project final report |  |
|  | Activity 2.9. Study Visit to MS to examine the range of services provided to job-seekers and employers through employment offices. | - 1 Study Visit focus upon the range of services provided to job-seekers and employers through employment offices for a min of 5 working days for min. 7 persons (including RTA Assistant/translator as a member of the group) organised | Project Quarterly reports Mission reports Attendance list of participants in the Study visit Project final report |  |
| COMPONENT 3 | Activity 3.1. Review of the WorkNet Information System | - Review of the WorkNet Information System to ensure that the WorkNet Information System is compatible with the wider Labour Market Information System being developed by the MoLHSA and to identify what methodologies and tools would be required to enable the ESS to develop a comprehensive overview of the current labour market, using the data gathered through the WorkNet Information System conducted | Review Report on WorkNet IT system Project Quarterly reports Mission reports Project final report |  |
|  | Activity 3.2. Elaboration of a Concept Paper for upgrading the WorkNet Information System | - Concept Paper developed, addressing three core areas: 1) Recommendations for refining the functionalities of the current WorkNet IT to ensure interoperability and interconnectivity with the wider Labour Market Information System; 2) upgrades in hardware and software; 3) approach, methodology, tools and templates to permit the ESS to develop monthly/quarterly and annual reports on the current state of the Georgian labour market | Concept Paper Project Quarterly reports Mission reports Attendance list of participants Project final report |  |
|  | Activity 3.3. Preparation of Terms of Reference/Technical Specifications for upgrading the WorkNet Information System | - Terms of Reference and Technical Specifications for the procurement of off-the-shelf or tailor-made software and hardware prepared | Terms of Reference and Technical Specifications document Project Quarterly reports Mission reports Project final report |  |
|  | Activity 3.4. Development of methodology and tools for the preparation of monthly and annual labour market reports | - Methodology, tools and templates developed which would permit the ESS to develop consolidated monthly/quarterly and annual reports on the current state of the Georgian labour market, and provide accurate data on supply and demand in the labour market, disaggregated by region/age/gender | Methodology document including tools and templates Project Quarterly reports Mission reports Project final report |  |
|  | Activity 3.5. Study Visit to MS to examine the collection, collation and analysis of labour market data by the employment services | 1 Study Visit focus upon the collection, collation and analysis of labour market data for a min of 5 working days for min 7 persons (including RTA assistant/interpreter) drawn from the MoLHSA and the ESS central and regional offices organised | Project Quarterly reports Mission reports Attendance list of participants in the Study visit Project final report |  |
| COMPONENT 4 | Activity 4.1. Review of current HRD policy | - Review of the current HRD policy with focus on the recruitment system, terms and conditions of employment, career development and promotions’ policy, in-service training, and performance appraisal conducted. - Revisions to the current HRD policy to the ESS management elaborated | Review Report on HRD Document containing revisions to the current HRD policy Project Quarterly reports Mission reports Project final report |  |
|  | Activity 4.2. Drafting of an HRD Manual | - HRD Manual which includes: a) transparent recruitment, b)career development and promotions procedures, c)standard contracts; templates and methodology for performance assessment, d) identifying standard induction and in-service training modules elaborated. | HRD Manual Project Quarterly reports Mission reports Attendance list of participants Project final report |  |
|  | Activity 4.3. Conduct Training Needs Analysis | - Training needs analysis (TNA) of the staff of the ESS (Headquarters and District Offices) elaborated | Training needs analysis document Project Quarterly reports Mission reports Project final report |  |
|  | Activity 4.4. Development of Training Programme and Training Materials | - Training Programme divided between formal and in-service training, and mentoring of senior management for the Headquarters and District staff prepared. - Training materials developed | Training Programme document Training materials Project Quarterly reports Mission reports Project final report |  |
|  | Activity 4.5. Conduct Formal and in-service trainings for the ESS staff | - Training programme implemented - 10 formal workshops for 1-2 days per each on different topics for 140 persons at least 75 hours of in-service training organised - Series of trainings in three main regional centres: Kakheti, Imereti and Ajara conducted. - in-service training to ESS Headquarters staff and mentoring the Director and Deputy Director conducted. | Project Quarterly reports Mission reports Attendance lists of participants at workshops Project final report |  |
|  | Activity 4.6. Development of the Training manual | - Training Manual elaborated including all training materials | Training Manual Project Quarterly reports Mission reports Project final report |  |
|  | Activity 4.7. Training/retraining platform (Train the trainers) | - Training of at least 5 trainers covering pedagogic methods, the design and implementation of induction training for new members of staff and the content of the Training Manual conducted | Project Quarterly reports Mission reports Attendance lists of participants at training Project final report |  |
| COMPONENT 5 | Activity 5.1. Review of current communications policies and recommendations for upgrading | - Review on current ESS communications policies and provisions to establish a dedicated communications unit conducted. - Assessment of the ESS’s communications needs elaborated - Recommendations for upgrading the approach, messages, target groups, and communications tools elaborated. | Review Report on ESS communication policies including Assessment of ESS needs Set of recommendations Project Quarterly reports Mission reports Project final report |  |
|  | Activity 5.2. Support to the establishment of a Communications Unit within the ESS | - Mission statement, functions and optimum staffing level of the communications unit prepared | Document Mission statement, functions and optimum staffing level of the communications unit Project Quarterly reports Mission reports Project final report |  |
|  | Activity 5.3. Elaboration of communications and awareness raising strategy and Action Plan | - Communication and Awareness Strategy and associated Action Plan elaborated. | Communication and Awareness Strategy Action Plan Project Quarterly reports Mission reports Project final report |  |
|  | Activity 5.4. Development and application of communications tools and materials | - Communications tools and materials developed focused on the establishment of consultative mechanisms with employers, the further development of the ESS’s interactive web-site, www.worknet.gov.ge ; elaboration of information materials for job-seekers and employers, and the organisation of promotional events | Communications tools and materials Project Quarterly reports Mission reports Project final report |  |
|  | Activity 5.5. Study Visit to MS to experience practical use of the promotion and marketing of services to job-seekers and employers | 1 Study Visit focus on the promotion and marketing of services to job-seekers and employers for a min of 5 working days for min 7 persons (including RTA assistant/interpreter) organised | Project Quarterly reports Mission reports Attendance list of participants in the Study visit Project final report |  |

ARTICLE 4.	TASKS (INPUTS)

The present Twinning project entitled “Capacity Building of the Employment Support Services (ESS) in Georgia” Georgia represents a logically designed components (corresponding to planned mandatory results) broken down into activities and detailed actions including the measurable indicators and monitoring and reporting mechanism.

All mandatory results are to be achieved following the same project sequence as per the Project Fiche.

The Twinning project is divided into 5 key components; one component is dealing with project visibility and overall project management including monitoring and ex-ante evaluation of each project milestone.

In addition to the above-mentioned, one of key elements which is part of the components is project sustainability, i.e. using the results already in the course of project implementation, further development and utilisation of these results by beneficiaries after project is accomplished, maintaining contacts and professional relations between the twinning partners after project end and mainstreaming of results for policy development in the employment area.

In line with above, the following key components are integral part of this twinning project:

| Component 0/Mandatory result 0 | Visibility events, project management and sustainability |
| --- | --- |
| Component 1/Mandatory result 1 | Revision of the Georgian Legal Framework of equal opportunities legislation and related to employment in line with the EU acquis and in accordance with the provisions of Annex XXX of the Association Agreement |
| Component 2/Mandatory result 2 | The structure and functions of the ESS have been revised to reflect it expanded role in the labour market management processes, the range and quality of services provided to job-seekers have been piloted and enhanced, the internal management and administrative processes have been clearly codified |
| Component 3/Mandatory result 3 | A comprehensive Labour Market Information Management System (WorkNet Information System) has been established and is fully operational |
| Component 4/Mandatory result 4 | Modern human resource management techniques have been introduced, the staff have acquired the necessary skills and experience to provide high quality services to job-seekers, and an in-house training and retraining platform has been established |
| Component 5/Mandatory result 5 | The ESS has acquired the necessary tools and materials to communicate effectively its range of services to clients and potential clients |

Every component has a component leader who is in charge for ensuring the quality and quantity of activities planned under the components,  to keep the planned timeframe and  ensure, together with the MS PL, BC PL, RTA and RTA-counterpart, effective communication among experts prior to their missions, as well as between all involved experts and stakeholders. Unless otherwise agreed by the twinning partners, the first drafts of the activity outputs will be the responsibility of the MS Component leaders. Continuous evaluation of every implemented activity and outputs/results will be ensured through obtaining regular feedback from: MS and BC experts; SC meetings, participants in the activities; stakeholders involved, interviews conducted.

All parties involved in this Twinning project declare that they are fully committed. This includes their commitment to prepare for, actively participate in and follow up the sessions and activities.

It is also understood that the beneficiary will provide the relevant MS experts with all and any documents required for them to be able to assist in reaching each activity's output, each component's result and thus the overall target of the project. Documents shall be made available in English, unless otherwise agreed, and in electronically readable formats. This also applies to any further explanations or information that might be necessary for the MS experts to gain a thorough understanding of these materials.

Any actions agreed between the parties, and as such included in the experts´ Mission Reports following each mission, shall be delivered on time.

The beneficiary agrees to provide adequate office equipment, conference equipment, and rooms at its premises for all working sessions, workshops and other meetings, unless stated otherwise for a specific activity.

A close coordination between the project components will be ensured in order to guarantee for the most efficient deployment of available resources (human, technical and financial) of both partners.

Component 0

Overall Project Management, Kick-off and Closure Events

| Activity 0.1. | Project management including the Steering Committee meetings, monthly meetings, project visibility and project sustainability |
| --- | --- |
| Activity 0.2. | Kick-off meeting |
| Activity 0.3. | Closure Meeting – Final conference |

Component leader: Mr Branislav Ondrus

This component is directly focused on ensuring proper and timely project management focused on achievement of high-quality results. In concrete terms it is dealing with:

- Ensure the good start and visibility of the project as well as overall commitment of key stakeholders to project activities and attainment of objectives.

- Create awareness about the project and its objective amongst the shareholders of the project and the public.

- Provide for wide and efficient dissemination on project results as well as ensuring mainstreaming, i.e. using the results achieved through the implementation for policy development in the employment area.

- Start of elaboration of a sustainability strategy applicable beyond project duration, i.e. after project has ended.

Activity 0.1.

Project management including the Steering Committee meetings, monthly meetings, project visibility and project sustainability

Method:

The MS Project Leader will dedicate a minimum of 3 days per month for the management of the project during 18 months of the implementation period. This time will include the kick-off meeting, SC meetings held on a quarterly basis, the closure event (Final conference), as well as specific attention for management supervision through direct participation at the monthly meetings where appropriate and important. This approach will guarantee the implementation is overseen and any difficulties are resolved immediately within the common twinning team SK-HU-CZ-GE without any delay in timing.

Six Steering Committee meetings will be organised regularly on quarterly basis to promote effective management and monitoring of the project activities (first SCM in month 4 following to the accomplishment of the 1stquarter). Progress in the areas of the project’s interventions will be discussed with the beneficiary and the members of the SC.

Monthly meetings planned to discuss the project progress and to resolve potential issues will be organised during the project implementation. This will serve as an additional quality instrument to foresee special coordination among the components in order to avoid duplications and ensure smooth implementation of activities. MSPL and BCPL will be present at the monthly meetings together with the RTA and key representatives of the beneficiary institutions, and relevant representation of the Contracting Authority (DEU Project manager). Coordination of opinions of the MSPL (SK) and two JPLs (HU&CZ) will be ensured on spot in member states, among the three MS PLs (MS PL/lead and the two JPLs).

Communication Guideline specifying the tasks, responsibilities and communication channels of the RTA, PLs, CLs and STE will be developed.

Apart from these meetings, it is planned that the Project Leaders (MS and BC), RTA and RTA-counterpart, on both sides, will carry out the necessary preparatory activities essential for the proper functioning of the SC.

The RTA during the first month of his arrival to Tbilisi will establish contacts and upon this he will support the creation of Co-ordination Committee (CC) that will bring together key representatives of the twinning project and another TA project (technical assistance: Europe Aid/135544/DH/SER/GE) to ensure no duplication or overlapping of activities planned in both projects could happen. This CC will be meeting on quarterly basis and regular information will be exchanged between the key officials of both projects.

The visibility costs are foreseen for material costs for communication and awareness activities, i.e. elaboration of project leaflets, banners, brochures, manuals, notebooks, pens, folders, USB and any other relevant visibility tools with a project logo in order to visualise the success and results of the project, as well as to cover part of the costs of a larger public visibility events foreseen to be organised during the lifetime of the project. It has also been foreseen that a press release and specialised promotion materials (e.g. project leaflet, fact sheet, banners, etc.) will be produced at the start of the project (as described in the activity 0.1). All visibility documentation will fully respect the EU visibility rules as set up in the visibility communication manual for twinning projects.

Two main visibility events (Kick-off meeting and closing event - Final conference) will be held in appropriate premises in Tbilisi;the agreement on this will be taken commonly by twinners.

Moreover, ex-ante evaluation will be a key element for ensuring proper feedback on the implementation of each step/action in order to achieve high-quality of planned mandatory results. Dissemination, awareness raising and visibility of project achievements are integral part of the whole implementation process.

The overall project management for the successful implementation of the project is presented by the scheme below:

Mandatory results

per each

Component

Results sustainability

(Sustainability Strategy)

Contracting Authority (DEU)

Project Steering Committee

Implementation process

(WORKPLAN - Project Methodology)

Project Fiche ToR

Indicators & milestones

Institutional support processes,

including political support by SK-HU-CZ for Georgia

Twinners Team – SK-HU-CZ-GE -common work

(MS PL, JPLs, STE + Georgian counterparts)

Consortium management

(Back up office Bratislava) Administration & logistics, Financial Management

Monitoring & Quality Assurance;

Reporting

Daily project implementation and administration on situ (RTA Office in Georgia)

Risk Mitigation Strategy

The mainstreaming is to be key element of the overall management process: using the project results for policy development in the targeted area from long-term perspective will be applied – “feeding” the national policy in the area of promoting active labour market measures and services to reduce unemployment and to support employment.

Resources:

MSs Staff: Participation of PL Mr Ondrus in project management meetings

The PL will dedicate 33 days/11 missions to take part in the foreseen 6 SC meetings every 3 months and in the monthly management meetings in Tbilisi (for the monthly meetings: where needed and appropriate).

Participants:

MS PL, RTA, RTA-Counterpart

EUD representatives, task managers, BC institution’s representatives (SC members)

Other resources:

- Infrastructure and facilities will be made available by SSA/ESS-MoLHSA

- translation/interpretation

Outputs

- SC meetings held quarterly in compliance with the project schedule

- QRss prepared, commented and approved

- Final report prepared, commented and approved

- Monthly meetings held in compliance with the project schedule

- Visibility materials  published, dissemination and awareness raising ensured

- Project Sustainability Strategy prepared, commented and approved

- Duration: on quarterly basis

Activity 0.2. Kick-off meeting (opening conference)

Method:

A public event to launch and officially present (kick-off) the twinning project and give it visibility will be organised in Tbilisi in a form of Opening Conference (0,5 day) followed by a twinning working meeting of the involved beneficiary institutions (0,5 day). This will be an opportunity for meeting key officials and representatives of beneficiary institutions, such as ESS/MoLHSA and other involved ministries, social partners representatives and civil society representatives, other key stakeholders, diplomats and media (about 50-80 participants total). The Opening Conference will contribute to awareness raising about the project, its objectives and mandatory results. It will be focused also on the importance of employment policy for the overall socio-economic development of the country and necessity of constructive dialogue among Georgian key players in the area of social policy and its challenges through dissemination of information and key messages to those involved in the targeted area (staff, decision makers/professionals, as well as social partners and CSO representatives) and wide public. In this respect, a common agenda will be developed by the twinning parties with the aim to present the project objectives, expected mandatory results and implementation methodology. The Opening Conference will be followed by a press conference and a press release will be issued prior and after the conference.

Project promotion materials will be developed to be distributed for this purpose, e.g. project leaflet, banner, fact sheet, folders, notebooks with project logo, etc.

The duration of the activity is 2 days: 1 day preparatory work and meetings with the officials of beneficiary institutions and 1 day including a half-day Opening Conference and a half-day working meeting with beneficiary institutions and other relevant stakeholders.

MS PL Ondrus, JPLs Komaromi and Kolmerova and CL Pavlovova and together with the BC PL and MS RTA, will take part in the opening conference and the twinning working meeting. In this respect, they will have combined presentation with those of the BC PL and RTA on Components 1, 2, 3, 4 and 5, particularly on the approaches, capacity building, concrete approaches and steps for implementation and necessity of results´ sustainability. These MS representatives MS PL Ondrus, JPLs Komaromi and Kolmerova and CL Pavlovova, each 2 days will cover issues of high importance for the beneficiary country and the presence of these key experts is highly desirable for the smooth start of the overall project implementation.

Documentation will be prepared for the participants. A press conference will be part of this event.

Resources:

- MS PL Ondrus, JPLs Komaromi and Kolmerova and CL  Pavlovova, each 2 days /1mission

- RTAs

- BC staff: BC PL, RTA-counterpart, experts – ESS/MoLHSA and other Georgian relevant stakeholders

Other resources:

- Translation  (a number of pages is an approximate number and covers all documents needing translation under this activity – invitation, agenda, press release, facts sheets, leaflet, project summary, banner, etc.)

- Printing project promotion materials

- Translation and Interpretation 1 day (simultaneous), 2 interpreters in the booth

- Infrastructure and facilities for kickoff event

- Small catering at the event

Outputs:

- 1 Kick-off meeting held

- 1 Press conference conducted, press release prepared and disseminated

- Visibility materials for the kick-off event prepared and published

- Number of published information on project event in Georgian media/press and beneficiaries’

websites

Duration: during the 1 month of project implementation

Activity 0.3. Closing (Final) conference including press conference

Method:

One day closing conference will be organised during the last month in Tbilisi to present, give visibility and disseminate the achievements of the twinning project, its outcomes and concrete results, including prepared and adopted measures, legislation aligned with EU acquis and improved conditions for its implementation. It will provide a basis for long–term sustainability of the results through the presentation of recommendations and Sustainability Strategy. The audience of the Final conference will include the beneficiary, all involved line ministries, other stakeholders, social partners and wider circles of civil society including media representatives.

The duration of the activity is 2 days - 1 day preparatory work, 1 day conference and the final SC (each half-day).

MS PL Ondrus, JPLs Komaromi and Kolmerova and CL Pavlovova will take part at the conference and prepare the key messages in relation to the achieved results within each of the components and further planned actions to be taken by the beneficiary after the project completion to ensure project sustainability. Their involvement will be complementary to this of the BC PL and RTA and RTA-counterpart and they will also take part in the preparation of the overall agenda of the final event and press conference dealing with questions of specific nature.

Documentation will be prepared for the participants. A press conference will be part of the event. Press release will be prepared and disseminative, too.

Resources:

MS PL Ondrus, JPLs Komaromi and Kolmerova and CL Pavlovova, each 2 days/1mission

RTA

BC staff: RTA counterpart, experts – ESS/MoLHSA and other Georgian relevant stakeholders

Other resources:

- USB – including all developed visibility materials, project results accomplished within each of components

- Translation and Interpretation 1 day (simultaneous), 2 interpreters in the booth

- Infrastructure and facilities

- Small catering for Final conference

Outputs:

- Final Conference  held

- Press conference conducted

- Visibility materials for the Final Conference event published

- Number of published information on project event in Georgian media/press and beneficiaries’

Duration: during the 18 (last) month of project implementation

Component 1:

Revision of the Georgian Legal Framework of equal opportunities legislation and related to employment in line with the EU acquis and in accordance with the provisions of Annexes of the Association Agreement

(Mandatory result 1)

Component leader: Mrs Elena Palikova

Work on this component are focused on the revision of the Georgian Legal Framework of equal opportunities legislation and related to employment in line with the EU acquis and in accordance with the provisions of Annexes of the Association Agreement. In concrete terms the following will be ensured:

- Assist and support the revision of Georgian Legal Framework of equal opportunities legislation and related to employment in line with the EU acquis and in accordance with the provisions of Annex XXX of the Association Agreement

- Draft a Concordance Report and recommendation for legal harmonisation

- Provide tailored support to law drafting on equal opportunities legislation related to employment service

- Ensure gap analysis of the equal treatment and non-discrimination sections of the regulations for which ESS has competence

- Support to the ESS to ensure compliance with EU equal opportunities legislation

- On-the-job training of the relevant staff of SSA staff in relation to the above-mentioned tasks (conduct analysis, identify of legal gaps, revise legislation, draft / amend legislation in compliance with EU law, draft reports in line with EU practices, etc.)

Activity 1.1.

Review of Georgian Equal Opportunities legislation related to employment and measure of concordance with EU Equal Opportunities legislation identified in Annexes of the Association Agreement

The purpose of this activity is to conduct an in-depth review focused on the comprehensive assessment of Georgian legislative framework related to equal opportunities and its compliance with the EU legislation in this field.

Taking into account the priorities set up in the Association Agreement and in particular chapter 14, as well as EC assessment of Georgia as expressed on the document “Implementation of the European Neighbourhood Policy in Georgia Progress in 2013 and recommendations for action“ and related ones, technical and analytical support in alignment of the country´s legislation with the EU Directives on equal opportunities and anti-discrimination will be provided respecting the current stage of the situation and works already done in the country and taking into account the  Commission’s recommendations.

Since the Georgian government is engaging in employment reforms also from legislative point of view, the MS project team (STE) will also make use of the experience of the BC ESS/Ministry’s representatives from works already done thus to how best harmonise the project activities with Georgia’s overall reform plan in the targeted area.  Implementation of project activities will be carried out through the separate tasks in close cooperation with the STE and the ESS/Ministry’s staff (MoLHSA/Employment Programmes Department) and relevant stakeholders´ representatives will be invited to carry out the relevant tasks together to feel the ownership and consensus of all proposals reached.

- Method

To ensure the comprehensive assessment and analysis (Review) of the Georgian Equal Opportunities legislation a core working group(WG) will be established consisting of ESS/MoLHSA staff and, if necessary, of some other relevant stakeholders as the main legislation task force dealing with the analysis of the broad legal framework to be examined. STE allocated to the activity will facilitate, assist and will work jointly with the working groups based on the agreed methodology.

The aim of the working group ‘s activity supported by the STE will be to conduct joint analysis of the relevant legislative framework of the Georgian Equal Opportunities legislation based on the priorities of alignment of the GE legislation with the EU Directives. Consultative sessions, peer-review meetings, brainstorming sessions and working meetings during conducting the review and elaboration of ToC (Table of Concordance) for equal opportunities legislations (directives) will be organised.

Subsequently, analysis of its compliance with EU Acquis and other international organisation’s legislation in that field as well will be jointly provided in a form of “Review report of Georgian Equal Opportunities legislation”. The STE together with their GE counterparts (WG) will also prepare first draft of ToC (table of concordance) for each of the EU directives vis-a-vis GE legislation which will be used as inputs for act. 1.2

The WG will focus to the alignment of the Georgian Equal Opportunities legislation with the EU, primarily, EU directives 2000/43, 2000/78 and 2006/54.

The main tasks of the STE’s work within the working group will concentrate on:

- Explanation of the Directives and other pieces of EU legislation and their application, with special focus to problems arising in practice

- Comparative legislations of the EU Member States concerning the application of the directive

- Links with other legal provisions

- Jurisprudence /case law of the European Court of Justice

- Development of the ToCs referred to this activity

- Assistance with the preparation of specific legislative solutions

- Review of Georgian Equal Opportunities legislation, gaps identification

More specifically, the following aspects will be examined:

- analysis of principles of the anti-discrimination law

- comparative analysis of the Georgian law and three MS (SK-CZ-HU) countries

- analysis of the foreign expertise and other reports related to the task

The task will be implemented by the WG for conducting the Review (gaps analysis), supervised and facilitated by the STE. The WG will meet with the STE at the first introductory workshop focused on the introduction to the scope of work and the methodology for implementing the activity

One Introductory workshop and at least1 analytical workshop and related coaching sessions will be conducted focusing on the following topics:

- Equal opportunities and anti-discrimination issues of the European Union, clarification and analyses of the existing system, institutional basis,

- Explanation of the Directives and other pieces of EU legislation and their application, with special focus to problems arising in practice

- Comparative analyses of the EU Member States concerning the application of the directives in SK-HU-CZ. This shall include an analysis of the legal framework and their application, with special focus to problems arising in practice, strengths and weaknesses of the different models and practise and possibilities of their application to BC conditions will be discussed, too

- Giving instructions and support on how to fill in the Tables of Concordance

- The MSs example/s of the Tables of Concordances  related EU Directives will be submitted to explain the scope of work and logic of the tasks

- Elaboration of the Table of Concordance to each above mentioned directive by the working group supported by the STE

- The statements to the Tables of Concordance will be elaborated by STE and the results will be presented during the open presentation and discussion to the statements focused on overview of the current situation of the BC legislation against the future alignment

- Workshops will target representatives from the following institutions: experts from ESS/MoLHSA, relevant line ministries.  The number of participants will be up to max 15 to keep the work efficient

- Based on the workshops and the conducted review of the state of play, the main needs and shortcomings will be identified, discussed and further assistance with the preparation of specific legislative solutions in the GE law assisted by STE will be provided in act. 1.2 & 1.3.

Output:

- WG established, Checklist for assessment prepared and consulted

- Review of Georgian Equal Opportunities legislation elaborated

- Table of concordance developed (template for GE)

- Analytical papers drafted

- Tables of concordances of the relevant Directives and legal sources of the beneficiary country prepared

- Number of workshops, working meetings, coaching sessions  related to analysis conducted

- At least 1 Introductory workshop and  1analytical workshop with involvement of all key stakeholders on presentation of legal framework, comparisons, findings, conclusions and recommendations conducted;

- A series of coaching sessions, working meetings related to analysis of the Directives, table of concordance preparation conducted

Duration: 2 to 3 month

Resources

RTA

MSs staff: 4 MS experts Palikova/5days, Kubalova/5days, Tkac/5days, Palik/5days / total 20days/4 missions

The BC staff for this activity is:

- BC PL, RTA counterpart;

- Working group created for assessment and compliance of the legislation: staff from the ESS/MoLHSA, other relevant stakeholders

- Up to 15 participants will be involved into this activity

Other resources:

- Translation and interpretation

Activity 1.2.

Drafting a Concordance Report and recommendations for harmonisation of the Georgian legislation related to employment with the EU Equal Opportunities Directives identified in Annexes of the Association Agreement

This activity is focused on concrete drafting the Concordance Report and a set of recommendations for harmonisation of the Georgian legislation related to employment with the EU Equal Opportunities Directives identified in Annexes of the Association. The outputs of activity 1.1 will be used as inputs for this one. As well the representatives of the WG created already within implementation of act.1.1 will play key role in this one.

Method

On the basis of the review (act. 1.1), the STE will draft a Concordance Report together with their colleagues – members of the WG. Thus, the same working method as proposed in the previous activity will be applied, meaning the WG members will be fully involved in the process.

The methodology for preparing the Concordance Report and its structure will be proposed by STE involved in the activity. It will be then discussed at the WG and commonly agreed at the beginning of the activity.

The Concordance Report will:

- Take into consideration the findings in the Review Report (gaps and shortages in the GE legislation vis-a-vis EU directives on equal opportunities and anti-discrimination on the basis of elaborated ToCs)

- highlight the current gaps in the GE Equal Opportunities legislation related to employment or where the current provisions are not completely aligned with the EU Equal Opportunities Directives identified in Annex of the Association Agreement.

The STE will also append to the Report a series of recommendations (Set of Recommendations) for closing these gaps and shortages and ensuring harmonisation with the relevant EU Directives.

- Working group will discuss, examine and agree on the final version of Concordance Report and recommendations as well as to pave the way for putting recommendations in practice

- Presentation of complex set of recommendations: 1 workshop will be organised to present the final Concordance Report and recommendations, discuss these recommendations and after the workshop, if any further comments are made by involved participants and if these comments are appropriate, the final version of the Concordance Report and concrete recommendations will be made ready for the GE side.

- Outputs from act. 1.2 will be also used as input for act. 1.3, i.e. for STE support to legal drafting regards equal opportunities legislation of the BC country with focus on employment service.

1 STE mission will be held to draft the Concordance Report; to consult, discuss and agree on the final version of the report with the Georgian counterparts. In close cooperation and work with the WG members the STE will prepare a set of concrete recommendations how identified legislative gaps to be closed

Outputs

- Concordance Report prepared, discussed, presented at workshop and final version ready

- Set of Recommendations as part of the Concordance report prepared, discussed, presented at workshop and final version in place

- Overview of available information sources in the beneficiary country relevant from the perspective of closing the gaps and shortages

- 1 Workshop on presentation of the Concordance Report combined with presentation of best practices in MSs (SK-HU-CZ) held

- A series of coaching sessions, working meetings related to analysis of the Directives, table of concordance preparation and legislation proposals conducted

Duration: 4 to 6 month

Resources

RTA

MSs staff: 2 MS experts Palikova/5days, Kubalova/5days/ total 2 missions

The BC staff for this activity is:

- BC PL, RTA counterpart;

- Working group created for assessment and compliance of the legislation: staff from the ESS/MoLHSA, other relevant stakeholders

- Up to max 15 participants will be involved into this activity

Other resources:

- Translation and interpretation

Activity 1.3.

Support to legal drafting with regard to the Equal Opportunities legislation related to the employment service identified in the relevant Annexes of the Association Agreement

The purpose of this activity is to ensure and provide tailored legal support for drafting GE legislation on equal opportunities related to the employment service identified in the relevant Annexes of the Association Agreement in order to close the gaps and shortages in line with the outputs of activity 1.1 and activity 1.2 (recommendations). It is also important to outline a mechanism that can contribute to enforcing these legal provisions in practice. This is important and it is in line with the GE obligations arising from the EU-GE Association Agreement and more specifically from its Title VI Other Cooperation Policies, Chapter 14, “Employment, social policy and equal opportunities”, where detailed areas of cooperation of immediate relevance to this Twinning Project are identified, i.e. Article 348 concretely states, among other that the parties shall strengthen their dialogue and cooperation on promoting the employment policy, social protection, social inclusion, gender equality and anti-discrimination, and corporate social responsibility and thereby contribute to the promotion of more and better jobs, poverty reduction, enhanced social cohesion, sustainable development and improved quality of life.

Moreover, the outputs will be reached on consensus basis while taking into consideration GE priorities and realities to be prepared, step-by-step, to ensure implementation of adapted/new legislation in practical terms.

Method

- In accordance with the recommendations (act. 1.2.) appended to the Concordance Report, the STE will assist staff within the ESS/MoLHSA to draft/amend Georgian legislation to ensure that it is harmonised with Council Directives 2000/43/EC, 2000/78/EC, and 2006/54/EC related to the principles of equal treatment and non-discrimination in employment supporting services.

- In this respect the members of the WG already operational in act. 1.1 and 1.2 will be fully involved in the implementation of this activity and will, together with STE, work on drafting legal proposals/provisions for closing the existing gaps and shortages in the GE legislation in the equal opportunities/anti-discrimination area thus GE legislation to be in compliance with the three EU dir. 200/43, 2000/78 and 2006/54 related to principles of equal treatment and non-discrimination in employment supporting services.

- 1 Workshop will be held with GE representatives and will be focused on experience of the EU MS (SK-HU-CZ) and some other EU MS including examples of templates, good practice and lessons learned by the Twinning partners, important issues and transparency to be taken into account.

- Consultative legal group (CLG) will work jointly with STE on legal drafting. This CLG will consist of legal experts and specialists who already took part in the WG in act. 1.1 and 1.2.

- Focus group involving key (high-level) representatives of ESS/MoLHSA will at first stage discuss the proposed legal provisions elaborated by the CLG so internal (inside the ESS/MoLHSA) mutual agreement on the prepared legal drafts is reached.

- Consequently 1 Workshop focused on the presentation of the work of the Consultation legal group and Focus group, i.e. of the complex legal provisions will be organised with representatives of ESS/MoLHSA, other relevant stakeholders (ministries, social partners, CSO). The proposed legal provisions will be discussed at this workshop and consequently the final version will be agreed and made ready for taking further steps in legislative procedure of the country (for adoption)

In addition to the above-mentioned, STE together with the members of CLG will outline a mechanism that could contribute to enforcing these legal provisions in practice. In this respect, experience and lessons learnt by all three MSs – SK, HU and CZ will be used as reference point.

Expert missions in order to provide support for legal drafting to Georgian counterparts (ESS/MoLHSA, other relevant stakeholders) will be held

Outputs

- Draft/Amendments to Georgian legislation to ensure that it is harmonised with Council Directives Nº2000/43/EC, Nº2000/78/EC, and Nº2006/54/EC related to the principles of equal treatment and non-discrimination in employment supporting services elaborated

- Mechanism for possible enforcement of legal provisions /amendments outline in a document appended to draft amendments

- 2 workshops held

Duration: 7 to 11 month

Resources

RTA

MSs staff: 4 MS experts Palikova, Kubalova, Tkac, Palik, each 10 days/2 missions each

The BC staff for this activity is:

- BC PL, RTA counterpart;

- Working group created for assessment and compliance of the legislation: Staff from the ESS/MoLHSA, other relevant stakeholders

- Up to 35 participants will be involved into this activity  including participants in the two planned workshops

Other resources:

- Infrastructure and facilities needed for the conducting of the two workshops planned under this activity

- Translation and interpretation

Activity 1.4

Gap analysis of the equal treatment and non-discrimination sections of the regulations for which the ESS has competence

The aim of this activity is to conduct a Gap Analysis in order to ensure that the regulations for which the ESS has competence are consistent with Georgian legislation that should be harmonised with Council Directives 2000/43/EC, 2000/78/EC, and 2006/54/EC related to the principles of equal treatment and non-discrimination in employment supporting services. The content of this activity is closely linked to the work planned for activity 1.3 and thus the work on both could be done in parallel manner.

Method

In order to reach the objective of the activity:

- The work will be done jointly, i.e. by a small working group consisting of STE and ESS relevant staff to keep the work effective in terms of activity content and timing;

- The STEwill prepare a methodology for conducting an analysis;

- This methodology will be discussed and agreed with ESS staff and based on this agreement the STE will carry out a Gap Analysis together with the staff of ESS to ensure that the regulations for which the ESS has competence are consistent with Georgian legislation that should be harmonised with Council Directives 2000/43/EC, 2000/78/EC, and 2006/54/EC related to the principles of equal treatment and non-discrimination in employment supporting services.

- Based on the work in the small group, the STE will prepare the first draft of the Gap Analysis and then discuss this draft within the small working group. Upon discussion, the final adjustments will be made and final version of the Gap Analysis document prepared

- Appended to the Gap Analysis will be a Set of Recommendations for revising the regulations in order to ensure compliance. The Set of recommendations will be prepared by STE, then discussed within the small working group and final version of the proposed recommendations will be then prepared by STE

- Round-table involving STE and Georgian counterpart/s (ESS/MoLHSA)and aiming at presentation of complex Gap Analysis and of recommendations will be held.

At the Round table the Analysis and Recommendations will be discussed in broader context, examined and agreed on the final version of Gap Analysis Report and Set of Recommendations for all the necessary revisions to be introduced, as well as to pave the way for putting recommendations in practice.

Expert missions to conduct gap analysis and prepare a set of concrete recommendations

Outputs:

- Gap Analysis document prepared

- Set of recommendations prepared as appended to the Gap Analysis

- Round table held

Duration: 7 to 11 month

Resources

RTA

MSs staff:  2 MS experts Palikova, Kubalova, each 5 days/1 missions each

The BC staff for this activity is:

- BC PL, RTA counterpart;

- Small working group consisting of STE and ESS relevant staff up to max 15 persons

Other resources:

- Infrastructure and facilities needed for the organisation of the round table

- Translation and interpretation

Activity 1.5

Regulatory drafting support to the ESS in order to ensure compliance of the regulations for which it has competence with the revised Georgian Equal Opportunities legislation harmonised with EU Equal Opportunities legislation

The purpose of this activity is in conjunction with the findings in the act. 1.4 to provide tailored regulatory drafting support to the ESS in order to ensure compliance of the regulations for which it has competence with the revised Georgian Equal Opportunities legislation harmonised with EU Equal Opportunities.

Method

- Based upon the conclusions of the Gap Analysis elaborated in act. 1.4 and in accordance with the recommendations appended to this Gap Analysis, the STE will assist the staff of ESS to revise those regulations for which it has competence ensuring that the revised regulations are consistent with Georgian legislation that should be harmonised with Council Directives 2000/43/EC, 2000/78/EC, and 2006/54/EC related to the principles of equal treatment and non-discrimination in employment supporting services. Any other reference legal documents will be also taken into consideration.

- Therefore, the STE will prepare the methodology for support delivering, i.e. on-job training, coaching and legal advice and thus the STE will directly work with Georgian colleagues – i.e. members of the Small working group as set up in act. 1.4. This will not only ensure effective continuation of the works already done in act. 1.4 but will also help to decide on the most appropriate legal solutions tailored to the real needs of ESS and, at the same time, ensuring compliance with the EU legal requirements.

- The work on legal revision of regulations (results) will be done within this small working group already working in act. 1.4. This work will be jointly developed by twinners-members of this group.

- Concrete legal proposals prepared upon findings in the Gap Analysis already elaborated in act. 1.4 will be then presented in a Workshop together with the experience of the three EU MS – SK-HU-CZ. In this respect, concrete examples of good practice from SK-HU-CZ but also of lessons learned (positive and negative/mistakes) by the Twinning partners will be presented to participants so that Georgian colleagues can learn from good lessons but avoid potential mistakes while implementing the legal rules in practical terms. Any comments arising from discussions held at the workshop will be carefully taken into consideration and after that the final text of legal proposals will be adjusted, if necessary and appropriate.

- The participants in the Workshop will be of ESS/MoLHSA, other relevant stakeholders who will be invited upon common agreement between the twinners involved in the activity. Some important issues and transparency regarding putting legal provisions in practice will be also discussed based on the experience of the MS institutions involved in the twinning implementation.

Expert missions to provide the support for legal revision to Georgian counterparts, give them concrete examples from MS SK, HU and CZ, commonly do the work on the necessary legal revision, ensure on-job training of ESS colleagues, coaching and tailored advice will be held.

Outputs:

- Legal Revision Document (of those regulations for which it has competence ensuring that the revised regulations are consistent with Georgian legislation that should be  harmonised with Council Directives Nº2000/43/EC, Nº2000/78/EC, and Nº2006/54/EC related to the principles of equal treatment and non-discrimination in employment supporting services)

- Workshop conducted

Duration: 10 to 13 month

Resources

RTA

MSs staff:  3 MS experts Palikova/5days/1 mission, Kubalova/10days, Palik/10 days/2 missions

The BC staff for this activity is:

- BC PL, RTA counterpart;

- Staff from the ESS and other relevant institutions (workshop), up to 30 people ;

- Small working group consisting of STE and ESS relevant staff

Other resources:

- Infrastructure and facilities for organisation of the workshop

- Translation and interpretation

Component 2:

The structure and functions of the ESS have been revised to reflect it expanded role in the labour market management processes, the range and quality of services provided to job-seekers have been piloted and enhanced, the internal management and administrative processes have been clearly codified

(Mandatory result 2)

Component leader: Boris Katuscak

This component is of specific importance as it is dealing with overall complex revision of ESS functions in order ESS be able to reflect its role in the labour market and provide modern high quality services to its clients – job-seekers and employers. The following issues will be in the centre of implementation:

- Support the Georgian colleagues to work together with experts on the revision of the structure and functions of the ESS in a way so that it reflects the ESS expanded role in the labour market management processes (focus on functional analysis)

- To draft complex Institutional Reform Plan for SSA/ESS and to ensure its implementation in practical terms incl. that not only the range but also the quality of new services for job seekers have been piloted

- To provide support, coaching and on-the-job training of SSA/ESS staff to ensure further development of job-seekers counselling services

- To provide tailor-made assistance for codification of the internal management and administrative procedures in SSA/EES and elaboration of Quality Assurance Plan for Head Office and district offices staff

- To prepare and organise a combined learning study visit in all three MS – Slovakia, Hungary and Czech Republic for Georgian colleagues to learn from know-how, experience and lessons learnt by all three countries but also to strengthen cooperation with colleagues in these countries and to pave the route for preparation of co-operation agreements between Georgia and the three MS (SK, HU, CZ) which will provide framework for collaboration from long-term perspective

Detailed methodology for the implementation of each activity is described below.

Activity 2.1.

Undertake Functional Review of the SSA/ESS

The purpose of this activity is to conduct an in-depth quality assessment - Functional Review of the SSA/ESS´s Charter and Mission Statement. This activity is of crucial importance as well-conducted FA will pave the way of improvement of SSA/ESS structure, its functions and overall internal management so that SSA/ESS is able to provide services of high-quality to job seekers as well as to employers at all levels in the country.

Method

The STE together with their colleagues from SSA/ESS will conduct in-depth Functional Analysis (FA) of the SSA/ESS´s including:

- Internal management structure,

- Range and quality of services offered and measures provided to job-seekers,

- Cooperation with employers,

- Work processes,

- Human resources - distribution of tasks and staffing (internal communication),

- Tools (physical facilities and capital equipment (hardware/software, management, monitoring and reporting systems, manuals, procedures, forms, etc., i.e. all job-aids which can enhance the effectiveness of the functioning of the SSA/ESS overall system,

and will recommend management/administrative and operational changes as appropriate in each of the above-mentioned issues.

In line with the above-mentioned, the methodological approach to the FA will be discussed and agreed with the Georgian counterparts. The following stages are proposed:

- Desk research and review of all relevant documents, specific focus on SSA/ESS´s Charter and Mission Statement

- Organisation of 1 initial workshop to which representatives of the SSA/EES – Head Office and its Regional offices/District offices will  participate

- Semi-structural interviews conducted with the management - Heads of all SSA/ESS Head Office Departments (central level). The purpose of these interviews will be to validate the data collected by cross-institutional and cross-departmental approach as well as to collect new information from different staff representatives as related to current organisational structure

- Site visits and interviews conducted with the Heads of all 10 Regional Offices (as well some of district offices will be visited to ensure complex information on current operations at all levels in the country) – it is important to involve the regional offices and district offices. The modalities of this involvement will be discussed and agreed with the SSA/ESS management

- Elaboration of methodological approach and tool for collection of relevant information also from the SSA/ESS local offices (guideline for interview, preferably questionnaires). It is also proposed to organise small focus groups bringing together representatives of several local offices.

- Analysing and processing the gathered information/data (includes main elements that define the structure, work processes, human resources and tools)

- Elaboration of Functional Analysis Report including a complex set of recommendations for management/administrative and operational changes

In relation to the above, participative approach will be backbone of the overall implementation process of this activity and more detailed Steps of the Functional Review methodology will consist of:

- Identify the strategic objectives of the SSA/ESS and the medium term objectives

- Relate the medium term objectives to the strategic objectives

- Identify and classify functions

- Identify resource usage of functions

- Identification of all SSA/ESS functions by organisational forms

- Classify functions as:

- Policy functions

- Co-ordination/performance monitoring functions

- Regulatory functions

- Service delivery functions

- Support functions

- Review of human resources allocated for each function

- Detailing tasks and responsibilities at the level of job descriptions

- Number and qualifications of staff

- Fulfilment of recruitment needs

- Identification of system and tools

- The availability of instruments, methods, guidelines, manuals, procedures, forms, IT support (latter will provide first information/input for component 3, act. 3.1)

- Relate the functions to the medium / long term objectives of SSA/ESS

- Consider what to do with each function

- Consider the implications of recommendations

- Prepare a Functional Analysis Report and Recommendations which will be used as input for act. 2.2 for the elaboration of the Institutional Reform Plan for SSA/ESS and its concrete implementation (act. 2.3)

The first draft of the FA will be discussed at a Workshop held together with SSA/ESS management. Upon the outcomes of this first Workshop, this draft will be adjusted accordingly and the final version will be presented in second Workshop organised with the representatives SSA/ESS from central, regional/district levels to present the Functional Review and proposed recommendations for improvement.

Expert missions to conduct functional analysis and prepare tailor-made recommendations will be held.

Outputs

- Functional Review Report

- Functional Analysis Report as integral part of the Functional Review Report

- Recommendations for improvement Functional Analysis Report

- 3 workshops held (initial one, first and the second ones)

Duration: 2 to 6 month

Resources

RTA

MSs staff:  4 MS experts Lorencic/5days, Pavlovova/5 days  Stefanik/5days, Kolmerova/5days

The BC staff for this activity is:

- BC PL, RTA counterpart;

- Staff from the SSA/ESS at various levels (up to 45 participants/each workshop);

Other resources:

- Infrastructure and facilities for organisation of the two workshops

- Translation and Interpretation

Activity 2.2

Support to drafting an Institutional Reform Plan for the SSA/ESS

The purpose of this activity is to assist the SSA/ESS management in elaboration of concise and complex Institutional Reform Plan. In this respect, the outcomes/results of activity 2.1 will provide input and the basis for the Institutional Reform Plan drafting.

Method

Upon the outcomes of the Functional Review and its recommendations, the STE will assist the management of the SSA/ESS to prepare a complex and concise Institutional Reform Plan for the SSA/ESS. This will be done upon the agreed common visions and objectives as result of activity 2.1 (Functional Review).

The Institutional Reform Plan (IRP) will also include a new service model which will be more customer-oriented and it will combine the good practices of employment services in the EU MS more specifically in 5 EU MS, i.e. in Slovakia, Hungary, Czech Republic but also in Slovenia and Austria with the current experience acquired so far by SSA/EES in the course of its capacity building.

Integral part of the methodology for implementation of this activity will be an empowerment approach so that SSA/ESS staff and other relevant actors in the labour market will be able to enhance the quality of their actions and the decisions taken by SSA/ESS management towards their role in the labour market and services they provide to the job seekers but also employers. This new service model is to be in the centre of the improved services and an integral part of the Institutional Reform Plan for the SSA/ESS.

Specific focus while drafting the IRP will be also put on the following issues:

- Uniform services provided by all regional/district and local employment offices (for job seekers and employers)

- Standardised work methods connected to each of the services

- Annually updated local employment action plans, if appropriate for Georgian beneficiary

- An open space for services with increased use of self-service tools, including CV-bank and vacancy bank

- Reliable labour market information for job seekers and employers (day-to-day cooperation with employers – in business-to-business dialogue as they are those creating new jobs)

- Labour market programmes for different target groups

The IRP will also include the desired organisational competencies and specific objectives/goals for each employee of SSA/ESS, developed measures for future activities and workload and description of competency set needed by the workforce of SSA/ESS.

The IRP will be supported by elaborated strategy based on the following approaches:

- Workforce approach: assesses the current workforce and occupations and predict the number and characteristics of jobs and staff number needed to fill these jobs

- Workload approach: focus on the amount and type of work the SSA/ESS anticipate and using this information to predict the number of staff and resources (people and skills) which are needed to perform this work

- Competency approach: indentifying the sets of competencies aligned with the SSA/ESS mission, vision and strategic goals. This also means that SSA/ESS has considered workforce and workload and SSA/ESS can focus not only on the number of people (employees needed) but also on the competencies the employees have to achieve for institutional success.

The overall work under this activity will be done by IRP Task Force consisting of STE involved in this activity and SSA/ESS staff. The following steps are proposed:

  - The STE will elaborate the first draft of the IRP and the draft strategy for IRP implementation in consultation with SSA/ESS colleagues involved in the IRP Task Force.

  - 1st Workshop aiming at presentation of the first draft will be held gathering all members of the IRP Task Force. Upon discussions at the workshop, common agreement among members will be reached for any necessary adjustments

  - The STE will, in collaboration with SSA/ESS colleagues, adjust the draft and

  - 2nd Workshop will be held with all members of the IRP Task Force to discuss  this updated draft and decide on its final version

  - Round-table with SSA/EES management (decision-makers) will be organised to present the IRP as developed by the members of the IRP Task Force and create space for last adjustments before taking final decision on practical implementation of the agreed IRP

  - The STE will, upon outcomes of the round table, submit the final version of the commonly agreed IRP and its strategy for practical implementation.

In addition to the above, a communication plan will be drafted to ensure awareness, understanding and support to the IRP implementation process at various levels in the country (national, regional/district and local) with all SSA/ESS employees, management and key stakeholders. This communication plan considered as an internal one will be also taken into consideration while implementing activities under component 5, but its elaboration is required as a part of this activity. The SSA/ESS internal communication plan will be prepared by STE, discussed within the IRP Task Force and consequently with the SSA/ESS management and it final version will be then submitted by STEs.

Expert missions to elaborate on Institutional Reform Plan will be held.

Outputs

- Institutional Reform Plan incl. strategy for its implementation

- SSA/ESS Internal communication plan on IRP

- Workshops held

- Roundtable held

Duration: 5 to 8 month

Resources

RTA

MSs staff: 4 MS experts Lorencic, Katuscak, Kolmerova, Pavlovova/5days Total 20 days

The BC staff for this activity is:

- BC PL, RTA counterpart;

- Staff from the SSA/ESS (up to 20 people per workshop/round table);

Other resources:

- Infrastructure and facilities for the organisation of two workshops and round-table

- Translation and Interpretation

Activity 2.3

Support to the implementation of institutional reforms within the SSA/ESS

The purpose of this activity is to ensure tailored support to SSA/ESS for the implementation of institutional reform as agreed in the IRP elaborated in activity 2.2.

Method

The STE will assist the management of the SSA/ESS to implement the Institutional Reform Plan. At this juncture it is anticipated that this will entail revisions to the ESS’s Charter, Mission Statement and Regulations, a redefinition of the range of services offered, and a scheme ensuring a more efficient distribution of tasks and human resources implemented.

The overall step-by-step approach for the implementation of this activity includes:

- Creation of the Support team to assist the implementation of the Institutional Reform Plan (IRP). This team will consist of the members of the IRP Task Force  formed under the activity 2.2 and enlarged by relevant management staff of SSA/ESS (national and regional/district levels).

- Support and facilitation provided by the STEs in piloting the measures designed in the Institutional Reform Plan (in selected Regional/District Offices) in partnership with regional/local stakeholders (based on the designed measures)

- Ensuring operational management within Head Office and selected pilot offices and networking

- Developing Coaching programme for SSA/ESS staff that enables smooth performance

- Reviewing the tools: ensuring the system and proper tools to support the implementation of IRP

- Establishing a monitoring and evaluation system for the implementation of IRP as a vital component in the success.

The purpose of this system will be:

- Monitoring the process of implementation - to ensure that the actions outlined in the change management strategy are being taken and that resources are being allocated and used effectively.

- Evaluating the progress towards the achievement of goals and objectives in relation to actions.

- Using feedback information to improve the process.

Supervision of defined monitoring indicators to be monitored during the implementation (piloting) phase will be done. Measurable indicators can be subdivided into:

- Process indicators, which monitor the basic progress of IRP implementation/piloting. This includes monitoring of implementation processes and inputs - people, money and equipment needed to achieve actions.

- Performance Indicators, linked with the agreed performance measurement framework that will establish targets for each of SSA/ESS sector/department and unit, as agreed with the SSA/ESS colleagues. This will provide a comprehensive view of the SSA/ESS performance, understanding of performance, guidelines for improving short-term results and the ability to assess and improve long-term organisational performance.

- Outcome indicators, which monitor the direct results of piloting actions.

- Impact indicators, which monitor progress towards achieving goals and objectives.

- Reporting on the implemented measures

- Assessment/evaluation of the measures based on agreed indicators

- Lessons learned: corrective measures/redefinition of services, improvement of the measure/s and overall improvement of Institutional Reform Plan in line with the results/outcomes from the implementation (piloting) and in harmony with the realities and needs of the country.

The feedback from employees and stakeholders gathered during the piloting process as well as results of monitoring and evaluation including reports on meetings, events, workshops, STE mission reports will be used as ground for the revision of the new IRP

The overall work as described above will be done by the Support team (STE+GE colleagues). Every step will be designed together taking into consideration specifics and realities in the country (regional/local level). A timetable for piloting will be also prepared together.

At least 3 workshops (2+1) will be held on training for IRP implementation/piloting (min 2) and final assessment (1) of piloting results and necessary adjustments of the IRP.

All outcomes from the piloting will be utilised for the revision and adjustment of the IRP and revision and redefinition of SSA/ESS´s Charter, Mission Statement and Regulations.

Expert missions to do the work planned under this activity and support to the implementation of institutional reforms within the SSA/ESS will be held.

Outputs

- Revised SSA/ESS´s Charter, Mission Statement and Regulations

- Revised IRP

- 3 Workshops held

Duration: 7 to 14 month

Resources

RTA

MSs staff: 5 MS experts Lorencic, Pavlovova, Kolmerova, Katuscak, Kubalova/ each 10days/2 missions each

The BC staff for this activity is:

- BC PL counterpart, RTA counterpart;

- Staff from the SSA/ESS (up to 60 persons in total taking part in all three workshops);

Other resources:

Infrastructure and facilities for the organisation of the workshops (3)

Translation and Interpretation

Activity 2.4

Review and revision (if required) of the current procedures for registration of job-seekers and job opportunities

The purpose of the activity is to ensure thorough review and revision, if appropriate, of the present procedures for registration of job-seekers and job opportunities.

Method

The STE involved in the implementation of this activity will assist the ESS to review its operating procedures and methodologies for the registration of job-seekers and job opportunities, and the provision of matching services to clients to ensure that the current procedures allow for the profiling and tracking of job seekers and job opportunities. In line with above, focus will be put on assisting the ESS to develop a more sensitive understanding of the needs of the labour market and the available skills.

On the basis of the review, the STE will make recommendations to the ESS for strengthening its registration procedures as appropriate.

STE will also elaborate on the process map of the current procedures for registration of job-seekers and job opportunities and, in line with the findings STE will also ensure transfer of verified good practices in relation to operating procedures and methodologies for the registration, maintaining of the evidence, de-registration and tracking of job-seekers and job opportunities from the MS (SK-HU-CZ) involved in the implementation

Also, STEs will not focus only on good practices but they will also provide Georgian colleagues with experience from which Georgian colleagues can learn from some mistakes the colleagues from SK, HU and CZ did and try to avoid such mistakes in their work (concrete cases will be outlined)

The above work will be done by the Support team group which already worked together in activity 2.3.

The Review Report (RR) of the current stage, i.e. existing procedures for registration of job-seekers and job opportunities and proposed revisions and proposed recommendations will be discussed and commonly agreed within the Support team. The RR will also include standard operation procedures and methodologies for the registration and tracking of job-seekers and job opportunities (vacancies). Then a workshop will be held together with the ESS management aiming at the presentation of revised procedures. Consequently, the final adjustment of the revision document will be done by STE in cooperation with colleagues from the Support team.

Expert missions aiming at support, assistance and couching of Georgian colleagues in works planned under this activity will be held.

Outputs

- Review Report including standard operating procedures and methodologies for the registration and tracking of job-seekers and job opportunities including recommendations for their revision

- 1Workshop held

Duration: 8 to 10 month

Resources

RTA

MSs staff: 4 experts: Eva Gellerne Lukacs, Danica Kelecinova, Kubalova  / each 5 days/1 mission

The BC staff for this activity is:

- BC PL counterpart, RTA counterpart;

- Staff from the SSA/ESS (up to 20 persons involved in the workshop);

Other resources:

Infrastructure and facilities for the workshop organisation

Translation and Interpretation

Activity 2.5

Introduction of new services within the ESS

The purpose of this activity is to ensure the introduction of the new services within ESS.

Method

In line with the recommendations of the Functional Review (FR), the STEs involved in this activity and taking an active part in the elaboration of FR thus experienced in the development of counselling and related advisory services for job seekers will assist the management of the ESS to introduce the new services as appropriate.

-    In this respect, this will also involve developing the:

- guidelines,

- methodologies and tools for each of the new services introduced and,

- trainings on their developing and applications.

- The Support team already involved in activity 2.4 will jointly work on the introduction of revised procedures - works as defined in a) – c)

- In line with above, training programme for ESS staff will be designed at first stage by STE, then consulted within the Support team and finally agreed by all twinners involved in this activity. Preparation of training sessions (workshops) for acquisition of necessary skills and for acquiring knowledge to deal with the implementation of the new service model – new services within ESS will be introduced and training materials developed by STE. While designing the training programme, the so-called cascade effect in training and (Training of trainers) approach will be utilised to ensure sustainability and have on spot Georgian trainers able to further train their colleagues (newcomers and those who did not attended the training sessions)

- Training sessions, in which interactive methods will be applied, will be conducted for approx. 60 in total, (national and regional level) and feedback (evaluation) from the training will be used as reference point for any necessary adjustments of the guidelines, methodologies and tools.

- In addition to the training workshops, also on-the job training for Georgian colleagues provided by STEs – complementary to the training workshops will be ensured including tailored advice and coaching

- Finally, all adjustments will be incorporated into the final version of theguidelines, methodologies and tools.

Expert missions: to support, assist and couch Georgian colleagues in works planned under this activity

Outputs

- Guidelines, methodologies, and tools for each of the new services introduced

- Training programme and training materials prepared

- Trainings (5 workshops) delivered

Duration: 5 to 9 month

Resources

RTA

MSs staff: 3 MS experts Lorencic, Kubalova, Katuscak/ each 10 days/2 missions each

The BC staff for this activity is:

- PL counterpart, RTA counterpart;

- Staff from the SSA/ESS ( in total 60 people);

Other resources:

Infrastructure and facilities for the training workshops

Translation and Interpretation

Activity 2.6

Support to the further development of job-seeker counselling services

Following to the works planned and done in the previous activities under this component and more concretely in activities 2.4 and 2.5, this activity is targeted to ensuring appropriate support for the further development of job-seekers counselling services.

Method

- The STE involved in the implementation of this activity will work closely with the ESS, MoLHSA and MoES to further develop counselling services for job-seekers. The counselling services should cover at least the following key issues:

- career guidance,

- opportunities for skilling/re-skilling,

- job interviewing techniques,

- preparation of job applications/curriculum vitae.

- Process Map of the current practices in the country related to job-seeker counselling services provided by ESS will be elaborated and from this point STE will focus on works towards improvements and/or introduction of completely new counselling services with their testing in practical terms in at least 30% of the of the total ESS offices

Focus will be put on career guidance, opportunities for skilling and re-skilling, job interviewing techniques, and the preparation of job application: some unique tools/products which were verified and very successfully implemented  in the MS for career guidance will be introduced to the Georgian colleagues by STE, as well different techniques used by staff of the three MS (SK-HU-CZ) – all this with a purpose to effectively support and assist the job seekers and other service users in the process of planning their work career as well as in the job search process. Professional information, professional counselling and orientation, and professional selection (preparation for employment by training, requalification or additional qualification of job seekers but also professional selection to be used in mediation to assist employers in their selection of unemployed candidates for their vacancies)

- The testing will also involve on-the-job trainings of the enhanced counselling services and will be done in at least 30% of the total ESS offices.

- The testing methodology will be prepared by STE, discussed with the Support team and agreed together. It will also include which of the ESS offices will take part in the testing process. At least 5 workshops focused on testing introduction will be held

- Focus will be also put on establishing a stronger link between the labour market and the educational system which is necessary for successful planning and harmonisation of the educational process with the current and forecasted needs of the labour market

- Assessment of piloting (involving on job training) and consequent revision: results of the evaluation of testing process and findings will be the basis for conclusions, recommendations and concrete steps in introducing improvements of job-seeker counselling services

- 1 workshop on outcomes of the testing and recommendations for improvement will be held with ESS management

- set of improved counselling services for the job-seekers which were tested and verified will be prepared for ESS staff by STE.

Expert missions will be held to ensure and execute the works planned under this activity.

Outputs

- Enhanced job-seeker counselling services are piloted through 30% of the total ESS offices and revised based on the results of the piloting

- ESS staff and other stakeholders (e.g. MoLHSA and MoES) trained

- 6 Workshops held (5 on testing, 1 on outcomes of the testing phase

- Handbook prepared

Duration: 5 to 9 month

Resources

RTA

MSs staff: 4 MS experts Lorencic, Kubalova, Katuscak, Kolmerova/each 5days/4 missions

The BC staff for this activity is:

- BC PL counterpart, RTA counterpart;

- Staff from the SSA/ESS (least 30% of the of the total ESS offices), relevant representatives of the MoLHSA

Other resources:

Infrastructure and facilities for testing workshops and final workshop (in total 6 planned workshops)

Translation and Interpretation

Activity 2.7

Development of a Procedures Manual

The purpose of the activity is developing a complex Procedures Manual for the staff of ESS.

Method

On the basis of the above work in activity 2.6, the STEs involved in the implementation of this activity will draft an internal Procedures Manual for use by Head Office and Regional and District Offices staff of the ESS to train the respective staff of the ESS on its practical application.

- The Handbook envisaged to be designed under the  activity 2.7 will be part of the complex Procedures Manual and will be elaborated in a friendly-user form

- The draft of the Procedures Manual will be prepared by STE, discussed in the Support team group and consequently agreed on its final version.

- After Procedures Manual is ready, it is necessary to ensure training of the ESS respective staff on the Manual application. In this respect:

- Training plan and training modules with developed content and timeframes of implementation will be previously brainstormed at working sessions of STE with Georgian counterparts in order to get support and “ownership” of the whole process by BC.

- Min. 2 training workshops will be held for the staff of the ESS Head Office and 10 regional offices; train-the trainer approach will be part of the workshops methodology for the training so that those attended the training will be able to train their colleagues and new colleagues of ESS.

- Wherever possible, also staff from district offices will be involved as well, to ensure wider understanding of the Procedures Manual and getting practical skills for its implementing in practical terms

- After the training was conducted and based on the feedback from training workshops, the Procedures Manual will be adjusted introducing of any necessary improvements, if necessary. Its final version will be translated into Georgian language and made available on paper and electronic form for the whole ESS staff (all levels)

- Expert missions to do the work planned under this activity will be held. Consultative discussion sessions with ESS management staff on the Procedures Manual will be conducted.

Outputs

- Procedures Manual elaborated

- Training conducted

- Evaluation of training conducted

Duration: 5 to 9 month

Resources

RTA

MSs staff: 3 MS experts Lorencic/5days, Kubalova/5days, Kolmerova/5days, in total 15 days

The BC staff for this activity is:

- BC PL counterpart, RTA counterpart;

- Staff from the ESS (up to 40 persons for both workshops);

Other resources:

Infrastructure and facilities for conducting of 2 training workshops

Translation and Interpretation

Activity 2.8

Development of a Quality Assurance Plan (QAP)

The purpose of the activity is prepare a QAP to install quality control mechanisms which will be used and maintained by the ESS staff of the Head Office, Regional Offices and District Offices.

Method

The MS STE will assist the management of the ESS to elaborate a Quality Assurance Plan (QAP) and to install the necessary quality controls for use by Head Office, Regional Offices and District Office staff.

To ensure complex and concise understanding of the quality assurance, specialised 2 workshops will be held with the Head Office, Regional Offices and District Office staff.

The workshops will be organised in smaller groups so that they are practical and allow every participant to become fully acquainted with the issues but also to give thorough feedback. The methodology for the workshop conducting will be based on train-the-trainers principle, i.e. those involved in the workshops will then train their colleagues at various levels.

The STE involved in this activity will prepare:

- Draft of the QAP including the necessary quality control measures

- Methodology for the workshops

- Materials and presentations at the workshops

- Selection of participants for the workshops

All as described in a) to d) will be discussed with the Support team and ESS management and after the final versions will be prepared by the STE.

Consequently the two planned workshops will be conducted. The results and outcomes (feedback) from the workshops will be the ground for any appropriate adjustments of the QAP and its final version will be prepared by the STE.

The final version of the QAP will be made available in Georgian language in paper and electronic form.

Expert missions to ensure the planned work under this activity is done will be held.

Outputs

- Quality Assurance Plan including the quality control measures

- 2 workshops held

Duration: 9 to 13 month

Resources

RTA

MSs staff: 2 MS experts Kubalova/5days, Pavlovova/5days, 2 missions in total

The BC staff for this activity is:

- BC PL counterpart, RTA counterpart;

- Staff from the ESS (up to 40 people for both workshops);

Other resources:

Infrastructure and facilities for conducting 2 workshops

Translation and Interpretation

Activity 2.9

Study Visit to MS to examine the range of services provided to job-seekers and employers through employment offices

Method

- The PL and the RTA together with the support of STE and institutions from Slovakia will organise a learning Study Visit for Georgian colleagues. The main aim of the visit will be to:

- examine the range of services provided to job-seekers and employers through employment offices in Slovakia

- learn on situ from colleagues and their experience – become acquainted with good practices on spot (“once to see and test than hundred times to hear only”)

- Compare models and systems; pick up for Georgia the most appropriate options and elaborate on Action Plan by Georgian participants how the acquired know-how can be transferred to SSA/ESS and the staff; it is also participants in the study visit to organise after their return a information (dissemination) workshop on lessons learnt for their colleagues in Georgia

- Deepen the contact and co-operations with  institutions from Slovakia; make direct contacts with their colleagues– so to pave long-term cooperation and collaboration; discuss possible cooperation agreement/s for deepening the cooperation between the Slovakia and Georgia and the employment institutions in the both countries

- Ensure complex evaluation of the learning study visit

Taking into consideration the unique opportunity to learn on spot in Slovakia, it is suggested that the study visit last 5- working days/6 overnights study visit to Slovakia for 10 participants (9 +1 interpreter) of the BC project team allow 9 Georgian colleagues to have opportunity to learn and visit not only one level (Central Office) but also Labour Offices at regional/local level in the MS Slovakia.

It is proposed that the following counterpart institutions be visited in Slovakia:

Slovakia:

- Central Office of Labour, Social Affairs and Family, Bratislava

- Ministry of Labour, Social Affairs and Family, Bratislava

- Office of Labour, Social Affairs and Family in Nitra/Banska Bystrica  (regional level) or Kosice plus 1-2 offices at local level near Bratislava or Nitra

Any other institutions can be included into the programme of the study visit upon request/wish of the Georgian colleagues, e.g. Ministry of Education, authorities in charge for lifelong learning, state authorities dealing with vocational training, employers and their associations, etc.

The detailed programme of the study visit will be prepared in advance in close cooperation with the MS PL, RTA, JPLs, and their counterparts in order to meet real needs for learning and skills acquisition by Georgian colleagues.

Outputs

- 1 study visit conducted

- Report of the Study visit

- Action Plan of Georgian participants on know-how transfer to other colleagues from ESS

- 1 information workshop held by Georgian colleagues on study visit lessons learnt to other colleagues from ESS

Duration: 6-7 month

Resources

RTA

MSs staff:  0 experts  (back up office will provide organisational support on situ in the MS – SK – HU – CZ in close cooperation with the MS PL, JPLs, RTA office and STE)

The BC staff for this activity is:

- 9 Georgian staff plus 1 interpreter

- Travel costs to MS– 10 fly tickets, transport costs within MS

- Per-diems for 9 Georgian staff plus 1 interpreter (6 per-diems/6 nights x 10 persons in line with per-diems rates for SK, HU, CZ)

Other resources:

Translation and Interpretation

Component 3:

A comprehensive Labour Market Information Management System (WorkNet Information System) has been established and is fully operational

(Mandatory result 3)

Component leader: Gero George

The following key works will be executed under this component:

- Ensure thorough review of WorkNet Information System and elaborate a Concept for its upgrading

- Develop ToR and methodology & tools for preparation of monthly, quarterly and annual labour market reports

- Support for putting the WorkNet Information System in operation in line with the Concept

- Guide SSA/ESS ’s employees and relevant stakeholders to implement the Concept – upgraded WorkNet Information System

- Create opportunity for Georgian colleagues to examine the collection, collation and analysis of labour market data by the employment services in the three MS – SK, HU and CZ

Below, the methodology of every activity belonging to this component is described in detail.

Activity 3.1

Review of the WorkNet Information System

The purpose of this activity is to review and assess the WorkNet Information System, its functionality, operability and compatibility with the wider Labour Market Information System in the country and prepare a complex set of recommendations for further improvement. The experience and verified good practices of the three member states – SK-HU-CZ in relation to IT systems operational in these countries will be taken as reference point for comparison.

Method

The works of STE will take into consideration the already achieved results (current situation) and further develop on it. The current state of play to be taken into account (i.e. the facts that in December 2013 within LMIMS Labour Market Information Management System/ - WorkNet Information System was introduced by ESS, which is designed to help job seekers, employers, education and training providers, recruiters and others to communicate on-line. A number of modules are planned: module one which is currently operational allows job-seekers to register on-line. There are presently 4650 registered job-seekers; module 2, which is planned to come on line in 2014, will be targeted at employers. A third analytical module will be introduced in 2015).

- Under Mandatory Result 3, support will be provided to ensure that the data collected through the WorkNet Information System is sufficiently comprehensive to permit the ESS to develop a comprehensive overview of the current labour market.

- STE, who are specialised in the design and implementation of automated LMIMS, will carry out a thorough Review of the WorkNet Information System.

- The purpose of this Review is two-fold:

- to ensure that the WorkNet Information System is compatible with the wider Labour Market Information System being developed by the MoLHSA

- to identify what methodologies and tools would be required to enable the ESS to develop a comprehensive overview of the current labour market, using the data gathered through the WorkNet Information System.

- In line with the above-mentioned focus will be put on:

- Collection of all relevant and necessary data (Real Data Collector) with connectors to various systems including preparation and aggregation of data

- Distribution of relevant data to key players in the labour market (SSA/EES staff, MoLHSA, MoES, MoF, other line-ministries, other Georgian state/public stakeholders etc.)

- Be compatible with the LMIMS

- Be secured in terms of function – data security

- Enable real-time Data collection

- IP-based network complexity and interoperability

- Availability, speed, reliability, scalability, efficiency

- Enable integration of third-party data

- Enable Cross-Platform data collection: beneficiary institutions need to collect, merge and correlate data on a real-time basis, across different technology and access platforms. In this respect they can then enrich the data with information from their IT systems and use the integrated information to provide decision makers, raise awareness, inform employees, employers, contract parties, all other stakeholders, government and EU

- Upgradability of the IT system

- Support to the complete work of the ESS

- Resolve Data inconsistencies

- Ability to extract data for Reports preparation; experience and verified practices used by the three MS – SK-HU-CZ will be presented

- IT Working Group (ITWG) consisting of nominated experts from the ESS, MoLHSA, and/or MoES, and, if necessary, of other relevant institutions will be created. This IWG will include experts who have hands-on experience in ICT as well as in labour market information systems (knowledge on processes and procedures, design, creation, operation and maintenance). The ITWG (Georgian and STE) will work together on conducting comprehensive analysis - review examining the current situation, real needs, identifying gaps and preparing recommendations which will be used as input for elaboration of the Concept Paper planned under activity 3.2. for up-grading. The Georgian side will provide STE with existing documentation of the existing system in English.

- The work to be done under this activity will be also linked to the outputs of component 2 especially with activities 2.1, 2.2, 2.3, 2.4, 2.5 and 2.6 as the upgrading of the whole WorkNet system should be integrated into overall institutional reform of the SSA/ESS.

- The elaborated Review Report will include the findings regarding the above-mentioned issues:

- present situation,

- existing gaps and shortages,

- concrete needs of the ESS, other relevant beneficiaries and common needs,

- level of compatibility, identifying the methodologies and tools which would be required to enable the ESS to develop a comprehensive overview of the current labour market, etc.

The findings will be served as a ground for the complex development of the Concept design

- Experience and good practices/standards of the three MS – SK, HU and CZ will be served as examples and reference points. In this respect, the newly modernised, unique, fully operational and already verified SK IT system which already became a reference and high-level standard for PES (public employment services in EU/V4) can be an inspiration for ESS. Information on this system is provided in Annex 1 of this proposal. Comparison of systems in all three MS can be used as options to build up on Georgian own, tailor-made system but fulfilling the necessary EU-standards for PES.

- Expert missions, consultative sessions, WG work, round-table involving key Georgian players on presentation of the Review Report and recommendations

- The IWG will meet at least twice during the implementation of this activity. STE will, with the support of Georgian colleagues, elaborated on the draft of Review Report and prepare a set of concrete recommendations for upgrading of the system. The draft Report will be discussed within the IWG, adjustment, where appropriate, will be done and final version will be prepared by STE.

- Consequently, a round table with ESS, MoLHSA and, if appropriate with other relevant stakeholders, will be organised to create space for expression of opinions of decision-makers and thus of ensuring common understanding and agreement on not only the final version of the Review Report and recommendations but also on the works that should follow within the rest of activities of this component, i.e. all Georgian key decision players are working together towards common objectives regarding upgrading of the WorkNet System.

Outputs

  - ITWG created and operational

  - Review Report covering the functionalities of the current WorkNet Information System together with recommendations for up-grading provided

Duration: 2 to 5 month

Resources

RTA

MSs staff:  4 MS experts George, Pavlov, Kelecinova, Majercak each 5 days/Total 20days/4 missions

The BC staff for this activity is:

- BC PL counterpart, RTA counterpart;

- Staff from the ESS/MoLHSA, other relevant stakeholders (up to 20 people);

Other resources:

Translation and Interpretation

Activity 3.2

Elaboration of a Concept Paper for upgrading the WorkNet Information System

This activity will play a key role in achieving a mutual consensus among Georgian stakeholders (SSA/ESS-MoLHSA, other relevant ones) on elaborating a clear, sound and realistic Concept for efficient upgrading of WorkNet IT System and upgrade/concept for the statistical hardware/software with established and upgrading databases. The main aim of this activity is to elaborate a complex Concept for effective IT system and network that will bring together the key players in the field (SSA/ESS/MoLHSA, other e.g. MoES).

Method

The STE will elaborate a Concept Paper, which will address three core areas:

- Recommendations for refining the functionalities of the current WorkNet Information System to ensure interoperability and interconnectivity with the wider Labour Market Information System and for ensuring that the data collected and functionalities of the operating system enable the ESS to model and report upon the current labour market;

- Identify upgrades in hardware and software that would be needed to ensure that the ESS possessed the technical capacities to implement recommendations under (a) above;

- Suggest the approach, methodology, tools and templates that would be required to permit the ESS to develop monthly/quarterly and annual reports on the current state of the Georgian labour market

The elaboration of the Concept Paper will be based on the findings in act. 3.1. (Review report & recommendations).

The Concept Paper will also:

- include written accurate understanding of specific institutions´ needs,

- define examples for changing requirements,

- contain best practices in how to obtain: software that's easy to maintain or extend; excellent software quality; acceptable software performance; trustworthy ‘build and release’ process

- increase transparency and compliance with EU standards

The upgraded IT system would also consider the following issues:

- to help to job counsellors at the employment offices at various levels in the country to effectively manage their clients through automatically generated reports on activity of registered job-seekers in their e-accounts

- multi-channelling features such as SMS and email notification of vacancies and public ESS employment offices´ events for clients (e.g. job fairs, interviews).

- for employers: bringing automated import of employer´s details from GE business register, automated export of vacancies from employers IT system to ESS WorkNet IT system. To consider enabling the creation of employers´ accounts with full management of vacancies and direct access to all registered job-seekers profiles to employers

- Complex monitoring system (including monitoring active labour market measures, passive ones, any state or EU/bilateral financed projects, job vacancies, reporting on job mediation, job interviews, job fairs, on mass layoffs of employers, on unemployment and employment of foreigners, etc.). All information in the monitoring system to be at disposal online for internal ESS employees.

- The work will be done by the ITWG as established in act. 3.1.

- Draft Concept Paper, elaborated by STE and discussed and agreed internally, i.e. within the ITWG, will be finalised by STE and then presented in a Round-table involving key responsible persons from ESS and MoLHSA (decision-makers), where appropriate also any other key stakeholders. The Final Version of Concept Paper including Recommendations will be finalised by ITWG members under with STE coaching/advice on the grounds of the Round-table outcomes. This Final Version will be made available to beneficiary in Georgian language.

- Expert missions linked to ITWG work; consultative sessions with ESS/MoLHSA, other key players in the labour market as well as, e-government Georgia (Data Exchange Agency which is in charge for e-government development coordination) will be held to ensure not only common understanding of any problematic issues but also to commonly agree on the final versions and decisions to be taken.

- By using these methods, the twinning team will be able, in addition to the above, to achieve as well:

- Improved government-to-government (G2G: ESS-MoLHSA-MoES, MoF, MoESD, MoAG, other line-ministries and public bodies, etc.),

- Government to-business (G2B: specifically to employers and their umbrella associations, etc.) and Government-to-citizen (G2C: unemployed, those who wish to change job and build on new career or take a second chance, etc.) services;

- Increased efficiency of Government spending – better investment of money for upgrading of WorkNet Information System;

- Improved cooperation between Government Agencies;

- Effective information sharing;

- Improved data quality;

- Standardized data;

- Improved quality and accuracy;

- Unified security standards;

Outputs

  - Concept Paper elaborated, presented, discussed and agreed

  - Round table held

Duration: 4 to 7 month

Resources

RTA

MSs staff:  4 MS experts George, Pavlov, Majercak/each 10 days; Vido/5days

The BC staff for this activity is:

- BC PL counterpart, RTA counterpart;

- Staff from the ESS/MoLHSA, other relevant stakeholders (up to 20 people);

Other resources:

Infrastructure and facilities for organisation of the round-table

Translation and Interpretation

Activity 3.3

Preparation of Terms of Reference/Technical Specifications (TS) for upgrading the WorkNet Information System

The purpose of the activity is the prepare ToT (technical specifications) for the upgrading of the WorkNet Information System. The implementation of the activity relates to the outputs of the previous activity 3.2.

Method

  - In line with the recommendations contained in Section (b) of the Concept Paper elaborated under activity 3.2, the STEs will support the ESS to prepare the Terms of Reference (ToR) and Technical Specifications for the procurement of off-the-shelf or tailor-made software and hardware.

  - The procurement of the hardware and software for the upgrade of the WorkNet Information System (LMIMS) will not be financed through this Twinning Contract.

  - The work under this activity will be done by ITWG operational already in the previous two activities 3.1 and 3.2. The ToR will be prepared by STE, consulted on ongoing manner with ESS counterpart, discussed within the ITWG and commonly agreed.

  - The final version of the ToR/technical specifications will be then presented in a Workshop involving ESS and MoLHSA management; then final adjustments, if necessary and appropriate and base on outcomes/feedback from the workshop, will be introduced and this final version will be made available to the Georgian side in Georgian language

  - In line with the above-mentioned, expert missions, ITWG work, workshop on final proposal of ToR and Technical specifications for upgrading of the WorkNet Information System will take place while working on accomplishment of this activity.

Outputs

- ToR and TS for procurement of supplies and services are prepared, discussed and agreed and are consistent with Georgian public procurement legislation

STE Mission report drafted

- Workshop held

Duration: 6 to 10 month

Resources

RTA

MSs staff:  2 MS experts George, Majercak, each 5 days/1 mission each

The BC staff for this activity is:

- BCPL counterpart, RTA counterpart;

- Staff from the ESS/MoLHSA, other relevant stakeholders (up to 20 people);

Other resources:

Infrastructure and facilities for workshop organisation

Translation and Interpretation

Activity 3.4

Development of methodology and tools for the preparation of monthly/quarterly and annual labour market reports

The purpose of the activity is to develop methodology and tools for the preparation of monthly/quarterly and annual labour market reports.

Method

In line with the recommendations contained in Section (c) of the above Concept Paper (activity 3.2), the STE involved in the implementation of this activity will support the ESS to design and develop the:

- methodology,

- tools (incl. those for proper self-service for ESS customers)

- required templates –

for modern reporting that would permit the ESS to develop consolidated monthly/quarterly and annual reports on the current state of the Georgian labour market, and provide accurate data on supply and demand in the labour market, disaggregated by region/age/gender as a minimum.

- The work will be done together in the same ITWG as established in act. 3.1. thus to ensure continuity and transparency of the works towards elaboration of overall methodology, tools and required templates

- Good practice examples will be presented by STEs from all three countries – SK-HU-CZ – EU standards will be reference point for the works. At the same time, STE will take into consideration the realities in Georgia and provide support tailored to Georgia/ESS needs to elaborate on high-level products

- Proposed methodology, tools and templates will be discussed and agreed by the ITWG members and after that it will be presented to ESS / MoLHSA officials (management)

- Expert missions, group work within the established ITWG, discussion and consultative sessions and presentation of developed products at a workshop will be done under this activity

- Final products will be made available in Georgian language to ESS counterpart

Outputs

- Methodology, tools and templates for preparing consolidated monthly/quarterly and annual reports on the current state of the Georgian labour market are defined and developed

- Workshop held

Duration: 8 to 11 month

Resources

RTA

MSs staff: 4 MS experts: George, Pavlov, Majercak, Vido/ each 5days

The BC staff for this activity is:

- BC PL counterpart, RTA counterpart;

- Staff from the ESS/MoLHSA, other relevant stakeholders (up to 10 persons);

Other resources:

Translation and Interpretation

Activity 3.5.

Study Visit to MS to examine the collection, collation and analysis of labour market data by the employment services

Method

The purpose of this activity is “3D”, i.e. has three key dimensions:

- To create opportunity for Georgian partners working on WorkNet system to learn from the experience of the two MS SK-HU on their IT system development including good practices verified in public employment services (PES) in SK and HU

- To improve the skills and knowledge of the Georgian colleagues in this specific area through getting concrete hands-on skills and knowledge from their colleagues in SK-HU

- To ensure transfer of experience, knowledge and skills acquired by participants from Georgia during the study visit to their colleagues in Georgia (at various levels:national, regional/district) through organisation of 3 information workshops in three different locations in the country. These locations will be agreed by all twinners.

- 1 Learning Study Visit will be organised with the support of the PL, RTA and STEs for 5working days/6 overnights for 8 persons (7 specialists + 1 interpreter) drawn from the ESS central and regional offices / MoLHSA.

- The Study Visit will be conducted in a combined manner in the twoMS – Slovakia and Hungary in order to create wider learning space for those dealing with the IT and get hands-on experience and skills in the area (not only see but also test the IT systems in the two countries), discuss advantages/disadvantages, own possibilities in Georgian institutions, pick up on the most reasonable solutions while taking into consideration the EU standards and requirements.

- Focus will be put on the collection, collation and analysis of labour market data and related issues and linked directly to the content of the activities planned under component 3.

Taking into consideration the unique opportunity to learn from the two EU MS – SK and HU, it is suggested that the study visit last 5- working days study visit to Slovakia and Hungary for 8 participants (7 +1 interpreter) of the BC project team (learning in each country on IT system and the way how it is used in various levels in the countries).

It is proposed that the following counterpart institutions be visited in Slovakia and Hungary:

Slovakia:

- Central Office of Labour, Social Affairs and Family, Bratislava

- Ministry of Labour, Social Affairs and Family, Bratislava

- 2 Offices of Labour, Social Affairs and Family in (regional and local levels)

- Optional: Ministry of Education and Science, other relevant stakeholders using the IT system, e-Slovakia

Hungary:

      - National Labour Office in Budapest

      - Ministry of Social Affairs and Labour, Budapest

      - 2 offices – one at regional and one at local level

Outputs

- Detailed tailor-made study visit programme prepared, discussed and agreed

- 1 study visit conducted

- Report of the Study visit

- 3 information workshop held by Georgian colleagues on study visit lessons learnt to other colleagues from ESS in 3 different locations

Duration: 7-8 month

Resources

RTA

MSs staff:  0 experts (back up office will provide organisational support on situ in the MS: SK and HU in close cooperation with the MS PL, JPLs, RTA office and STE)

The BC staff for this activity is:

- 5- working days study visit to Slovakia and Hungary for 8 participants (7 +1 interpreter)

- Travel costs to MS – 8 fly tickets

- Per-diems for Georgian staff plus 1 interpreter (6 per-diems/6 nights x 8 persons in line with per-diems rates for SK/HU)

- Transport costs for transfer within and between the two MS (SK and HU)

Other resources:

Translation and Interpretation

Component 4:

Modern human resource management techniques have been introduced, the staff has acquired the necessary skills and experience to provide high quality services to job-seekers, and an in-house training and retraining platform has been established

(Mandatory result 3)

Component leader: Luba Pavlovova

The main tasks to be carried out under this component are:

- To ensure introduction of modern human resource techniques

- To guide, support and train the staff of SSA/ESS to acquire complex of skills, experience and knowledge necessary for delivery of high-quality of services to job seekers

- To establish and put in operation in-house training and re-training platform for sustainable HR management

This will be done within the implementation of 7 activities which are logically connected to each another.

Activity 4.1

Review of current Human Resource Development (HRD) policy

Method

The training of the employees is an important tool for each public employment service that strives towards fulfilment of its objectives and developing its activities. It should support and strengthen the effects of other measures and activities that are implemented. The successful implementation of the Institutional Reform Plan (IRP) which is developed under component 2 and which is directly linked to SSA/ESS improvement of existing services or introduction of new services requires strengthening the ESS human resources, not only in terms of quantity but also in terms of quality. Therefore, continuous upgrading and training of the ESS staff will be necessary.

In line with the above, this activity is targeted to conducting thorough review of the ESS overall HRD policy so that ESS is able to meet requirements, needs and challenges in the employment matters and be able to fully fulfil its functions as modern PES (public employment service) in all its complexity while taking into account the EU standards and verified good practices. These practices will be based on the long-term improvements introduced by the three EU-countries: Slovakia, Hungary and Czech Republic and, at the same time, taking outlining experience of another EU MS – Slovenia.

A successful implementation of the upgraded services model requires not only improvement but also strengthening the HR in ESS – not only in terms of quantity but also in terms of quality.

- In line with this, the STEs in HRD/training will carry out a Review of the current HRD policy together with the management of the ESS.

- In particular, the review will focus upon the:

- recruitment system,

- terms and conditions of employment,

- career development and promotions’ policy,

- in-service training,

- performance appraisal.

Based upon the results of the review analysis, the STE will suggest revisions to the current HRD policy to the ESS management while taking into consideration the needs for institutional reforms as outlined in the IRP (comp2).

- The overall work under this activity will be done by HR Task Force working group (HRTF) consisting of STE and ESS management staff. The HRTF will carry out on the review and STE, upon this work, will prepare the 1st draft of the Review Report on HRD, i.e. a document containing revisions to the current HRD policy and concrete recommendations for improvement and/or introduction of new measures towards HRD of ESS. This Report will also take into account the specifics and realities of the country´s regional/district situations so that recommendations are indeed tailor-made to the real needs and requirements arising from these realities.

- After 1st draft Review Report is prepared, internal (inside the HRTF) workshop will be held to discuss this draft and to outline any outstanding issues which are to be also taken into consideration. Upon the outcomes of this 1st workshop, the pre-final version of the Review Report will be elaborated by STE.

- Consequently, 2nd workshop will be organised with the ESS staff involving all levels: national, regional and district to present this pre-final draft, discuss its findings and recommendations, get opinions of various ESS representatives from all the country and based on the feedback, the final version of the Review Report and recommendations will be prepared by STE. This way of work will also allow for ownership of all ESS staff, i.e. be part of the whole process and be identified and agreed with the findings and what (recommendations) is necessary to be done from mid- and long-term perspective. The Review Report will also outline the priorities, i.e. what are the most important measures to be taken in first stage towards ESS HR development.

- The findings and recommendations outlined and commonly agreed in the Review Report will serve as input for activities 4.2, 4.3 and specifically for 4.4

- In line with the above, expert missions, consultative sessions within established HRTF working group, two important workshops and various working meetings will be conducted.

- The final version of the Review Report: findings & outcomes and proposed improvements/recommendations / appropriate/necessary adaptations and/or novelties will be translated into Georgian language and made available to the ESS staff in paper and electronic form.

Outputs

- Review Report of current HRD policy carried out and recommendation for revision provided.

- 2 Workshops held

Duration: 7 to 10 month

Resources

RTA

MSs staff:  3 MS experts Pavlovova, Dobesova, Lorencic/30 days in total, each 10 days/total 6 missions

The BC staff for this activity is:

- BC PL counterpart, RTA counterpart;

- Staff from the ESS, other relevant stakeholders (up to 40 people for both workshops);

Other resources:

Infrastructure and facilities for conducting the two workshops

Translation and Interpretation

Activity 4.2

Drafting of an HRD Manual

Method

The works planned under this activity will be accomplished in two main steps:

      - On the basis of the Review Report and its recommendations developed in activity 4.1, and agreed by ESS management, the STEs will introduce the necessary revisions to the ESS´s HRD policy.

This will include:

- developing transparent recruitment

- career development and promotions procedures

- elaborating standard contracts

- defining templates and methodology for performance assessment including self-assessment by ESS staff

- identifying standard induction and in-service training modules

Also, any other important issues linked to the outcomes/findings and recommendations of act. 4.1 will be taken into consideration and included into the Manual.

These revisions and adaptation will be first discussed internally within the HRTF working group as established in activity 4.1 in a form of Consultative Session. Upon feedback of members of the HRTF as presented at the Consultative Session, some adaptations will be done, where necessary and appropriate.

      - The work done in step 1) related to the new upgraded ESS HRD policy will be consolidated into a complex HRD Manual. The Manual will be prepared in a way, so that it will not only include all above-mentioned issues but also it will be drafted in “understandable language” to be practically used in daily operation of the ESS staff at various levels. The draft HRD Manual will be introduced at a Working Seminar with the ESS key staff (decision-makers) and after incorporating of any issues of specific importance its final version will be prepared by STE, translated in Georgian language and made available to the ESS staff in paper and electronic form.

- To ensure proper accomplishment of works planned under two main steps for this activity, expert missions, consultative working meetings and presentation of the draft Manual will be ensured in a form of a working seminar involving the ESS management and, if appropriate, any other relevant stakeholders

Outputs

- HRD Manual developed

- Consultative Session and 1 Working Seminar conducted

Duration: 9 to 11 month

Resources

RTA

MSs staff:  3 experts Pavlovova, Turner, Lorencic x 2 missions/in total 30days/6 missions

The BC staff for this activity is:

- BC PL counterpart, RTA counterpart;

- Staff from the ESS, other relevant stakeholders (up to 25 people);

Other resources:

Infrastructure and facilities for conducting the working seminar

Translation and Interpretation

Activity 4.3

Conduct Training Needs Analysis (TNA)

Method

In order ESS staff (at all levels in the country) to properly execute its activities and provide required services, it is necessary for the staff to know what to do, how to work, what services to provide and what working methods to use.

The effects of training will depend on several factors, i.e.:

- decisions regarding the structure and organisation of the daily work

- management (central, regional and district)

- sufficient financial means to ensure effective training not only within this twinning project but also to have clear vision how sustainability in further training will be ensure including how ESS will finance this after project has ended.

It is much easier to design precise and cost-effective training programmes for the ESS staff, if all the ESS employees are well informed about their work tasks and work methods and the background policies for their work.

Therefore, the above-mentioned will be taken into consideration while implementing not only this activity but the whole component 4 and the real must for ongoing upgrading and training of the ESS staff is to be put in the centre.

To meet actual needs for organising tailor-made training sessions, it is necessary to properly conduct TNA within ESS at various levels (central, regional and district). This will provide a complex picture of any specifics which could exist at these various levels and thus, the TNA should not only outline but also take into consideration such specific needs which will serve as input for the preparation of the Training Programme and materials (activity 4.4).

Steps and methods for implementation of this activity:

- The STE will carry out a comprehensive TNA of the staff of the ESS (Headquarters and District Offices).

- The TNA is inter-related to other four components as it shall detect needs and their complexity in relation to issues covered by these components. Therefore, the TNA will be conducted in a very complex and concise manner so all needs are identified and consequently covered by the Training Programme (to be designed under act. 4.4)

- The TNA will be concentrated on the areas which are key importance for proper execution of ESS services while taking into consideration three main target groups:

  - Managers (senior management, i.e. directors, deputies, etc.)

  - ESS other staff (levels: headquarter, regional and district offices)

  - Training of Trainers

- The TNA will review and assess (thorough survey) the needs of the target groups A, B& C as above-mentioned, identify the shortages in general and specific:

- skills,

- knowledge and competencies

and based on the outcomes to laid down the grounds for the complex modular training programme development in order to be tailored to the identified needs for capacity building. Questionnaires, face-to-face interviews with the two target groups’ representatives will be used as working methods.

- To execute the works as above, expert missions will be held to:

      - carry out on the TNA;

      - collate and evaluate the outcomes/findings of the TNA;

      - elaborate on a TNA document;

      - prepare the structure of training programmes;

      - discuss the first draft of the training structure with the beneficiary;

      - get the feedback, and consequently,

      - fine-tune the training programmes structure

The draft document TNA prepared by STE will be discussed in a working meeting with the HRTF working group and after taking into consideration any remaining issues and feedback from the group, the TNA document will be finalised, translated into Georgian language and delivered to ESS staff.

Outputs

- Training Needs Analysis conducted and available

- Training report delivered

- Training programme structure prepared, discussed and agreed with the beneficiary

Duration: 8 to 10 month

Resources

RTA

MSs staff:  3 experts Pavlovova, Turner, Lorencic / in total 30days/6 missions

The BC staff for this activity is:

- BC PL counterpart, RTA counterpart;

- Staff from the ESS, other relevant stakeholders (up to 15 people);

Other resources:

Translation and Interpretation

Activity 4.4

Development of Training Programme and Training Materials

Method

The purpose of this activity is to develop complex Training Programme for ESS staff. This training programme and its concrete plan will be drafted while taking into consideration the significance of the training of  ESS employees as outlined in the above activity 4.3 and will include proposed training for the three key target groups (A), B) and C)), i.e. ESS managers, other staff and trainers with the purpose of further strengthening the capacity of ESS in the implementation of the national institutional reform plan (act. 2.2 & 2.3). It is necessary that there is a chain that starts with central level and leads to the practical work in the regional and district employment offices.

The following steps and methods will be basis for all works execution:

- On the basis of the TNA the STEs will draft a Training Programme for the Headquarters and District staff – for the three target groups as described above in act. 4.3. (A., B. & C.)

- The programme will be divided between formal and in-service training, and mentoring/coaching of the senior management as well as for the trainers (as part of act. 4.7). In addition the STE will prepare all training materials and organise the translation in Georgian language.

- The Training Programme will be prepared as modular and it will cover at least the principal components of this project (single modules):

- Legal and regulatory drafting

- Modern management and administrative practises;

- Service design and delivery

- Counselling and career guidance

- Quality assurance and quality controls

- Methodologies, tools and techniques for analysing labour market data and forecasting labour market supply and demand

- Modern Human Resource Management theory and practise

- Communications and Awareness Raising tools and techniques

In addition to the above modules, specific modules will be prepared for the Training-of-Trainers. These modules will include the following key topics important for trainers competencies development:

- trainer´s competencies,

- principles of adults learning & skills-based training,

- training needs identification,

- training design &training methods, training delivery,

- communication & presentation skills,

- training environment management,

- training evaluation

The implementation of this specific ToT will be done under act. 4.7. The STE intend, if there would be appropriate, to involve ESS trainers already trained under activity 4.7 in the training delivery planned under activity 4.5. Such involvement could be done only together with STE and under STE supervision of the ESS trained trainers. This could allow ESS trainers to make practical use of acquired trainers´ skills already during the project implementation and thus, to get, under STE supervision and with STE coaching/advice, confidence and knowledge as trainers. This would also be excellent opportunity for ensuring good sustainability of skills and knowledge already during the project implementation.

- The STEs will also include any other issues which are important for proper and effective execution of ESS staff works and duties (e.g. issue of ability to create, develop, strengthen and maintain partnerships with regional/ local stakeholders, upgraded IT tools, examples of good practice on specific issues – work with employers and career guidance and counselling, enhancing leadership and management skills in a way to improve the service delivery, etc.)

- Expert missions will be conducted to:

- Create new interactive and practical Training Programme (training modules) and update existing training programmes, if any

- To prepare training material in compliance with the Training Programme

- Consultative Core Group consisting of STE and ESS will be set up to:

- Discuss on the developed Training Programme

- Outline any existing problematic issues, needs and flexibility for any additional training

- Incorporate any outstanding issues which are important for the beneficiary

- Set up of a realistic training plan (incl. the schedule)

- Agree on evaluation approach for the Training programme implementation

- Finalise the Training Programme

- Elaborate on Training Action Plan(commonly STEs and Georgian  beneficiary)

Final version of the prepared Training Programme will be agreed by the Consultative Core Group and then put in operation (act. 4.5) and translated into beneficiary language.

Outputs

- Formal and in-service Training Programme prepared, discussed and agreed

- Training materials developed

Duration: 9 to 11 month

Resources

RTA

MSs staff:  7 experts - Kubalova, Kubisova, Turner, Lorencic, Kolmerova, Katuscak, Dobesova x 1 mission/expert x 5 days each mission, in total 35days/7 missions

The BC staff for this activity is:

- BC PL counterpart, RTA counterpart;

- Staff from the ESS, other relevant stakeholders (up to 10 people for consulting on the training programme design);

Other resources:

Translation and Interpretation

Activity 4.5

Conduct formal and in-service training for the ESS staff

The purpose of this activity is to practically implement tailor-prepared series of training envisaged for the ESS staff. The content of this activity closely relates to the results of the previously implemented activities under component 4.

Method

The activity is going to be implemented in line with the Training Programme developed in activity 4.4 and will be focused on conducting both – formal and in-service training for the staff of ESS.

- The STE will implement the formal training programme through a series of practical workshops (residential) at national and regional/district levels.

- A minimum of 10 formal workshops for 1-2 days per each on different topics for at least 140 persons in total will be provided. Their sequence and exact duration will follow the Training programme schedule as agreed with the Consultative Core group involved in the elaboration of the overall Training Programme.

- In addition to the training sessions (workshops), at least 75 hours of in-service training including mentoring/coaching to ESS staff will be ensured by STE involved in the implementation of this activity.

- Series of trainings will be also conducted in three main regional centres: Kakheti, Imereti and Ajara. If there would any need for rescheduling and/or changing of the above-mentioned locations, this will be agreed by the STE with ESS management.

- In addition to the above-mentioned, the STE will provide in-service training to ESS Headquarters staff and will mentor/coach and advice the Directors and Deputy Directors.

- Training methodology will be developed by the STE, consulted with the ESS counterparts and all logistics and administrative matters will be ensured by RTA office in conjunction with the ESS staff in Tbilisi (central office) and selected regional centres, i.e. Kakheti, Imereti and Ajara.

- Evaluation of each training session/workshop will be ensured on a basis of developed questionnaire by STE for getting feedback on the training quality and learning outcomes.

- Evaluation report will be prepared for each training and 1 Evaluation Training Report summarising the evaluations/findings and feedback from all training workshops, as well as for in-service training will be prepared by STE and presented to the ESS counterpart.

- Based on this, and if this is appropriate, some recommendations towards training activities (content & organisation) will be prepared by STE for ensuring sustainability of the training itself, i.e. ESS to use the results for continuing in the organisation of ongoing tailor-made training focus on further capacity development of  the ESS staff.

To ensure that all work planned under this activity is effectively executed:

- expert missions will be held,

- residential workshops (training sessions) in locations as above will be organised,

- mentoring/coaching and advice for ESS staff will be ensured by STE,

- evaluation of all conducted training sessions will be done and,

- improvements of future training activities of ESS including any recommendations which can lead to better results and sustainability of all training process will be prepared by STE

Outputs

- Training workshops delivered

- Post-training questionnaires/evaluation completed

- Min 10 training workshops conducted

- Min 75 hours of in-service training including mentoring/coaching to ESS staff held

- Evaluation Report (summary) of all training events and in-service training

Duration: 10 to 16 month

Resources

RTA

MSs staff:  7 MS experts - Kubalova, Kubisova, Lorencic, Kolmerova, Pavlovova, Györgyi, Katuscak, / 5days/1 mission; In total 35 days/7 missions

The BC staff for this activity is:

- BC PL counterpart, RTA counterpart;

- Staff from the ESS, other relevant stakeholders (in total min. 140 people will attend the training);

Other resources:

Infrastructure and facilities for organisation of the planned 10 workshops

Translation and Interpretation

Activity 4.6

Development of the Training Manual

Method

In the final three months of the project, the STEs in charge for the training will consolidate the all training materials into a concise and practical Training Manual for the use and further development (after project has ended) by ESS.

In order to ensure elaboration of the draft Training Manual, as well as finalising the works on the Manual, its translation and printing plus electronic version (online via website of ESS), expert mission/s, consultation sessions and quality check will be carried out by STE and ESS colleagues.

Outputs

- Training Manual developed, consulted and finalised in both – paper and electronic form (available on website of the ESS)

Duration: 14 to 16 month

Resources

RTA

MSs staff:  2 MS experts: Kubalova, Lorencic, each 5days/1 mission each

The BC staff for this activity is:

- BC PL counterpart, RTA counterpart;

- Staff from the ESS (up to 10 persons – managerial staff - with whom consultations on manual will be conducted)

Other resources:

Translation and Interpretation

Activity 4.7

Training/retraining platform (Train the trainers)

Method

The content of this activity is of specific importance as it is focus on those who suppose to act as trainers of ESS and thus this is crucial for project sustainability regarding further capacity building of ESS staff in central, regional/district levels. The ESS already possesses a cadre of 5 trainers. However, it is acknowledged that these trainers would benefit from refreshment of their existing skills and the development of further skills and materials to reflect the widening range of services being provided by the ESS and the skills sets needed by the central and district level staff. It is also needed to enlarge the number of trainers (i.e. more than 5 only) able to deliver tailor-made training throughout the whole country and to encourage the networking among these trainers for further mutual support, exchange of experience; common planning of training events and other related actions once the project is ended. Therefore, STE will put specific effort to accomplish this activity on the most effective and practical manner.

In this respect:

- The STE will provide further training to the 5 trainers who are already on place but also to identify another 5 potential trainers who will also attend the ToT (group of trainers consisting of 10 people). The objective is to strengthen capacity within the ESS to train and re-train staff.

- The STE will map the type of skills of the future trainers to avoid any “useless” training sessions for trainers and based on this a concise training programme will be created.

- The training will cover the:

- pedagogic methods,

- design and implementation of induction training for new members of staff

- content of the Training Manual

- In line with the above, if this is the training programme will include:

- Part A: focused on organisation of a training, new approaches in adult education/training; new tools for methodology preparation; how and when to use different methods in training – novelties in methods and approaches; how to prepare interactive training for different target groups; building up self-confidence of trainers; how to work with a group of trainees, dealing with problematic situations/issues, presentation & communication skills – examples of good practice and mistakes, etc.

- Part B: focused on professional knowledge in relation to the new upgraded services model of ESS.

- Work session will be held: STEs and beneficiary to discuss the ToT programme content and finalise the training programme and all training materials

- Elaborate on Train-The-Trainers Training Action Plans for each of the trainers: to be done commonly STE and Georgian trainers

- Elaborate on “Train the Trainers Platform”: i.e. system of train the trainers incorporating all training modules/materials with possibility to further improve these materials/modules

- Evaluation of each ToT session, measures for quality assurance of training results

Outputs

- Min 5 ESS staff trained as trainers, target for 10 trainers

- Training assessment report prepared

- Train-The-Trainers Training Action Plans prepared for each of trainers

- Train the Trainers Platform ready

Duration: 15 to 17 month

Resources

RTA

MSs staff:  2 MS experts Kubalova, Pavlovova/5days each, in total 10 days

The BC staff for this activity is:

- PL counterpart, RTA counterpart;

- Staff from the ESS (target for 10 trainers)

Other resources:

Translation and Interpretation

Component 5:

The ESS has acquired the necessary tools and materials to communicate effectively its range of services to clients and potential clients

(Mandatory result 5)

Component leader: Vera Kolmerova

The main tasks to be carried out under this component are:

- Review the ESS present communication policies and provide support for improvement of the situation including support and advice for establishing Communication Unit within ESS

- Work towards elaboration of ESS´s Communication and Awareness Raising Strategy

- Provide support and assistance for development of effective communication tools and materials

Build capacity of ESS’s staff to understand and integrate effectively the communication and awareness raising activities in the ESS´s portfolio and ESS staff to acquire necessary skills to use these tools and materials in the daily work with customers.

This will be done within the implementation of 5 key activities as described below.

Activity 5.1

Review of current communications policies and recommendations for upgrading

Method

The introduction and implementation of SSA/ESS Institutional Reform Plan (IRP, developed under component 2) is an excellent opportunity for ESS to increase awareness and knowledge among customers, stakeholders and the public about the improved and new services of the ESS and ambitions of the ESS from mid and long-term perspective.

But first it is necessary to conduct thorough review (analysis) of the present communication policies of ESS. The communication is one of the PES (public employment service) strategic management tools. The MoLHSA has indicated that the ESS should assume responsibility for communications and awareness raising related to its own activities and to that end should establish a unit/section responsible for communications.

In order to do the work envisaged under this activity the:

- STE will support the ESS to review its current communications policies and provisions and to help the Service to establish a dedicated Communications Unit (activity 2.2).

- In the first instance, the STE will assess the ESS’s communications needs and provide recommendations for upgrading the:

- approach

- messages

- target groups

- communications tools (especially with focus on modern and timely promptly accessible messages, information and advice)

- In this respect, the focus will be paid as well to the ESS:

- Internal communication

- External communication

- mass media relations

- Visual identity

- Expert missions to conduct the review and thus to identify the weaknesses & opportunities, prepare Review Report and concrete recommendations for improvement will be held.

- The overall work will be done be CWG (Communication Working Group) consisting of STE and ESS representatives who are or will be dealing with communication issues in ESS

- The draft of the Review Report of the current ESS communications policies and recommendations for improvement will be first prepared by STE in close consultation with the CWG members of ESS, then this draft will be consulted internally within the CWG at a Communication workshop and consequently the final version of the Review Report and recommendations will be finalised.

- This final version of the Review Report will be presented to the ESS management at a working meeting. Upon the last feedback of ESS management, if any specific adjustment are needed and are appropriate, these will be incorporated into the Review Report.

- The ready document (Review Report and recommendations) will be made available in Georgian language and delivered to the ESS staff in an electronic form.

- The Review Report will be served as input for works planned under activities 5.2, 5.3 and 5.4.

Outputs

- Review of current communications policies and provisions drafted

- Recommendations for upgrading the approach, messages, target groups, and communications tools prepared

- Communication workshop organised

Duration: 3 to 5 month

Resources

RTA

MSs staff:  3 MS experts Cerna, Pavlovova, each 5 days/1 mission each

The BC staff for this activity is:

- BC PL counterpart, RTA counterpart

- Staff from the ESS (up to 10 persons dealing or will be dealing with communication issues)

Other resources:

Infrastructure and facilities for the communication workshop

Translation and Interpretation

Activity 5.2

Support to the establishment of a Communications Unit within the ESS

Method

On the basis of the output of the activity 5.1 (Review Report and recommendations), the STEs and the ESS management will draft and agree on the mission statement, functions and optimum staffing level of the communications unit (CU).

The STE will:

- Outline the role, vision, mission and impact of CU as well as its, tasks and duties in order to become of a modern communication unit which will play indispensable role in the implementation of the ESS policy in the employment area

- Plan staffing and prepare/revise job descriptions per each vacancy in the CU

- Support the CU to effectively pass on information towards clients (external), i.e. focus on a customer oriented approach (job-seekers and employers at first stage and also to general public or other stakeholders),

- Support CU to develop effective internal communication tools including effective working relationships (informal and formal meetings, normal work situation, team briefings, specific training on communication matters, etc.)

- Provide in-service mentoring to the staff of the Communications Unit

- Prepare a short draft plan and tips for improving communication towards ESS´s customers and internally, i.e. within the ESS/CU

- Prepare draft for the monitoring the CU´s operation and for evaluation of the CU´s success of operation

To execute this work, expert mission /consultative sessions and working discussions will be held for:

- providing full support for the establishment of the new Communication Unit,

- setting up its structure, responsibilities – duties/staff and job descriptions,

- CU´s overall operation plan in line with verified practices, workflow, present and share good practice examples and samples of all three MS – SK-HU-CZ

- in-service training, mentoring & coaching improving capacity of CU staff for effective operation

Outputs

- Communications Unit fully operational

Duration: 3 to 5 month

Resources

RTA

MSs staff:  3 MS experts Cerna, Lehocka, Pavlovova each 5 days/1 mission each

The BC staff for this activity is:

- BC PL counterpart, RTA counterpart

- Staff from the ESS  (up to 10 people – managerial staff of the ESS - CU staff)

Other resources:

Translation and Interpretation

Activity 5.3

Elaboration of communications and awareness raising Strategy and Action Plan

Method

As communication is to be one of ESS’s strategic management tools, a complex communication strategy will be developed under this activity. This strategy will covers internal and external information, mass-media relations and the visual identity of the ESS. Internal information targets the

staff of ESS and external information to  its customers, mainly job seekers and employers, and also the public and the mass media. Stakeholders are group which might have an interest in both internal and external information. The Communication Strategy (CS) will provide rules and guidelines for the handling of the communication activities of the ESS.

In this respect, the key words are:

- simplicity,

- accuracy,

- availability,

- credibility and

- customer focus.

It will be foreseen that all communication is coherent and based on the same values and principles of the ESS and be consistent across audiences. It is of particular importance that the rules for the graphic and visual identity of the ESS are followed without exception.

In accordance with the above-mentioned and with the results and recommendations of the above Review Report (act. 5.1), the STE and the ESS counterpart will prepare a Communication and Awareness Raising Strategy (CARS) and associated Action Plan for implementation.

As a minimum the Strategy will identify the:

- priorities

- objectives and anticipated results

- define the approach

- messages

- target groups

- communications tools to be used

- In addition, the Strategy will include monitoring, evaluation and quality assurance tools, milestones and clear communication channels as well as tools for upgrading of the Strategy and Action Plan according to the needs of ESS customers, ESS own needs and requirements of the labour market. Also financial coverage should be discussed in order Strategy and Action Plan become practically implemented.

- The associated Action Plan will include clear timeframes, indicators of achievement and sources of verification.

- During the elaboration of the Strategy and Action Plan, STEs will provide examples of similar strategies from all three countries and emphasise the good practices and necessary standards to be maintained.

For execution of tasks planned under this activity expert missions and consultations with the ESS/CU be held. Also members of the CWG established already under activity 5.1 will be used as resource group for precisely identifying the CS structure and content. While deciding on communication means, any specifics of the country (regional/district) will be taken into consideration so that every message/information of the ESS can reach customers.

The final version of the Strategy and Action Plan will be presented at a Seminar involving relevant ESS staff and other stakeholders/experts from Georgia, translated into Georgian language and made at disposal to the ESS colleagues.

Outputs

- Communications and Awareness Raising Strategy and associated Action Plan elaborated discussed  and submitted for adoption

- Seminar held

Duration: 5 to 7 month

Resources

RTA

MSs staff:  3 MS experts Kolmerova, Pavlovova, Lehocka, each 5 days/1 mission each

The BC staff for this activity is:

- BC PL counterpart, RTA counterpart

- Staff from the ESS (up to 20 people – managerial staff and staff dealing or suppose to deal with communication matters – CU staff)

Other resources:

Infrastructure and facilities for conducting of the seminar

Translation and Interpretation

Activity 5.4

Development and application of communications tools and materials

Method

The STE together with the ESS/CU and members of the CWG will develop the necessary communications tools and materials tailored to the needs of ESS as outlined in the Communication Strategy (CS, in activity 5.3).

This will entail the:

- establishment of consultative mechanisms with employers as well as for contact creation, developing, strengthening and maintaining as cooperation and partnership with employers is of high importance for the quality of ESS services

- further development of the ESS’s interactive web-site, www.worknet.gov.ge, - to be friendly-usable by all customers

- elaboration of information materials for job-seekers and employers – in line with the real needs

- organisation of promotional events, in this respect reference examples/good practices of concrete events regularly organised by employment services in the three countries – SK-HU-CZ will be provided

The costs of production of the materials and the organisation of the events will not be met from this Twinning Contract.

Expert missions to ensure the above works will be conducted.

- Applications and communication tools and developed materials will be discussed and agreed within the established Communication Working Groups (CWG) (in act. 5.1).

- All final versions of tools and materials will be discussed within the CWG, if necessary with any other relevant ESS staff and final versions will be presented at Promotion Event (max ½ day) involving the ESS staff, MoLHSA, other relevant line-ministries and/or media, if appropriate).

Outputs

- Communications tools and materials developed

Duration: 8 to 10 month

Resources

RTA

MSs staff:  3 MS experts Cerna, Kolmerova, Pavlov - each 5 days/1 mission each

The BC staff for this activity is:

- BC PL counterpart, RTA counterpart

- Staff from the ESS (up to 10 people – managerial staff and staff dealing and to be dealing with communication matters)

Other resources:

Translation and Interpretation

Activity 5.5

Study Visit to MS to experience practical use of the promotion and marketing of services to job-seekers and employers

Method

The purpose of this learning Study visit is two-fold:

    - Create opportunity for Georgian colleagues to learn from their colleagues in the two MS – CZ and SK. Thus, this study visit will:

- take focus towards the promotion and marketing of services to job-seekers and employers

- be organised on combined manner, i.e. to SK-CZ for giving opportunity to the Georgian colleagues dealing with communication and awareness raising issues to acquire hands-on experience and skills for ensuring effective and timely communication and awareness raising events

- create also space for Georgian colleagues to meet their counterparts (colleagues) in the two MS – SK and CZ, to discuss all issues of practical nature in the area, exchange experience and create contacts from long-term cooperation perspective

- provide opportunity to see on situ operation of communication services of the two EU MS (SK-CZ) at various levels (central, region/local employment offices)

    - Georgian colleagues who participated in the study visit, upon their return back, ensure transfer of experience, skills and knowledge to their colleagues. This will be done by:

- Organisation of 3 information workshops in three different locations in the country. These locations will be agreed by all Georgian twinners.

- Prepare a Report common for the whole group on the lessons learnt by Georgian colleagues participating in the study visit and what of the seen practices/tools, etc,  could be used and/or adjusted by ESS in Georgia. This Report will be prepared by Georgian counterpart.

1 Learning Study Visit will be organised with the support of the PL, RTA and STEs for 5- working days/6 overnights study visit to Slovakia and Czech Republic for 9 participants (8 +1 interpreter) of the BC project team (drawn from the ESS central and regional offices / MoLHSA)

Detailed study visit programmes will be prepared in consultation with the Georgian colleagues and all logistical and administrative matters will be ensured by the project back –up office in cooperation with the MS PL, JPLs RTA office and STEs in communication.

It is suggested at least the following institutions to be visited:

Slovakia:

- Central Office of Labour, Social Affairs and Family – Communication Department, Bratislava

- Ministry of Labour, Social Affairs and Family, Bratislava – synergy between players in the communication and awareness raising area

- 2 Offices of Labour, Social Affairs and Family in (regional and local levels) – communication units and officers

Czech Republic:

      - Labour Office of the Czech Republic - Communication Department

- 2 offices nearby Prague/Brno (regional + local levels) communication units and officers

Evaluation of the Study visit will be done to measure to what extent the visit fulfilled its objectives

Outputs

- Detailed tailor-made study visit programme prepared, discussed and agreed

- 1 study visit conducted

- Report of the Study visit

- 3 information communication workshops aiming at transfer of experience from the study visitorganised by Georgian colleagues who participated in 3 different location

Duration: 11-12 month

Resources

RTA

MSs staff:  0 experts (back up office will provide organisational support on situ in the MS: SK and CZ in close cooperation with the MS PL, JPLs, RTA office and STE)

The BC staff for this activity is:

- 9 participants (8 +1 interpreter) / 6- working days study visit to Slovakia and Czech Republic for of the BC project team

- Travel costs to MS– 9 fly tickets

- Per-diems for 9 Georgian staff incl. 1 interpreter (6 per-diems/6 nights x 9 persons in line with per-diems rates for SK, HU, CZ)

- Travel costs between and within the two MS

Other resources

Translation and Interpretation

ARTICLE 5. RISKS

The project provides a list of assumptions and risks, which may have impact on the overall implementation of the activities and affect the successful completion of the project. The twinning team will take into consideration the following risks split into 2 categories:

Internal related risks:

- Insufficient and/or inefficient inter-institutional coordination and cooperation, especially among social dialogue representatives;

- Lack of available Georgian and MSs staff to cover the joint activities within the relevant time schedule

- Lack of staff with adequate profile (such as legal analytical thinking, economic/statistical knowledge and skills) in the ESS, the relevant Department/s of the MoLHSA and/or other stakeholders representatives (e.g. MoES);

- Insufficient commitments of the representatives in charge of the key  institutions (ESS/MoLHSA) into the project activities

- Allocation of offices and appropriate funding

- Financial obstacles or delays in payment

- Shortage of appropriate  meeting rooms or technical facilities

External related risks:

- Lack of decisions at the governmental or intra-ministerial level that might influence the political support for the EU integration thus of the project smooth implementation

- Political interventions or unexpected changes in Georgian counterpart staff

These unforeseeable risks will be considered in close co-operation between the relevant Georgian staff, the RTA and the MS Project leader and RTA-counterpart. In serious cases, changes in places, dates, experts or means may be necessary. The relevant regulations of the Twinning Manual 2012 concerning addenda and side letters as well as budget flexibility will be followed. The Twinning team will work on the basis of the risks prevention and, if necessary, immediately take decision towards minimising the above mentioned internal risks through its Steering Committee and setting up of an action plan for elimination of these risks so that the mandatory results are achieved and the project smoothly implemented.

ARTICLE 6.		SCHEDULE

|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GENERAL ACTIVITIES – COMPONENT 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 0.1. Project management including the Steering Committee meetings, monthly meetings and project visibility |  |  |  | X |  |  | X |  |  | X |  |  | X |  |  | X |  | X |
| 0.2. Kick-off meeting (opening conference) | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 0.3. Closure Meeting – Final conference |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |
| ACTIVITIES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| COMPONENT 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY/MONTH | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| 1.1. Review of Georgian Equal Opportunities legislation related to employment and measure of concordance with EU Equal Opportunities legislation identified in Annexes of the Association Agreement |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 Drafting a Concordance Report and recommendations for harmonisation of the Georgian legislation related to employment with the EU Equal Opportunities Directives identified in Annexes of the Association Agreement |  |  |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |
| - Support to legal drafting with regard to the Equal Opportunities legislation related to the employment service identified in the relevant Annexes of the Association Agreement |  |  |  |  |  |  | X | X | X | X | X |  |  |  |  |  |  |  |
| 1.4. Gap analysis of the equal treatment and non-discrimination sections of the regulations for which the ESS has competence |  |  |  |  |  |  | X | X | X | X | X |  |  |  |  |  |  |  |
| 1.5. Regulatory drafting support to the ESS in order to ensure compliance of the regulations for which it has competence with the revised Georgian Equal Opportunities legislation harmonised with EU Equal Opportunities legislation |  |  |  |  |  |  |  |  |  | X | X | X | X |  |  |  |  |  |
| COMPONENT 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY/MONTH | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| 2.1 Undertake Functional Review of the SSA/ESS |  | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2 Support to drafting an Institutional Reform Plan for the SSA/ESS |  |  |  |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |
| 2.3 Support to the implementation of the Institutional reform of the SSA/ESS |  |  |  |  |  |  | X | X | X | X | X | X | X | X |  |  |  |  |
| 2.4 Review and revision (if required) of the current procedures for registration of job-seekers and job opportunities |  |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |  |  |
| 2.5 Introduction of new services within the ESS |  |  |  |  | X | X | X | X | X |  |  |  |  |  |  |  |  |  |
| 2.6 Support to the further development of job-seeker counselling services |  |  |  |  | X | X | X | X | X |  |  |  |  |  |  |  |  |  |
| 2.7 Development of a Procedures Manual |  |  |  |  | X | X | X | X | X |  |  |  |  |  |  |  |  |  |
| 2.8 Development of a Quality Assurance Plan |  |  |  |  |  |  |  |  | X | X | X | X | X |  |  |  |  |  |
| 2.9 Study Visit to MS to examine the range of services provided to job-seekers and employers through employment offices. |  |  |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |
| COMPONENT 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY/MONTH | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| 3.1 Review of the WorkNet Information System |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2 Elaboration of a Concept Paper for upgrading the WorkNet Information System |  |  |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |
| 3.3 Preparation of Terms of Reference/Technical Specifications for upgrading the WorkNet Information System |  |  |  |  |  | X | X | X | X | X |  |  |  |  |  |  |  |  |
| 3.4 Development of methodology and tools for the preparation of monthly and annual labour market reports |  |  |  |  |  |  |  | X | X | X | X |  |  |  |  |  |  |  |
| 3.5 Study Visit to MS to examine the collection, collation and analysis of labour market data by the employment services |  |  |  |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |
| COMPONENT 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY/MONTH | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| 4.1 Review of current HRD policy |  |  |  |  |  |  | X | X | X | X |  |  |  |  |  |  |  |  |
| 4.2 Drafting of an HRD Manual |  |  |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |  |
| 4.3 Conduct Training Needs Analysis |  |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |  |  |
| 4.4 Development of Training Programme and Training Materials |  |  |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |  |
| 4.5 Conduct Formal and in-service trainings for the ESS staff |  |  |  |  |  |  |  |  |  | X | X | X | X | X | X | X |  |  |
| 4.6 Development of the Training manual |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X |  |  |
| 4.7 Training/retraining platform (Train the trainers) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X |  |
| COMPONENT 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY/MONTH | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| 5.1 Review of current communications policies and recommendations for upgrading |  |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.2 Support to the establishment of a Communications Unit within the ESS |  |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.3 Elaboration of communications and awareness raising strategy and Action Plan |  |  |  |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |
| 5.4 Development and application of communications tools and materials |  |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |  |  |
| 5.5 Study Visit to MS to experience practical use of the promotion and marketing of services to job-seekers and employers |  |  |  |  |  |  |  |  |  |  | X | X |  |  |  |  |  |  |
| Ex-ante evaluation and quality assurance of twinning implementation | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |

ARTICLE 7.	RESOURCES

7.1. Human Resources

7.1.1. 	Member State(s)

The Ministry of Labour, Social Affairs and Family of the Slovak Republic will have the overall responsibility and supervision of the project-coordination. The responsibility of institutional project leadership is taken by MS PL, State Secretary (Deputy Minister) Mr Branislav Ondrus.

The coordination and will be ensured between all involved institutions from all three EU MS, i.e.:

Slovak Republic:

- Ministry of Labour, Social Affairs and Family of the Slovak Republic

- Central Office of Labour,  Social Affairs and Family of the Slovak Republic

- RDA Senec Pezinok

Hungary:

- National Employment Office (NLO) of Hungary

Czech Republic:

- Labour Office of the Czech Republic

The institutional commitment will be ensured by the three project leaders: MS PL Mr Ondrus in close cooperation with the two JPLs (junior project leaders) - Mr Komaromi and Mrs Kolmerova.

The two JPL will ensure the good coordination with Project Leader Ondrus and Junior MSs inputs appropriate to the project and line with the designed work plan.

The RDA Senec Pezinok as a fully mandated body will have the overall responsibility for administrative, logistic, financial management and supervision of the project-implementation.

The Agency has the status of a fully mandated body for EU-Twinning projects, acting as the Slovak Twinning Platform which integrates state authorities and their subordinated institutions ensuring tailored transfer of know-how to potential candidates’ countries and countries in transition.

Contact address:

Regional Development Agency Senec Pezinok

Vysoká 35

811 06 Bratislava

Slovak Republic

Contact person:

Ms Luba Pavlovova

Director of the Regional Development Agency Senec Pezinok

Vysoká 35

811 06 Bratislava

Slovak Republic

Phone: +421 903 77 36 74 or +421 2 20 72 83 92

E-mail: Lpavlovova@rrasenec-pezinok.sk

Ministry of Labour, Social Affairs and Family of the Slovak Republic

Špitálska 4, 6, 8

816 43 Bratislava

Slovak Republic

Contact details:

MS Project Leader

Mr Branislav Ondruš

State Secretary

Ministry of Labour, Social Affairs and Family of the Slovak Republic

Špitálska 4, 6, 8

816 43 Bratislava

Phone: +421 (0)2/ 2046 2713 or 2046 2723

E-mail: branislav.ondrus@employment.gov.sk

JPL Hungary

Mr Robert Komaromi – Director General

National Employment Office (NLO)

(Nemzeti Munkaügyi Hivatal)

Szeszgyár u. 4. VII/703

Budapest

Hungary

Tel: +36 1 303 0810/2120

Tel.: +36-1-299-1090; +36-30-638-6873

Email:fh.foigazgato@lab.hu

JPL Czech Republic

Mrs Vera Kolmerova – Acting Director

Labour Office of the Czech Republic

Karlovo náměstí 1359/1,

Nové Město,

128 00 Praha 28
Tel.: +420 950 191 111

Tel: tel.+420 773 114 609, +420 950 193 524

Email: vera.kolmerova@uradprace.cz

7.1.1.1 Project leader MS and two Junior Project leaders

The project is managed by the project leader Mr Branislav Ondrus, State Secretary of the Ministry of Labour, Social Affairs and Family of the Slovak Republic in close cooperation and coordination with the two junior project leaders.

The responsibilities of the Project leader in cooperation and coordination of all approaches and decisions on project implementation shall:

- ensure a close political steering

- conceive, supervise and coordinate the overall preparation of the project

- efficient leadership of the project

- overall management and coordination of the project according to the project work-plan

- close co-operation with the RTA and RTA’s counterpart

- close co-operation with the beneficiary administration

- support in organising study visit

- participation in the Steering Committee meetings

- ensure project reporting

In line with the Twinning manual, the MS project leader will dedicate a minimum of 3 days per month to project management and to monitor and evaluate the project‘s progress during the 18 - month implementation period.  He will meet with the JPLs prior to taking any decisions on project implementation prior to his involvement in the quarterly project Steering committee meetings or in monthly meeting, if this is necessary and appropriate. He will also meet with RTA, the BC Project leader and BC RTA Counterpart during his visits, and whenever necessary with other relevant representatives from the beneficiaries institutions.  They will jointly review progress against targets and guaranteed results and consider the status of the project risks and issues.  The participation of the PL in the quarterly PSC meetings (month 4, 7, 10, 13, 16, 18) is included herein. The two JPLs can attend the quarterly PSC meetings if the budget is sufficient to allow for such visits to the BC, however, the first priority will be to ensure sufficient financial means for smooth implementation of each project activity, thus of accomplishment of each component works and thus of achieving project mandatory results.

Contact details:

Project Leader MS

Mr Branislav Ondruš

Ministry of Labour, Social Affairs and Family of the Slovak Republic

Špitálska 4, 6, 8

816 43 Bratislava

Phone: +421 (0)2/ 2046 2713 or 2046 2723

E-mail: branislav.ondrus@employment.gov.sk

JPL Hungary

Mr Robert Komaromi – Director General

National Employment Office (NLO)

(Nemzeti Munkaügyi Hivatal)

Szeszgyár u. 4. VII/703

Budapest

Hungary

Tel: +36 1 303 0810/2120

Tel.: +36-1-299-1090; +36-30-638-6873

Email:fh.foigazgato@lab.hu

JPL Czech Republic

Mrs Vera Kolmerova – Acting Director

Labour Office of the Czech Republic

Karlovo náměstí 1359/1,

Nové Město,

128 00 Praha 28
Tel.: +420 950 191 111

Tel: tel.+420 773 114 609, +420 950 193 524

Email: vera.kolmerova@uradprace.cz

7.1.1.2 Resident Twinning Adviser

Mr Borbély-Pecze Tibor Bors,National Employment Office, Hungary is assigned as the RTA for a period of 18 months in Tbilisi, Georgia. The RTA will work on a daily basis with the counterpart and component leaders to implement the project, as well as support and coordinate the activities in Tbilisi (Budget section 1).

The responsibilities and tasks of the RTA, working in close co-operation with the BC Ministry of Labour, Employment and Social Policy of the Slovak Republic as well as with other MS institutions from Hungary and Czech Republic and relevant Georgian institutions and stakeholders shall be:

- carrying out the day-to-day implementation of the twinning project in the Beneficiary Country/BC (Georgia);

- ensuring  overall co-ordination of the twinning activities;

- day-to-day work with the counterpart in the Beneficiary Country;

- ensuring the permanent support of MS Project Leader, two JPLs and MSs adequate experts and their missions and work in the BC;

- monitoring the project's progress and guarantee smooth implementation of the work plan including monitoring of budget spending;

- organisation of monthly meetings and Steering Committee meetings and coordination and involvement in the Co-ordination Committee common for this twinning project and TA project (technical assistance)

- organisation of  visibility events

- organisation of the study visits,

- to assess continuously the Twinning-project in all stages and to compare it with the specified benchmarks and time-frame;

Contact details:

Resident Twinning Adviser

MrBorbély-PeczeTibor Bors

Senior Consultant at the Hungarian Labour Office

in Budapest

National Employment Office (NLO)

(Nemzeti Munkaügyi Hivatal)

Szeszgyár u. 4. VII/703

Budapest

Hungary

Tel: +36 1 303 0810/2120

E-mail: borbelytibor@lab.hu

7.1.1.3 Component Leaders

| Mr Branislav Ondrus | Component 0 Overall Project Management, Kick-off and Closure Events |
| --- | --- |
| Mrs Elena Palikova | Component 1 Revision of the Georgian Legal Framework of equal opportunities legislation and related to employment in line with the EU acquis and in accordance with the provisions of Annexes of the Association Agreement |
| Mr Boris Katuscak | Component 2 The structure and functions of the ESS have been revised to reflect it expanded role in the labour market management processes, the range and quality of services provided to job-seekers have been piloted and enhanced, the internal management and administrative processes have been clearly codified |
| Mr Gero George | Component 3 A comprehensive Labour Market Information Management System (WorkNet Information System) has been established and is fully operational |
| Mrs Luba Pavlovova | Component 4 Modern human resource management techniques have been introduced, the staff has acquired the necessary skills and experience to provide high quality services to job-seekers, and an in-house training and retraining platform has been established |
| Mrs Vera Kolmerova | Component 5 The ESS has acquired the necessary tools and materials to communicate effectively its range of services to clients and potential clients |

Short term experts

| Name | Present position | Institution | Years of expe-rience | Natio-nality | Education | Specialist knowledge | BC experience | Languages | Involvement in component (C) | EXPERT CLASS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Leader |  |  |  |  |  |  |  |  |  |  |
| 1. Mr Branislav Ondrus MS PL (lead) | State Secretary | Ministry of Labour, Social Policy and Family, Slovakia | 10 | SK | University of Economy of Bratislava | Excellent management skills and leadership ability, education in political science; Highly respected expert in the employment and labour market policy, social dialogue and industrial relations, extraordinary communication skills, twining experience as PL in tw “out” | FYROM Bosnia and Herzegovina Serbia | English Russian Czech Slovak | C 0, C2, C3, C4, C5 | High-ranking official (Deputy Minister), Class 3 |
| Junior Project Leader 1 - Hungary |  |  |  |  |  |  |  |  |  |  |
| 2. Mr Robert Komaromi JPL - HU | Director General | National Employment Service Hungary | 16 | HU | ELTE University, Budapest | Professional record in employment policy; comprehensive knowledge of EU employment policy and related legislation; Management of large scale programmes/projects in the employment area – nationally and internationally; Extraordinary leadership ; Excellent inter-communication skills; Work in multinational, cross-cultural teams of experts | United States, India, Luxembourg, Brussels/EC, The Netherlands | English Hungarian French | C 2, C3, C4, C5 | Civil servant, Class 1 |
| Junior Project Leader 2 – Czech Republic |  |  |  |  |  |  |  |  |  |  |
| 3. Mrs Vera Kolmerova JPL – CZ, CL5 | Director of Mediation and Counselling Department | Labour Office of the Czech Republic | 25 | CZ | Charles University, Prague | Professional in delivery services to PES customers (job-seekers, employers, public bodies), counselling and mediation; communication policies in the LO of Czech Republic, elaboration of guideline for effective passing on information to customers; long-term experience & leadership of Foreign Employment Unit at Ministry of Labour and Social Affairs responsible for Public Employment Service strategy in employment of foreigners | Poland Slovakia Austria | English Czech Slovak | C5, C2, C4 | Civil servant, Class 1 |
| Resident Twinning Advisor |  |  |  |  |  |  |  |  |  |  |
| 4. Mr. BORBELY-PECZE Tibor RTA | Senior Officer | National Employment Service Hungary | 11 | HU | Eotvos Lorand University, Budapest MA, PhD. | Extraordinary academic background directly linked to the area; proven experience as civil servant; Lifelong Career Guidance (LLG) and PES development and strong research and methodological background; excellent management and leadership skills proven in large governmental projects - taking responsibilities as project manager/team leader, comprehensive knowledge of EU employment policy and legislation; experience in twinning “in”, wide hands-on experience in countries in transition and restructuring of their social and economy systems | Croatia Moldova Macedonia Slovakia Estonia Belgium Austria | English Hungarian French | C0, C1, C2, C3, C4, C5 | RTA |
| Short-term expert pool including component leaders |  |  |  |  |  |  |  |  |  |  |
| 5. Mgr. Elena Palikova CL1 | Lawyer of Department for EU relations and international cooperation | Ministry of Labour, Social Affairs and Family in the Slovak Republic | 13 | SK | Comenius University, Bratislava, Faculty of Law | Labour law relations transposition and in practice - employment/antidiscrimination/OHS/labour market; Proven record in drafting law for acquis transposition; Experience in pre-accession process and approximation of law in social area - transposition and implementation of EU Directives; Practical negotiation skills in terms of EU lobbying and EU negations in the decision-making bodies of European Community; Good knowledge of the labour market matters; Preparing and evaluation of positions and statements for minister for the EPSCO Council; Overall view of primary and secondary EU legislation – labour law, employment and occupational health and safety; Proven twinning experience in twinning “IN” and “OUT”; International and mainly European experience – working in multicultural, cross-beneficiary groups on legal matter | EU bodies, Macedonia Croatia | English German | C1, C4 | Civil servant, Class 1 |
| 6. Mr Boris Katuscak Component leader 2 | State advisor to DG for EURES | Central Office of Labour, Social Affairs and Family, Slovakia | 10 | SK | University in Economy, Bratislava | Excellent knowledge of structure and functions of PES, familiar with harmonisation of the Slovak legislation with the EU and institutional reforms; professional experience and knowledge in strategic management, steering, coordination and supervision of labour offices (employment offices) in the area of employment services and active labour market policy implementation; twinning experience | Hungary Poland Czech Republic Austria Spain USA | English Slovak Czech | C2, C3, C4 | Civil servant, Class 1 |
| 7. Mr Gero George Component leader 3 | Head of IT Department | National Employment Service, Hungary | 36 | HU | Technical University of Budapest | Development and implementation of IT applications; profound knowledge of IT systems and databases - employment systems operational in PES; Management of IT organisations; Management and business administration; Project management; Business process planning; Strategic planning; Change management; System design and analysis; Effective decision making ability, flexibility, creativity and initiative spirit; Motivation and team building skill | Slovakia Belgium Austria Czech Republic | English Hungarian French | C3, C4 | IT Director, class 2 |
| 8. Mrs Luba Pavlovova Component leader 4 | RDA Director | RDA, Slovakia | 23 | SK | University in Engineering, Moscow Postgraduate in EU institutions and law, Comenius University, Bratislava | Extraordinary professional skills in area of employment and social policy at all levels; Strong leadership skills; HRD, ToT, TNA, certified trainer in change management and proved record as trainer at EU-level; proven record in project management, excellent negotiation, presentation and communication skills (all levels: local/regional/national/ international; over 19 years of experience in Labour Market policies development and implementation and 23 years in HR, Strong and practical experience in Twinning projects; result-oriented | Macedonia Bosnia and Herzegovina Romania Serbia Bulgaria Croatia Azerbaijan Albania Turkey | English Serbian Russian Croatian Bosnian French Bulgarian Macedonian Czech Slovak | C4, C5, C2 | High ranking official, (mandated body RDA) Class 3 |
| 9. Danica Lehocka | State Counsellor for Employment Director for Employment Section | Ministry of Labour, Social Affairs and Family in the Slovak Republic | 16 | SR | Economic University and Comenius University Bratislava | Professional record in employment policy – Analysis of activities in the fields of labour market, human capital and educational studies. Cooperation in creating methodology to forecast Slovak labour market needs. In charge of the preparation of Employment Strategies, Operational Programmes for Human Resources Development and Social Inclusion; Implementation of EU agenda at the MoLFSA, excellent knowledge in communication strategies related to employment and labour market matters | Czech Republic Poland Slovakia Hungary Austria | English Czech Slovak | C5, C4 | Civil servant, Class 1 |
| 10. Mrs Meri Lorencic | Employment Officer | RDA | 34 | SI | University Degree in Pedagogies | professional experience in the field of employment policy, human capital development, life-long career guidance and social inclusion; 18 years working at the Employment Service; 6 years working in provision of technical assistance related to enhancing capacities of Public Employment Services in Croatia, Serbia, Montenegro and FYRoM – hands on experience in conducting functional analysis in PES in transition countries; Good analytical skills; Reach experience in HRD programmes identification, design, management, implementation, monitoring& evaluation; inter-personal skills, team worker | Croatia Macedonia Montenegro Bosnia and Herzegovina | English Serbian/Croatian/Montenegrin Macedonian Slovenian | C2, C4 | RDA, mandated body, class 2 |
| 11. Mr. Vojtech Tkac | Counsellor of the Minister | Ministry of Labour, Social Policy and Family, Slovakia | 25 | SK | Comenius University, Faculty of Law, Bratislava, Slovakia | Highly respected expert on labour and social security law, in charge of labour, wage and social affairs legislation; collective and tripartite bargaining expert, development of labour law legislation (Labour Code, collective agreements, etc., in charge of social and economic reforms; Representing the Czech and Slovak trade union in the committees of ILO | Bosnia-Herzegovina | English French, Russian Czech Slovak | C1 | High-level counsellor, class 2 |
| 12. Mrs Danica Kelecinova | Director of Information Systems Methodology | Central Office of Labour, Social Affairs and Family, Slovakia | 24 | SK | Trnava University | proven professional experience in labour market field as a civil servant dealing with labour market/employment issues; proven experience in the management and leading people; professional experience in capacity building of PES and relevant stakeholders to implement new active measures; excellent experiences in a field of informatics (labour market systems analysing, development, merging, testing and implementing) – one of designer of the IT system of COLSAF; Strong leadership and management skills (coordination and management of 79 labour offices in different areas of employment and informatics); Experience in evaluation of active labour market policies; Comprehensive knowledge of labour market policies, legislation and regulations; understanding of relationships, issues, possibilities, needs and challenges in employment area due professional long career in this area | Serbia Hungary Austria | English Russian German Slovak | C3, C1, C2, C4 | Civil servant, Class 1 |
| 13. Mr Martin Vido | Team leader Cognos and Data warehouse team | Central Office of Labour, Social Affairs and Family, Slovakia | 19 | SK | Komensky University Prague; Matej Bell University Banská Bystrica | 19 years of experiences in a field of informatics (labour market systems analyzing, development, merging, testing and implementing); 15 years of proven experience in evaluation of active labour market policies and statistics; Most of the professional career spent in labour market institutions on regional and national level solving the labour market policy agenda; Experience in work with international teams, experience in twinning “in” projects | Serbia Hungary Austria | English Slovak | C3, C5 | Civil servant, Class 1 |
| 14. Mrs Veronika Cerna | Advisor in the field of mass media policy | Central Office of Labour, Social Affairs and Family, Slovakia | 7,5 | SK | University of Matej Bel, Slovakia | Hands-on experience in elaboration of Communication Strategy and communication action plans for improving services in terms of providing targeted information to job-seekers, employers and other stakeholders; Planning awareness raising activities; Evaluation of communication strategies, plans and events; Good understanding of PES functions and operation; international experience | Austria, Czech Republic, Germany, Hungary, Italy, Poland, Slovak Republic, Slovenia | English Spanish German Italian Slovak | C5, C4 | Civil servant, Class 1 |
| 15. Mrs Eva Gellérné Lukács | Senior Counsellor | Ministry of Employment and Social Affairs | 15 | HU | University of ELTE, Faculty of Law, Budapest PhD | Wider long-term experience in international affairs in social area with focus on employment: negotiation, mediation, drafting of target-oriented documents, ability to channel different views, ability to reach consensus, ability to achieve the designated objective with mutual consent of the respective parties; leadership and management skills; experience as researcher; European Law expert in the field of social policy- employment-related equal treatment issues; ability to work on long-term projects aimed at producing focused outputs, either short or long versions of texts; experience in EU funded projects; Proven experience in two twinning light projects | Germany Austria Slovakia V4 countries (CZ, HU, SK, PL) | English German French Russian Hungarian | C2, C1 | Civil servant, Class 1 |
| 16. Mr Ignits Györgyi | Deputy Head of Department of Statistics and Analysis | National Employment Service, Hungary | 6 | HU | Lóránd Eötvös University Hungary | Statistics and analysis regarding to the labour market and activities of public employment service, active labour market measures, earnings; Strong statistical skills in handling databases and analysis of several sources of labour market information including internationally comprehensive data also; developing the Labour Market Information System in the National Employment Office; Performance Management System in the Hungarian Public Employment Service; coordinating and evaluation researches in the field of active labour market policies, including effectiveness studies also; quantitative labour market prognoses in Hungary ; international benchmarking and bench-learning activities among Public Employment Services in the EU; Strong analytical skills; Experience of making presentations in the field of labour market policies | Slovakia Czech Republic Belgium UK Austria Germany | English Hungarian | C3, C2 | Civil servant, Class 1 |
| 17. Mrs Lubica Turner | Head of Unit for HRD / Chief Training Specialist in HRD | RDA, Slovakia | 19 | SK | P.J.Safarik University Slovakia | Long-term proven record in training design and delivery in social area; professional skills in elaboration of training methodologies and evidence-based learning; Extensive international experience in HRD, development of HR policies, performance appraisal, career development and training development and delivery for HR managers and specialists; Excellent trainer recognised at EU-level; Strategic planning, results based management, project management in EU projects; leadership; Sound experience in change management and organisational development including design, delivery and management of relevant capacity building programmes; TNA and TOT; women’s empowerment and equal opportunities development; proven language competencies; Impressive international experience, result-oriented, ability to deliver training in mixed cross-cultural groups/teams; Proven twinning experience in the Region | Serbia, Jordan Croatia The Netherlands Macedonia Montenegro Russia Yugoslavia | English Serbian/Croatian/Bosnian Russian French Macedonian | C4, C5 | RDA, mandated body, class 2 |
| 18. Mrs Maria Dobesova | Adult Education Specialist/ HRD | RDA, Slovakia | 23 | SK | University PJŠ Kosice Slovakia | Long-term proven record in training of various target groups including social partners representatives; Proven record in TNA and training methodologies aiming at capacity building measures; ToT, Excellent knowledge in training delivery, nationally recognised trainer; Knowledge of EU-legal rules in the area of social dialogue and capability to provide tailor-made advise and education; Excellent presentation, mediation and negotiation skills; Extraordinary networking skills and knowledge, work with stakeholders at all levels ; Long-term experience with disadvantaged groups; Direct twinning experience on work with state authorities and social partners in Croatia; Work and training of women; Experience in CSR; International experience and excellent language skills |  | English German Russian Slovak | C4, C5 | RDA, mandated body, class 2 |
| 19. Ms Valeria Kubalova | Senior Programme Manager | RRA | 22 | SK | Matej Bell University, Banskka Bystrica | Expert in the field employment and social policy; proven experience as a grant scheme manager for Phare projects (PRAG) and grant schemes for ESF; Expert in management, monitoring and evaluation of ESF funded projects; Proven management/supervision capacities and professional practice in the management and implementation of projects in the field of employment policy; Hands-on Twinning experience and coordination of large-scale Twinning projects | Macedonia Bosnia and Herzegovina Romania Croatia | English Russian Czech Romanian Croatian Serbian Macedonian | C1, C4, C5 | RDA, mandated body, class 2 |
| 20. Mr. Pavlov Ilian | IT specialist of the RDA | RDA, Slovakia | 11 | SK | Technical University in Sofia | Highly experienced in developing institutional and administrative capacities in ICT Government sector Proven experience in delivery of web based e-Services solutions Twinning experience in the Region: IT solutions | Slovakia, Denmark, Germany, Italy, Litany, Portugal, Ukraine, Montenegro | Slovak, Czech, English, Russian | C3, C5 | RDA, mandated body, class 2 |
| 21. Mr Ivan Majercak | IT Expert/IT Senior Architect | RDA, Slovakia | 13 | SK | Academic diploma, Comenius University, Faculty of Management, Bratislava | IT strategies development, software engineering, systems integrations, networking, database development and administration; networking and protocols Twinning experience in the Region: IT solutions | Ireland, Austria and Slovakia Croatia | English German Slovak Czech Bulgarian | C3 | RDA, mandated body, class 2 |
| 22. Mr Miroslav Stefanik | Analyst of the labour market | Ministry of Labour, Social Affairs and Family in the Slovak Republic | 7 | SK | University of Economics Bratislava | Proven record in analytical skills related to labour market and educational policies; Long term focus on skills mismatch analysis on the labour market; Monitoring and creation of indicators; Extensive experience in monitoring and evaluation of active labour market measures; Experience in providing training on data management, policy analysis, monitoring and evaluation procedures; Excellent presentation skills proven during participation in various international projects, proven twinning experience | Macedonia Serbia | English German Polish Macedonian Russian Slovak Czech | C2, C4 | Civil servant, Class 1 |
| 23. Mr Maros Palik | Chief lawyer for labour relations | RDA, Slovakia | 12 | SK | Faculty of Law, Comenius University, Bratislava | Proved record in: Civil law - labour law, employment law, collective bargaining law, family law, contractual law; Proven experience in representation in legal proceedings in employment and legal relations pursuant to the Labour Code; Legal analysis to the draft labour law and legislation proposals drafting; Proven experience in transposition of the labour law to the EU legislation (table of compliance; legal statements and analysis, legal agreements; comparative analysis and legislative proposals); Capacity building expert –delivery of trainings, lectures statements on labour and contractual law; Twinning experience as STE – lawyer in Serbia; Proven skills in working in cross-beneficiary, multicultural teams | Serbia Czech Republic | English German Slovak Czech | C1 | RDA, mandated body, class 2 |
| 24. Mrs Maria Kubisova | HRD Manager | RDA, Slovakia | 25 | SK | Technical University of Kosice | Professional experience and knowledge in adult education; trainer and career counsellor; professional experience in the employment services, also as a director of local PES in Martin, Slovakia; Working as an expert for solving the services of employment policy in Kirgizstan, Macedonia and Serbia; Certified Expert in career counselling in Slovakia , trainer, coach and methodologist in career guidance & counselling and adult training, experienced in experiential learning methodology; professional experience in programming/implementation of HRD/ESF-funded projects; Setting up the Grant management system for the implementation of the HRD/ESF interventions for Employment service; experienced in design/delivery of active labour market programmes and measures (ALMPMs) e.g. developing and implementing training programs for job seekers – different target groups (women, young people, Roma’s, disadvantaged groups, etc.; delivery of on-the-job training courses based on the demand of employers; | Austria Luxemburg Italy Greece Switzerland France Croatia Macedonia Serbia Kirgizstan | English German Russian Slovak Czech | C4 | RDA, mandated body, class 1 |
| Other experts ready to be involved, if necessary and appropriate |  |  |  |  |  |  |  |  |  |  |
| 25. Mrs. Maria Nadazdyova | State Counsellor | Ministry of Labour, Social Affairs and Family in the Slovak Republic | 21 | SK | Comenius University, Bratislava | EU policies and standards–EU decision making process, social policy, employment, non-discrimination, labour law; Excellent knowledge of EU law on anti-discrimination and equal treatment – directives 2000/43, 2000/78, 2006/54, its transposition and enforcement in practice; Twinning experience - work experience and activity on legal transposition of above-mentioned directives and capacity building of the Depart. Of Equal Opportunities of the MK Ministry of Labour and Social Policy; proven record in training on anti-discrimination in FYROM & Serbia; interview conducting, team leading, awareness raising campaigns, development of inquiry tools and methods for different target groups; TNA, ToT, training provision on social policy issues, EU affairs and HRD; good knowledge of PES based on long-term expert and management practice; communication skills and work experience in multicultural and multilingual environment; systems and reforms, people with disabilities; social inclusion processes – elimination of poverty and social exclusion; international relations, development and cooperation programs, EU financial instruments (EES) and programmes, European construction; institutional and capacity building, project development and management | Macedonia | Slovak, Czech, English | C1, C2, C4, C5 | Civil servant, Class 1 |
| 26. Mr Jiří Beran | Head of Section of labour market, analyst of labour market | Labour Office of the Czech Republic | 20 | SK | Faculty of Health and Social Studies of South Bohemian University | excellent knowledge in statistics, data analysis and data processing in the labour market proven record as analyst of the labour market Evaluation skills of projects and project outcomes Knowledge of instruments of active labour market measures Wide experience at local and central level in relation to employment policy International experience and project management skills | Hungary Belgium Austria Slovakia | English German Czech | C1, C2 | Civil servant, Class 1 |
| 27. Mr Robert Zemko | IT system methodologist | Central Office of Labour, Social Affairs and Family, Slovakia | 21 | SK | University of Technology Bratislava | 21 years of working experience on labour market offices; proven experience as methodologist of IT systems; Managing and communication skills (managing of 79 labour offices in different areas of employment and informatics); Experience in working in international teams, presentation and explanation skills | Hungary Czech Republic | English Hungarian Slovak German | C3, C2, C4, C5 | Civil servant, Class 1 |
| 28. Mr Peter Grosch | IT system methodologist | Central Office of Labour, Social Affairs and Family, Slovakia | 23 | SK | Technical University of Košice | 23 years of working experience on labour market offices; 15 years head of informatics department; wide knowledge, skills and experience directly related to labour market and employment policies and IT systems applicable in this area; Excellent knowledge in ICT with focus on needs of PES; Ability to work in an international environment | Hungary Poland The Netherlands | English Hungarian Slovak | C3, C2, C4, C5 | Civil servant, Class 1 |
| 29. Mr. Andras Kalmar | Manager of EURES department | National Employment Service, Hungary | 11 | HU | Corvinus University of Budapest | professional experience in strategic management, development and co-ordination of county and regional labour centres as regards services; co-ordinating, integrating and standardising services and labour market measures for 174 local offices; managing activities connected to labour market services on local and regional level; management of national European funding mechanisms on local and national level; professional experience in knowledge management and training for PES services development; developing strategies and rules of procedures of services on local, regional and national level; confirmed management and specialisation on communication and promotion activities as regards employment services; Strong leadership and management skills -coordination and management of 19 county labour offices and 174 local offices as regards to European Employment Services; pre-accession bilateral and post-accession international and cross-border co-operations; International experience; Proven twinning record as RTA in Macedonia (FYROM); Excellent skills in working with multinational teams, experience as trainer in ToT | Slovakia Austria Romania Turkey Macedonia | English Hungarian | C2, C4, C5 | Civil servant, Class 1 |
| 30. Mrs Helena Schaumannová | Senior manager of the EU projects department | Labour Office of the Czech Republic | 18 | CZ | Masaryk University Brno | professional experience in public and private administration in the Employment Policy, Education, HR and Research; professional experience in evaluation, creation and implementation EU projects aiming at HRD; proven record in Employment Strategies, Labour Market policies and controlling of public resources - cooperation with employers, partnership networking; professional experience in evaluation of EU-projects-cooperation with Public Employment and Education Services, wide experience in HRD – management of HRD EU-funded projects; proven record in employment policy at national and EU-level | Slovakia | English Russian | C4, C2 | Civil servant, Class 1 |
| 31. Mrs Patricia Kralikova | Director of Department of Employment Services District Labour Office | Central Office of Labour, Social Affairs and Family, Slovakia | 14 | SK | Slovak Agricultural University | Professional experience in programming/implementation of HRD in employment area; management of large scale EU-funded projects in HRD; proven experience in design/delivery of active labour market programmes and measures (ALMPMs); professional record in development and provision of carrier guidance in Slovakia – development and provision of carrier guidance and mediation; experience as trainer for adult, drafting training curricula, organising and conducting trainings; delivery of training courses for labour offices staff based on the TNA, international experience and skills in working in multinational teams | Czech Republic Poland Hungary Macedonia | English Russian German Czech Slovak | C2, C4, C5 | Civil servant, Class 1 |
| 32. Mrs Zdenka Simova | Labour Market Manager | Labour Office of the Czech Republic | 21 | CZ | University of Pardubice | Labour Market development forecast in Usti nad Orlici district; Analysis of particular Labour Market factors, processing of the analysis results; Performing analysis and statistical records for Labour Market analysis and employment development, processing of monthly statistical statements and other statistical reports; Monitoring of employers and database updating; development of Employment Information Systems; Creating of Employment Maps using MS Map and ArcGIS; Verifying of contracts of ALAMPs in Usti nad Orlici district | Slovakia | English Russian Slovak | C2, C3, C4 | Civil servant, Class 1 |
| 33. Marie Bilkova | Senior Officer | Labour Office of the Czech Republic | 22 | CZ | University of Economics, Faculty of National Economy, Praha | Excellent management and leadership skills being the director general for more than 15 years, vast experience in budgetary and auditing issues, profound experience in labour market, flexible employment and pension systems | EU HQ Sweden Slovakia Austria | English Czech Slovak Russian | C 2, C3, C4 | Civil servant, Class 1 |
| 34. Mr Jan Marek | Director of Labour Office in Vyškov | Labour Office of the Czech Republic | 33 | CZ | University of Economics, Prague | Excellent professional experience in comprehensive management of separate organizational units of the state, ensuring the state employment policy and non-insurance social welfare in the administrative district and to the extent applicable laws;Proven skills in negotiation and cooperation with local government, state government, tripartite institutions, politics, business community; negotiations with foreign investors; professional experience as change management ; experience in design/delivery of active labour market programmes and measures (ALMPMs); programming/implementation of HRD projects - national projects. | Germany France Italy Slovakia Austria | English German Russian Slovak | C2, C4 | Civil servant, Class 1 |
| 35. Mrs Jarmila Materankova | Director of Local Labour Office in Opava | Labour Office of the Czech Republic | 23 | CZ | Mining University, Ostrava - computer science | 23 years of experience in labour market analysis and in managing positions, with up to 150 subordinates, and the budget of 1 billion CZK; active labour market policy implementation, incl. ESF financed projects, in the region heavily hit by extremely high rate of unemployment and long-term unemployment; experience in subsidies for creating new jobs for unemployed within the firms, start up subsidies for unemployed to become new entrepreneurs, subsidies for municipal work as a tool for combating long term unemployment, subsidies for creating and maintaining sheltered work for disabled; lecturer on labour market issues, proven by Ministry of Labour and Social Affairs; member of the Czech Ministry of Labour and Social Affairs working group for labour market monitoring, analysis and statistics; strong analytical skills, proved by frequent contracts with top Czech labour market research institutions; ability to work in multinational teams | Poland Italy Latvia Belgium Slovenia Slovakia | English German Russian | C2, C3, C4 | Civil servant, Class 1 |
| 36. Mr Gabor Balaban | EURES reform coordinator | National Labour Office of Hungary | 15 | HU | University of Miskolc, Faculty of Economics | Experience in preparation of business plans, HR development and marketing plans Proven record in elaboration, coordination, monitoring and evaluation of labour market and social economy projects | Hungary Slovakia | English German Hungarian | C2, C4, C5 | Civil servant, Class 1 |
| 37. Mr Istvan Sziklai | Senior expert on employment | National Labour Office of Hungary | 14 | HU | University of Eotvos Lorand, Faculty of Social Sciences, Budapest, Hungary PhD. | Proven experience in the development and implementation of equal opportunity developments (both horizontal and targeted) Professional experience in strategic management, steering, coordination and supervision of programmes in the field of labour market and social services; Experience in conducting research in the targeted area | Hungary | English German Hungarian | C2, C4 | Civil servant, Class 1 |

7.1.2.	Beneficiary Country

7.1.2.1. Project Leader

The Social Service Agency/Ministry of Labour, Health and Social Affairs entrust the leadership of the project and the responsibility for it to Ms Tea Sturua, Head of Employment Programmes Department of the Social Service Agency.

The Beneficiary Country Project Leader acts as the counterpart of the MS Project Leader and two JPLs and in close cooperation with them; she ensures the overall steering and co-ordination of the project.

The ESS/MoLHSA will ensure that the adequate resources (human and technical, e.g. office) are available. The ESS/MoLHSA is also responsible for selection of the Georgian experts to be involved in the implementation of the project. The ESS/MoLHSA has declared its willingness to fulfil the institutional and organisational requirements, in terms of commitment of the personnel, as well as in terms of any measures which will contribute to the successful implementation of the project and the achievement of each of its benchmarks and all guaranteed results.

The BC project leader is responsible for:

- Coordinating BC team/s established for implementation of the project

- Cooperating with different departments and other BC institutions involved in project implementation

- Submitting all necessary reports (jointly prepare and co-sign the reports with MS PL)

- Ensuring attendance of BC experts (working groups), according to the work plan.

Contact details:

Project Leader:

Ms Tea Sturua

Head of Employment Programmes Department

Social Service Agency

Ministry of Labour, Health and Social Affairs of Georgia

144 Tsereteli ave, Tbilisi 0119, Georgia

Mob: + 995 599 97 62 88

E-mail: tsturua@saesa.gov.ge

7.1.2.2. RTA Counterpart

The MoLESP assigns Ms. Maia Asatiani, IR Specialist at Employment Programmes Department, Social Service Agency as the RTA counterpart for the period of RTA assignment at ESS/MoLHSA.

The RTA counterpart is responsible for:

- Coordinating working activities in line with the Work plan

- Participating in analysis and estimations of the current situation

- Organizing and supporting activities necessary to reach guaranteed results

- Participating in elaboration of the Work plan

- Submitting all necessary reports

RTA counterpart contact details

RTA Counterpart:

Ms. Maia Asatiani

IR Specialist at Employment Programmes Department

Social Service Agency

Ministry of Labour, Health and Social Affairs of Georgia

144 Tsereteli ave.

Tbilisi 0119

Georgia

Mob: +995 577 57 44 09

E-mail: masatiani@ssa.gov.ge

7.1.2.3. BC Counterparts for the Component Leaders

| Ms Tea Sturua | BC Counterpart of the CL 0 |
| --- | --- |
| Mr Mamuka Gogashvili | BC Counterpart of the CL 1 |
| Mr Shota Makharashvili | BC Counterpart of the CL 2 |
| Mr Irakli Tabatade | BC Counterpart of the CL 3 |
| Ms Qeta Xachidze and Ms Lili Bibilashvili | BC Counterpart of the CL 4 |
| Mr Nika Chanadiri | BC Counterparts of the CL 5 |

7.1.3. Curricula Vitae

Attached (in Annex 9) are the EU format CVs of the following persons:

| MS Project Leader | Mr Branislav Ondrus |
| --- | --- |
| JPL Hungary | Mr Robert Komaromi |
| JPL Czech Republic | Mrs Vera Kolmerova |
| BC Project Leader | Ms Tea Sturua |
| RTA | Mr Borbely-Pecze Tibor Bors |
| RTA Counterpart in the BC | Ms Maia Asatiani |
| Key STEs from the MS |  |
| Component Leader 0 | Mr Branislav Ondrus |
| Component Leader 1 | Mrs Elena Palikova |
| Component Leader 2 | Mr Boris Katuscak |
| Component Leader 3 | Mr Gero George |
| Component Leader 4 | Mrs Luba Pavlovova |
| Component Leader 5 | Mrs Vera Kolmerova |
| STE | Danica Lehocka, State Counsellor for Employment, Director of Employment Section, Ministry of Labour, Social Affairs and family of the Slovak Republic |
| STE | Gabor Balaban, EURES reform coordinator, National Labour Office of Hungary |
| STE | Istvan Sziklai, Senior expert on employment,National Labour Office of Hungary |

Additional three STE are proposed:

- one STE (employment and communication expert) is proposed to be included into the list of STEs to provide employment and communication expertise for components 5 and 2. Mrs Danica Lehocka is one of Ministry key officials directly involved in the employment policy creation in Slovakia,

- two STE – Mr Gabor Balaban and Mr Istvan Sziklai are proposed to be included into the list of STE to strengthen the team of STE and provide expertise and good practice from Hungary in employment and HRD.

7.2. Material Resources

The BC commits itself to cover the costs of the following provisions:

- Adequately equipped office space for the RTA and the RTA assistant and Translator/ Interpreter for the entire duration of their secondment.

- Adequate conditions for the STEs to perform their work while on mission to the BC.

- Training and conference venues, as well as presentation and interpretation equipment.

(Costs for travel by BC officials from their capitals to a MS and/or between MS, e.g. in the framework of study visits, may be eligible for funding for Twinning projects financed under ENI. Costs for travel by BC officials within a MS are also eligible for reimbursement from the project budget.

7.3. Indicative Budget

The total budget for the Twinning contract is € 1 100 000 EUR.A detailed breakdown of the budget is shown in Annex A3.

ARTICLE 8 	MANAGEMENT AND MONITORING

8.1. Language

The official language of the project will be English. All formal communication regarding the project, including all reports will be produced in the agreed language.

8.2. Project Steering Committee (PSC)– check twinning fiche for composition

At quarterly intervals, the Project Leaders, the RTA, RTA counterpart, representatives of the administrative office and the EU Delegation will meet to discuss the progress of the project, verify the achievement of the outputs and mandatory results and discuss actions to be undertaken in the following quarter. The Project Steering Committee will also discuss the draft of the quarterly and final reports submitted to it beforehand, recommend corrections and approve these reports.

In addition, monthly progress monitoring meetings should be held. As a gathering of RTA, RTA counterpart, EU Delegation and PAO representative the meetings are to monitor progress and solve any emerging operational problems on a monthly base. As the outcome, it is recommended to record proceedings of the meetings in one-page minutes.

The responsibility for the organisation of the Project Steering Committee meeting lies with both Project Leaders.

Members of the Project Steering Committee (attending the meetings)

MSs staff

Mr Branislav Ondrus, MS PL

Mr Borbely-Pecze Tibor Bors, RTA

BC staff

Ms Tea Sturua, BC PL

Ms Maia Asatiani, BC RTA Counterpart

Mr Roman Kakulia, Head of EU Assistance Coordination Department/Programme Administration Office (PAO)

Ms Elza Jgerenaia, Head of Labour and Employment Policy, MoLHSA
Mr Tengiz Abazadze, Deputy Head of Social Service Agency (SSA)

DEU

Dr Stephen Stork, Deputy Head of Operations

Ms Nino Kochishvili, Project Manager, Operations

8.3. Reporting

Every three months, the MS Project Leader in co-operation with the two JPLs and BC Project Leader will submit interim quarterly reports to the respective institution identified in section 6.4 to the Twinning manual. Each report will cover a three months period calculated from the date of notification of the contract.

.

The interim quarterly reports will be prepared and distributed in electronic copy to all participants at least one week in advance of the meetings of the Project Steering Committee. The template of the report is detailed in Annex C4 to the Twinning manual. The comments provided by the PSC should be integrated within 2 weeks upon which they should be submitted to the Contracting Authority (EUD), with a copy to the ESS/MoLHSA Project Leader and PAO.

The first report will be due in the fourth month counting from the date of notification of the Twinning contract. Failure to submit satisfactory reports in time may lead to the decision to suspend EU financing for the project.

The MS Project Leader in coordination with the two JPLs shall submit the final report before the end of the legal duration of the Twinning contract.

The final report will be accompanied by a verification expenditure report.

ARTICLE 9 	TWINNING REVIEW MISSIONS

Each Twinning project is in principle followed, 6 to 12 months after its finalisation, by a Twinning Review Mission (TRM). This mission aims at reporting whether sustainable impacts or spin offs have been observed after Twinning project finalisation.

The overall objective of a TRM is to assess if the achievements of the Twinning project are still present and if they produced a standing impact, in particular in terms of sustainability. Normally, a TRM should also identify lessons learned and recommend improvements for the managing of Twinning projects in the given country and/or sector.

A TRM shall analyse the situation in the area/sector covered by the Twinning project concerned, comparing it to the situation prevailing when the project’s implementation ended and taking into account the initial situation that the project was called to correct. The scope of the analysis shall be determined by the mandatory results of the Twinning project.

A TRM shall focus on the developments intervened after the end of the Twinning project concerned with particular regard to the legal and institutional level (legislative progress and administrative adaptation), to capacity and skills building (further training of staff and spreading of know-how) and to the structural changes introduced (irreversibility of the new framework).

The Team charged with the performance of the TRM is led by the Twinning Review Expert (TRE), a public sector (or mandated body) expert from a different MS than the Lead or Junior MS partners of the project concerned, who did not participate in the Twinning project in question. In principle and when possible the TRE is a former RTA of a similar project.

The TRE is selected by the Institution Building Unit (IBU) of the Commission, in consultation with MS National Contact Points (NCP) and other stakeholders. He/She is directly invited by the IBU to perform the TRM.

The TRE is responsible for preparing the Reporting Form. The Reporting Form, which the TRE timely distributes to all members of the TRM Team, mentions the project's deliveries and the final report's recommendations

The TRE drafts the review report.

For all or part of the TRM the TRE can be assisted and accompanied by a team of persons who were involved in the project concerned:

•	the MS RTA;

•	the BC RTA counterpart;

•	the MS Project Leader (when appropriate and if available);

•	the BC Project Leader (or the official who might have replaced him/her in the same

position);

•	the task manager from the pertinent EU Delegation who followed the project or the sector

involved (or the official who might have replaced him/her in the same position).

If the MS RTA and/or the BC RTA counterpart are not available, the selection of a replacement is decided on a case by case basis by the IBU in close consultation with the pertinent stakeholders.

A more detailed set of guidelines and the template of the Reporting Form are available on the Twinning web-page:http://ec.europa.eu/enlargement/pdf/financial_assistance/institution_building/2013/guidelines_trm.pdf .

TRM are organised as TAIEX events whose cost is covered by the TAIEX budget. The request to launch a TRM is initiated by the relevant EU Delegation.

The final reports produced by TRM will be included in a database of Twinning assessments accessible to all those involved.

For the administration of the Member State

Mr Branislav Ondrus

Member State Project Leader

Ministry of Labour, Social Affairs and Family of the Slovak Republic

Špitálska 4, 6, 8

816 43 Bratislava

Slovak Republic

Signature

Date

For the administration of the BC

Ms Tea Sturua

Beneficiary Country Project Leader

Head of Employment Programmes Department

Social Service Agency

Ministry of Labour, Health and Social Affairs of Georgia

144 Tsereteli ave.

Tbilisi 0119

Georgia

Signature

Date

# ANNEX A2
General Conditions applicable to European Union-financed grant contracts for external actions

CONTENTS

Explanations of the terms used throughout these General Conditions may be found in the 'Glossary of terms', Annex A1 to the Practical Guide to contract procedures for EU external actions.

In case of operating grants, the term "Action" should be understood as "Work Programme".

The term "Coordinator" refers to the Beneficiary identified as the Coordinator in the Special Conditions.

The term "Beneficiary(ies)" refers collectively to all Beneficiaries, including the Coordinator, of the Action. When there is only one Beneficiary of the Action, the terms Beneficiary(ies) and Coordinator should both be understood as referring to the only Beneficiary of the Action.

The term "party(ies) to this Contract" refers to the party signatory of this Contract (i.e. the Beneficiary(ies) and the Contracting Authority).

All references to "days" in this Contract are to calendar days, unless otherwise specified.

# Table of content

Article 1 - General provisions

Article 2 - Obligation to provide financial and narrative reports

Article 3 - Liability

Article 4 - Conflict of interests

Article 5 - Confidentiality

Article 6 - Visibility

Article 7 - Ownership/use of results and assets

Article 8 - Evaluation/monitoring of the Action

Article 9 - Amendment of the contract

Article 10 - Implementation

Article 11 - Extension and suspension

Article 12 - Termination of the contract

Article 13 - Applicable law and dispute settlement

Article 14 - Eligible costs

Article 15 - Payment and interest on late payment

Article 16 - Accounts and technical and financial checks

Article 17 - Final amount of the grant

Article 18 - Recovery

GENERAL AND ADMINISTRATIVE PROVISIONS

Article 1 - General Provisions

General principles

1.1	The Beneficiary(ies) and the Contracting Authority are the only parties to this Contract. Where the European Commission is not the Contracting Authority, it is not party to this Contract, which confers on the European Commission only the rights and obligations explicitly mentioned in this Contract.

1.2	This Contract and the payments attached to it may not be assigned to a third party in any manner whatsoever without the prior written consent of the Contracting Authority.

Data protection

1.3	Any personal data will be processed solely for the purposes of the performance, management and monitoring of this Contract by the Contracting Authority and may also be passed to the bodies charged with monitoring or inspection tasks under European Union law. Beneficiaries will have the right of access to their personal data and the right to rectify any such data. If the Beneficiary(ies) have any queries concerning the processing of personal data, they shall address them to the Contracting Authority. The Beneficiary(ies) will have right of recourse at any time to the European Data Protection Supervisor.

1.4	The Beneficiary shall limit access and use of personal data to that strictly necessary for the performance, management and monitoring of this Contract and shall adopt all appropriate technical and organisational security measures necessary to preserve the strictest confidentiality and limit access to this data.

Role of the Beneficiary(ies)

1.5	The Beneficiary(ies) shall:

a)	carry out the Action jointly and severally vis-a-vis the Contracting Authority taking all necessary and reasonable measures to ensure that the Action is carried out in accordance with the Description of the Action in Annex I and the terms and conditions of this Contract.

To this purpose, the Beneficiary(ies) shall implement the Action with the requisite care, efficiency, transparency and diligence, in line with the principle of sound financial management and with the best practices in the field.

b)	be responsible for complying with any obligation incumbent on them from this Contract jointly or individually;

c)	forward to the Coordinator the data needed to draw up the reports, financial statements and other information or documents required by this Contract and the Annexes thereto, as well as any information needed in the event of audits, checks, monitoring or evaluations, as described in Article 16;

d) 	ensure that all information to be provided and request made to the Contracting Authority is sent via the Coordinator;

e) 	agree upon appropriate internal arrangements for the internal coordination and representation of the Beneficiary(ies) vis-a-vis the Contracting Authority for any matter concerning this Contract, consistent with the provisions of this Contract and in compliance with the applicable legislation(s).

Role of the Coordinator

1.6	The Coordinator shall:

a)	monitor that the Action is implemented in accordance with this Contract and ensure coordination with all Beneficiary(ies) in the implementation of the Action;

b)	be the intermediary for all communications between the Beneficiary(ies) and the Contracting Authority;

c)	be responsible for supplying all documents and information to the Contracting Authority which may be required under this Contract, in particular in relation to the requests for payment. Where information from the Beneficiary(ies) is required, the Coordinator shall be responsible for obtaining, verifying and consolidating this information before passing it on to the Contracting Authority.

Any information given, as well as any request made by the Coordinator to the Contracting Authority, shall be deemed to have been given in agreement with all Beneficiary(ies);

d)	inform the Contracting Authority of any event likely to affect or delay the implementation of the Action;

e)	inform the Contracting Authority of any change in the legal, financial, technical, organisational or ownership situation of any of the Beneficiary(ies), as well as, of any change in the name, address or legal representative of any of the Beneficiary(ies);

f)	be responsible in the event of audits, checks, monitoring or evaluations, as described in Article 16 for providing all the necessary documents, including the accounts of the Beneficiary(ies), copies of the most relevant supporting documents and signed copies of any contract concluded according to Article 10.

g)	have full financial responsibility for ensuring that the Action is implemented in accordance with this Contract;

h)	make the appropriate arrangements for providing the financial guarantee, when requested, under the provisions of Article 4.2 of the Special Conditions

i)	establish the payment requests in accordance with the Contract;

j)	be the sole recipient, on behalf of all of the Beneficiary(ies), of the payments of the Contracting Authority. The Coordinator shall ensure that the appropriate payments are then made to the Beneficiary(ies) without unjustified delay;

k)	not delegate any, or part of, these tasks to the Beneficiary(ies) or other entities.

Article 2 - Obligation to provide financial and narrative reports

2.1. 	The Beneficiary(ies) shall provide the Contracting Authority with all required information on the implementation of the Action. The report shall be laid out in such a way as to allow comparison of the objective(s), the means envisaged or employed, the results expected and obtained and the budget details for the Action. The level of detail in any report should match that of the Description of the Action and of the Budget for the Action. The Coordinator shall collect all the necessary information and draw up consolidated interim and final reports. These reports shall:

a)	cover the Action as a whole, regardless of which part of it is financed by the Contracting Authority;

b)	consist of a narrative and a financial report drafted using the templates provided in Annex VI;

c)	provide a full account of all aspects of the Action's implementation for the period covered, including in case of simplified cost options the qualitative and quantitative information needed to demonstrate the fulfilment of the conditions for reimbursement established in this Contract ;

d)	be drafted in the currency and language of this Contract;

e)	include any update on the Communication plan as provided by Article 6.2

f)	include any relevant reports, publications, press releases and updates related to the Action;

2.2	Additionally the final report shall:

a)	cover any period not covered by the previous reports

b)	include the proofs of the transfers of ownership as referred to in Article 7.5.

2.3	The Special Conditions may set out additional reporting requirements.

2.4	The Contracting Authority may request additional information at any time. The Coordinator shall provide this information within 30 days of the request, in the language of the Contract.

2.5	Reports shall be submitted with the payment requests, according to Article 15. If the Coordinator fails to provide any report or fails to provide any additional information requested by the Contracting Authority within the set deadline without an acceptable and written explanation of the reasons, the Contracting Authority may terminate this Contract according to Article 12.2 (a) and (f).

Article 3 - Liability

3.1	The Contracting Authority cannot under any circumstances or for any reason whatsoever be held liable for damage or injury sustained by the staff or property of the Beneficiary(ies) while the Action is being carried out or as a consequence of the Action. The Contracting Authority cannot, therefore, accept any claim for compensation or increases in payment in connection with such damage or injury.

3.2	The Beneficiary(ies) shall assume sole liability towards third parties, including liability for damage or injury of any kind sustained by them while the Action is being carried out or as a consequence of the Action. The Beneficiary(ies) shall discharge the Contracting Authority of all liability arising from any claim or action brought as a result of an infringement of rules or regulations by the Beneficiary(ies) or the Beneficiary(ies)'s employees or individuals for whom those employees are responsible, or as a result of violation of a third party's rights.

Article 4 - Conflict of interests

4.1	The Beneficiary(ies) shall take all necessary measures to prevent or end any situation that could compromise the impartial and objective performance of this Contract. Such conflict of interests may arise in particular as a result of economic interest, political or national affinity, family or emotional ties, or any other relevant connection or shared interest.

4.2	Any conflict of interests which may arise during performance of this Contract must be notified in writing to the Contracting Authority without delay. In the event of such conflict, the Coordinator shall immediately take all necessary steps to resolve it.

4.3	The Contracting Authority reserves the right to verify that the measures taken are appropriate and may require additional measures to be taken if necessary.

4.4	The Beneficiary(ies) shall ensure that its staff, including its management, is not placed in a situation which could give rise to conflict of interests. Without prejudice to its obligation under this Contract, the Beneficiary(ies) shall replace, immediately and without compensation from the Contracting Authority, any member of its staff in such a situation.

Article 5 - Confidentiality

5.1	Subject to Article 16, the Contracting Authority and the Beneficiary(ies) undertake to preserve the confidentiality of any information, notwithstanding its form, disclosed in writing or orally in relation to the implementation of this Contract and identified in writing as confidential until at least 5 years after the payment of the balance.

5.2	The Beneficiary(ies) shall not use confidential information for any aim other than fulfilling their obligations under this Contract unless otherwise agreed with the Contracting Authority.

5.3	Where the European Commission is not the Contracting Authority it shall still have access to all documents communicated to the Contracting Authority and shall maintain the same level of confidentiality.

article 6 - Visibility

6.1	Unless the European Commission agrees or requests otherwise, the Beneficiary(ies) shall take all necessary steps to publicise the fact that the European Union has financed or co- financed the Action. Such measures shall comply with the Communication and Visibility Manual for Union External Actions laid down and published by the European Commission, that can be found at:

http://ec.europa.eu/europeaid/work/visibility/documents/communication_and_visibility_manual en.pdf.

6.2	The Coordinator shall submit a communication plan for the approval of the European Commission and report on its implementation in accordance with Article 2.

6.3	In particular, the Beneficiary(ies) shall mention the Action and the European Union's financial contribution in information given to the final recipients of the Action, in its internal and annual reports, and in any dealings with the media. It shall display the European Union logo wherever appropriate.

6.4	Any notice or publication by the Beneficiary(ies) concerning the Action, including those given at conferences or seminars, shall specify that the Action has received European Union funding. Any publication by the Beneficiary(ies), in whatever form and by whatever medium, including the internet, shall include the following statement: 'This document has been produced with the financial assistance of the European Union. The contents of this document are the sole responsibility of <Beneficiary(ies)'s name > and can under no circumstances be regarded as reflecting the position of the European Union. '

6.5	The Beneficiary(ies) authorises the Contracting Authority and the European Commission (where it is not the Contracting Authority) to publish its name and address, nationality, the purpose of the grant, duration and location as well as the maximum amount of the grant and the rate of funding of the Action's costs, as laid down in Article 3 of the Special Conditions. Derogation from publication of this information may be granted if it could endanger the Beneficiary(ies) or harm their interests.

article 7 - Ownership/use of results and assets

7.1	Unless otherwise stipulated in the Special Conditions, ownership of, and title and intellectual and industrial property rights to, the Action's results, reports and other documents relating to it will be vested in the Beneficiary(ies).

7.2	Without prejudice to Article 7.1, the Beneficiary(ies) grant the Contracting Authority (and the European Commission where it is not this Contracting Authority) the right to use freely and as it sees fit, and in particular, to store, modify, translate, display, reproduce by any technical procedure, publish or communicate by any medium all documents deriving from the Action whatever their form, provided it does not thereby breach existing industrial and intellectual property rights.

7.3	The Beneficiary(ies) shall ensure that it has all rights to use any pre-existing intellectual property rights necessary to implement this Contract.

7.4	In case natural, recognizable persons are depicted in a photograph or film, the Coordinator shall, in the final report to the Contracting Authority, submit a statement of these persons giving their permissions for the described use of their images. The above does not refer to photographs taken or films shot in public places where random members of the public are identifiable only hypothetically and to public persons acting in their public activities.

7.5	Where a Beneficiary(ies) does not have its headquarter(s) in the country where the Action is implemented and unless otherwise specified in the Special Conditions, its equipment, vehicles and supplies paid for by the Budget for the Action shall be transferred to any local Beneficiary(ies) and/or to any local affiliated entity(ies) and/or to the final beneficiaries of the Action, at the latest when submitting the final report. Copies of the proofs of transfer of any equipment and vehicles for which the purchase cost was more than EUR 5 000 per item, shall be attached to the final report. Proofs of transfer of equipment and vehicles whose purchase cost was less than EUR 5 000 per item shall be kept by the Beneficiary(ies) for control purposes..

Article 8 - Evaluation/monitoring of the Action

8.1	If the European Commission carries out an interim or ex post evaluation or a monitoring mission, the Coordinator shall undertake to provide it and/or the persons authorised by it with any document or information which will assist with the evaluation or monitoring mission, and grant them the access rights described in Article 16.

8.2	If either the Beneficiary(ies) or the European Commission carries out or commissions an evaluation in the course of the Action, it shall provide the other with a copy of the evaluation report.

Article 9 - Amendment of the Contract

9.1	Any amendment to this Contract, including the annexes thereto, shall be set out in writing. This Contract can be modified only during its execution period.

9.2	The amendment may not have the purpose or the effect of making changes to this Contract that would call into question the grant award decision or be contrary to the equal treatment of applicants. The maximum grant referred to in Article 3.2 of the Special Conditions may not be increased.

9.3	If an amendment is requested by the Beneficiary(ies), the Coordinator shall submit a duly justified request to the Contracting Authority thirty days before the date on which the amendment should enter into force, unless there are special circumstances duly substantiated and accepted by the Contracting Authority.

9.4	Where the amendment to the Budget or Description of the Action does not affect the basic purpose of the Action and the financial impact is limited to a transfer between items within the same main budget heading including cancellation or introduction of an item, or a transfer between main budget headings involving a variation of 25% or less of the amount originally entered (or as modified by addendum) in relation to each concerned main heading for eligible costs, the Coordinator may amend the budget and inform in writing without delay the Contracting Authority accordingly. This method may not be used to amend the headings for indirect costs, for the contingency reserve, for in-kind contributions or the amounts or rates of simplified cost options.

9.5	Changes of address, bank account or auditor may simply be notified by the Coordinator. However, in duly substantiated circumstances, the Contracting Authority may oppose the Coordinator's choice.

9.6	The Contracting Authority reserves the right to require that the auditor referred to in Article 5.2 of the Special Conditions be replaced if considerations which were unknown when this Contract was signed cast doubt on the auditor's independence or professional standards.

Article 10 — Implementation

Implementation contracts

10.1	If the Beneficiary(ies) have to conclude implementation contracts with contractors in order to carry out the Action, these may only cover a limited portion of the Action and shall respect the contract-award procedures and rules of nationality and origin set out in Annex IV of this Contract.

10.2	The Beneficiary(ies) shall also ensure that contractors awarded an implementation contract comply with Articles 3, 4, 5, 6, 7, 8 and 16 of this Contract.

10.3	The Coordinator shall provide in its report to the Contracting Authority a comprehensive and detailed report on the award and implementation of any contract awarded under article 10.1.

Financial support to third parties

10.4	In order to support the achievement of the objectives of the Action, and in particular where the implementation of the Action requires financial support to be given to third parties, the Beneficiary(ies) may award financial support if so provided by the Special Conditions.

10.5	The maximum amount of financial support shall be limited to EUR 60 000 per each third party, except where the main purpose of the Action is to redistribute the grant.

10.6	The Description of the Action, in conformity with the relevant instructions given in this regard by the Contracting Authority, shall define the types of entities eligible for financial support and include a fixed list with the types of activity which may be eligible for financial support. The criteria for the selection of the third parties recipient of this financial support, including the criteria for determining its exact amount, shall also be specified. The Beneficiary(ies) shall respect the rules of nationality and origin set out in Annex IV of this Contract.

10.7	The Coordinator shall provide in its report to the Contracting Authority a comprehensive and detailed report on the award and implementation of any financial support given. These reports should provide, amongst other, information on the award procedures, on the identities of the recipient of financial support, the amount granted, the results achieved, , the problems encountered and solutions found, the activities carried out as well as a timetable of the activities which still need to be carried out.

10.8	The Beneficiary(ies) shall also ensure that third parties awarded financial support comply with Articles 3, 4, 5, 6, 7, 8 and 16 of this Contract.

Article 11 - Extension and suspension

Extension

11.1	The Coordinator shall inform the Contracting Authority without delay of any circumstances likely to hamper or delay the implementation of the Action. The Coordinator may request an extension of the Action's implementation period as laid down in Article 2 of the Special Conditions in accordance to Article 9. The request shall be accompanied by all the supporting evidence needed for its appraisal.

Suspension by the Coordinator

11.2	The Coordinator may suspend implementation of the Action, or any part thereof, if exceptional circumstances, notably of force majeure, make such implementation excessively difficult or dangerous. The Coordinator shall inform the Contracting Authority without delay, stating the nature, probable duration and foreseeable effects of the suspension.

11.3	The Coordinator or the Contracting Authority may then terminate this Contract in accordance with Article 12.1. If the Contract is not terminated, the Beneficiary(ies) shall endeavour to minimise the time of its suspension and any possible damage and shall resume implementation once circumstances allow, informing the Contracting Authority accordingly.

Suspension by the Contracting Authority

11.4	The Contracting Authority may request the Beneficiary(ies) to suspend implementation of the Action, or any part thereof, if exceptional circumstances, notably of force majeure, make such implementation excessively difficult or dangerous. To this purpose, the Contracting Authority shall inform the Coordinator stating the nature and probable duration of the suspension.

11.5	The Coordinator or the Contracting Authority may then terminate this Contract in accordance with Article. 12.1. If the Contract is not terminated, the Beneficiary(ies) shall endeavour to minimise the time of its suspension and any possible damage and shall resume implementation once circumstances allow and after having obtained the approval of the Contracting Authority.

11.6	The Contracting Authority may also suspend this Contract or the participation of a Beneficiary(ies) in this Contract when, or, if necessary to verify, that:

a)	the grant award procedure or the implementation of the Action have been subject to substantial errors, irregularities or fraud;

b)	the Beneficiary(ies) have breached any substantial obligation under this Contract.

11.7	The Coordinator shall provide any requested information, clarification or document within 30 days of receipt of the requests sent by the Contracting authority. If, notwithstanding the information, clarification or document provided by the Coordinator, the award procedure or the implementation of the grant proves to have been subject to substantial errors, irregularities, fraud, or breach of obligations, then the Contracting Authority may terminate this Contract according to Article 12(2) h.

Force majeure

11.8	The term force majeure, as used herein covers any unforeseeable events, not within the control of either party to this Contract and which by the exercise of due diligence neither party is able to overcome such as acts of God, strikes, lock-outs or other industrial disturbances, acts of the public enemy, wars whether declared or not, blockades, insurrection, riots, epidemics, landslides, earthquakes, storms, lightning, floods, washouts, civil disturbances, explosion. A decision of the European Union to suspend the cooperation with the beneficiary country is considered to be a case of force majeure when it implies suspending funding under this Contract.

11.9	The Beneficiary(ies) shall not be held in breach of its contractual obligations if it is prevented from fulfilling them by circumstances of force majeure.

Extension of the implementation period following a suspension

11.10	In case of suspension according to Articles 11.2, 11.4 and 11.6, the implementation period of the Action shall be extended by a period equivalent to the length of suspension, without prejudice to any amendment to the Contract that may be necessary to adapt the Action to the new implementing conditions. Article 11.10 does not apply in case of an operating grant.

Article 12 — Termination of the Contract

Termination in case of force majeure

12.1	In the cases foreseen in Article 11.2 and 11.4, if the Coordinator or the Contracting Authority believes that this Contract can no longer be executed effectively or appropriately, it shall duly consult the other. Failing agreement on a solution, the Coordinator or the Contracting Authority may terminate this Contract by serving two months written notice, without being required to pay compensation.

Termination by the Contracting Authority

12.2	Without prejudice to article 12.1, in the following circumstances the Contracting Authority may, after having duly consulted the Coordinator, terminate this Contract or the participation of any Beneficiary(ies) in this Contract without any indemnity on its part when:

a)	a Beneficiary(ies) fails, without justification, to fulfil any substantial obligation incumbent on them individually or collectively by this Contract and, after being given notice by letter to comply with those obligations, still fails to do so or to furnish a satisfactory explanation within 30 days of receipt of the letter;

b)	a Beneficiary(ies) is bankrupt or being wound up, is having its affairs administered by the courts, has entered into an arrangement with creditors, has suspended business activities, is the subject of proceedings concerning those matters or is in any analogous situation arising from a similar procedure provided for in national legislation or regulations;

c)	a Beneficiary(ies), or any related entity or person, have been found guilty of an offence concerning their professional conduct proven by any means;

d)	a Beneficiary(ies), or any related entity or person, have committed fraud, corruption, or are involved in a criminal organisation, money laundering or any other illegal activity detrimental to the European Union's financial interests;

e)	a change to a Beneficiary(ies)'s legal, financial, technical, organisational or ownership situation or the termination of the participation of a Beneficiary(ies) substantially affects the implementation of this Contract or calls into question the decision awarding the grant;

f)	a Beneficiary(ies) or any related person, are guilty of misrepresentation in supplying the information required in the award procedure or in the implementation of the Action or fails to supply - or fails to supply within the deadlines set under this Contract - any information related to the Action required by the Contracting Authority;

g)	a Beneficiary(ies) has not fulfilled obligations relating to the payment of social security contributions or the payment of taxes in accordance with the legal provisions of the country in which it is established;

h)	the Contracting Authority has evidence that a Beneficiary(ies), or any related entity or person, has committed substantial errors, irregularities or fraud in the award procedure or in the implementation of the Action;

i)	a Beneficiary(ies) is subject to an administrative penalty referred to in Article 12(8);

j)	the Contracting Authority has evidence that a Beneficiary(ies) is subject to a conflict of interests;

k)	the European Commission has evidence that a Beneficiary(ies) has committed systemic or recurrent errors or irregularities, fraud, or serious breach of obligations under other grants financed by the European Union and awarded to that specific under similar conditions, provided that those errors, irregularities, fraud or serious breach of obligations have a material impact on this grant.

12.3	In the cases referred to in points (c), (d) (f) (h) and (k) above, any related person means any physical person with powers of representation, decision-making or control in relation to the Beneficiary(ies). Any related entity means, in particular, any entity which meets the criteria laid down by Article 1 of the Seventh Council Directive No 83/349/EEC of 13 June 1983.

Termination of a Beneficiary(ies) participation by the Coordinator

12.4	In duly justified cases, the participation of a Beneficiary(ies) in this Contract may be also terminated by the Coordinator. To this purpose, the Coordinator shall communicate to the Contracting Authority the reasons for the termination of its participation and the date on which the termination shall take effect, as well as a proposal on the reallocation of the tasks of the Beneficiary(ies) whose participation is terminated, or on its possible replacement. The proposal shall be sent in good time before the termination is due to take effect. If the Contracting Authority agrees, the Contract shall be amended accordingly in conformity with Article 9.

End date

12.5	The payment obligations of the European Union under this Contract shall end 18 months after the implementation period laid down in Article 2 of the Special Conditions, unless this Contract is terminated according to Article 12. The Contracting Authority shall notify the Coordinator of any postponement of the end date.

12.6	This Contract will be terminated automatically if it has not given rise to any payment by the Contracting Authority within two years of its signature.

Effects of Termination

12.7	In the event of termination, the Beneficiary(ies) shall be entitled to payment only for the part of the Action carried out, excluding costs relating to current commitments that are not due to be executed until after termination.

To this purpose, the Coordinator shall introduce a payment request to the Contracting Authority within the time limit set by Article 15(2) starting from the date of termination.

In the cases of termination foreseen in Article 12.2 a), c), d), f), h) and k) the Contracting Authority may, after having properly consulted the Coordinator and depending on the gravity of the failings, request full or partial repayment of amounts already paid for the Action.

Administrative and Financial penalties

12.8	Without prejudice to the application of other remedies laid down in the Contract, a Beneficiary(ies) who has made false declarations, substantial errors, irregularities and fraud or was in serious breach of its contractual obligations may be excluded from all contracts and grants financed by the EU for a maximum of five years from the date on which the infringement is established, to be confirmed after an adversarial procedure with the European Commission, in accordance with the Financial Regulations applicable to the contracts covered by the Budget or the EDF. The period may be increased to ten years in the event of a repeated offence within five years of the first infringement.

12.9	In addition or in alternative to the administrative sanctions laid down in Article 12.8, a Beneficiary(ies) may also be subject to financial penalties representing 2-10% of the total value of this Contract. This rate may be increased to 4-20% in the event of a repeated offence within five years of the first infringement.

12.10	The European Commission shall formally notify the Beneficiary(ies) concerned of any decision to apply such penalties.

Article 13 — Applicable law and dispute settlement

13.1	This Contract shall be governed by the law of the country of the Contracting Authority or, where the Contracting Authority is the European Commission, by the European Union law supplemented as appropriate by Belgian law.

13.2	The parties to this Contract shall do everything possible to settle amicably any dispute arising between them during implementation of this Contract. To that end, they shall communicate their positions and any solution that they consider possible in writing, and meet each other at either's request. The Coordinator and the Contracting Authority shall reply to a request sent for an amicable settlement within 30 days. Once this period has expired, or if the attempt to reach amicable settlement has not produced an agreement within 120 days of the first request, the Coordinator or the Contracting Authority may notify the other part that it considers the procedure to have failed.

13.3	In the event of failure to reach an amicable agreement, the dispute may by common agreement of the Coordinator and the Contracting Authority be submitted for conciliation by the European Commission if it is not the Contracting Authority. If no settlement is reached within 120 days of the opening of the conciliation procedure, each party may notify the other that it considers the procedure to have failed.

13.4	In the event of failure of the above procedures, each party to this Contract may submit the dispute to the courts of the country of the Contracting Authority, or to the Brussels courts where the Contracting Authority is the European Commission.

FINANCIAL PROVISIONS

Article 14 — Eligible costs

Cost eligibility criteria

14.1	Eligible costs are actual costs incurred by the Beneficiary(ies) which meet all the following criteria:

a)	they are incurred during the implementation of the Action as specified in Article 2 of the Special Conditions. In particular:

(i)	Costs relating to services and works shall relate to activities performed during the implementation period. Costs relating to supplies shall relate to delivery and installation of items during the implementation period. Signature of a contract, placing of an order, or entering into any commitment for expenditure within the implementation period for future delivery of services, works or supplies after expiry of the implementation period do not meet this requirement;

(ii)	Costs incurred should be paid before the submission of the final reports. They may be paid afterwards, provided they are listed in the final report together with the estimated date of payment;

(iii)	An exception is made for costs relating to final reports, including expenditure verification, audit and final evaluation of the Action, which may be incurred after the implementation period of the Action;

(iv)	Procedures to award contracts, as referred to in Article 10, may have been initiated and contracts may be concluded by the Beneficiary(ies) before the start of the implementation period of the Action, provided the provisions of Annex IV have been respected.

b)	they are indicated in the estimated overall budget for the Action;

c)	they are necessary for the implementation of the Action;

d)	they are identifiable and verifiable, in particular being recorded in the accounting records of the Beneficiary(ies) and determined according to the applicable accounting standards of the country where the Beneficiary(ies) is established and according to the usual cost accounting practices of the Beneficiary(ies);

e)	they comply with the requirements of applicable tax and social legislation;

f)	they are reasonable, justified and comply with the requirements of sound financial management, in particular regarding economy and efficiency.

Eligible direct costs

14.2	Subject to Article 14.1 and, where relevant, to the provisions of Annex IV being respected, the following direct costs of the Beneficiary(ies) shall be eligible:

a)	the cost of staff assigned to the Action, corresponding to actual gross salaries including social security charges and other remuneration-related costs; salaries and costs shall not exceed those normally borne by the Beneficiary(ies), unless it is justified by showing that it is essential to carry out the Action;

b)	travel and subsistence costs for staff and other persons taking part in the Action, provided they do not exceed those normally borne by the Beneficiary(ies) nor the rates published by the European Commission at the time of such mission;

c)	purchase costs for equipment and supplies (new or used) specifically for the purposes of the Action, provided that ownership is transferred at the end of the Action when required in Article 7.5;

d)	costs of consumables;

e)	costs entailed by contracts awarded by the Beneficiary(ies) for the purposes of the Action referred to in Article 10.

f)	costs deriving directly from the requirements of the Contract (dissemination of information, evaluation specific to the Action, audits, translation, reproduction, insurance, etc.) including financial service costs (in particular the cost of transfers and financial guarantees where required according to the Contract);

g)	duties, taxes and charges, including VAT, paid and not recoverable by the beneficiaries, unless otherwise provided in the Special Conditions:

h)	overheads, in the case of an operating grant.

Simplified cost options

14.3	In accordance with the detailed provisions in Annex III, eligible costs may also be constituted by any or a combination of the following cost options:

a)	unit costs;

b)	lump sums;

c)	flat-rate financing.

14.4	The methods used by the Beneficiary(ies) to determine unit costs, lump sums or flat-rates shall be clearly described and substantiated in Annex III and shall ensure compliance with the no-profit rule and shall avoid double funding of costs. The information used can be based on the Beneficiary(ies)'s historical and/or actual accounting and cost accounting data or on external information where available and appropriate.

Costs declared under simplified cost options shall satisfy the eligibility criteria set out in Article 14.1 and 14.2. They do not need to be backed by accounting or supporting documents, save those necessary to demonstrate the fulfilment of the conditions for reimbursement established in Annex I and III.

These costs may not include ineligible costs as referred to in Article 14.9 or costs already declared under another costs item or heading of the budget of this Contract.

The amounts or rates of unit costs, lump sums or flat-rates set out in Annex III may not be amended unilaterally and may not be challenged by ex post verifications.

14.5	The total amount of financing on the basis of simplified cost options may not exceed EUR 60 000 per each Beneficiary, unless otherwise provided for in the Special Conditions.

Contingency reserve

14.6	A reserve for contingencies and/or possible fluctuations in exchange rates not exceeding 5 % of the direct eligible costs may be included in the budget for the Action, to allow for adjustments necessary in the light of unforeseeable changes of circumstances on the ground. It can be used only with the prior written authorisation of the Contracting Authority, upon duly justified request by the Coordinator.

Indirect costs

14.7	The indirect costs for the action are those eligible costs which may not be identified as specific costs directly linked to the implementation of the action and may not be booked to it directly according to the conditions of eligibility in Article 14.1. However, they are incurred by the beneficiary(ies) in connection with the eligible direct costs for the action. They may not include ineligible costs as referred to in Article 14.9 or costs already declared under another costs item or heading of the budget of this Contract.

A fixed percentage of the total amount of direct eligible costs of the Action not exceeding the percentage laid down in Article 3 of the Special Conditions may be claimed to cover indirect costs for the Action. Flat-rate funding in respect of indirect costs does not need to be supported by accounting documents. This amount shall not be taken into account with regard to the maximum amount of simplified cost options.

Indirect costs shall not be eligible under a grant for an action awarded to a beneficiary who already receives an operating grant financed from the Union budget during the period in question.

This Article 14.7 does not apply in the case of an operating grant.

In kind contributions

14.8	Any contributions in kind, which shall be listed separately in Annex III, do not represent actual expenditure and are not eligible costs. Unless otherwise specified in the Special Conditions, contributions in kind may not be treated as co-financing by the Beneficiary(ies).

If contributions in kind are accepted as co-financing, the Beneficiary(ies) shall ensure they comply with national tax and social security rules.

Notwithstanding the above, if the Description of the Action provides for contributions in kind, such contributions have to be provided.

Non-eligible costs

14.9	The following costs shall not be considered eligible:

a)	debts and debt service charges (interest);

b)	provisions for losses or potential future liabilities;

c)	costs declared by the Beneficiary(ies) and financed by another action or work programme receiving a Union (including through EDF) grant;

d)	purchases of land or buildings, except where necessary for the direct implementation of the Action, in which case ownership shall be transferred to the final beneficiaries and/or local Beneficiary(ies), at the latest at the end of the Action, in accordance with Article 7.5;

e)	currency exchange losses;

f)	credits to third parties, unless otherwise specified in the Special Conditions.

Article 15 — Payment and interest on late payment

Payment procedures

15.1	 The Contracting Authority must pay the grant to the Coordinator following one of the payment procedures below, as set out in Article 4 of the Special Conditions.

Option 1: Actions with an implementation period of 12 months or less or grant of EUR 100 000 or less

(i)	an initial pre-financing payment of 80 % of the maximum amount referred to in Article 3.2 of the Special Conditions (excluding contingencies);

(ii)	the balance of the final amount of the grant.

Option 2: Actions with an implementation period of more than 12 months and grant of more than EUR 100 000

(i)	an initial pre-financing payment of 100 ϋ/ΰ of the part of the estimated budget financed by the Contracting Authority for the first reporting period (excluding contingencies). The part of the budget financed by the Contracting Authority is calculated by applying the percentage set out in Article 3.2 of the Special Conditions;

(ii)	further pre-financing payments of 100 ϋ/ΰ of the part of the estimated budget financed by the Contracting Authority for the following reporting period (excluding not authorised contingencies);

-	the reporting period is intended as a twelve-month period unless otherwise provided for in the Special Conditions. When the remaining period to the end of the Action is up to 18 months, the reporting period shall cover it entirely;

-	within 60 days following the end of the reporting period, the Coordinator shall present an interim report or, if unable to do so, it shall inform the Contracting Authority of the reasons and provide a summary of progress of the Action;

-	if at the end of the reporting period the part of the expenditure actually incurred which is financed by the Contracting Authority is less than 70 ϋ/ΰ of the previous payment (and 100 ϋ/ΰ of any previous payments), the further pre-financing payment shall be reduced by the amount corresponding to the difference between the 70 ϋ/ΰ of the previous prefinancing payment and the part of the expenditure actually incurred which is financed by the Contracting Authority;

-	the Coordinator may submit a request for further pre-financing payment before the end of the reporting period, when the part of the expenditure actually incurred which is financed by the Contracting Authority is more than 70 0/ΰ of the previous payment (and 100 0/ΰ of any previous payments). In this case, the following reporting period starts anew from the end date of the period covered by this payment request;

-	in addition, for grants of more than EUR 5 000 000, a further pre-financing payment may be made only if the part financed by the Contracting Authority of the of eligible costs approved is at least equal to the total amount of all the previous payments excluding the last one;

-	the total sum of pre-financing payments may not exceed 90 % of the amount referred to in Article 3.2 of the Special Conditions, excluding not authorised contingencies;

(iii)	the balance of the final amount of the grant.

Option 3: All Actions

(i)	the balance of the final amount of the grant.

Submission of final reports

15.2	The Coordinator shall submit the final report to the Contracting Authority no later than three months after the implementation period as defined in Article 2 of the Special Conditions. The deadline for submission of the final report is extended to six months where the Coordinator does not have its headquarters in the country where the Action is implemented.

Payment request

15.3	The payment request shall be drafted using the model in Annex V and shall be accompanied by:

a)	a narrative and financial report in line with Article 2;

b)	a forecast budget for the following reporting period in case of request of further pre-financing;

c)	an expenditure verification report or a detailed breakdown of expenditure if required under Article 15.7;

For the purposes of the initial pre-financing payment, the signed contract serves as payment request. A financial guarantee shall be attached if required in the Special Conditions.

Payment shall not imply recognition of the regularity or of the authenticity, completeness and correctness of the declarations and information provided.

Payment deadlines

15.4	Initial pre-financing payments shall be made within 30 days of receipt of the payment request by the Contracting Authority.

Further pre-financing payments and payments of the balance shall be made within 60 days of receipt of the payment request by the Contracting Authority.

However, further pre-financing payments and payments of the balance shall be made within 90 days of receipt of the payment request by the Contracting Authority in any of the following cases:

a)	one Beneficiary with affiliated entity(ies);

b)	if more than one Beneficiary is part to this Contract;

c)	if the Commission is not the Contracting Authority

d)	for grants exceeding EUR 5 000 000

The payment request is deemed accepted if there is no written reply by the Contracting Authority within the deadlines set above.

Suspension of the period for payments

15.5	Without prejudice to Article 12, the Contracting Authority may suspend the time-limits for payments by notifying the Coordinator that:

a)	the amount indicated in its request of payments is not due, or;

b)	proper supporting documents have not been supplied, or;

c)	the Contracting Authority needs to request clarifications, modifications or additional information to the narrative or financial reports, or;

d)	the Contracting Authority needs to carry out additional checks, including on-the- spot checks to make sure that the expenditure is eligible or;

e)	it is necessary to verify whether presumed substantial errors, irregularities, fraud have occurred in the grant award procedure or the implementation of the Action.

f)	it is necessary to verify whether the Beneficiary(ies) have breached any substantial obligations under this Contract.

The suspension of the time-limits for payments starts when the above notification is sent by the Contracting Authority to the Coordinator. The time-limit starts running again on the date on which a correctly formulated request for payment is recorded. The Coordinator shall provide any requested information, clarification or document within 30 days of the request.

If, notwithstanding the information, clarification or document provided by the Coordinator, the payment request is still inadmissible, or if the award procedure or the implementation of the grant proves to have been subject to substantial errors, irregularities, fraud, or breach of obligations, then the Contracting Authority may refuse to proceed further with payments and may, in the cases foreseen in Article 12, terminate accordingly this Contract.

In addition, the Contracting Authority may also suspend payments as a precautionary measure without prior notice, prior to, or instead of, terminating this Contract as provided for in Article 12.

Interest on late payment

15.6	If the Contracting Authority pays the coordinator after the time limit, it shall pay default interest as follows:

a)	at the rediscount rate applied by the central bank of the country of the Contracting Authority if payments are in the currency of that country;

b)	at the rate applied by the European Central Bank to its main refinancing transactions in euro, as published in the Official Journal of the European Union, C series, if payments are in euro,

on the first day of the month in which the time-limit expired, plus three and a half percentage points. The interest will be payable for the time elapsed between the expiry of the payment deadline and the date on which the Contracting Authority's account is debited.

By way of exception, when the interest calculated in accordance with this provision is lower than or equal to EUR 200, it will be paid to the Coordinator only upon demand submitted within two months of receiving late payment.

The default interest is not considered as income for the purposes of Article 17.2.

This Article 15.6 does not apply if the coordinator is a European Union Member State, including regional and local government authorities or other public body acting in the name and on behalf of the Member State for the purpose of the Contract.

Expenditure verification report

15.7	The Coordinator must provide an expenditure verification report for:

a)	any request for further pre-financing payment in case of grants of more than EUR 5 000 000;

b)	any final report in the case of a grant of more than EUR 100 000.

The expenditure verification report shall conform to the model in Annex VII and shall be produced by an auditor approved or chosen by the Contracting Authority. The auditor shall meet the requirements set out in the Terms of Reference for expenditure verification in Annex VII.

The auditor shall examine whether the costs declared by the Beneficiary(ies) and the revenue of the Action are real, accurately recorded and eligible under this Contract. The expenditure verification report shall cover all expenditure not covered by any previous expenditure verification report.

If no expenditure verification is required, a detailed breakdown of expenditure covering the preceding reporting periods not already covered, shall be provided for every other request for further pre-financing payment and starting with the second request for further pre-financing payment (i.e. 3rd, 5th,7th... pre-financing payment).

The detailed breakdown of expenditure should provide the following information for each cost heading in the financial report and for all underlying entries and transactions: amount of the entry or transaction, accounting reference (e.g. ledger, journal or other relevant reference) description of the entry or transaction (detailing the nature of the expenditure) and reference to underlying documents (e.g. invoice number, salary slip or other relevant reference), in line with Article 16.1. It shall be provided in electronic form and spread sheet format (excel or similar) whenever possible.

The detailed breakdown of expenditure shall be supported by a declaration of honour by the Coordinator that the information in the payment request is full, reliable and true and that the costs declared have been incurred and can be considered as eligible in accordance to this Contract.

The final report shall in all cases include a detailed breakdown of expenditure covering the whole Action.

Where the Coordinator is a government department or a public body, the Contracting Authority may accept to substitute the expenditure verification with a detailed breakdown of expenditure.

The expenditure verification report shall not be provided by the Coordinator if the verification is directly done by the Contracting Authority's own staff, by the Commission or by a body authorised to do so on their behalf, according to Article of 5.2 of the Special Conditions.

Financial guarantee

15.8	If the grant exceeds EUR 60 000 the Contracting Authority may request a financial guarantee for the amount of the initial pre-financing payment.

The guarantee shall be denominated in euro or in the currency of the Contracting Authority, conforming to the model in Annex VIII and, unless the Contracting Authority agrees otherwise, provided by an approved bank or financial institution established in one of the Member States of the European Union. This guarantee shall remain in force until its release by the Contracting Authority when the payment of the balance is made.

This provision shall not apply if the Coordinator is a non-profit organisation, an organisation which has signed a framework partnership agreement with the European Commission, a government department or public body, unless otherwise stipulated in the Special Conditions.

Rules for currency conversion

15.9	The Contracting Authority shall make payments to the Coordinator to the bank account referred to in the financial identification form in Annex V, which allows the identification of the funds paid by the Contracting Authority. The Contracting Authority shall make payments in euro or in the currency of the country to which it belongs, in accordance with the currency set in the Special Conditions.

Reports shall be submitted in the currency set out in the Special Conditions, and may be drawn from financial statements denominated in other currencies, on the basis of the Beneficiary(ies)'s applicable legislation and applicable accounting standards. In such case and for the purpose of reporting, conversion into the currency set in the Special Conditions shall be made using the rate of exchange at which the Contracting Authority 's contribution was recorded in the Beneficiary(ies)'s accounts, unless otherwise provided for in the Special Conditions.

Costs incurred in other currencies than the one used in the Beneficiary(ies)'s accounts shall be converted using the monthly Inforeuro on the date of payment or according to its usual accounting practices if so provided for in the Special Conditions.

In the event of an exceptional exchange-rate fluctuation, the Parties shall consult each other with a view to amending the Action in order to lessen the impact of such a fluctuation. Where necessary, the Contracting Authority may take additional measures such as terminating the Contract.

Article 16 — Accounts and technical and financial checks

Accounts

16.1	The Beneficiary(ies) shall keep accurate and regular accounts of the implementation of the Action using an appropriate accounting and double-entry book-keeping system.

The accounts:

a)	may be an integrated part of or an adjunct to the Beneficiary(ies)'s regular system;

b)	shall comply with the accounting and bookkeeping policies and rules that apply in the country concerned;

c)	shall enable income and expenditure relating to the Action to be easily traced, identified and verified.

16.2	The coordinator shall ensure that any financial report as required under Article 2 can be properly and easily reconciled to the accounting and bookkeeping system and to the underlying accounting and other relevant records. For this purpose the Beneficiary(ies) shall prepare and keep appropriate reconciliations, supporting schedules, analyses and breakdowns for inspection and verification.

Right of access

16.3	The Beneficiary(ies) shall allow verifications to be carried out by the European Commission, the European Anti-Fraud Office, the European Court of Auditors and any external auditor authorised by the Contracting Authority. The Beneficiary(ies) have to take all steps to facilitate their work.

16.4	The Beneficiary(ies) shall allow the above entities to:

a)	access the sites and locations at which the Action is implemented;

b)	examine its accounting and information systems, documents and databases concerning the technical and financial management of the Action;

c)	take copies of documents;

d)	carry out on the-spot-checks;

e)	conduct a full audit on the basis of all accounting documents and any other document relevant to the financing of the Action;

16.5	Additionally the European Anti-Fraud Office shall be allowed to carry out on-the-spot checks and inspections in accordance with the procedures laid down by the European Union legislation for the protection of the financial interests of the European Union against fraud and other irregularities.

Where appropriate, the findings may lead to recovery by the Commission.

16.6	Access given to agents of the European Commission, European Anti-Fraud Office and the European Court of Auditors and to any external auditor authorised by the Contracting Authority carrying out verifications as provided for by this Article as well as by Article 15.7 shall be on the basis of confidentiality with respect to third parties, without prejudice to the obligations of public law to which they are subject.

Record keeping

16.7	The Beneficiary(ies) shall keep all records, accounting and supporting documents related to this Contract for five years following the payment of the balance and for three years in case of grants not exceeding EUR 60 000, and in any case until any on-going audit, verification, appeal, litigation or pursuit of claim has been disposed of.

They shall be easily accessible and filed so as to facilitate their examination and the Coordinator shall inform the Contracting Authority of their precise location.

16.8	All the supporting documents shall be available in the original form, including in electronic form.

16.9. In addition to the reports mentioned in Article 2, the documents referred to in this Article include:

a)	Accounting records (computerised or manual) from the Beneficiary(ies)'s accounting system such as general ledger, sub-ledgers and payroll accounts, fixed assets registers and other relevant accounting information;

b)	Proof of procurement procedures such as tendering documents, bids from tenderers and evaluation reports;

c)	Proof of commitments such as contracts and order forms;

d)	Proof of delivery of services such as approved reports, time sheets, transport tickets, proof of attending seminars, conferences and training courses (including relevant documentation and material obtained, certificates) etc.;

e)	Proof of receipt of goods such as delivery slips from suppliers;

f)	Proof of completion of works, such as acceptance certificates;

g)	Proof of purchase such as invoices and receipts;

h)	Proof of payment such as bank statements, debit notices, proof of settlement by the contractor;

i)	Proof that taxes and/or VAT that have been paid cannot actually be reclaimed;

j)	For fuel and oil expenses, a summary list of the distance covered, the average consumption of the vehicles used, fuel costs and maintenance costs;

k)	Staff and payroll records such as contracts, salary statements and time sheets. For local staff recruited on fixed-term contracts, details of remuneration paid, duly substantiated by the person in charge locally, broken down into gross salary, social security charges, insurance and net salary. For expatriate and/or European- based staff (if the Action is implemented in Europe) analyses and breakdowns of expenditure per month of actual work, assessed on the basis of unit prices per verifiable block of time worked and broken down into gross salary, social security charges, insurance and net salary.

Article 17 — Final amount of the grant

Final amount

17.1	The grant may not exceed the maximum ceiling in Article 3.2 of the Special Conditions either in terms of the absolute value or the percentage stated therein.

If the eligible costs of the Action at the end of the Action are less than the estimated eligible costs as referred to in Article 3.1 of the Special Conditions, the grant shall be limited to the amount obtained by applying the percentage laid down in Article 3.2 of the Special Conditions to the eligible costs of the Action approved by the Contracting Authority.

17.2	In addition and without prejudice to its right to terminate this Contract pursuant to Article 12, if the Action is not implemented or is implemented poorly, partially or late, the Contracting Authority may, by a duly reasoned decision and after allowing the Beneficiary to submit its observations, reduce the initial grant in line with the actual implementation of the Action and in accordance with the terms of this Contract.

No profit

17.3	The grant may not produce a profit for the Beneficiary(ies), unless specified otherwise in Article 7 of the Special Conditions. Profit is defined as a surplus of the receipts over the eligible costs approved by the Contracting Authority when the request for payment of the balance is made.

17.4	The receipts to be taken into account are the consolidated receipts on the date on which the payment request for the balance is made by the Coordinator that fall within one of the two following categories:

a)	income generated by the action, unless otherwise specified in the Special conditions;

b)	financial contributions specifically assigned by the donors to the financing of the same eligible costs financed by this Contract. Any financial contribution that may be used by the Beneficiary(ies) to cover costs other than those eligible under this contract or that are not due to the donor where unused at the end of the action are not to be considered as a receipt to be taken into account for the purpose of verifying whether the grant produces a profit for the Beneficiary(ies).

17.5	In case of an operating grant, amounts dedicated to the building up of reserves shall not be considered as a receipt.

17.6	Where the final amount of the grant determined in accordance with the Contract would result in a profit, it shall be reduced by the percentage of the profit corresponding to the final Union contribution to the eligible costs approved by the Contracting Authority.

17.7	The provisions in Article 17.3 shall not apply to:

a)	actions the objective of which is the reinforcement of the financial capacity of a beneficiary, if specified in Article 7 of the Special Conditions;

b)	actions which generate an income to ensure their continuity beyond the end of this Contract, if specified in Article 7 of the Special Conditions;

c)	other direct support paid to natural persons in most need, such as unemployed persons and refugees, if specified in Article 7 of the Special Conditions;

d)	study, research or training scholarships paid to natural persons;

e)	grants of EUR 60 000 or less.

Article 18 — Recovery

Recovery

18.1	If any amount is unduly paid to the Coordinator, or if recovery is justified under the terms of this Contract, the Coordinator undertakes to repay the Contracting Authority these amounts.

18.2	In particular, payments made do not preclude the possibility for the Contracting Authority to issue a recovery order following an expenditure verification report, an audit or further verification of the payment request.

18.3	If a verification reveals that the methods used by the Beneficiary(ies) to determine unit costs, lump sums or flat-rates are not compliant with the conditions established in this Contract and, therefore an undue payment has been made, the Contracting Authority shall be entitled to recover proportionately up to the amount of the unit costs, lump sums or flat rate financing.

18.4	The Coordinator undertakes to repay any amounts paid in excess of the final amount due to the Contracting Authority within 45 days of the issuing of the debit note, the latter being the letter by which the Contracting Authority requests the amount owed by the Coordinator.

Interest on late payments

18.5	Should the Coordinator fail to make repayment within the deadline set by the Contracting Authority, the Contracting Authority may increase the amounts due by adding interest:

a)	at the rediscount rate applied by the central bank of the country of the Contracting Authority if payments are in the currency of that country;

b)	at the rate applied by the European Central Bank to its main refinancing transactions in euro, as published in the Official Journal of the European Union, C series, where payments are in euros;

on the first day of the month in which the time-limit expired, plus three and a half percentage points. The default interest shall be incurred over the time which elapses between the date of the payment deadline set by the Contracting Authority, and the date on which payment is actually made. Any partial payments shall first cover the interest thus established.

Offsetting

18.6	Amounts to be repaid to the Contracting Authority may be offset against amounts of any kind due to the Coordinator, after informing it accordingly. This shall not affect the Parties' right to agree on payment in instalments.

Other provisions

18.7	The repayment under Article 18.4 or the offsetting under Article 18.7 amount to the payment of the balance.

18.8	Bank charges incurred by the repayment of amounts due to the Contracting Authority shall be borne entirely by the Coordinator.

18.9	The guarantee securing the pre-financing may be invoked in order to repay any amount owed by the Beneficiary(ies), and the guarantor shall not delay payment nor raise objections for any reason whatsoever.

18.10	Without prejudice to the prerogative of the Contracting Authority, if necessary, the European Union may, as donor, proceed itself to the recovery by any means.

# ANNEX A3
Budget

The Administration of Georgia, the Ministry of Labour, Health and Social Affairs (hereinafter referred to as the BC) represented by MsTea Sturua, Head of Employment Programmes Department and the BC P r o j e c t   L e a d e r

of the one part,

And the Administration of the Slovak Republic, Regional Development Agency Senec-Pezinok (hereinafter referred to as the Member State) represented by Ms. Luba Pavlovova, Director, who entrusts the implementation of the project to Mr. Branislav Ondrus, State Secretary and MS  P r o j e c t  L e a d e r

of the other part,

HAVE AGREED ON THE FOLLOWING BUDGET:

BUDGET TEMPLATE: BREAKDOWN OF COSTS

| Action to be undertaken under the Twinning project |  |  |  | Responsibility |  | Cost |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | BC | MS | Unit cost | No of units | Total MS costs | BC Co - financing |
| 1. | Resident Twinning Advisor Remuneration |  |  |  |  |  |  |  |  |
|  | RTA Mr Borbély-Pecze Tibor Bors |  |  |  |  |  |  |  |  |
| Basic salary |  |  |  |  | x | 4 393,31 | 18 | 79 079,58 |  |
| 6% of salary and non wage labour costs |  |  |  |  | x | 263,60 | 18 | 4 744,77 |  |
| Total RTA remuneration |  |  |  |  |  |  |  | 83 824,35 |  |
| 2. | Resident Twinning Advisor Allowances |  |  |  |  |  |  |  |  |
| Daily allowances (50%) |  |  |  |  | x | 87,00 | 549 | 47 763,00 |  |
| Allowances for RTA for first 30 days |  |  |  |  | x | 174,00 | 30 | 5 220,00 |  |
| Health and accident insurance for RTA |  |  |  |  | x | 200,00 | 18 | 3 600,00 |  |
| Accommodation |  |  |  |  | x | 1 100,00 | 17 | 18 700,00 |  |
| Estate Agent’s Fee |  |  |  |  | x | 1 100,00 | 1 | 1 100,00 |  |
| Travel to and from place of duty - RTA |  |  |  |  | x | 250,00 | 2 | 500,00 |  |
| Monthly allowance for special economically return trips |  |  |  |  | x | 550,00 | 17 | 9 350,00 |  |
| Total RTA allowances |  |  |  |  |  |  |  | 86 233,00 |  |
| 3. | RTA Training |  |  |  |  |  |  |  |  |
| Return fare Budapest - Brussels |  |  |  |  | x | 350,00 | 1 | 350,00 |  |
| 3 per diems BE |  |  |  |  | x | 232,00 | 2 | 464,00 |  |
| Total RTA Training |  |  |  |  |  |  |  | 814,00 |  |
| 4. | RTA Assistants salary (RTA assistant and RTA translator/interpreter), 2 persons x 18 months x 1000 Eur |  |  |  |  |  |  |  |  |
| RTA-Assistant salary (See ceilings established per country) |  |  |  |  | x | 1 200,00 | 18 | 21 600,00 |  |
| Interpreter/linguist for the project |  |  |  |  | x | 1 250,00 | 18 | 22 500,00 |  |
| Total RTA Assistant costs |  |  |  |  |  |  |  | 44 100,00 |  |
| Component 0: Overall Project Management, Kick-off and Closure Events |  |  |  |  |  |  |  |  |  |
| 0.1 Project management, including SC meetings |  |  |  |  |  |  |  |  |  |
| Participation of Lead MS PL in SC meetings - Mr Ondrus |  |  |  |  | x | 450,00 | 18 | 8 100,00 |  |
| Participation of Junior MSs PLs in SC meetings: Mr Komaromi and Mrs Kolmerova |  |  |  |  | x | 250,00 | 36 | 9 000,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 25 650,00 |  |
| Per diems: Ondrus, Komaromi, Kolmerova |  |  |  |  | x | 174,00 | 54 | 9 396,00 |  |
| Travel from Bratislava, Budapest and Prague: 1LMS PL, 2 JPLs MSs, (6SC meetings x 3 persons) |  |  |  |  | x | 550,00 | 18 | 9 900,00 |  |
| Visibility costs (e.g. preparation of visibility leaflets, brochures, communication of project results) |  |  |  |  | x | 10 000,00 | 1 | 10 000,00 |  |
| Audit certificate costs |  |  |  |  | x | 5 000,00 | 1 | 5 000,00 |  |
| 0.2 Kick-off meeting (MS PL Ondrus, JPL Komaromi JPL Kolmerova and 1 MS Expert CL4 Pavlovova) /each 2 days |  |  |  |  | x |  |  |  |  |
| Expert fees Ondrus, Pavlovova/ 4 days (class3) |  |  |  |  | x | 450,00 | 4 | 1 800,00 |  |
| Expert fees Komaromi (class1) |  |  |  |  | x | 250,00 | 2 | 500,00 |  |
| Expert fee Kolmerova (class1) |  |  |  |  | x | 250,00 | 2 | 500,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 4 200,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 8 | 1 392,00 |  |
| Travel costs from Bratislava, Budapest, Prague |  |  |  |  | x | 550,00 | 4 | 2 200,00 |  |
| Small Catering |  |  |  |  | x | 500,00 | 1 | 500,00 |  |
| Conference infrastructure: conference equipment |  |  |  |  | x | 500,00 | 1 | 500,00 |  |
| Translation |  |  |  |  | x | 12,00 | 13 | 156,00 |  |
| Interpretation (2 interpreters in booth * 0,5 day x 220 Eur) |  |  |  |  | x | 110,00 | 2,0 | 220,00 |  |
| 0.3 Closing conference (MS PL Ondrus, JPL Komaromi JPL Kolmerova and 1 MS Expert CL4 Pavlovova) /each 2 days |  |  |  |  | x |  |  |  |  |
| Expert fees Ondrus, Pavlovova/ 4 days (class3) |  |  |  |  | x | 450,00 | 4 | 1 800,00 |  |
| Expert fees Komaromi (class1) |  |  |  |  | x | 250,00 | 2 | 500,00 |  |
| Expert fee Kolmerova (class1) |  |  |  |  | x | 250,00 | 2 | 500,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 4 200,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 8 | 1 392,00 |  |
| Travel costs from Bratislava, Budapest, Prague |  |  |  |  | x | 550,00 | 4 | 2 200,00 |  |
| Small Catering |  |  |  |  | x | 500,00 | 1 | 500,00 |  |
| Conference infrastructure: conference equipment |  |  |  |  | x | 500,00 | 1 | 500,00 |  |
| Translation |  |  |  |  | x | 12,00 | 13 | 156,00 |  |
| Interpretation (2 interpreters * 0,5 day x 220 Eur) |  |  |  |  | x | 110,00 | 2,0 | 220,00 |  |
| Total Project Co-ordination Costs |  |  |  |  |  |  |  | 100 982,00 |  |
|  | PROJECT ACTIVITIES |  |  |  |  |  |  |  |  |
| COMPONENT 1: Revision of the Georgian Legal Framework of equal opportunities legislation and related to employment in line with the EU acquis and in accordance with the provisions of Annexes of the Association Agreement |  |  |  |  |  |  |  |  |  |
| Activity 1.1 Review of Georgian Equal Opportunities legislation related to employment and measure of concordance with EU Equal Opportunities legislation identified in Annexes of the Association Agreement |  |  |  |  |  |  |  |  |  |
| 4 MS experts Palikova/5days, Kubalova/5days, Tkac/5days, Palik/5days / 20days |  |  |  |  | x |  |  |  |  |
| Expert fees Kubalova, Tkac, Palik (class2) |  |  |  |  | x | 350,00 | 15 | 5 250,00 |  |
| Expert fees Palikova (class1) |  |  |  |  | x | 250,00 | 5 | 1 250,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 9 750,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 20 | 3 480,00 |  |
| Travel from Bratislava |  |  |  |  | x | 550,00 | 4 | 2 200,00 |  |
| Translation |  |  |  |  | x | 12,00 | 73 | 876,00 |  |
| Activity 1.2 Drafting a Concordance Report and recommendations for harmonisation of the Georgian legislation related to employment with the EU Equal Opportunities Directives identified in Annexes of the Association Agreement |  |  |  |  |  |  |  |  |  |
| 2 MS experts Palikova/5days, Kubalova/5days/ total 2 missions |  |  |  |  | x |  |  |  |  |
| Expert fees Palikova (class1) |  |  |  |  | x | 250,00 | 5 | 1 250,00 |  |
| Expert fees Kubalova (class2) |  |  |  |  | x | 350,00 | 5 | 1 750,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 4 500,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 10 | 1 740,00 |  |
| Travel from Bratislava |  |  |  |  | x | 550,00 | 2 | 1 100,00 |  |
| Translation |  |  |  |  | x | 12,00 | 100 | 1 200,00 |  |
| Activity 1.3 Support to legal drafting with regard to the Equal Opportunities legislation related to the employment service identified in the relevant Annexes of the Association Agreement |  |  |  |  |  |  |  |  |  |
| 4 MS experts Palikova, Kubalova, Tkac, Palik, each 10 days/2 missions each |  |  |  |  | x |  |  |  |  |
| Expert fees Palikova (class1) |  |  |  |  | x | 250,00 | 10 | 2 500,00 |  |
| Expert fees Kubalova, Tkac, Palik (class2) |  |  |  |  | x | 350,00 | 30 | 10 500,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 19 500,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 40 | 6 960,00 |  |
| Travel from Bratislava |  |  |  |  | x | 550,00 | 8 | 4 400,00 |  |
| Translation |  |  |  |  | x | 12,00 | 100 | 1 200,00 |  |
| Activity 1.4 Gap analysis of the equal treatment and non-discrimination sections of the regulations for which the ESS has competence |  |  |  |  |  |  |  |  |  |
| 2 MS experts Palikova, Kubalova, each 5 days/1 missions each |  |  |  |  | x |  |  |  |  |
| Expert fees Palikova (class1) |  |  |  |  | x | 250,00 | 5 | 1 250,00 |  |
| Expert fees Kubalova (class2) |  |  |  |  | x | 350,00 | 5 | 1 750,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 4 500,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 10 | 1 740,00 |  |
| Travel from Bratislava |  |  |  |  | x | 550,00 | 2 | 1 100,00 |  |
| Translation |  |  |  |  | x | 12,00 | 80 | 960,00 |  |
| Activity 1.5. Regulatory drafting support to the ESS in order to ensure compliance of the regulations for which it has competence with the revised Georgian Equal Opportunities legislation harmonised with EU Equal Opportunities legislation |  |  |  |  |  |  |  |  |  |
| 3 MS experts Palikova/5days/1 mission, Kubalova/10days, Palik/10 days/2 missions |  |  |  |  | x |  |  |  |  |
| Expert fees Palikova (class1) |  |  |  |  | x | 250,00 | 5 | 1 250,00 |  |
| Expert fees Kubalova, Palik (class2) |  |  |  |  | x | 350,00 | 20 | 7 000,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 12 375,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 25 | 4 350,00 |  |
| Travel from Bratislava |  |  |  |  | x | 550,00 | 5 | 2 750,00 |  |
| Translation |  |  |  |  | x | 12,00 | 90 | 1 080,00 |  |
| Total Activities Costs Component 1 |  |  |  |  |  |  |  | 119 511,00 |  |
| Component 2: The structure and functions of the ESS have been revised to reflect it expanded role in the labour market management processes, the range and quality of services provided to job-seekers have been piloted and enhanced, the internal management and administrative processes have been clearly codified |  |  |  |  |  |  |  |  |  |
| Activity 2.1.Undertake Functional Review of the SSA/ESS |  |  |  |  |  |  |  |  |  |
| 4 MS experts Lorencic/5days,Pavlovova/5 days Stefanik/5days, Kolmerova/5days |  |  |  |  | x |  |  |  |  |
| Expert fees Kolmerova, Stefanik (class1) |  |  |  |  | x | 250,00 | 10 | 2 500,00 |  |
| Expert fees Pavlovova (class3) |  |  |  |  | x | 450,00 | 5 | 2 250,00 |  |
| Expert fees Lorencic (class2) |  |  |  |  | x | 350,00 | 5 | 1 750,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 9 750,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 20 | 3 480,00 |  |
| Travel from Bratislava, Ljublana, Pague |  |  |  |  | x | 550,00 | 4 | 2 200,00 |  |
| Translation |  |  |  |  | x | 12,00 | 90 | 1 080,00 |  |
| Activity 2.2 Support to drafting an Institutional Reform Plan for the SSA/ESS |  |  |  |  |  |  |  |  |  |
| 4 MS experts Lorencic, Katuscak, Kolmerova, Pavlovova/5days Total 20 days |  |  |  |  | x |  |  |  |  |
| Expert fees Pavlovova, 5 days / 1 mission (class3) |  |  |  |  | x | 450,00 | 5 | 2 250,00 |  |
| Expert fees Lorencic, 5 days / 1 mission (class2) |  |  |  |  | x | 350,00 | 5 | 1 750,00 |  |
| Expert fees Katuscak, Kolmerova, each 5 days / 1 mission expert (class1) |  |  |  |  | x | 250,00 | 10 | 2 500,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 9 750,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 20 | 3 480,00 |  |
| Travel from Bratislava, Ljublana, Pague |  |  |  |  | x | 550,00 | 4 | 2 200,00 |  |
| Translation |  |  |  |  | x | 12,00 | 80 | 960,00 |  |
| Activity 2.3 Support to the implementation of institutional reforms within the SSA/ESS |  |  |  |  |  |  |  |  |  |
| 5 MS experts Lorencic, Pavlovova, Kolmerova, Katuscak, Kubalova/ each 10days/2 missions each |  |  |  |  | x |  |  |  |  |
| Expert fees Pavlovova (class3) |  |  |  |  | x | 450,00 | 10 | 4 500,00 |  |
| Expert fees Lorencic/10 days, Kubalova/10days (class2) |  |  |  |  | x | 350,00 | 20 | 7 000,00 |  |
| Expert fees Katuscak, Kolmerova/each 10days (class1) |  |  |  |  | x | 250,00 | 20 | 5 000,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 24 750,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 50 | 8 700,00 |  |
| Travel from Bratislava, Lubljana, Prague |  |  |  |  | x | 550,00 | 10 | 5 500,00 |  |
| Translation |  |  |  |  | x | 12,00 | 120 | 1 440,00 |  |
| Activity 2.4 Review and revision (if required) of the current procedures for registration of job-seekers and job opportunities |  |  |  |  |  |  |  |  |  |
| 3 MS experts: Eva Gellerne Lukacs, Danica Kelecinova, Kubalova / each 5 days/1 mission each |  |  |  |  | x |  |  |  |  |
| Expert fees Eva Gelerne, Kelecinova/10 days (class1) |  |  |  |  | x | 250,00 | 10 | 2 500,00 |  |
| Expert fees Kubalova/5days (class2) |  |  |  |  | x | 350,00 | 5 | 1 750,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 6 375,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 15 | 2 610,00 |  |
| Travel from Bratislava, Budapest, Lubljana |  |  |  |  | x | 550,00 | 3 | 1 650,00 |  |
| Translation |  |  |  |  | x | 12,00 | 70 | 840,00 |  |
| Activity 2.5 Introduction of new services within the ESS |  |  |  |  |  |  |  |  |  |
| 3 MS experts Lorencic, Kubalova, Katuscak/ each 10 days/2 missions |  |  |  |  | x |  |  |  |  |
| Expert fees Kubalova, Lorencic (class2) |  |  |  |  | x | 350,00 | 20 | 7 000,00 |  |
| Expert fees Katuscak (class1) |  |  |  |  | x | 250,00 | 10 | 2 500,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 14 250,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 30 | 5 220,00 |  |
| Travel from Bratislava, Ljubljana |  |  |  |  | x | 550,00 | 6 | 3 300,00 |  |
| Translation |  |  |  |  | x | 12,00 | 70 | 840,00 |  |
| Activity 2.6 Support to the further development of job-seeker counselling services |  |  |  |  |  |  |  |  |  |
| 4 MS experts Lorencic, Kubalova, Katuscak, Kolmerova/each 5days/4 missions |  |  |  |  | x |  |  |  |  |
| Expert fees Kubalova, Lorencic (class2) |  |  |  |  | x | 350,00 | 10 | 3 500,00 |  |
| Expert fees Katuscak, Kolmerova (class1) |  |  |  |  | x | 250,00 | 10 | 2 500,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 9 000,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 20 | 3 480,00 |  |
| Travel from Bratislava, Ljubljana |  |  |  |  | x | 550,00 | 4 | 2 200,00 |  |
| Interpretation - done by project language assistant |  |  |  |  | x |  |  | 0,00 |  |
| Translation |  |  |  |  | x | 12,00 | 48 | 576,00 |  |
| Activity 2.7 Development of a Procedures Manual |  |  |  |  |  |  |  |  |  |
| 3 MS experts Lorencic/5days, Kubalova/5days, Kolmerova/5days, In total 15 days in total for all experts |  |  |  |  | x |  |  |  |  |
| Expert fees Kubalova, Lorencic (class2) |  |  |  |  | x | 350,00 | 10 | 3 500,00 |  |
| Expert fees Kolmerova (class1) |  |  |  |  | x | 250,00 | 5 | 1 250,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 7 125,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 15 | 2 610,00 |  |
| Travel from Bratislava, Ljubljana |  |  |  |  | x | 550,00 | 3 | 1 650,00 |  |
| Translation |  |  |  |  | x | 12,00 | 70 | 840,00 |  |
| Activity 2.8 Development of a Quality Assurance Plan (QAP) |  |  |  |  |  |  |  |  |  |
| 2 MS experts Kubalova/5days, Pavlovova/5days, 2 missions in total |  |  |  |  | x |  |  |  |  |
| Expert fee Pavlovova (class3) |  |  |  |  | x | 450,00 | 5 | 2 250,00 |  |
| Expert fees Kubalova, (class2) |  |  |  |  | x | 350,00 | 5 | 1 750,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 6 000,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 10 | 1 740,00 |  |
| Travel from Bratislava |  |  |  |  | x | 550,00 | 2 | 1 100,00 |  |
| Translation |  |  |  |  | x | 12,00 | 40 | 480,00 |  |
| Activity 2.9 Study Visit to MS to examine the range of services provided to job-seekers and employers through employment offices |  |  |  |  |  |  |  |  |  |
| 5- working days study visit to Slovakia for 10 participants (9 +1 interpreter) of the BC project team |  |  |  |  | x |  |  |  |  |
| Per diems Slovakia for BC participants (205 * 6 overnights) |  |  |  |  | x | 205,00 | 60 | 12 300,00 |  |
| Travel costs Georgia to MS (Slovakia) |  |  |  |  | x | 500,00 | 10 | 5 000,00 |  |
| Incidental costs (at 10 per participants /day) |  |  |  |  | x | 10,00 | 60 | 600,00 |  |
| Interpreter fees |  |  |  |  | x | 200,00 | 5 | 1 000,00 |  |
| Travel costs within the member state: Slovakia |  |  |  |  | x | 600,00 | 1 | 600,00 |  |
| Translation |  |  |  |  | x | 12,00 | 30 | 360,00 |  |
| Total Activities Costs Component 2 |  |  |  |  |  |  |  | 223 036,00 |  |
| Component 3: A comprehensive Labour Market Information Management System (WorkNet Information System) has been established and is fully operational |  |  |  |  |  |  |  |  |  |
| Activity 3.1 Review of the WorkNet Information System |  |  |  |  |  |  |  |  |  |
| 4 MS experts Gero George, Pavlov, Kelecinova, Majercak each 5 days/Total 20days/4 missions |  |  |  |  | x |  |  |  |  |
| Expert fees Kelecinova (class1) |  |  |  |  | x | 250,00 | 5 | 1 250,00 |  |
| Expert fees George, Pavlov, Majercak (class2) |  |  |  |  | x | 350,00 | 15 | 5 250,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 9 750,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 20 | 3 480,00 |  |
| Train tickets from Bratislava, Budapest |  |  |  |  | x | 550,00 | 4 | 2 200,00 |  |
| Translation |  |  |  |  | x | 12,00 | 40 | 480,00 |  |
| Activity 3.2 Elaboration of a Concept Paper for upgrading the WorkNet Information System |  |  |  |  |  |  |  |  |  |
| 4 MS experts Gero George, Pavlov, Majercak/each 10 days; Vido/5days |  |  |  |  | x |  |  |  |  |
| Expert fees Vido (class1) |  |  |  |  | x | 250,00 | 5 | 1 250,00 |  |
| Expert fees Majercak, Pavlov, George (class2) |  |  |  |  | x | 350,00 | 30 | 10 500,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 17 625,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 35 | 6 090,00 |  |
| Travel from Bratislava, Budapest |  |  |  |  | x | 550,00 | 7 | 3 850,00 |  |
| Translation |  |  |  |  | x | 12,00 | 40 | 480,00 |  |
| Activity 3.3 Preparation of Terms of Reference/Technical Specifications (TS) for upgrading the WorkNet Information System |  |  |  |  |  |  |  |  |  |
| 2 MS experts George, Majercak, each 5 days/1 mission each |  |  |  |  | x |  |  |  |  |
| Expert fees George, Majercak (class2) |  |  |  |  | x | 350,00 | 10 | 3 500,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 5 250,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 10 | 1 740,00 |  |
| Travel from Bratislava, Budapest |  |  |  |  | x | 550,00 | 2 | 1 100,00 |  |
| Translation |  |  |  |  | x | 12,00 | 35 | 420,00 |  |
| Activity 3.4 Development of methodology and tools for the preparation of monthly/quarterly and annual labour market reports |  |  |  |  |  |  |  |  |  |
| 4 MS experts: Gero George, Pavlov, Majercak, Vido/ each 5days |  |  |  |  | x |  |  |  |  |
| Expert fees Vido (class1) |  |  |  |  | x | 250,00 | 5 | 1 250,00 |  |
| Expert fees Majercak, Pavlov, George (class2) |  |  |  |  | x | 350,00 | 15 | 5 250,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 9 750,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 20 | 3 480,00 |  |
| Travel from Bratislava, Budapest |  |  |  |  | x | 550,00 | 4 | 2 200,00 |  |
| Translation |  |  |  |  | x | 12,00 | 31 | 372,00 |  |
| Activity 3.5 Conducting study visit to MSs |  |  |  |  |  |  |  |  |  |
| 5- working days study visit to Slovakia and Hungary for 8 participants (7 +1 interpreter) of the BC |  |  |  |  | x |  |  |  |  |
| Per diems Slovakia for BC participants (205 * 3 overnights) |  |  |  |  | x | 205,00 | 24 | 4 920,00 |  |
| Per diems Hungary for BC participants (222 * 3 overnights) |  |  |  |  | x | 222,00 | 24 | 5 328,00 |  |
| Travel costs Georgia to MS (Slovakia) |  |  |  |  | x | 550,00 | 8 | 4 400,00 |  |
| Incidental costs participants |  |  |  |  | x | 10,00 | 60 | 600,00 |  |
| Interpreter fees |  |  |  |  | x | 200,00 | 5 | 1 000,00 |  |
| Travel costs within the member states: Slovakia |  |  |  |  | x | 500,00 | 1 | 500,00 |  |
| Travel costs within the member states: Hungary |  |  |  |  | x | 500,00 | 1 | 500,00 |  |
| Travel costs between the two MS: SK and HU |  |  |  |  | x | 500,00 | 1 | 500,00 |  |
| Translation |  |  |  |  | x | 12,00 | 30 | 360,00 |  |
| Total Activities Costs Component 3 |  |  |  |  |  |  |  | 114 625,00 |  |
| Component 4: Modern human resource management techniques have been introduced, the staff has acquired the necessary skills and experience to provide high quality services to job-seekers, and an in-house training and retraining platform has been established |  |  |  |  |  |  |  |  |  |
| Activity 4.1 Review of current Human Resource Development (HRD) policy |  |  |  |  |  |  |  |  |  |
| 3 MS experts Pavlovova, Dobesova, Lorencic/30 days in total, each 10 days/6 missions |  |  |  |  | x |  |  |  |  |
| Expert fees Pavlovova (class3) |  |  |  |  | x | 450,00 | 10 | 4 500,00 |  |
| Expert fees Lorencic, Dobesova (class2) |  |  |  |  | x | 350,00 | 20 | 7 000,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 17 250,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 30 | 5 220,00 |  |
| Travel from Bratislava, Ljublana, Kosice |  |  |  |  | x | 550,00 | 6 | 3 300,00 |  |
| Translation |  |  |  |  | x | 12,00 | 40 | 480,00 |  |
| Activity 4.2 Drafting of an HRD Manual |  |  |  |  |  |  |  |  |  |
| 3 experts: Pavlovova, Turner, Lorencic x 2 missions/in total 30days/6 missions |  |  |  |  | x |  |  |  |  |
| Expert fees Pavlovova (class3) |  |  |  |  | x | 450,00 | 10 | 4 500,00 |  |
| Expert fees Turner, Lorencic (class2) |  |  |  |  | x | 350,00 | 20 | 7 000,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 17 250,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 30 | 5 220,00 |  |
| Travel from Bratislava, Ljublana, Kosice |  |  |  |  | x | 550,00 | 6 | 3 300,00 |  |
| Translation |  |  |  |  | x | 12,00 | 70 | 840,00 |  |
| Activity 4.3 Conduct Training Needs Analysis (TNA) |  |  |  |  |  |  |  |  |  |
| 3 experts Pavlovova, Turner, Lorencic / in total 30days/6 missions |  |  |  |  | x |  |  |  |  |
| Expert fees Pavlovova (class3) |  |  |  |  | x | 450,00 | 10 | 4 500,00 |  |
| Expert fees Turner, Lorencic (class2) |  |  |  |  | x | 350,00 | 20 | 7 000,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 17 250,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 30 | 5 220,00 |  |
| Travel from Bratislava, Ljublana, Kosice |  |  |  |  | x | 550,00 | 6 | 3 300,00 |  |
| Interpretation - done by project language assistant |  |  |  |  | x |  |  |  |  |
| Translation |  |  |  |  | x | 12,00 | 30 | 360,00 |  |
| Activity 4.4 Development of Training Programme and Training Materials |  |  |  |  |  |  |  |  |  |
| 7 experts: Kubalova, Kubisova, Turner, Lorencic, Kolmerova, Katuscak, Dobesova x 1 mission/expert x 5 days each mission, in total 35days/7 missions |  |  |  |  | x |  |  |  |  |
| Expert fees Pavlovova (class3) |  |  |  |  | x | 450,00 | 5 | 2 250,00 |  |
| Expert fees Kubalova, Kubisova, Turner, Lorencic (class2) |  |  |  |  | x | 350,00 | 20 | 7 000,00 |  |
| Expert fees Katuscak, Kolmerova (class1) |  |  |  |  | x | 250,00 | 10 | 2 500,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 17 625,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 35 | 6 090,00 |  |
| Travel from Bratislava., Ljiblana, Prague, Kosice |  |  |  |  | x | 550,00 | 7 | 3 850,00 |  |
| Translation |  |  |  |  | x | 12,00 | 80 | 960,00 |  |
| Activity 4.5 Conduct formal and in-service training for the ESS staff |  |  |  |  |  |  |  |  |  |
| 7 MS experts: Kubalova, Kubisova, Lorencic, Kolmerova, Pavlovova, Ignits Györgyi, Katuscak, / 5days/1 mission; In total 35 days/7 missions |  |  |  |  | x |  |  |  |  |
| Expert fees Pavlovova (class3) |  |  |  |  | x | 450,00 | 5 | 2 250,00 |  |
| Expert fees Kubalova, Lorencic (class2) |  |  |  |  | x | 350,00 | 10 | 3 500,00 |  |
| Expert fees Kubisova,Györgyi, Katuscak, Kolmerova (class1) |  |  |  |  | x | 250,00 | 20 | 5 000,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 16 125,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 35 | 6 090,00 |  |
| Travel from Bratislava, Kosice, Ljublana, Budapest |  |  |  |  | x | 550,00 | 7 | 3 850,00 |  |
| Translation |  |  |  |  | x | 12,00 | 30 | 360,00 |  |
| Activity 4.6 Development of the Training Manual |  |  |  |  |  |  |  |  |  |
| 2 MS experts: Kubalova, Lorencic, each 5days/1 mission each |  |  |  |  | x |  |  |  |  |
| Expert fees Kubalova, Lorencic (class2) |  |  |  |  | x | 350,00 | 10 | 3 500,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 5 250,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 10 | 1 740,00 |  |
| Traval from Bratislava, Kosice, Ljublana |  |  |  |  | x | 550,00 | 2 | 1 100,00 |  |
| Translation |  |  |  |  | x | 12,00 | 60 | 720,00 |  |
| Activity 4.7 Training/retraining platform (Train the trainers) |  |  |  |  |  |  |  |  |  |
| 2 MS experts Kubalova, Pavlovova/5days each, in total 10 days |  |  |  |  | x |  |  |  |  |
| Expert fees Pavlovova (class3) |  |  |  |  | x | 450,00 | 5 | 2 250,00 |  |
| Expert fees Kubalova (class2) |  |  |  |  | x | 350,00 | 5 | 1 750,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 6 000,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 10 | 1 740,00 |  |
| Traval from Bratislava, Kosice, Ljublana |  |  |  |  | x | 550,00 | 2 | 1 100,00 |  |
| Translation |  |  |  |  | x | 12,00 | 30 | 360,00 |  |
| Total Activities Costs Component 4 |  |  |  |  |  |  |  | 216 450,00 |  |
| Component 5: The ESS has acquired the necessary tools and materials to communicate effectively its range of services to clients and potential clients |  |  |  |  |  |  |  |  |  |
| Activity 5.1 Review of current communications policies and recommendations for upgrading |  |  |  |  |  |  |  |  |  |
| 3 MS experts Veronika Cerna, Pavlovova, each 5 days |  |  |  |  | x |  |  |  |  |
| Expert fees Pavlovova (class3) |  |  |  |  | x | 450,00 | 5 | 2 250,00 |  |
| Expert fees Cerna (class1) |  |  |  |  | x | 250,00 | 5 | 1 250,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 5 250,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 10 | 1 740,00 |  |
| Travel from Bratislava |  |  |  |  | x | 550,00 | 2 | 1 100,00 |  |
| Translation |  |  |  |  | x | 12,00 | 30 | 360,00 |  |
| Activity 5.2 Support to the establishment of a Communications Unit within the ESS |  |  |  |  |  |  |  |  |  |
| 3 MS experts Cerna, Lehocka, Pavlovova each 5 days |  |  |  |  | x |  |  |  |  |
| Expert fees Pavlovova (class3) |  |  |  |  | x | 450,00 | 5 | 2 250,00 |  |
| Expert fees Cerna, Lehocka (class1) |  |  |  |  | x | 250,00 | 10 | 2 500,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 7 125,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 15 | 2 610,00 |  |
| Travel from Bratislava |  |  |  |  | x | 550,00 | 3 | 1 650,00 |  |
| Translation |  |  |  |  | x | 12,00 | 20 | 240,00 |  |
| Activity 5.3 Elaboration of communications and awareness raising Strategy and Action Plan |  |  |  |  |  |  |  |  |  |
| 3 MS experts Kolmerova, Pavlovova, Lehocka, each 5 days |  |  |  |  | x |  |  |  |  |
| Expert fees Pavlovova (class3) |  |  |  |  | x | 450,00 | 5 | 2 250,00 |  |
| Expert fees Kolmerova, Lehocka (class1) |  |  |  |  | x | 250,00 | 10 | 2 500,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 7 125,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 15 | 2 610,00 |  |
| Travel from Bratislava, Prague |  |  |  |  | x | 550,00 | 3 | 1 650,00 |  |
| Translation |  |  |  |  | x | 12,00 | 30 | 360,00 |  |
| Activity 5.4 Development and application of communications tools and materials |  |  |  |  |  |  |  |  |  |
| 3 MS experts Cerna, Kolmerova, Pavlov /each 5 days |  |  |  |  | x |  |  |  |  |
| Expert fees Pavlov (class2) |  |  |  |  | x | 350,00 | 5 | 1 750,00 |  |
| Expert fees Cerna, Kolmerova (class1) |  |  |  |  | x | 250,00 | 10 | 2 500,00 |  |
| "Twinning Management Costs" |  |  |  |  | x | 150% |  | 6 375,00 |  |
| Per diems |  |  |  |  | x | 174,00 | 25 | 4 350,00 |  |
| Travel from Bratislava, Prague |  |  |  |  | x | 550,00 | 5 | 2 750,00 |  |
| Translation |  |  |  |  | x | 12,00 | 60 | 720,00 |  |
| Activity 5.5 Conducting study visit |  |  |  |  |  |  |  |  |  |
| 5- working days study visit to Slovakia and Czech Republic for 9 participants (8 +1 interpreter) of the BC |  |  |  |  | x |  |  |  |  |
| Per diems Slovakia for BC participants (205 * 3 overnights) |  |  |  |  | x | 205,00 | 27 | 5 535,00 |  |
| Per diems Czech Republic for BC participants (230 * 3 overnights) |  |  |  |  |  | 230,00 | 27 | 6 210,00 |  |
| Travel costs Georgia to MS (Slovakia/Czech Republic) |  |  |  |  | x | 550,00 | 9 | 4 950,00 |  |
| Incidental costs (at 10 per participants /day) |  |  |  |  | x | 10,00 | 54 | 540,00 |  |
| Interpreter fees |  |  |  |  | x | 200,00 | 6 | 1 200,00 |  |
| Travel costs within the member states: Slovakia |  |  |  |  | x | 500,00 | 1 | 500,00 |  |
| Travel costs within the member states: Czech Republic |  |  |  |  | x | 500,00 | 1 | 500,00 |  |
| Travel costs between the two MS: CZ and SK |  |  |  |  | x | 500,00 | 1 | 500,00 |  |
| Translation |  |  |  |  | x | 40,00 | 10 | 400,00 |  |
| Total Activities Costs Component 5 |  |  |  |  |  |  |  | 83 600,00 |  |
| Total BC Co-financing |  |  |  |  |  |  |  |  | 0,00 |
| PROJECT SUB - TOTAL |  |  |  |  |  |  |  |  | 1 073 175,35 |
| Provision for changes in prices (at maximum 2,5 % of sub-total) |  |  |  |  |  |  |  |  | 26 824,64 |
| PROJECT TOTAL |  |  |  |  |  |  |  |  | 1 100 000,00 |

For the administration of the Member State

Ms. Luba Pavlovova, Director

Regional Development Agency

Vysoka 35

811 06 Bratislava

Slovak Republic

signature

date

For the administration of the BC

Ms. Tea Sturua

Head of Employment Programmes Department

Social Service Agency

Ministry of Labour, Health and Social Affairs of Georgia

144 Tsereteli ave

Tbilisi 0119

Georgia

signature

date

# ANNEX A4
CONTRACT AWARD PROCEDURES

Introductory remarks

As a matter of principle, Twinning projects are exclusively based on the transfer of public sector expertise and know-how to the beneficiary administration with a view to achieving a mandatory result. This entails that private sector input in the form of equipment or of services must only be included in exceptional cases, subject to due justification, and limited to an overall ceiling of EUR 5 000 in the case of equipment and to EUR 10 000 per budget item in case of services (see sections 3.6 to 3.9 of Annex A7).

Twinning projects are in other words self-contained projects centred on public sector co-operation.

The exceptionally required private sector inputs are in principle tendered by the MS partner(s), which applies the provisions described in the present Annex.

Where the MS partner(s) is a contracting authority and/or a contracting entity within the meaning of the EU Directives applicable to procurement procedures, it must apply the relevant provisions of those texts, in preference to the rules set out in sections 3 to 7 of the present Annex.

Where the MS partner(s) is not a contracting authority and/or a contracting entity within the meaning of the EU Directives applicable to procurement procedures, it must apply the rules set out in sections 3 to 7 of the present Annex.

In both cases, the general principles and rules on nationality and origin set out in sections 1 and 2 of the present Annex always apply.

An overview of the applicable rules:

Supply of goods

Up to EUR 5 000 per twinning project:

Where the MS partner(s) is a contracting authority and/or a contracting entity within the meaning of the EU Directives applicable to procurement procedures, it must apply the relevant provisions of those texts, while always respecting the rules and principles laid down in sections 1 and 2 of the present Annex.

Where MS partner(s) is not a contracting authority and/or a contracting entity within the meaning of the EU Directives applicable to procurement procedures, it may use its own procedures, while always respecting the rules and principles laid down in sections 1, 2 and 3 of the present Annex.

Examples: small equipment to ensure smooth implementation of the project (e.g. laboratory consumables or small measuring equipment)

over EUR 5 000 per Twinning project :

Such investment MUST NOTbe financed by the Twinning contract. It can be mentioned in the Budget (Annex A3)but only to signify the commitment of the BC that the relevant equipment will be available to the project.

Examples: equipment to measure air quality control, veterinary control materials.

Supply of services

Up to EUR 10 000 per budget item:

Where the MS partner(s) is a contracting authority and/or a contracting entity within the meaning of the EU Directives applicable to procurement procedures, it must apply the relevant provisions of those texts, while always respecting the rules and principles laid down in sections 1 and 2 of the present Annex.

The MS partner(s) that is not a contracting authority and/or a contracting entity within the meaning of the EU Directives applicable to procurement procedures may use its own procedures, while always respecting the rules and principles laid down in sections 1, 2 and 3 of the present Annex.

Examples: travel costs, translation and interpretation services, software, training material, expert private sector inputs to training.

Above EUR 10 000 and up to EUR 60 000 per budget item:

Where the MS partner(s) is a contracting authority and/or a contracting entity within the meaning of the EU Directives applicable to procurement procedures, it must apply the relevant provisions of those texts, while always respecting the rules and principles laid down in sections 1 and 2 of the present Annex.

Where the MS partner(s) is not a contracting authority and/or a contracting entity within the meaning of the EU Directives applicable to procurement procedures, it may use its own procedures, while always respecting the rules and principles laid down in sections 1, 2 and 3 of the present Annex.

Above EUR 60 000 per budget item:

Where the MS partner(s) is a contracting authority and/or a contracting entity within the meaning of the EU Directives applicable to procurement procedures, it must apply the relevant provisions of those texts, while always respecting the rules and principles laid down in sections 1 and 2 of the present Annex.

Where the MS partner(s) is not a contracting authority and/or a contracting entity within the meaning of the EU Directives applicable to procurement procedures, it must apply the rules set out in sections 1 to 7 of the present Annex.

Examples of possible subcontracting: RTA Assistant, translation and interpretation services, software, training material, expert private sector inputs to training.

Procurement by the Contracting Authority

Given the fact that in some instances the MS partner(s) is a public sector body not allowed to engage in commercial contracts and given the exceptional nature of private sector inputs, the MS partner(s) may ask the Contracting Authority to manage the exceptionally requested private sector inputs on its behalf. This may be appropriate especially where the contracting entails VAT charges which cannot be handled by the Member state partner(s).

If the MS partner(s) avails itself of such assistance, corresponding amounts will be included in the Budget of the Twinning contract (Annex A3) with an annotation indicating clearly that these items will be contracted and paid by the Contracting Authority.

Payments to the MS partner(s) will not include these items, which are paid directly by the Contracting Authority to the supplier(s)/service provider(s).

The Contracting Authority applies its own procurement procedures.

# General principles

If the implementation of an Action requires procurement by the Beneficiary(ies), the contract must be awarded to the most cost-effective tender (ie, the tender offering the best price-quality ratio), or, in case of works or supply contracts not involving after-sales service, the sole award criterion should be the price. Contracts must be awarded in accordance with transparency and fair competition, avoiding any conflicts of interest. Contracts must not be split artificially to circumvent procurement thresholds.

To this end, the rules set out in sections 2 to 7 below, subject to section 8, must be followed. These lay down the minimum procedures to be followed and it is not precluded that other procedures offering more competition are used.

The European Commission will carry out ex post checks on Beneficiary(ies)'s compliance with these rules. Failure to comply with these rules would render the related expenditure ineligible for EU/EDF funding.

The provisions of this Annex apply mutatis mutandis to contracts to be concluded by the Beneficiary(ies)’s affiliated entity(ies).

# Eligibility for contracts

## The nationality rule

Participation in tender procedures managed by the Beneficiary(ies) is open on equal terms to all natural and legal persons of the Member States and the States and territories of regions expressly covered and/or allowed by the Financial Regulation and the basic acts or other instruments governing the aid programme under which the grant is being financed. Tenderers must state in their tenders the country of which they are nationals by presenting the usual proof of nationality under their national legislation.

This rule does not apply to the experts proposed under service tenders financed by the grant.

## The rule of origin

If the basic act or the other applicable instruments so require, the tenderer must prove the origin of the supplies acquired under the grant. For the purpose of this annex, the term "origin" is defined in chapter 2 of Regulation (EC) No 450/2008 of the European Parliament and of the Council of 23 April 2008 laying down the EU Customs Code (Modernised Customs Code). For equipment and vehicles of a unit cost on purchase of more than EUR 5 000, contractors must present proof of origin to the Beneficiary(ies), at the latest when the first invoice is presented. The certificate of origin must be made out by the competent authorities of the country of origin of the supplies and must comply with the rules laid down by the relevant Union legislation.

## Exceptions to the rules on nationality and origin

Where an agreement on widening the market for procurement of goods, works or services applies, access must also be open to nationals and goods originating from other countries under the conditions laid down in that agreement.

In addition, in duly substantiated exceptional cases, foreseen by the applicable regulations, the European Commission may give access to nationals or goods originating from countries other than those referred to in section 2.1.

## Grounds for exclusion from participation in procurement

Candidates or tenderers will be excluded from taking part in a procurement procedure if:

they are bankrupt or being wound up, are having their affairs administered by the courts, have entered into an arrangement with creditors, have suspended business activities, are the subject of proceedings concerning those matters, or are in any analogous situation arising from a similar procedure provided for in national legislation or regulations;

they have been convicted of an offence concerning their professional conduct by a judgment which has the force of res judicata;

they have been guilty of grave professional misconduct proven by any means which the Beneficiary(ies) can justify;

they have not fulfilled obligations relating to the payment of social security contributions or the payment of taxes in accordance with the legal provisions of the country in which they are established or with those of the country of the Beneficiary(ies) or those of the country where the contract is to be performed;

they or persons having powers of representation, decision making or control over them have been the subject of a judgment which has the force of res judicata for fraud, corruption, involvement in a criminal organisation, money laundering or any other illegal activity detrimental to the EU’s financial interests;

they are currently subject to an administrative penalty referred to in section 2.3.4 of the Practical Guide to contract procedures for EC external actions.

Candidates or tenderers must certify that they are not in one of the situations listed above.

Points (1) to (4) do not apply to the purchase of supplies on particularly advantageous terms from either a supplier which is definitively winding up its business activities, or the receivers or liquidators of a bankruptcy, through an arrangement with creditors, or through a similar procedure under national law.

## Exclusion from award of contracts

Contracts may not be awarded to candidates or tenderers which, during the procurement procedure:

(a)	are subject to a conflict of interests;

(b)	are guilty of misrepresentation in supplying the information required by the Beneficiary(ies) as a condition of participation in the contract procedure or fail to supply this information.

# Common procurement rules

The tender documents must be drafted according to best international practice. If they do not have their own documents, Beneficiaries may voluntarily use the models published in the Practical Guide to EU contract procedures for EU external actions on the EuropeAid website. The European Commission will not publish notices and tender documents issued by the Beneficiary(ies).

The time-limits for applications and/or tenders must be long enough to give interested parties a reasonable period to prepare and submit their tenders.

An evaluation committee must be set up to evaluate both applications and.or tenders of a value of EUR 60 000 or more on the basis of the exclusion, selection and award criteria published by the Beneficiary(ies)in advance in the  tender documents. This committee must have an odd number of members, at least three, with all the technical and administrative capacities necessary to give an informed opinion on the tenders.

# Specific rules for service contracts

## Contracts from EUR 300 000 and above

Service contracts from EUR 300 000 and above must be awarded by means of an international restricted tender procedure following publication of a procurement notice.

The procurement notice is to be published in all appropriate media, in particular on the Beneficiary’s web site, in the international press and the national press of the country in which the Action is being carried out, or in other specialist periodicals. It must state the number of candidates which will be invited to submit tenders within a range of four to eight candidates, and must be sufficient to ensure genuine competition.

All would-be service providers fulfilling the conditions referred to in section 2 may take part but only candidates satisfying the published selection criteria and invited in writing by the Beneficiary may submit a tender.

## Contracts of less than EUR 300 000 but more than EUR 60 000

Such contracts must be awarded by means of a competitive negotiated procedure without publication, in which the Beneficiary consults at least three service providers of its choice and negotiates the terms of the contract with one or more of them.

## Contracts of EUR 60 000 or less

For services of a value of EUR 60 000 or less, the procedures established by the Beneficiary(ies) may be used, while respecting the rules and principles laid down in articles 1, 2 and 3 of this annex.

# Specific rules for supply contracts

## Contracts from EUR 300 000 and above

Supply contracts from EUR 300 000 and above must be awarded by means of an international open tender procedure following publication of a procurement notice.

The procurement notice is to be published in all appropriate media, in particular on the Beneficiary’s web site, in the international press and the national press of the country in which the Action is being carried out, or in other specialist periodicals.

Any would-be supplier which fulfils the conditions referred to in section 2 may submit a tender.

## Contracts between EUR 100 000 and less than EUR 3000 000

Such contracts are awarded by means of an open tender procedure published locally: the procurement notice is published in all appropriate media but only in the country in which the Action is being carried out.

A local open tender procedure must provide other eligible suppliers with the same opportunities as local firms.

## Contracts of less than EUR 100 000 but more than EUR 60 000

Such contracts must be awarded by means of a competitive negotiated procedure without publication, in which the Beneficiary consults at least three suppliers of its choice and negotiates the terms of the contract with one or more of them.

## Contracts of EUR 60 000 or less

For supply contracts of EUR 60 000 or less, the procedures established by the Beneficiary(ies) may be used, while respecting the rules and principles laid down in articles 1, 2 and 3 of this annex.

# Specific rules for works contracts

## Contracts from EUR 5 000 000 and above

Works contracts of EUR 5 000 000 and above must be awarded by means of an international open tender procedure following publication of a procurement notice.

The procurement notice is to be published in all appropriate media, in particular on the Beneficiary’s web site, in the international press and the national press of the country in which the Action is being carried out, or in other specialist periodicals.

Any contractor which fulfils the conditions referred to in section 2 may submit a tender.

## Contracts of between EUR 300 000 and less than EUR 5 000 000

Such contracts must be awarded by means of an open tender procedure published locally: the procurement notice is published in all appropriate media but only in the country in which the Action is being carried out.

A local open tender procedure must provide other eligible contractors with the same opportunities as local firms.

## Contracts of less than EUR 300 000 but more than EUR 60 000

Such contracts must be awarded by means of a competitive negotiated procedure without publication, in which the Beneficiary consults at least three contractors of its choice and negotiates the terms of the contract with one or more of them.

## Contracts of EUR 60 000 or less

For works contracts of EUR 60 000 or less, the procedures established by the Beneficiary(ies) may be used, while respecting the rules and principles laid down in articles 1, 2 and 3 of this annex..

# Use of negotiated procedure

The Beneficiary(ies) may decide to use the negotiated procedure on the basis of a single tender in the following cases:

(a)	for the purposes of humanitarian aid and civil protection operations or for crisis management aid. Crisis situations may be invoked only when they have been formally recognised by the European Commission. The Contracting Authority will inform the Coordinator if a crisis situation has been declared and the period for which the declaration will be in force;

(b)	where the services are entrusted to public-sector bodies or to non-profit institutions or associations and relate to activities of an institutional nature or designed to provide assistance to peoples in the social field;

(c)	where contracts extend on-going activities:

(i)	 not included in the main service contract, which have become necessary to perform the contract for unforeseen circumstances, and provided that the additional service cannot be technically and economically separated from the principal contract without serious inconvenience for the Beneficiary(ies) and the aggregate amount of additional services does not exceed 50 % of the value of the principal contract, or

(ii)	which consist in the repetition of similar services entrusted to the contractor providing services under the initial contract, provided that:

(a)	a contract notice was published for the first service and the possibility of using the negotiated procedure for new services for the project and the estimated cost were clearly indicated in the contract notice published for the first service; and

(b)	the extension of the contract for a value and duration not exceeding the value and the duration of the initial contract;

(d)	for additional deliveries by the original supplier intended either as a partial replacement of normal supplies or installations or as the extension of existing supplies or installations, where a change of supplier would oblige the Beneficiary(ies) to acquire equipment having different technical characteristics which would result in either incompatibility or disproportionate technical difficulties in operation and maintenance;

(e)	for additional works not included in the initial contract concluded which have, through unforeseen circumstances, become necessary for carrying out the works and on condition that such works cannot be technically or economically separated from the main contract without serious inconvenience for the Beneficiary(ies)  and on the condition that, although separable from the performance of the original contract, are strictly necessary for its completion and where the aggregate value of contracts awarded for additional works does not exceed 50 % of the value of the principal contract;

(f)	where the tender procedure has been unsuccessful, that is where no qualitatively and/or financially worthwhile tender has been received. In such cases, after cancelling the tender procedure, the Beneficiary may negotiate with one or more tenderers of its choice, from among those that took part in the tender procedure, provided that the initial terms of the tender procedure are not substantially altered;

(g)	where the contract concerned follows a contest and must, under the rules applying, be awarded to the winner of the contest or to one of the winners of the contest, in which case, all winners shall be invited to participate in the negotiations;

(h)	where, for technical reasons, or for reasons connected with the protection of exclusive rights, the contract can be awarded only to a particular service provider;

(i)	where warranted by the nature or particular characteristics of the supplies, for example, where performance of the contract is exclusively reserved for the holders of patents or licences to use patents;

(j)	where the orders are placed with a humanitarian central buying office, recognised as such by the relevant service of the European Commission;

(k)	for the issue of the expenditure verification report and the financial guarantee where they are required under the Contract;

(l)	for contracts declared to be secret, or for contracts whose performance must be accompanied by special security measures or when the protection of the essential interests of the European Union or the beneficiary country so requires;

(m)	for contracts in respect of supplies quoted and purchased on a commodity market;

(n)	for contracts in respect of purchases on particularly advantageous terms, either from a supplier which is definitively winding up its business activities, or from the receivers or liquidators of a bankruptcy, an arrangement with creditors, or a similar procedure under national law;

(o)  where a new contract has to be concluded after early termination of an existing contract.

# Special cases

Different rules than those specified in this annex may apply in the following cases, with the exception of the principles described in section 1 and the rules on nationality and origin provided for in section 2, which always apply.

## Co-financing

When the Action is co-financed by several donors and one of the other donors, whose contribution is greater than that of the European Commission, imposes procurement rules on the Beneficiary(ies) that differ from those set out in sections 3 to 7, the Beneficiary(ies) may apply these rules.

## Public administrations of the Member States

Where the Beneficiary(ies) or an affiliated entity is a contracting authority and/or a contracting entity within the meaning of the EU Directives applicable to procurement procedures, it must apply the relevant provisions of those texts, in preference to the rules set out in sections 3 to 7. In all cases, the general principles and rules on nationality and origin set out in section 2 still apply

## International Organisations

Where the Beneficiary(ies) or an affiliated entity is an international organisation, it applies its own procurement rules if they offer guarantees equivalent to internationally accepted standards. If they do not or in specific cases, the European Commission and the Beneficiary will agree on the use of other procurement procedures offering such guarantees.

If allowed by the applicable regulatory provisions of the European Union, the origin of the goods and the nationality of the organisations, companies and experts selected for carrying out activities in the Action shall be determined in accordance with the Organisation’s relevant rules.  In any event goods, organisations, companies and experts eligible under the applicable regulatory provisions of the European Union shall be eligible.

In all other cases the partners, contractors, experts and goods, the cost of which are financed out of the Contracting Authority’s contribution, shall originate in the European Union or the country or countries eligible under the programme of which the Action is part. Any departure from the rules of origin and nationality set out above is subject to the specific provisions of the applicable regulatory provisions of the European Union.

## Traditional Agencies

Where the Beneficiary(ies) or an affiliated entity is a traditional agency (public legal entities created by the Union legislator to exercise Union competences is specific areas of expertise), it applies its own procurement rules.

## Central Buying Offices

Where the Beneficiary(ies) uses a central buying office as service provider, he selects it in conformity with the procedures set out above for service contracts.

A central buying office mentioned under point 7 (j) is a non-profit making, autonomous and professional structure, specialised in the technical and commercial management of supplies.

This central buying office applies the rules imposed on the Beneficiary. Where it is a humanitarian central buying office recognised as such by the European Commission (see http://ec.europa.eu/echo/partners/humanitarian_aid/procurement_en.htm), it applies the rules agreed upon at the time of its approval.

## Framework Partnership Agreements with Humanitarian Organisations

Where the Beneficiary(ies) or an affiliated entity has concluded a Framework Partnership Agreement with the European Commission for Humanitarian Aid & Civil Protection and the controls applicable at the time of signature of the present contract follows the "P" control mechanism, it may use the procurement rules recognised under this mechanism.

# ANNEX A5
Request for payment for Twinning Contract
European Union external actions

[Date of the payment request]

For the attention of

[address of the Contracting Authority]

[Financial unit indicated in the Contract]

Reference number of the Twinning Contract:

Title of the Twinning Contract:

Name and address of the [Lead] Member State Partner:

Payment request for number:

Period covered by the request for payment

Dear Sir/Madam,

I hereby request <a pre-financing payment/payment of the balance] > under the Twinning Contract mentioned above.

The amount requested is <according to the Option indicated in Article 4(1) of the Special Conditions of the Contract/the following: ...>.

Please find attached the following supporting documents:

-	<technical and financial interim report [for further pre-financing payments]>

-	<a forecast budget for the subsequent reporting period [for further pre-financing payments]>

- 	<final implementation report [for payment of the balance]>.

-	<expenditure verification report [for payment of the balance]>

The payment should be made to the following bank account: <give the account number shown on the financial identification form annexed to the Contract>

I hereby certify that the information contained in this request for payment is full, reliable and true, and is substantiated by adequate supporting documents that can be checked.

I hereby certify that the costs declared have been incurred in accordance with this Contract and that they can be considered as eligible in accordance with the Contract.

Yours faithfully,

[ signature ]

# ANNEX A6
 EXPENDITURE VERIFICATION

To be completed by the (Member State Partner (MSP) and to be agreed with the Auditor.

The Auditor must be designated in accordance with the regulation prevailing for the (Lead) MSP.

The expenditure verification report must be issued by the Auditor

# Terms of Reference for an Expenditure Verification of a Twinning contract

# – External Action of the European Union -

HOW TO USE THIS TERMS OF REFERENCE MODEL? All text highlighted in yellow in this ToR model and in Annexes1 and 2 is for instruction only and Member State Partners (MSP should remove it after use. The parts of the ToR presented in <……..> (e.g. <name of the (Lead) Member State Partner (MSP)> must be completed by the (Lead) MSP

The following are the terms of reference (‘ToR’) under which <name of the Coordinator (The term ‘Coordinator’ refers to the (Lead) Member State PartnerP)> ‘agrees to engage <name of the audit firm> (‘the Auditor’) to perform an expenditure verification and to report in connection with a European Union financed Institution Building Twinning contract concerning <title and reference number of the Twinning contract> (the ‘Twinning contract’). Where in these ToR the ‘Contracting Authority’ is mentioned, this refers to <the European Commission or name of another contracting authority> which has signed the Twinning contract with the (Lead) Member State Partner and is providing the funding. The Contracting Authority is not a party to this agreement.

# 1.1	Responsibilities of the Parties to the Engagement

In case of consortium of Member State Partners, the Member State Partner signing the Twinning contract and leading the consortium is referred to as the Lead Member State Partner.

The term “Member State Partner(s)” refers collectively to all Member State Partners (MSP), including the Lead Member State Partner.

The term “Coordinator” refers to the Lead Member State Partner.

When there is only one Member State Partner, the terms Member State Partner(s) and Coordinator should both be understood as referring to the only Member State Partner.

- The Coordinator is responsible for providing a Financial Report for the action financed by the Twinning contract which complies with the terms and conditions of the Twinning contract and for ensuring that this Financial Report reconciles to the Member State Partner(s)’s accounting and bookkeeping system and to the underlying accounts and records. The Member State Partner(s) is responsible for providing sufficient and adequate information, both financial and non-financial, in support of the Financial Report.

- The Coordinator accepts that the ability of the Auditor to perform the procedures required by this engagement effectively depends upon the Member State Partner(s) , providing full and free access to its(their)  staff and its(their) accounting and bookkeeping system and underlying accounts and records.

- The Auditor’ is responsible for performing the agreed-upon procedures as specified in these ToR. ‘Auditor’ refers to the audit firm contracted for performing this engagement and for submitting a report of factual findings to the Coordinator. ‘Auditor’ can refer to the person or persons conducting the verification, usually the engagement partner or other members of the engagement team. The engagement partner is the partner or other person in the audit firm who is responsible for the engagement and for the report that is issued on behalf of the firm, and who has the appropriate authority from a professional, legal or regulatory body.

By agreeing these ToR the Auditor confirms that he/she meets at least one of the following conditions:

- The Auditor and/or the firm is a member of a national accounting or auditing body or institution which in turn is member of the International Federation of Accountants (IFAC).

- The Auditor and/or the firm is a member of a national accounting or auditing body or institution. Although this organisation is not member of the IFAC, the Auditor commits him/herself to undertake this engagement in accordance with the IFAC standards and ethics set out in these ToR.

- The Auditor and/or the firm is registered as a statutory auditor in the public register of a public oversight body in an EU member state in accordance with the principles of public oversight set out in Directive 2006/43/EC of the European Parliament and of the Council (this applies to auditors and audit firms based in an EU Member State).

- The Auditor and/or the firm is registered as a statutory auditor in the public register of a public oversight body in a third country and this register is subject to principles of public oversight as set out in the legislation of the country concerned (this applies to auditors and audit firms based in a third country).

# 1.2	Subject of the Engagement

The subject of this engagement is the Financial Report in connection with the Twinning contract for the period covering <dd Month yyyy to dd Month yyyy> and the action entitled <title of the action>, the 'Action'.. Annex 1 to these ToR contains information about the Twinning contract.

# 1.3	Reason for the Engagement

The Coordinator is required to submit to the Contracting Authority an expenditure verification report produced by an external auditor in support of the payment requested by the Coordinator under Article 15 of the General Conditions of the Twinning contract. The Authorising Officer of the Commission requires this report because the payment of expenditure requested by the Coordinator is conditional on the factual findings of this report.

# 1.4	Engagement Type and Objective

This expenditure verification is an engagement to perform certain agreed-upon procedures with regard to the Financial Report for the Twinning Contract. The objective of this expenditure verification is for the Auditor to carry out the specific procedures listed in Annex 2A to these ToR and to submit to the Coordinator a report of factual findings with regard to the specific verification procedures performed. Verification means that the Auditor examines the factual information in the Financial Report of the Coordinator and compares it with the terms and conditions of the Twinning Contract. As this engagement is not an assurance engagement the Auditor does not provide an audit opinion and expresses no assurance. The Contracting Authority assesses for itself the factual findings reported by the Auditor and draws its own conclusions from these factual findings.

# 1.5	Standards and Ethics

The Auditor shall undertake this engagement in accordance with:

-	the International Standard on Related Services (‘ISRS’) 4400 Engagements to perform Agreed-upon Procedures regarding Financial Information as promulgated by the IFAC;

-the IFAC Code of Ethics for Professional Accountants (developed and issued by IFAC's International Ethics Standards Board for Accountants (IESBA), which establishes fundamental ethical principles for Auditors with regard to integrity, objectivity, independence, professional competence and due care, confidentiality, professional behaviour and technical standards. Although ISRS 4400 provides that independence is not a requirement for agreed-upon procedures engagements, the Contracting Authority requires that the Auditor is independent from the Member State Partner(s) and complies with the independence requirements of the IFAC Code of Ethics for Professional Accountants.

# 1.6	Procedures, Evidence and Documentation

The Auditor plans the work so that an effective expenditure verification can be performed. The Auditor performs the procedures listed in Annex 2A of these ToR (‘Listing of specific procedures to be performed’) and applies the guidelines in Annex 2B (Guidelines for specific procedures to be performed). The evidence to be used for performing the procedures in Annex 2A is all financial and non-financial information which makes it possible to examine the expenditure claimed by the Coordinator in the Financial Report. The Auditor uses the evidence obtained from these procedures as the basis for the report of factual findings. The Auditor documents matters which are important in providing evidence to support the report of factual findings, and evidence that the work was carried out in accordance with ISRS 4400 and these ToR.

# 1.7	Reporting

The report on this expenditure verification should describe the purpose, the agreed-upon procedures and the factual findings of the engagement in sufficient detail to enable the Coordinator and the Contracting Authority to understand the nature and extent of the procedures performed by the Auditor and the factual findings reported by the Auditor.

The use of the Model Report for an Expenditure Verification of an EU Twinning Contract in Annex 3 of these ToR is compulsory. This report should be provided by the Auditor to <name of the Coordinator>within <xx; number of working days to be indicated by the Coordinator> working days after the day of signature of these ToR.

# 1.8	Other Terms

The fee for this engagement shall be <fee amount and currency>

[The Coordinator may want to agree a fixed fee for the engagement or otherwise. The Coordinator and the Auditor may want to agree specific terms if the Auditor needs to extend the verification coverage from 65% to 85%. The Coordinator should specify any reimbursable expenses and allowances (e.g. travelling, other) agreed with the Auditor and whether VAT and/or other relevant taxes are included in the fees/expenses.]

[The Coordinator and the Auditor can use this section to agree any other specific terms]

Annex 1	Information about the Twinning Contract

Annex 2A	Listing of specific procedures to be performed

Annex 2B	Guidelines for specific procedures to be performed

Annex 3	Model report for an expenditure verification of an EU Twinning contract

| For the Member State Partner: Signature <name and function> <date> | For the Auditor: Signature <name and unction> <date> |
| --- | --- |

## Annex 1: Information about the Twinning Contract

[Annex to be completed by the Coordinator]

| Information about the Twinning Contract |  |
| --- | --- |
| Reference number and date of the Twinning contract | < Contracting Authority’s reference of the Twinning contract> |
| Twinning contract title |  |
| Country |  |
| Member State Partner(s) | < full name and address of the Member State Partner(s) as per the Twinning contract> |
| Steering Committee opinion – date |  |
| Start date of the implementation period of the Action |  |
| End date of the implementation period of the Action |  |
| Total cost of the Action | <amount in Art. 3.1 of the Special Conditions of the Twinning contract> |
| Grant maximum amount | <amount in Art. 3.2 of the Special Conditions of the Twinning contract> |
| Total amount received to date by Coordinator from Contracting Authority | < Total amount received as per dd.mm.yyyy> |
| Total amount of the payment request | < provide the total amount requested for payment as per Annex A5 to the Special Conditions for Twinning contracts ((payment request for a Twinning contract) > |
| Contracting Authority | <Provide the name, position/title, phone and E-mail of the contact person at the Contracting Authority>. [To be completed only if the Contracting Authority is not the Commission. ] |
| European Commission | < provide the name, position/title, phone and E-mail of the contact person in the Delegation of the European Union in the country concerned, or if applicable at Headquarters> |
| Auditor | < Name and address of the audit firm and names/positions of the auditors> |

Annex 2A	Listing of Specific Procedures to be performed

[This Annex is a standard listing of specific procedures to be performed and it shall not be modified]

- General Procedures

## 2..1	Terms and Conditions of the Twinning Contract

The Auditor:

- obtains an understanding of the terms and conditions of the Twinning Contract by reviewing the Twinning Contract and its annexes and other relevant information, and by inquiry of Coordinator;

- Obtains a copy of the original Twinning Contract (signed by the Coordinator and the Contracting Authority) with its annexes;

- obtains and reviews the Report (which includes a narrative and a financial section) as per Article 2.1 of the General Conditions;

- verifies whether the Twinning Contract is signed with one single Member State Partner or with a consortium of Member State Partners (in this case the term 'Coordinator' is used);

- Note: the purpose of this procedure is for the Auditor to understand the Member State Partner(s)  responsibilities for reporting and access to staff and documents.

The Twinning Manual a	nd its Annexes provide important information for Twinning contracts (e.g. basic rules and award procedures). Where necessary or useful reference will be made to the Twinning Manual and /or its annexes.

The Twinning Manual and its Annexes can be found at:

[IPA: http://ec.europa.eu/enlargement/tenders/twinning/index_en.htm]

[ENPI: http://ec.europa.eu/europeaid/where/neighbourhood/overview/twinning_en.htm]

## 2.2	Financial Report for the Twinning Contract

The Auditor verifies that the Financial Report complies with the following conditions of Article 2 of the General Conditions of the Twinning Contract:

-	The Financial Report must conform to the model in Annex C5 of the Common Twinning Manual;

-	The Financial Report should cover the Action as a whole, regardless of which part of it is financed by the Contracting Authority;

-	The Financial Report should be drawn up in the language of the Twinning Contract;

-	The proof of the transfers of ownership of equipment, vehicles and supplies for which the purchase cost was more than EUR 5 000 per time (Article 7.5 of the General Conditions of the Twinning Contract) as well as the respective certificate of origin (Annex A4 of the Twinning contract) should be annexed to the final Financial Report.

## 2.3	Rules for Accounting and Record keeping

The Auditor examines – when performing the procedures listed in this Annex - whether the Member State Partner(s) have complied with the following rules for accounting and record keeping of Article 16 of the General Conditions of the Twinning Contract:

-	The accounts kept by the Member State Partner(s) for the implementation of the Action must be accurate and up-to-date;

-	The Member State Partner(s) must have a double-entry book-keeping system;

-	The accounts and expenditure relating to the Action must be easily identifiable and verifiable;

## 2.4	Reconciling the Financial Report to the Member State Partner(s) Accounting System and Records

The Auditor reconciles the information in the Financial Report to the Member State Partner(s) ‘'s (MSP) accounting system and records (e.g. trial balance, general ledger accounts, sub ledgers etc.).

## 2.5	Exchange Rates

The Auditor verifies that amounts of expenditure incurred in a currency other than the Euro have been converted at the exchange rate published in InforEuro for the month in which the expenditure is incurred, applicable according to Article 7.2.12 of the Special Conditions of the Twinning Contract:

By derogation from to Article 15.9 of the General Conditions of Annex A2, costs incurred in other currencies are converted in Euro at the rate published by the Directorate General of the European Commission for Budget, at InforEuro (http://ec.europa.eu/budget/inforeuro/index.cfm) for the month in which the expenditure is incurred.

2.6	Simplified Cost Options

- As provided for in the Twinning Manual, the Twinning contract includes a system of simplified costs in the form of unit costs (fee per day worked in the Beneficiary Country and per diems) and flat-rate financing (twinning management costs and 6% of salary and non-wage labour costs for the RTA).

- In respect of these simplified costs, the Auditor obtains an understanding of the conditions set out in:

-	Article 2.1.c) of the General Conditions. This Article stipulates that in case of simplified cost options the Report for the Action (narrative and financial) shall provide the qualitative and quantitative information needed to demonstrate the fulfilment of the conditions for reimbursement established in the Special Conditions;

-	Section 5 of the Twinning Manual, in particular sections 5.4, 5.6 and 5.8 thereof.

Accordingly, the Auditor performs the specific procedures related to verification of simplified costs options that are set out at 4.1.(2) below.

- Procedures to verify conformity of Expenditure with the Budget and Analytical Review

## 3.1	Budget of the Twinning Contract

The Auditor carries out an analytical review of the expenditure headings in the Financial Report.

The Auditor verifies that the budget in the Financial Report corresponds with the budget of the Twinning Contract (authenticity and authorisation of the initial budget) and that the expenditure incurred was indicated in the budget of the Twinning Contract.

## 3.2	Amendments to the Budget of the Twinning Contract

The Auditor verifies whether there have been amendments to the budget of the Twinning Contract. Where this is the case the Auditor verifies that the Coordinator has:

-	requested an amendment to the budget and obtained an addendum to the Twinning Contract if such an addendum was required (Article 9 of the General Conditions as derogated and complemented by section 6.6 of the Twinning Manual and Annex A7 to the Twinning contract).

-	notified the Contracting Authority about the amendment if the amendment was limited (section 6.6 of the Twinning Manual and Annex A7 to the Twinning contract) and an addendum to the Twinning Contract was not required.

- Procedures to verify selected Expenditure

## 4.1	Eligibility of Costs

The Auditor verifies, for each expenditure item selected, the eligibility criteria set out below.

(1)	Costs actually incurred (Article 14.1 of the General Conditions)

The Auditor verifies that the actual expenditure for a selected item was incurred by and pertains to the Member State Partner(s). The Auditor should take into account the detailed conditions for actual costs incurred as set out in Article 14.1.(i) to (iii). For this purpose the Auditor examines supporting documents (e.g. invoices, contracts) and proof of payment. The Auditor also examines proof of work done, goods received or services rendered and he/she verifies the existence of assets if applicable.

At final reporting stage the costs incurred during the implementation period but not yet  paid can be accepted as actual costs incurred, provided that  (1) a liability exists (order, invoice or equivalent) for services rendered or goods supplied during the implementation period of the action, (2) the final costs are known and (3) these costs are listed in the final Financial Report (Annex C5 to the Twinning Manual) together with the estimated date of payment (see Article 14.1.a).(ii) of the General Conditions). The Auditor verifies whether these cost items have effectively been paid at the moment of the auditor's verification.

(2)	Simplified cost options (Section 5 of the Twinning Manual, in particular sections 5.4, 5.6 and 5.8 thereof, and Article 14.3 to 14.5 of the General Conditions as derogated by Article 7.2.6.of the Special Conditions)

As provided for in the Twinning Manual, the Twinning contract includes a system of simplified costs in the form of unit costs (fee per day worked in the Beneficiary Country and per diems) and flat-rate financing (twinning management costs and 6% of salary and non-wage labour costs for the RTA). In this respect, the Auditor verifies:

-	to which (sub)cost-headings and/or cost items (Annex A3 (Budget) of the Twinning contract) this system of simplified costs apply;

-	which amounts, unit costs and flat-rates have been contractually agreed (Annex A3 (Budget) of the Twinning Contract);

-	which quantitative and/or qualitative information was used to determine and justify the declared costs (e.g. number of staff, number of items purchased; type of costs and activities financed by unit costs);

-	whether the maximum amounts of simplified cost options for each Member State Partner are not exceeded, in accordance with the conditions established in the Contract;

-	the plausibility (i.e. necessity, reasonableness, reality) of the quantitative and qualitative information related to the declared costs;

-	that the costs covered by unit costs and/or flat-rates are not included (no double funding) in other direct costs, either actual or under simplified cost options;

-	that the total costs stated in the Financial Report have been correctly determined;

Note: the Auditor is not required to verify the actual costs on which unit costs and/or flat-rates are based.

(3)	Cut-off - Implementation period (Article 14.1a of the General Conditions)

The Auditor verifies that the expenditure for a selected item was incurred during the implementation period of the Action. An exception is made for costs relating to final reports including expenditure verification report, which may be incurred after the implementation period of the Twinning contract.

(4)	Budget (Article 14.1b of the General Conditions)

The Auditor verifies that the expenditure for a selected item was indicated in the Action budget.

(5)	Necessary (Article 14.1c of the General Conditions)

The Auditor verifies whether it is plausible that the expenditure for a selected item was necessary for the implementation of the Action and that it had to be incurred for the contracted activities of the Action by examining the nature of the expenditure with supporting documents, notably in line with the provisions of the Common Twinning Manual.

(6)	Records (Article 14.1d of the General Conditions)

The Auditor verifies that expenditure for a selected item is recorded in the Member State Partner(s) accounting system and was recorded in accordance with the applicable accounting standards of the country where the Member State Partner(s) is established and the Member State Partner(s) usual cost accounting practices.

(7)	Applicable legislation (Article 14.1.e of the General Conditions)

The Auditor verifies that expenditure complies with the requirements of tax and social security legislation where this is applicable (for example: employers part of taxes, pension premiums and social security charges).

(8)	Justified (Article 14.1e of the General Conditions)

The Auditor verifies that expenditure for a selected item is substantiated by evidence (see section 1 of Annex 2B, Guidelines for Specific Procedures to be performed) and supporting documents as specified in the Annexes to the Twinning contract, in the CommonTwinning Manual and in Article 161., 16.2, 16.7, 16.8 and 16.9 of the General Conditions of the Twinning Contract.

(9)	Valuation

The Auditor verifies that the monetary value of a selected expenditure item agrees with underlying documents (e.g. invoices, salary statements) and that correct exchange rates are used where applicable.

(10)	Classification

The Auditor examines the nature of the expenditure for a selected item and verifies that the expenditure item has been classified under the correct (sub)heading of the Financial Report.

(11)	Compliance with Procurement, Nationality and Origin Rules

Where applicable the Auditor examines which procurement, nationality and origin rules apply for a certain expenditure (sub)heading, a class of expenditure items or an expenditure item. The Auditor verifies whether the expenditure was incurred in accordance with such rules by examining the underlying documents of the procurement and purchase process. Where the Auditor finds issues of non-compliance with procurement rules, he/she reports the nature of such issues as well as their financial impact in terms of ineligible expenditure. When examining procurement documentation the Auditor takes into account the risk indicators listed in Annex 2B and he/she reports, if applicable, which of these indicators were found.

## 4.2	Eligibility of Direct Costs (Article 14.2 of the General Conditions)

(1)	The Auditor verifies that expenditure for selected items which are recorded under one of the direct costs headings of the Financial Report, are covered by the direct costs as defined in Article 14.2 by examining the nature of these expenditure items.

(2)	The Auditor verifies that duties, taxes and charges, including VAT which are recorded under direct costs are not recoverable by the Member States Partner(s) (see Article 14.2.g) of the General Conditions). This procedure is not necessary in case Article 7.1 of the Special Conditions provides that duties, taxes and charges, including VAT are not eligible.

The Auditor obtains evidence that the Member States Partner(s) cannot reclaim the duties, taxes or charges, including VAT through an exemption system and/or a refund a posteriori. For this purpose the Auditor should refer to Annex E3a1to the PRAG (Information on the tax regime) which provides information on the tax regime applicable to grant contracts (Note: the standard template / text is annexed to the PRAG and it can be found at

http://ec.europa.eu/europeaid/prag/getAnnex.do?annexId=1425).

## 4.3	Provisions for changes in prices

The Auditor verifies that provisions for changes in prices do not exceed 2.5% of the total eligible costs (direct and indirect) of the Action (sections 5.6.3 of the Common Twinning Manual).

## 4.4	In kind contributions (Article 14.8 of the General Conditions)

The Auditor verifies that the costs in the Financial Report do not include contributions in kind. Any contributions in kind (these should be listed separately in Annex A3 (Budget of the Twinning contract), do not represent actual expenditure and are not eligible costs.

4.5	Non-eligible costs (Article 14.9 of the General Conditions)

The Auditor verifies that the expenditure for a selected item does not concern an ineligible cost as described in Article 14.9 of the General Conditions. These costs include inter alia currency exchange losses.

## 4.6	Revenues of the Action

The Auditor examines whether the revenues which should be attributed to the Action (including grants and funding received from other donors and other revenue generated by the Member State Partner(s) in the context of the Action have been allocated to the Action and disclosed in the Financial Report. For this purpose the Auditor inquires with the Member State Partner(s) and examines documentation obtained from the Member State Partner(s). The Auditor is not expected to examine the completeness of the revenues reported.

Annex 2B	Guidelines for Specific Procedures to be performed

[This Annex provides standard guidelines for the specific procedures to be performed and these guidelines must not be modified]

- Verification Evidence

When performing the specific procedures listed in Annex 2A, the Auditor may apply techniques such as inquiry and analysis, (re)computation, comparison, other clerical accuracy checks, observation, inspection of records and documents, inspection of assets and obtaining confirmations.

The Auditor obtains verification evidence from these procedures to draw up the report of factual findings. Verification evidence is all information used by the Auditor in arriving at the factual findings and it includes the information contained in the accounting records underlying the Financial Report and other information (financial and non-financial).

The contractual requirements that relate to verification evidence are:

- Expenditure should be identifiable, verifiable and recorded in the accounting records of the Member State Partner(s) (Article 14.1.d of the General Conditions of the Twinning Contract);

- The Member State Partner(s) will allow any external auditor to carry out verifications on the basis of supporting documents for the accounts, accounting documents and any other document relevant to the financing of the Action. The Member State Partner(s) give access to all documents and databases concerning the technical and financial management of the Action (Article 16.3 of the General Conditions);

- Article 16.9 of the General Conditions of the Twinning Contract provides a list of the types and nature of evidence that the Auditor will often find in expenditure verifications.

Moreover, for the purpose of the procedures listed in Annex 2A, records, accounting and supporting documents:

- shall be easily accessible and filed so as to facilitate their examination (Article 16.7 of the General Conditions);

- shall be available in the original form, including in electronic form (Article 16.8 of the General Conditions);

Guidance: records and accounting and supporting documents should be available in documentary form, whether paper, electronic or other medium (e.g. a written record of a meeting is more reliable than an oral presentation of the matters discussed. Electronic documents can be accepted only where:

-	the documentation was first received and created (e.g. an order form or confirmation) by the Member State Partner(s) in electronic form; or

-	the Auditor is satisfied that the Beneficiary uses an electronic archiving system which meets established standards (e.g. a certified system which complies with national law).

- should preferably be obtained from independent sources outside the entity (an original supplier’s invoice or contract is more reliable than an internally approved receipt note);

- which is generated internally is more reliable if it has been subject to control and approval;

- obtained directly by the Auditor (e.g. inspection of assets) is more reliable than evidence obtained indirectly (e.g. inquiry about the asset).

If the Auditor finds that the above criteria for evidence are not sufficiently met, he/she should detail this in the factual findings.

- Obtaining an understanding of the terms and conditions of the Twinning Contract (Annex 2A - procedure 1.1)

The Auditor obtains an understanding of the applicable Common Twinning Manual and of the terms and conditions of the Twinning Contract. He/she should pay particular attention to Annex 1 of the Twinning Contract (the Description of the Action), Annex 2 (General Conditions) and Annex 4 (Contract-award procedures), which provides rules for procurement (including nationality and origin rules) by grant beneficiaries in the context of Twinning. Failure to comply with these rules makes expenditure ineligible for EU financing. These procurement rules apply to all Twinning contracts but depending on the legal basis for the Twinning Contract nationality and origin rules may vary. The Auditor ensures with the Member State Partner(s) that the applicable nationality and origin rules are clearly identified and understood.

Applicable rules on nationality and origin are set out in Annex A2 to the PRAG. See:

http://ec.europa.eu/europeaid/work/procedures/implementation/index_en.htm

The rules are set out in Section 2.3.1 of the PRAG (by clicking on 2. Basic rules, then on 2.3 Eligibility criteria and other essentials).

If the Auditor finds that the terms and conditions to be verified are not sufficiently clear he/she should request clarification from the Beneficiary.

- Selecting Expenditure for Verification (Annex 2A - procedures 4.1 – 4.6)

The expenditure claimed by the Coordinator in the Financial Report is generally presented under the standard template for the Twinning Final Report (Annex C5 to the Common Twinning Manual). Expenditure headings can be broken down into expenditure subheadings.

Expenditure subheadings can be broken down into individual expenditure items or classes of expenditure items with the same or similar characteristics. The form and nature of the supporting evidence (e.g. a payment, a contract, an invoice etc.) and the way expenditure is recorded (e.g. journal entries) vary with the type and nature of the expenditure and the underlying actions or transactions. However, in all cases expenditure items should reflect the accounting (or financial) value of the underlying actions or transactions, whatever the type and nature of the action or transaction concerned.

Value should be the principal factor used by the Auditor to select expenditure items or classes of expenditure items for verification. The Auditor selects high-value expenditure items to ensure an appropriate coverage of expenditure.

- Verification Coverage of Expenditure (Annex 2A - procedures 4.1 – 4.6)

The Auditor applies the principles and criteria set out below when planning and performing the specific verification procedures for selected expenditure in Annex 2A (procedures 3.1 – 3.7).

Verification by the Auditor and verification coverage of expenditure items does not necessarily mean a complete and exhaustive verification of all the expenditure items that are included in a specific expenditure heading or subheading. The Auditor should ensure a systematic and representative verification. Depending on certain conditions (see further below) the Auditor may obtain sufficient verification results for an expenditure heading or subheading by looking at a limited number of selected expenditure items.

The Auditor may apply statistical sampling techniques for the verification of one or more expenditure headings or subheadings of the Financial Report. The Auditor examines whether ‘populations’ (i.e. expenditure subheadings or classes of expenditure items within expenditure subheadings) are suitable and sufficiently large (i.e. are made up of large numbers of items) for effective statistical sampling.

If applicable the Auditor should explain in the report of factual findings for which headings or subheadings of the Financial Report sampling has been applied, the method used, the results obtained and whether the sample is representative.

The Expenditure Coverage Ratio (‘ECR’) is the total amount of expenditure verified by the Auditor expressed as a percentage of the total amount of expenditure reported by the Coordinator in the Financial Report. This amount is reported in Annex V of the Twinning Contract.

The Auditor ensures that the overall ECR is at least 65%. If he/she finds an exception rate of less than 10% of the total amount of expenditure verified (i.e. 6.5%) the Auditor finalises the verification procedures and continues with reporting.

If the exception rate found is higher than 10% the Auditor extends verification procedures until the ECR is at least 85%. The Auditor then finalises verification procedures and continues with reporting regardless of the total exception rate found. The Auditor ensures that the ECR for each expenditure heading and subheading in the Financial Report is at least 10%.

- Procedures to verify selected Expenditure (Annex 2A - procedures 4.1 – 4.6)

The Auditor verifies the selected expenditure items by carrying out procedures 3.1 - 3.7 listed in Annex 2A and reports all the factual findings and exceptions resulting from these procedures. Verification exceptions are all verification deviations found when performing the procedures set out in Annex 2A.

The Auditor quantifies the amount of verification exceptions found and the potential impact on the EU contribution, should the Commission declare the expenditure item(s) concerned ineligible (taking into account the percentage by funding of the Commission and the impact on indirect expenditure (e.g. administrative costs, overheads)). The Auditor reports all exceptions found including those for which he/she cannot quantify the amount of the verification exception found and the potential impact on the EU contribution.

Example: if the Auditor finds an exception of EUR 1 000 with regard to procurement rules for a Twinning contract where the EU finances 60% of the expenditure and where indirect costs represent  7% of total direct eligible expenses, the Auditor reports an exception of EUR 1 000 and a financial impact of EUR 642 (EUR 1 000 x 60% x 1.07).

Specific guidance for procedure 4.1.2 (compliance with Simplified cost options)

The Auditor verifies that the Twinning management costs comply with the requirements as set forth in the Special Conditions of the Twinning contract and in section 5.8 of the Common Twinning Manual.

Specific guidance for procedure 4.1.11 (compliance with Procurement, Nationality and Origin Rules)

The Auditor verifies whether the expenditure for a selected item was incurred in accordance with the applicable procurement, nationality and origin rules by examining the underlying documents on the procurement and purchase processes (as per Annex A4). These documents relate to the opening of tenders, the assessment of the eligibility of tenderers and conformity of tenders, the evaluation of the tenders and the decisions with regard to the awarding of the contract. When examining these procurement documents the Auditor takes into account the risk indicators listed at the end of this Annex and he/she reports, if applicable, which of these indicators were identified.

Specific guidance for procedure 4.3 (Provisions for changes in prices)

The Auditor verifies that provisions for changes in prices do not exceed 2.5% of the total eligible costs (direct and indirect) of the Action (sections 5.6.3 of the Common Twinning Manual).

RISK INDICATORS PROCUREMENT

- Inconsistencies in the dates of the documents or illogical sequence of dates. Examples:

  - Offer dated after the award of contract or before the sending of the invitations to tender

  - Offer of the winning tenderer dated before the publication date of the tender or dated significantly later than offers from other tenderers

  - Tenders by different candidates all having the same date

  - Dates on documents not plausible/consistent with dates on accompanying documentation (e.g. date on the offer not plausible/consistent with the postal date on the envelope; date of a fax not plausible/consistent with the printed date of the fax machine)

- Unusual similarities in offers by candidates participating in the same tender. Examples:

  - Same wording, sentences and terminology in tenders of different tenderers

  - Same layout and format (e.g. font type, font size, margin sizes, indents, paragraph wrapping, etc.) in tenders from different tenderers

  - Similar letterhead paper or logos

  - Same prices used in tenders from different tenderers for a number of subcomponents or line items

  - Identical grammar, spelling or typing errors in tenders from different tenderers

  - Use of similar stamps and similarities in signatures

- Financial statement or other information indicating that two tenderers participating in the same tender are related or part of a same group (e.g. where financial statements are provided, the notes to the financial statements may disclose ultimate ownership of the group. Ownership information may also be found in public registers for accounts)

- Inconsistencies in the selection and award decision process. Examples:

  - Award decisions not plausible / consistent with selection and award criteria

  - Errors in the application of the selection and award criteria

  - A regular supplier of the beneficiary participates as a member of a tender evaluation committee

    - Other elements and examples indicating a risk of privileged relationship with tenderers:

  - The same tenderer (or small group of tenderers) is invited with unusual frequency to tender for different contracts

  - The same tenderer (or small group of tenderers) wins an unusually high proportion of the bids

  - A tenderer is frequently awarded contracts for different types of goods or services

  - The winning tenderer invoices additional goods not foreseen in the tender (e.g. additional spare parts invoiced without clear justification, installation costs invoiced although not provided for in the offer).

- Other documentation, issues and examples indicating a risk of irregularities:

- Use of photocopies instead of original documents

- Use of pro-forma invoices as supporting documents instead of official invoices

- Manual changes on original documents (e.g. figures manually changed, figures "tippexed" etc.)

- Use of non-official documents (e.g. letterhead paper not showing certain official and/or compulsory information such as commercial registry number, company tax number etc.)

Annex 3	Model Report for an Expenditure Verification of a Twinning Contract

HOW TO USE THIS MODEL REPORT? All text highlighted in yellow in this model report is for instruction only and auditors should remove it after use. Information requested in pointed brackets <……..> (e.g. <name of the Coordinator> must be filled in by the auditor.

<To be printed on AUDITOR'S letterhead>

Report for an Expenditure Verification of a Twinning Contract

<Title of and number of the twinning contract>

TABLE OF CONTENTS

Report of Factual Findings

1	Information about the Grant Contract

2	Procedures performed and Factual Findings

Annex 1	Financial report for the Grant Contract

Annex 2	Terms of Reference Expenditure Verification

Report of Factual Findings

<Name of contact person(s)>, <Position>

<name of the Coordinator>

<Address>

<dd Month yyyy>

Dear <Name of contact person(s)>

In accordance with the terms of reference dated <dd Month yyyy> that you agreed with us, we provide our Report of Factual Findings (“the Report”), with respect to the accompanying Financial Report for the period covering <dd Month yyyy - dd Month yyyy> (Annex 1 of this Report). You requested certain procedures to be carried out in connection with your Financial Report and the European Union financed Twinning Contract concerning <title and number of the contract>, the ‘Twinning Contract’.

Objective

Our engagement was an expenditure verification which is an engagement to perform certain agreed-upon procedures with regard to the Financial Report for the Twinning Contract between you and <the European Commission or the name of another contracting authority>the ‘Contracting Authority’. The objective of this expenditure verification is for us to carry out certain procedures to which we have agreed and to submit to you a report of factual findings with regard to the procedures performed.

Standards and Ethics

Our engagement was undertaken in accordance with:

-	International Standard on Related Services (‘ISRS’) 4400 Engagements to perform Agreed-upon Procedures regarding Financial Information as promulgated by the International Federation of Accountants (‘IFAC);

-	theCode of Ethics for Professional Accountants issued by the IFAC. Although ISRS 4400 provides that independence is not a requirement for agreed-upon procedures engagements, the Contracting Authority requires that the auditor also complies with the independence requirements of the Code of Ethics for Professional Accountants;

Procedures performed

As requested, we have only performed the procedures listed in Annex 2A of the terms of reference for this engagement (see Annex 2 of this Report).

These procedures have been determined solely by the Contracting Authority and the procedures were performed solely to assist the Contracting Authority in evaluating whether the expenditure claimed by you in the accompanying Financial Report is eligible in accordance with the terms and conditions of the Twinning Contract.

Because the procedures performed by us did not constitute either an audit or a review made in accordance with International Standards on Auditing or International Standards on Review Engagements, we do not express any assurance on the accompanying Financial Report.

Had we performed additional procedures or had we performed an audit or review of the financial statements of the Member state Partner(s) in accordance with International Standards on Auditing, other matters might have come to our attention that would have been reported to you.

Sources of Information

The Report sets out information provided to us by you in response to specific questions or as obtained and extracted from your accounts and records

Factual Findings

The total expenditure which is the subject of this expenditure verification amounts to EUR <xxxxxx>.

The Expenditure Coverage Ratio is <xx%>. This ratio represents the total amount of expenditure verified by us expressed as a percentage of the total expenditure which is the subject of this expenditure verification. The latter amount is equal to the total amount of expenditure reported by you in the Financial Report and claimed by you for deduction from the total sum of pre-financing under the Twinning Contract as per your Payment Request of <dd Month yyyy>.

We report the details of our factual findings which result from the procedures that we performed in Chapter 2 of this Report.

Use of this Report

This Report is solely for the purpose set forth above under objective.

This report is prepared solely for your own confidential use and solely for the purpose of submission by you to the Contracting Authority in connection with the requirements as set out in Article 15 of the General Conditions of the Twinning Contract. This report may not be relied upon by you for any other purpose, nor may it be distributed to any other parties.

The Contracting Authority is not a party to the agreement (the terms of reference) between you and us and therefore we do not owe or assume a duty of care to the Contracting Authority who may rely upon this expenditure verification report at its own risk and discretion. The Contracting Authority can assess for itself the procedures and findings reported by us and draw its own conclusions from the factual findings reported by us.

The Contracting Authority may only disclose this Report to others who have regulatory rights of access to it in particular the European Commission [Delete if the Commission is the Contracting Authority], the European Anti Fraud Office and the European Court of Auditors.

This Report relates only to the Financial Report specified above and does not extend to any of your financial statements.

We look forward to discussing our Report with you and would be pleased to provide any further information or assistance which may be required.

Yours sincerely

Auditors’ signature [person or firm or both, as appropriate and in accordance with company policy]

Name of Auditor signing [person or firm or both, as appropriate]

Auditors’ address [office having responsibility for the engagement]

Date of signature <dd Month yyyy>[date when the final report is signed]

# Information about the Twinning Contract

[Chapter 1 should include a brief description of the Twinning Contract and the Action, the Coordinator/Member State Partner(s) and key financial/budget information. (maximum 1 page)]

# Procedures performed and Factual Findings

We have performed the following specific procedures listed in Annex 2A of the terms of reference for the expenditure verification of the Twinning Contract ('ToR'):

1	General Procedures

2	Procedures to verify conformity of expenditure with the budget and 	nalytical review

3	Procedures to verify selected expenditure

We have applied the rules for selection of expenditure and the principles and criteria for verification coverage as set out in Annex 2B (sections 3 and 4) of the ToR for this expenditure verification.

[Explain here any difficulties or problems encountered]

The total expenditure verified by us amounts to EUR <xxxx> and is summarised in the table below. The overall Expenditure Coverage Ratio is <xx%>.

[Provide here a summary table of the Financial Report in Annex 1, presenting for each (sub) heading the total expenditure amount reported by the Coordinator, the total expenditure amount verified and the percentage of expenditure covered]

We have verified the selected expenditure as shown in the above summary table and we have carried out, for each expenditure item selected, the verification procedures specified at point 3.1 to 3.7 of Annex 2A of the ToR for this expenditure verification. We report our factual findings resulting form these procedures below.

# General Procedures

## 1.1	Terms and Conditions of the Twinning Contract

We have obtained an understanding of the terms and conditions of this Twinning Contract in accordance with the guidelines in Annex 2B (section 2) of the ToR.

[Describe factual findings and specify errors and exceptions. Procedures 4.1 - 4.6 in Annex 2A. If there are no factual findings this should be explicitly stated as follows for each procedure: 'No factual findings have arisen from this procedure'.]

## 1.2	Financial Report for the Twinning Contract

## 1.3	Rules for Accounting and Record keeping

## 1.4	Reconciling the Financial Report to the Member State Partner(s) Accounting System and Records

## 1.5	Exchange Rates

1.6	Simplified Cost Options

# Procedures to verify conformity of Expenditure with the Budget and Analytical Review

## 2.1	Budget of the Twinning Contract

## 2.2	Amendments to the Budget of the Twinning Contract

[Describe factual findings and specify errors and exceptions. Procedures 2.1 – 2.2 in  Annex 2A. If there are no factual findings this should be explicitly stated as follows for each procedure: 'No factual findings have arisen from this procedure'.]

# Procedures to verify selected Expenditure

We have reported further below all the exceptions resulting from the verification procedures specified at point 4.1– 4.6 of Annex 2A of the ToR for this expenditure verification insofar these procedures applied to the selected expenditure item.

We have quantified the amount of the verification exceptions found and the potential impact on the EU contribution, should the Commission declare the expenditure item(s) concerned ineligible (where applicable taking into account the percentage of funding of the Commission and the impact on indirect expenditure (e.g. administrative costs, overheads)). We have reported all the exceptions found including the ones for which we cannot quantify the amount or the potential impact on the EU contribution.

[Specify the  expenditure amounts / items for which exceptions (= deviations between facts and criteria) were found, and the nature of the exception – this means which of the specific condition described at point 4.1 to4.6 of Annex 2A of the ToR were not respected. Quantify the amount of verification exceptions found and the potential impact on the EU contribution, should the Commission declare the expenditure item(s) concerned ineligible]

## 3.1	Eligibility of Costs

We have verified, for each expenditure item selected, the eligibility criteria set out at procedure 3.1 in Annex 2A of the ToR for this expenditure verification.

[Describe factual findings and specify errors and exceptions. Procedure 3.1 in Annex 2A: eligibility of costs and the eligibility criteria (1) to (9). Example: we found that an expenditure amount of EUR 6 500 included in subheading 3.2 (furniture, computer equipment) of the Financial Report was not eligible. An amount of EUR 2 000 related to expenditure incurred outside the implementation period. Supporting evidence was not available for 3 transactions totalling EUR 1 200. The required procurement rules for purchases of office computers for EUR 3 300 were not respected. (Note: relevant details such as accounting record references or documents should be provided).]

## 3.2	Eligible Direct Costs (Article 14.2 of the General Conditions)

## 3.3	Provision for changes in prices (Section 5.6.3 of the Common Twinning Manual)

## 3.4	Twinning Management Costs (Section 5.8 of the Common Twinning Manual)

## 3.5	In kind contributions (Article 14.8)

## 3.6	Non-eligible costs (Article 14.9 of the General Conditions)

## 3.7	Revenues of the Action

[Describe factual findings and specify errors and exceptions. Procedures 4.2 - 4.6 in Annex 2A]

## Annex 1	Financial Report for the Twinning Contract

[Annex 1 should include the Member State Partne(s)) financial report for the Twinning Contract which is the subject of the verification. The financial report should be dated and indicate the period covered.]

## Annex 2	Terms of Reference Expenditure Verification

[Annex 2 should include a signed and dated copy of the terms of reference for the expenditure verification of this Twinning Contract including Annex 1 (information about the Twinning Contract) and Annex 2A (Listing of the specific procedures to be performed).]

# ANNEX A7
Special Financial Annex

1.  The Project Budget(Annex A3)

All Twinning contracts comprise a Twinning work plan, accompanied by a detailed budget, respectively annexes A1 and A3 to the Twinning contract. Expenditures listed in the budget must correspond to the activities listed in the Twinning work plan.

All activities foreseen in the framework of the Twinning project, irrespective of whether they are carried out under the responsibility of the BC or of the MS, should be listed. The only activities to which a sum is allocated in the budget are those for which financing is allowed from the EU programme, and those for which co-financing from the BC is provided.

Level of details in Annex A3 under IPA

Under IPA, apart from the RTA-related expenditure and other general budget items the budget presented in Annex A3 may indicate only the foreseen costs per component and per activity (see section 3.8, 'General remark' of the Twinning Manual), reflecting so the level of details of the work plan (Annex A1). The detailed breakdown of expenditures is included, at least the first six months of implementation, in the initial operative side letter signed by the Project Leaders at the same time as the contract. The successive operative side letters drafted by the Project Steering Committee on a quarterly basis include the corresponding detailed breakdown of costs (see section 4.1.1 of the Twinning Manual)

## 2.	Changes to a Twinning Contract

The work plan of a Twinning project needs to be prepared and agreed with sufficient detail before the twinning project is launched, in order to provide objective grounds for the funding requested. However, in practice, with many different activities taking place, a Twinning project is subject to all sorts of unforeseen events and may need to be adjusted in the course of implementation. A certain degree of flexibility is therefore necessary.  Changes to the mandatory results should be exceptional and duly justified and should not contradict the provisions of the respective financing decisions.

Twinning contract modifications cannot apply retroactively.

It is hereby reminded that the breakdown of costs in a Twinning budget (Annex A3) follows the logic of the work plan (Annex A1) (RTA, delivery of a seminar, expert mission on a particular topic, elaboration of training material, etc.). In other terms, the budget must follow an activity based budget format and under normal circumstances any change in the work plan will entail a corresponding change in the budget.

The following section therefore firstly details (1) the requirements for all changes to a Twinning Contract and thereafter (2) the more specific rules regarding budgetary changes.

(1)  Changes in General

Two procedures shall apply:

A.  Addenda

Substantial changes to the Twinning Contract must be formalised in an addendum signed by both MS administration and BC administration and requiring prior approval by the AO/PAO (when appropriate) or the EU Delegation (Twinning under IPA before conferral of management power without ex ante control and Twinning under ENPI, in a centralised management framework).

The following changes to a Twinning Contract require a formal addendum:

- Under IPA: the EU Acquis related to the project /Under ENPI: the relevant field of co-operation with the EU and the EU Acquis related to the project.  (Article 2 of the Work plan)

- The MS administration involved in the Twinning project as mentioned in Article 5 of the Twinning Contract

- The execution period of the contract and the implementation period of the Action. (Article 2 of the Twinning Contract)

- Mandatory results and the benchmarks to be achieved (Articles 3 and 4 of the Work plan). (for changes concerning the means used for implementation, the time schedule and dates, the identity of short term MS experts an addendum is not needed).

- Identity of the MS and BC Project Leaders, of the RTA and of component leaders (key MS experts).

- Reallocations beyond 25% of the total Twinning Budget (see below).

Under IPA, the binding opinion of the Steering Committee at Headquarters shall be requested on the above mentioned proposed changes except for the change of the BC Project Leader or for the budgetary reallocations beyond 25%.

An addendum is not required when the implementation and/or the funding of the Twinning Contract is suspended or resumed, or when the Twinning Contract is terminated. The decisions to suspend and resume the implementation and/or the funding of the Twinning Contract, or to terminate the Twinning Contract must be notified to the concerned parties as listed in Article 5 of the Special Conditions (Annex A).

As a result of the lifting of a suspension, an addendum may be required to extend the duration of the contract and, if relevant, to adapt the Twinning Contract to the new implementing conditions. The extended implementation period must however not go beyond the end of the operational implementation phase of the Financing Agreement under which the Twinning contract is funded (where there is a Financing Agreement).

Under IPA, the decision to suspend or terminate the Twinning Contract requires that the EU Delegation (in case of centralised management or after conferral of management power with ex-ante control) or the Administrative Office (after conferral of management power without ex-ante control) must request a binding opinion from Commission Headquarters (Steering Committee).

Under ENPI, when the Contracting Authority is not the European Commission, the decision to suspend or terminate the Twinning Contract requires the prior approval of the EU Delegation.

B.  Side letters

If the changes sought do not concern one of the points listed under A above, side letters suffice where there are:

- Changes which do not affect the basic purpose of the project as explained above;

- Reallocations below 25% of the total Twinning budget

- Changes concerning the identity of MS experts and Junior Project Leader

The two Project Leaders (MS and BC) can autonomously and jointly decide on a side letter, provided the principles described in the present section as well as the Twinning rules are respected. They formalise the change in the form of a side letter to the Twinning Contract, which lays down the changes and which is jointly signed by both MS and BC PL. MS PL may however delegate RTA to sign side letters on his/her behalf. The side letter is addressed to the Contracting Authority.

The duly signed side letter must be notified by a secure means of communication, so that dispatch can be proven in the event of dispute.

| Side Letters (Administrative Orders) to be notified to: | IPA centralised | IPA decentralised with ex ante control | IPA decentralised without ex-ante control | ENPI (Centralised) | ENPI (Decentralised) |
| --- | --- | --- | --- | --- | --- |
| EU Delegation | X | X |  | X | Copy |
| Administrative Office |  | X CFCE | X | Copy | X |

Changes must be notified before they can apply or be implemented: the changes will only become effective 48 hours (two working days) after the date of notification of the side letter. In duly justified cases and in agreement with the CA, the deadline can be reduced to 24 hours. Costs incurred before the side-letter comes into effect are not eligible and shall not be reimbursed.

Under IPA, constitute side letters also the documents providing full details of activities and their corresponding budgeted costs ('operative side letters' see sections 3.8, 4.1.1 and 5.1.1.1 of the Twinning Manual and Annex C15). Considering their relevance for the implementation of the project, they must be signed by the two Project Leaders, without the possibility of delegating the RTA. The initial operative side letter is signed and endorsed at the same time as the contract. For the subsequent operative side letters a duly signed copy shall be notified by a secure means of communication as shown in the table above. They can be implemented as of the sixth working day following the date of dispatch, unless the institution in receipt has comments or reservations. In case changes are required, the amended version, signed by the two Project Leaders, shall be notified again; the same terms and conditions of the original notification apply.

(2)  Changes with budgetary impact

The following principles apply to all budgetary changes whatever their impact:

- The overall budget for a Twinning project cannot be increased: existing activity(ies) must be reduced or cancelled to introduce and finance new activity(ies);

- The unit costs (fees, daily allowances, etc.) must respect the rates set in the Twinning Manual; each Twinning project must include a full-time Resident Twinning Advisor, resident in the BC for a minimum of 12 consecutive months; transfers of budgetary resources may not jeopardise this requirement.

- Introduction of a new activity must be justified by showing that it will be of real use in achieving the mandatory results; availability of funds (following savings under or cancellation of existing activities) is not sufficient to justify the introduction of new activities and/or the extension of the execution period of the Twinning contract.

- Twinning Contracts can only be modified during the execution period of the Contract.

- Modifications cannot  apply retroactively. The budget must be reallocated by addendum or side-letter before a new activity can be implemented. Costs related to activities implemented before the entry into force of the corresponding addendum or side-letter are not eligible and shall not be reimbursed.

Specific budgetary changes through addenda:

Budgetary changes are summed up after each side letter. Once the total cumulated amount of modifications reaches 25% of the total budget, any further modification (independent of its size) requires an addendum to the Twinning Contract. After such an addendum, budgetary changes can again be introduced through side letters, until the total cumulated amount of the further modifications reaches again 25% of the total budget.

Specific budgetary changes through Side letters:

- As long as the budgetary reallocations of appropriations remain under a cumulated total amount not exceeding 25% of the total budget of the Twinning contract, these changes can be introduced trough side letters. In other terms, all budgetary changes through side letters are summed until the threshold of 25% of the total budget of the Twinning contract is reached. The budget modification by which the 25% threshold is reached requires an addendum. After such an addendum, budgetary changes can again be introduced through side letters, until the total cumulated amount of the further modifications reaches again 25% of the total budget of the Twinning contract.

| Region | Signatures of the Addendum | Addendum to be submitted to: | Who decides what? | Approval of the addendum |
| --- | --- | --- | --- | --- |
| IPA centralised | The addendum is drafted and jointly signed by the signatories of the Twinning Contract (who may delegate this authority to the Project Leaders). | The Addendum is submitted for approval to the EU Delegation | The EU Delegation is entitled to agree or refuse endorsement of addenda on behalf of the Commission. It must request a binding opinion from Commission Headquarters (Steering Committee) before agreeing addenda concerning: changes to the mandatory results; change of the MS administration or mandated body; removal, addition or change of Partner MS; change of MS Project Leader; change of RTA; modification of legal duration. Addenda introducing budgetary changes once the 25% budgetary threshold is reached are approved or refused by the EU Delegation without referral to the Steering Committee at Headquarters. | Following a positive opinion from the Commission Headquarters (Steering Committee) when required, the EU Delegation endorses the Addendum and notifies it to the parties. The addendum enters into force on the date of its notification by the EU Delegation. Addenda are drawn up in three original copies: one for the MS administration, one for the BC administration and one for the EU Delegation. |
| IPA decentralised with ex ante control | The addendum is drafted and jointly signed by the signatories of the Twinning Contract (who may delegate this authority to the Project Leaders). | The Addendum is submitted for approval to the EU Delegationand to the CFCE | The EU Delegation is entitled to agree or refuse endorsement of addenda on behalf of the Commission. It must request a binding opinion from Commission Headquarters (Steering Committee) before agreeing addenda concerning: changes to the mandatory results; change of the MS administration or mandated body; removal, addition or change of Partner MS; change of MS Project Leader; change of RTA; modification of legal duration. Addenda introducing budgetary changes once the 25% budgetary threshold is reached are approved or refused by the EU Delegation without referral to the Steering Committee at Headquarters. | Following a positive opinion from the Commission Headquarters (Steering Committee) when required, the EU Delegation requests the written approval of the Addendum by the CFCE and then notifies it to the parties. The addendum enters into force on the date of its notification by the CFCE Addenda are drawn up in four original copies: one for the MS administration, one for the BC administration, one for the EU Delegation and one for the CFCE. |
| IPA decentralised without ex-ante control | The addendum is drafted and jointly signed by the signatories of the Twinning Contract (who may delegate this authority to the Project Leaders). | The Addendum is submitted for approval to the Administrative Office | The Administrative Office is entitled to agree or refuse endorsement of addenda. It must request the binding opinion of the Commission Headquarters (Steering Committee) before agreeing addenda concerning: changes to the mandatory results; change of the MS administration or mandated body; removal, addition or change of Partner MS; change of MS Project Leader; change of RTA; modification of legal duration.Addenda introducing budgetary changes once the 25% budgetary threshold is reached are approved or refused by the AO, without referral to the Steering Committee at Commission Headquarters. | Following a positive opinion from the Commission Headquarters (Steering Committee) when required, the The Administrative Office notifies approval to both MS and BC administrations by sending them their request bearing the signed acceptance of the Administrative Office. The addendum enters into force on the date of its notification by the Administrative Office. Addenda are drawn up in three original copies: one for the MS administration, one for the BC administration and one for the Administrative Office. |
| ENPI | The addendum is drafted and signed by the signatories of the Twinning Contract the signatories of the Twinning Contract can delegate authority to the Project Leaders to sign any addenda on their behalf. | The Addendum is submitted for approval to the Contracting Authority with a copy to the EU Delegation (decentralised) or to the PAO (centralised). | The Contracting Authority is entitled to agree or refuse signature of the addendum. Where the Commission is not the Contracting Authority, it is entitled to agree or refuse endorsement of the addendum. | Centralised management Once the addendum is signed by the EU Delegation (= Contracting Authority) notifies approval to both MS and BC administrations by sending them their request bearing the signed acceptance of the EU Delegation. Decentralised management Once the addendum is endorsed by the EU Delegation, the PAO (= Contracting Authority) notifies approval to both MS and BC administrations by sending them their request bearing the signed acceptance of the PAO. In both cases (centralised and decentralised management): - the addendum enters into force on the date of its notification by the Contracting Authority; - addenda are drawn up in four original copies: one for the MS administration, one for the BC administration, one for the PAO and one for the EU Delegation. Additionally, Commission Headquarters must be sent a copy of the signed addendum. |

## 3.	Eligible costs

## 3.1. Preparatory costs

Preparatory costs are not eligible inTwinning light contracts.

### 3.1.1. Reimbursement of costs arising during the preparation of the Twinning Contract and Twinning Work Plan and Budget

Twinning preparatory costs shall be reimbursed under the following cumulative conditions:

(1):

Only costs incurred by the designated MS Project Leader, the junior MS Project Leader and/or RTA (no other experts authorised) can be reimbursed.

(2):

A. Under IPA: Preparatory costs can be reimbursed for a period of maximum four months starting as from the date of the official notification of selection up to the submission of the final draft Twinning Contract for Steering Committee consultation at Commission Headquarters.

B. Under ENPI: Preparatory costs can be reimbursed when incurred within a period of maximum five months starting as from the date of the official notification of selection up to the signature of the Twinning Contract. The time span between the reception date of the first consolidated draft contract in the EU Delegation and the date of dispatch of the first consolidated reply by the EU Delegation is excluded from this five months period.

When the drafting of the Twinning Contract takes place over a period including July and/or August a maximum of 30 days can be added to the preparation time under both IPA and ENPI.

(3):

The Twinning contract must be signed and notified: if the Twinning partners fail to terminate the preparation of the Twinning Contract within the four (under IPA) /five (under ENPI) months period, or if the Twinning project/contract is cancelled before it is signed and notified, preparatory costs shall not be reimbursed, even partially.

The Commission reserves the right to shorten the aforementioned period of 4/5 months in view of specific circumstances.

The applicable ceilings for the preparatory costs are as follows:

For Twinning Contracts up to and including EUR 1 million: - Up to 6 trips to the BC - Fees for up to 20 working days in the BC - Corresponding ‘project management costs’ compensation for work outside the BC - Per diem allowance for days in the BC For Twinning Contracts over EUR 1 million: - Up to 9 trips to the BC - Fees for up to 30 working days in the BC - Corresponding ‘project management costs’ compensation for work outside the BC - Per diem allowance for days in the BC

Preparatory costs shall be reported as part of the first interim quarterly report of the Twinning contract.

### 3.1.2. Training of RTAs

RTAs are invited by the Commission to attend a training seminar at the Commission Headquarters in Brussels. Costs for travel and per diems (according to the rules laid down in section 3.3 of this Annex) to attend this training must be included in the budget of the Twinning Contract (Annex A3): either as part of the preparatory costs if the training is takes place before the start of the Twinning contract, or as part of the project costs if the training takes place after the Twinning contract has started.

When possible, attendance before taking up duties in the BC is preferable.

If the training is attended before the start of the Twinning contract, reimbursement of the corresponding costs is subject to signature and notification of the Twinning contract. If the Twinning partners fail to terminate the preparation of the Twinning Contract or if the Twinning project/contract is cancelled before it is signed and notified, these costs shall not be reimbursed.

BC Project Leaders can attend the training together with the RTA of the same project. Costs for travel and per diems can be financed by the budget of the project, unless the person concerned has attended the same training in the course of the previous three calendar years. Attendance cannot be deputised to a third person.

MS Project leaders may also attend the training seminar at Commission Headquarters, but the corresponding costs are not eligible under the Twinning contract.

## 3.2. 	Reimbursement of Staff Cost

### 3.2.1. Staff Categories and rates of reimbursement

Employment status and corresponding rate of reimbursement

1.	As a rule, MS experts (RTA and experts undertaking short and medium duration missions) will be civil servants (see sections 3.2.2 and 3.2.3)

2.	For RTAs emanating from a mandated body, the reimbursement of salary will be based on the person's actual salary plus non-wage labour costs, without any profit margin. For short and medium duration missions, please refer to section 3.2.3.1 for the respective rates.

3.	Temporary public employees may exceptionally be hired by MS administrations or mandated bodies, if there are not enough civil servants available to act as experts in Twinning projects. These experts, temporarily recruited by the administration, may only act on its behalf provided they have the necessary experience and are not subject to any conflict of interest. The contract between such experts and the recruiting administration or mandated body must clearly integrate the expert into the contracting organisation, identify the person to whom they report and who is responsible for their backup, thus attributing full responsibility for the quality of their services. The duration of the employment of temporary public employees should as a rule not be limited or should not be identical to the duration of their Twinning involvement. In practical terms, temporary employees must be contractually linked to the administration or MB for at least six months prior to the start of their assignment.

If they are contracted by an administration, reimbursement for their remuneration will be the same as for a civil servant of comparable competence and seniority.

If a mandated body contracts them, reimbursement will be based on the rate for a comparable expert from the same body.

4.	Recently retired experts (less than two years before the call for proposals) may be reactivated as temporary public agents, either by administrations or mandated bodies. Like non-statutory civil servants, they must be linked to the body responsible for a Twinning project by a contract.

Reimbursement of the salary of retired experts will be based on the above principles for temporary public employees.

Where national legislation provides for deduction of the pension amount from a public sector salary, the project will only reimburse actual salaryexpenditure of the contractor.

These provisions do not apply to the Project Leaders who must be currently working in the MS administration or mandated body (see section 2.2.1 of the Manual).

The fees and rates defined below in section 3.2.3 for the different categories of experts are compulsory. Compliance with these fees and rates is essential for the sound financial management of Twinning projects. Any departure endangers equality between the MS administrations engaging in Twinning and/or undermines Twinning as a credible instrument for targeted administrative co-operation.

5.	Member States administrations should avoid at all costs:

(a) The use of Mandated bodies involving civil servants in Twinning projects with the sole purpose of attracting the higher mandated bodies fees;

(b) The use of Mandated bodies as umbrella organisations to involve private sector experts (including private lawyers or NGO employees) hired for contractual assignments limited to their Twinning involvement, without any structural linkage to the body involved.

6.	Twinning offers hands-on, practical expertise, provided by civil service from peer administrations. To preserve this distinctive quality of Twinning it is essential that the experts proposed by the MS administrations are administrative practitioners. University scholars and professors including from public universities, researchers or private lawyers do not belong to the administrative services entrusted with legal interpretation of the acquis and must normally be excluded. Universities or research institutes may only be proposed in very exceptional cases (for instance in highly specialised and technical fields) for ad hoc Twinning mandates but not for general mandated body status.

## 3.2.2. Remuneration of the Resident Twinning Adviser (RTA)

In the framework of a Twinning light project, there is no RTA.

The RTA continues to be paid his/her normal salary by his/her home administration or mandated body in the MS concerned throughout his/her secondment.

The EU programme reimburses the payroll institution of the RTA an amount equivalent to what he/she would have received, had he/she continued to work in his/her home administration (not abroad), including related and/or connected non-wage labour costs, plus an additional 6% of the whole amount to cover the extra cost of a replacement.

The amount for reimbursement must be included in the detailed breakdown of costs and inserted in the budget, (Annex A3).

RTAs who are not statutory public sector employees, must have signed, before the deadline for the submission of proposals, a fixed-term contract with an administration or mandated body in the MS, which seconds them to the Twinning project on the same terms as civil servants. If they are hired by an administration, their remuneration must be aligned to that of civil servants of the same level and experience. If they are hired by a mandated body, their remuneration must be aligned to that of the permanent staff of the same level and experience. All their other costs will be covered by the project as though they were civil servants from the MS.

RTAs receive, where appropriate and provided they have qualifications equivalent to university level and have a good knowledge of the EU working language (English, French or German) widely spoken in the administration of the BC, an additional flat-rate allowance equal to the difference between the gross annual salary (less family allowances) paid by his/her employer plus the subsistence allowance paid by the Commission and the basic salary payable to an official of the EU Institutions of grade AD5, step 1.

RTAs receive additional allowances and reimbursement of costs including: a subsistence allowance, reimbursement for housing, health and accident insurance, school fees, travel and removal costs. These costs arising from the RTA's secondment, be they allowances or statutory reimbursements, are borne by EU funding according to a scale applying to all MS, as outlined in the Twinning Manual and detailed in the following sections.

In addition, RTAs receive, throughout the period of their secondment, a subsistence allowance equal to 50% of the per diem rate in the BC. The applicable rate is fixed at the time of the signature of the Twinning contract for its entire duration and is not subject to revision.

All costs related to the RTA must be quantified and included in the budget. Verifiable evidence of the real salary cost (wage and non-wage labour cost) to the administration must be provided in order to corroborate expenditure on salary.

Costs related to the provision of working facilities (offices, furniture, computer, telephone, fax etc.) for the RTA are covered by the host administration in the BC (see section 5.13 of the Manual).

## 3.2.2.1. Housing

RTAs are expected to find housing and register with the authorities without assistance from the Commission. They may however obtain advice from their own Embassy, the EU Delegation and the BC administration.

RTAs are reimbursed for their housing expenses in the BC within limits calculated on the basis of family size and on average rent paid for equivalent housing for Commission staff on posting to the Delegation in this country.

### Hotel accommodation

# On arrival in the BC whilst looking for a permanent accommodation, and in order to cover temporary hotel accommodation and living expenses, RTAs are entitled to receive in addition to their normal subsistence allowance:

# - an additional, full per diem for themselves; and

# - an additional half per diem for each accompanying family member.

# This provision is subject to the presentation of hotel invoice(s). It applies for a period of up to 30 days, which may be extended subject to prior approval by the AO/PAO/EU Delegation.

### Permanent accommodation

A single person or a couple is entitled to two bedrooms. For each child they are entitled to one additional room. Where a family includes more than two children, the need for the fifth and any subsequent bedrooms must be justified to the AO/PAO/EU Delegation.

Prices in the BC will vary according to local market conditions: RTAs are expected to seek value for money and to be reasonable in their expectations. While the accommodation selected may be furnished or unfurnished, RTAs may find considerable practical benefits in renting furnished accommodation.

RTAs will receive guidance as to the acceptable rental costs for different sizes of accommodation either from the EU Delegation or from the AO/PAO. This guidance will follow international standards and indicate the upper and lower margins (“bands”) of acceptable rents in the BC.

RTAs are expected to select accommodation within these pre-approved bands, for which no prior approval is required.. Rental amounts in excess of the approved bands require prior approval from the AO/PAO/EU Delegation. This will be granted only in exceptional and duly justified circumstances. No payments for accommodation shall be made if rental costs exceed the approved bands and have not been approved, and no retroactive reimbursement will be made.

The use of housing agencies is permitted but reimbursement of agency fees is limited to a maximum of two months of rent.

Housing costs are reimbursed according to actual rental costs and based on receipts for actual payments. Reimbursement is limited to only the basic rental cost. Rental deposits, household insurance and utilities costs such as water, telephone, gas, electricity etc. are borne by RTAs, as are cleaning and other domestic services.

## 3.2.2.2. Health Insurance

RTAs are obliged to contract insurance coverage, for themselves and their accompanying family members, for health care costs arising from accident or illness throughout the entire period of their secondment. The costs for such insurance are reimbursed by the project for up to EUR 200/person/month. It is the responsibility of the MS Project Leaders to ensure that RTA are adequately insured.

Where there is a bilateral agreement for social security coverage between the MS of origin and the host BC, RTAs must make use of its provisions. In this case, complementary coverage for costs not covered under the bilateral agreement and for emergency repatriation in case of accident or severe illness may be charged to the project within the ceilings set above.

Where there is no bilateral agreement on social security, the project will reimburse full coverage for health insurance covering care costs due to sickness or accident, including emergency repatriation within the ceilings set above.

The insurance coverage reimbursed by the project will not include capital indemnity in case of death or invalidity due to accident or illness. It is understood that such coverage is provided by the MS employer.

# List of items recommended to be included in the health insurance policy:

- full coverage for health care costs due to sickness and accident (in-patient and emergency out-patient)

- emergency repatriation from the country of RTA’s assignment

- transportation to medical centre

- sending of a doctor

- emergency dental care costs

- in case of death, repatriation of the body to the country of origin.

## 3.2.2.3. Schooling fees

School fees eligible for reimbursement by the project are those incurred from the first year in which schooling would be available free of charge in the home country to the last year of the child’s secondary education, the duration of this period to be in accordance with the education system in the RTA’s home country. Fees will vary according to the age of the child. Childcare costs are not eligible for reimbursement. Schooling is defined as a minimum of 16 hours of teaching per week, for a minimum period of 3 consecutive months.

Fees eligible for reimbursement are the following: enrolment fees, exam fees, transport to and from school provided by the school and itemised in the school fees, cost of books and other material required for participation in compulsory classes. Costs, which are not covered, include, for example, private transport to and from school, school meals, uniforms, after-school music or other extra-curricular classes and activities.

Where a school charges separately materials required in a compulsory class, including music, art or sports classes, these costs will be reimbursed, whereas the cost of non-compulsory school trips or after-school classes will not be reimbursed.

School fees will be reimbursed up to a ceiling of EUR 12 000 per child and per academic year. Fees above this amount may be reimbursed on a case-by-case basis and require prior approval from the AO/PAO/EU Delegation. Grounds for approval of higher fees may be: age of the child; comparable fees in international schools in the same city; lack of alternative educational options in the same city.

RTAs may claim reimbursement only for the school fees of a 'dependent child', i.e. his/her or his/her spouse’s legitimate, natural, adopted or foster child, who is actually being maintained by him/her and who moves with him/her to the country of his/her posting. This definition also applies to a child for whom an application for adoption has been lodged and the adoption procedure started. Boarding school fees in the country of origin may be charged only in very exceptional cases, and is subject to prior approval from the AO/PAO/EU Delegation.

Reimbursement will be based on itemised bills.

RTAs must provide the following information, in a document duly certified by the educational establishment in question:

-	first name and family name of each child

-	the sum incurred per child

-	the date on which payment was made by the RTA

-	the currency in which payment was made

-	the relevant academic year and the period covered (month, term, semester)

## 3.2.2.4. Travel Costs

### a) Personal travel costs to and from the BC at the beginning and at the end of the Twinning Project

RTAs will be reimbursed for themselves and for their accompanying family members the cost of an economy air ticket per person, or a first class train ticket, whichever is more appropriate and economically advantageous. If RTAs travel by car, an official quote for one of these two options must be obtained from a travel agency.

RTAs are entitled to reimbursement of travel expenses:

| (a) | for him/herself: |  |
| --- | --- | --- |
|  |  | From his/her place of recruitment to his/her place of employment at the beginning of the period of secondment; |
|  |  | From his/her place of employment to his/her place of recruitment at the end of the period of secondment. |
| (b) | for the spouse and dependent children |  |
|  |  | From the place of recruitment to the place of employment when removal takes place; |
|  |  | From the place of employment to the place of recruitment at the end of the period of secondment. |

The place of recruitment is defined as the place where the RTA performed his/her duties prior to secondment. The place of employment is defined as the place where the BC administration to which he/she is assigned is located.

### b) Annual leave

RTAs and their accompanying family members will be reimbursed the cost of an annual trip home. RTAs will be reimbursed the cost of a special economically priced return air ticket (standard economy ticket if special economically priced ticket not available for the length of stay required) or first class train ticket for themselves and for their accompanying family members according to the same rules as described under section a).

### c) Monthly travel allowance

# Only applicable if no removal of personal belongings or any other costs related to accompanying family members are charged to the project

If the RTAs have moved without spouse and/or children, and have not been reimbursed for the removal of personal effects, household contents or personal vehicle to the BC, they will be entitled to an allowance amounting to the price of a return ticket for each month, starting the second month of the secondment.

This flat-rate payment will be based on the cost of a first class rail fare or of a special economically priced air ticket, whichever is appropriate and economically more advantageous. The rate applied will be that in force on 1 January of the current year, quoted by a travel agency.

Where a whole month is not worked, the amount will be calculated in proportion to the number of days worked.

The RTA is not entitled to any extra allowance for annual leave.

### d) Proof of travel

Original proofs of travel must be provided according to national MS rules, in order for reimbursement to be made. The only two exceptions are

a)	the monthly travel allowance for RTAs who do not claim any removal costs or costs for family members and

b)	for travel by personal car, reimbursed according to the rules defined above.

## 3.2.2.5. Removal Costs

### a) General provisions

RTAs may choose to travel with the minimum of personal belongings (no charge to the project), or charge the removal of a selection of personal effects (for secondment of minimum secondment 1 year) or of their entire household contents (for secondments of minimum 2 years) to the BC. They are responsible for organising their removal and should attempt to do so in the most economical way. The guidelines for removals presuppose one complete removal, rather than a series of smaller moves, which would be more expensive. In all cases, the route selected must be the most common, most economical and shortest one.

It is the responsibility of RTAs to organise the removal so that storage costs in the BC are avoided. The project will not cover any costs arising from storage in customs warehouses. RTAs must respect the customs regulations of the host country, subject to possible exemptions (see point 3.2.2.7).

### b) Option 1: Removal of personal effects only (secondment of minimum 1 year)

RTAs seconded for at least one year may charge to the project the costs of moving their personal effects (clothes, books, stereo equipment, microwave oven, washing machine, television, video etc.) to the BC. They will be reimbursed for transport of freight up to the following limits (packaging weight is included in these figures):

RTA 		780 kg

Spouse		390 kg

Each child	195 kg

# The actual cost of transportation will be reimbursed.

Costs of transportation of personal effects exceeding the above limits, including corresponding insurance costs, will not be reimbursed,..

Costs for storage in the MS (transport to and from place of storage, insurance and rent) for furniture which is not moved to the BC may be charged to the project, with  a maximum volume of 60m³. The actual cost of storage will be reimbursed.  Costs of storage of personal effects exceeding the above limit, including corresponding insurance costs, will not be reimbursed.

### c) Option 2: Removal of complete household contents to the BC (secondment of minimum 2 years)

RTAs seconded for at least 2 years and for whom the distance between the place of recruitment and duty is at least 50km, may charge to the project the costs for the removal to the BC of their household contents (i.e. their personal effects, plus household furniture and furnishings). The removal must take place no later than six months after taking up duty.

RTAs entitled to reimbursement of the actual cost of transportation of up to 60m³ of freight.  Costs of transportation exceeding 60m³, including corresponding insurance costs, will not be reimbursed.

### d) Air vs. Surface Transport

RTAs may choose to send all or part of their belongings by surface transport, rather than by air, provided the resulting costs do not exceed air transport costs. The route selected must be the most common, most economic and shortest one.

### e) Cost of Excess Baggage

The costs for excess baggage up to 50kg, if this consists of books, papers, equipment etc. required for work purposes, may be charged to the project in connection with the first trip to the BC when taking up duty, as well as with the last trip at the end of the project, when leaving the BC.

### f) Transport of Personal Vehicle

# The project may reimburse the cost of surface transport of a personal vehicle which the RTA owns at the time of secondment.. It is the RTA’s sole responsibility to comply with any regulations associated with importing, exporting and registering a personal vehicle in the BC.

### g) Quotes

In all cases (i.e. for removals of personal effects, household contents, personal vehicle and storage costs), RTAs must obtain at least two quotes, preferably for ‘door-to-door’ delivery.

Quotes based on volume are not accepted for removal of personal effects as defined under section b) above..

### h) Insurance

The project may cover ‘all risk’ insurance costs for the transport of personal effects, household contents, and vehicles, as well as for items in storage. Insurance may be contracted with the removal/storage firm, or directly with an insurance company. Reimbursement of premiums is limited to:

# 0.625% - 1.25% of the value of personal effects transported by air

# 1.25% - 2.5% of the value of personal effects transported by road or sea

# 1.25% - 2.5% of the value of a vehicle transported by road or sea

Where the RTA chooses to move his/her entire household contents, the maximum insured value authorised to be charged to the project is EUR 150 000.

# Note:

-	The same terms apply to removals back to the home country, which must take place within three months of the end of the period of secondment.

# -	Costs resulting from any delay in the delivery of freight by any means will not be reimbursed.

-	Any dispute between RTAs and a removal/storage company, regarding any aspect of removal/storage or payment, is the sole responsibility of RTAs.

3.2.2.6  Leave Entitlement

# a)	Basic Leave Entitlement

# RTAs’ leave entitlement is aligned with that of National Experts seconded to the Commission.

All RTAs will be entitled to annual leave amounting to 2.5 working days per month of completed service i.e. 30 days per year.

# b)	Travelling Time Allowance

In addition, RTAs will receive an annual travelling time allowance proportional to the distance between their normal place of residence and their residence in the BC.

- 50 to 250 km	1 day

- 251 to 600 km	2 days

- 601 to 900 km	3 days

- 901 to 1400 km	4 days

- 1401 to 2000 km	5 days

- over 2000 km	6 days

# c)	Public Holidays

In addition, RTAs will be entitled to take leave on public holidays. The public holidays will be the same as those allowed for counterpart BC officials in the administration with which they work.

# d)	Special Leave

In addition, the RTA may, on demand, be accorded special leave:

- marriage of the RTA			4 days

- household removals of the RTA		2 days

- serious illness of spouse or child		3 days

- death of spouse or child			4 days

- serious illness or death of close relative	2 days

- birth or marriage of child			2 days.

# e)	Leave Authorisation

Leave authorisation must be obtained from the MS Project Leader in writing and in advance.

3.2.2.7 Fiscal situation of RTAs

The Resident Twinning Adviser must observe the national tax legislation of his/her home country with regard to income earned during the period of secondment in the beneficiary host country.

The possible exemptions from customs duties, import duties, taxes and other fiscal charges for the RTA are governed by the Financing Agreement signed between the Commission and the BC, which funds the Twinning project .

### 3.2.3. Project Leader, Short & Medium Term Expert Inputs

3.2.3.1. Missions of civil servants

The EU will finance the cost of short and medium term MS missions in the framework of the project. The contribution of each short or medium term expert to project activities must be specified in the Twinning work plan or, under IPA, in the pertinent operativeside letters.

Mission expenses (transport, per diem, etc.) will be reimbursed in accordance with section 3.3. Visits of MS management and support staff to the BC cannot be separately covered by the project’s budget. The financial contribution of the EU programme to the staff costs of short and medium-term missions is EUR 250/day for civil servants or acting civil servants.

3.2.3.2 Missions of staff from mandated bodies

Definition of the three expert categories and their respective rates of reimbursement

# Class 1 expert: Rate of reimbursement per day worked in BC: EUR 250

Personal experience in the implementation of institutional aspects targeted by the Twinning project: minimum 3 years.

Class 2 senior expert: Rate of reimbursement per day worked in BC: EUR 350

Personal experience in the implementation of institutional aspects targeted by the Twinning project: minimum 8 years.

Capacity to demonstrate innovative approach by abstracting from own experience and adapting to the needs, constraints and culture of the beneficiary. Experience in co-operation with non-EU countries.Capacity to communicate in one of the European Union languages widely spoken in the administration of the BC.

# Class 3 special counsellor: Rate of reimbursement per day worked in BC: EUR 450

Personal experience in the implementation of institutional aspects targeted by the Twinning project: minimum 15 years.

In addition to the above and to the qualifications expected of senior experts, special counsellors will be past or present holders of a high-level post (junior minister, head of a government department or head or chairman of a public or private sector body with a record of government work, or equivalent).

This category is strictly reserved for individuals with exceptional experience, whose contribution to the Twinning project justifies the high rating and associated costs.

Exception

Mandated bodies able to provide evidence that they cannot cover their staff’s real costs with the standard rates of reimbursement may apply for authorisation to charge up to a maximum of EUR 100 more for each category of experts. These requests must be supported by detailed documentary evidence on real salary costs according to the following mode of calculation:

The real salary costs of a mandated bodies’ expert consist of the expert’s gross annual salary plus any compulsory non-wage labour costs payable by the employer in direct connection with the expert’s salary. These annual costs must be divided by 180 in order to calculate the total actual salary costs per day.

In case that the actual salary costs per day are higher than the rates of reimbursement for the respective expert category specified above, the mandated body may apply to the Commission Headquarters for approval of the non-standard increase up to a maximum of EUR 100 more for each category. The non-standard rate may under no circumstances generate a profit.

Applications for the increased expert fee must be channelled through the respective MS’s NCP, who will certify the veracity of the financial data submitted in support of the application. If the Commission agrees to the exception, the non-standard fee level will be published in the list of mandated bodies (indicated in square brackets after the name of the mandated body). Approval of higher fee levels must be sought before presenting proposals to ensure full transparency.

Explanatory comments regarding classification of experts

For the purpose of classifying experts assigned to Twinning projects all factors will be considered together; a shortfall on one criterion may be offset by outstanding qualifications on another. In case of divergence of opinion, the Commission Headquarters have the final say regarding expert classification.

Practical Points

When calculating the costs for short and medium term staff inputs, it is important to budget for the appropriate unit number of working days and daily allowances. For example:

- 2 weeks: if an expert comes to the BC on a Sunday and leaves on a Saturday, 10 working days and 13 per diems shall be budgeted.

- 1 week: if an expert comes on a Sunday and leaves on a Friday, 5 working days and 5 per diems shall be budgeted.

- 1 week: if an expert comes on a Sunday and leaves on a Saturday, 5 working days and 6 per diems shall be budgeted.

The working days invoiced will be equal to the days actually spent working in the BC (excluding travelling time and weekends), irrespective of the exact time of arrival in and departure from the BC:

- A full working day will be counted if the expert spends at least seven working hours (excluding any break) working with the beneficiary administration in the BC.

- A half working day will be counted if the expert spends at least four working hours (excluding any break) working with the beneficiary administration in the BC.

The per diems will be equal to the number of nights spent in the BC, calculated on the basis of the actual arrival and departure dates.

Inputs in the MS Home Administration or Mandated Body

For work performed in the MS for the benefit of the Twinning project  the MS receives a financial contribution in the form of twinning management costs compensation as detailed under section 3.5.

3.3. Travel & Per Diem

### 3.3.1. Travel

- Travel costs are estimated in the budget and reimbursed upon the actually incurred cost.

- The basic rules for travel are: economy class air fare or first class train ticket, whichever is more appropriate and economically advantageous.

- Travel by car is reimbursed the price (as quoted by a travel agency) of the equivalent air or train ticket according to the rule set in the previous paragraph. Where neither air, nor rail transport is available or appropriate, travel by car is reimbursed at a rate of EUR 0.25/km (use of private car)or at actual cost (other cases). Where several experts jointly make use of a car, the reimbursement will be made only once.

- Whatever the means of transport chosen (car, plane, train, rented minibus etc.) the solution must be financially sound and economically advantageous.

- The only exception is the RTA monthly travel allowance (see section 3.2.2.4), which is calculated at the beginning of the project and is paid monthly without requiring a proof of travel.

- Visa costs are eligible for reimbursement as part of the travel costs.

For air travel the cheapest possible tariff must be applied. If the use of a reduced rate air fare requires an additional overnight stay, the expert is entitled to receive the corresponding per diem, limited to the amount of the saving on the air fare if the latter is lower than the applicable per diem rate. Where the use of a special economically priced ticket is not possible, a standard economy ticket shall be used instead.

Transport to and from the airport of the city where the expertise is to be delivered is considered as local transportation and is covered by the per diem. Exception is granted for flight departures before 7.00 and arrivals after 22.00 hours, in which case a taxi fare can be charged separately. Where inter-city travel is required to reach the airport, the rules for travel by train apply.

Travel of MS experts, including RTA, within the BC must be identified and budgeted separately. Whenever possible, the use of public transport is mandatory. In case of travel by car, the rules of reimbursement defined above shall apply.

Travel by car is under the own responsibility of the MS experts.

Under ENPI, costs for travel by BC officials from their capital to a MS or between MS (e.g. in the framework of study visits) may be eligible . Under IPA these costs are borne by the BC administration.

Costs for travel by BC officials within a MS are eligible under both IPA and ENPI.

### 3.3.2. Per Diem (for short term experts and RTAs on mission outside BC)

MS experts are entitled to an allowance (per diem) when working in the BC. The per diem covers hotel, food and local transportation costs.

Per diem rates are communicated by Commission Headquarters to National Contact Points in MS and BC as well as to other stakeholders. They are based on the list published by the United Nations, which is available on EuropeAid website, and may be adapted for the purpose of Twinning. They are maximum rates: lower rates may also be applied.

Per diem rates are generally updated twice a year, in January and July. The per diem rate will therefore vary over the lifetime of the project, depending on the moment when a mission takes place. The rate applicable for a mission is the one applicable on the first day of travel.

The number of per diems is calculated upon the number of nights spent away from the home base (no half per diems are paid).

BC staff travelling to MS in the framework of a Twinning project is entitled to per diems according to the same rules.

## 3.4. Training and Seminars

### 3.4.1. Training in the BC

Eligible costs for trainings in the BC are mainly fees of MS experts. However, fees of MS experts present in the BC for an activity that is not limited to the training should not be allocated to the budget of the training but to the budget of the activity: no additional fees or per diems can be counted in excess of what has been budgeted under the activity.

Other eligible costs for trainings may be:

- training documentation;

- interpretation (see section 3.7);

- transport for on-site visits etc.

Where (part of) the training is sub-contracted to the private sector, the MS shall apply the appropriate procurement procedures as described in Annex A4.

Costs related to participation of BC staff in the training, including transport and per diems, are paid by the BC.

### 3.4.2. Study visits in the MS and Trainee/internships for BC officials in MS Partner Administration

When planning study visits in the MS partner administration, twinning partners must apply the following principles, which may be further detailed by the Contracting Authority:

- Cost effectiveness and sound financial management;

- Direct link between the objectives defined in the Project Fiche and the planned study visit(s) ;

- Direct relevance for the participating BC officials and for the mandatory results of the Twinning project;

- Adequate and intensive follow-up of the study visit(s);

- Adequate evaluation by the BC participants and direct involvement in the activities undertaken in the framework of the study visit(s);

- Study visits to non EU MS are not eligible.

The MS Twinning partner may also propose a limited number of administrative internships in its own administration for selected BC officials. Internship may indeed contribute to the further reinforcement of the structural links between the administrations involved in the Twinning project. Internships differ from study tours not only in number of participants and duration, but also in methodology (following the MS peers in their day-to-day tasks).

Under ENPI, costs for travel by BC officials from their capital to MS or between MS may be eligible. Under IPA these costs are borne by the BC administration.

Costs for travel by BC officials within a MS are eligible under both IPA and ENPI.

Per Diem allowances for BC trainees are eligible in all countries. For traineeships of more than 2 months the per diem allowance rate is reduced by 30% as of the 3rd month.

Certain dedicated MS training institutions delivering intensive highly specialised training operate on a fee basis for any trainee; such fees are eligible. If these fees include accommodation or/and meals, the corresponding amounts must be deducted from the per diem paid to the participants in order that the total amount paid does not exceed the applicable per diem rate..

Costs for expert fees of MS experts (including transport, per diem, expert fees) accompanying study visits in MS are not eligible. These costs are covered by the twinning management costs compensation as detailed under section 3.5.

Small incidental costs may be charged to the budget and paid to the MSP(s) on a unit cost basis (maximum EUR 10 per trainee per day) and reported without supporting evidence.

## 3.5. ‘Twinning Management Costs’

The Twinning contract budget (Annex A3) must not include any expert or other fees corresponding to work performed outside the BC. This rule applies whatever is the nature of the work performed or of the expenditure incurred: preparation or follow-up of mission, accompaniment of study visit, delivery of seminars, co-ordination, logistical management (accounts) overheads or any other incidental costs.

Instead, taking the form of a global contribution to the costs arising from the preparation and implementation of a Twinning project, all fees included in the budget for short and medium-term expertise (including fees for MS PL) delivered in the BC is complemented with a compensation of 150% for Twinning  management costs. The MS organisation in charge of the Twinning project may dispose of it for covering any costs arising in the MS in connection with the project, including any related overhead costs.

The twinning management costs compensation is invariably reported by and paid as a flat rate to the MS (Lead) Partner in conjunction with any fees corresponding to work performed in the BC.

Where several MS are involved in a Twinning project, the Lead MS Partner is responsible for transferring to the other MS Partner(s) in the consortium all or a proportion of the twinning management costs compensation corresponding to their participation in the work performed in the BC.. The Lead MS Partner may retain a reasonable proportion of the Twinning management costs compensation to cover the additional work and costs incurred due to its leadership. It is important for the good implementation of the project that the consortium agreement signed between the Lead MS Partner and the other MS partner(s) involved in the project lays down clear and precise modalities in this respect. The members of the consortium elaborate this agreement independently without advice or interference from BC administration or Commission services.

In the Budget (Annex A3) and within each activity, every budget item corresponding to fees for work performed in the BC is immediately followed by a budget item entitled ‘twinning management costs compensation’ and quantified at 150% of the preceding item.. These amounts are indicative: payment will be based on the actual number of days of work performed in the BC.

## 3.6. Intangible supplies and provision of services

Such items as development or purchase of computer software, provision of documentation, translation of texts, private interpreters and similar fall under this category and should be included in the budget of the Twinning contract (Annex A3).

Rules and limitations applicable to the provision of these services are detailed in section 3.8 (provision of translation and interpretation) and in section 3.10 (private sector inputs).

## 3.7. RTA Assistant

RTAs should be assisted by a full-time project assistant for providing translation and interpretation services on a daily basis, and for performing general project duties. Only in very exceptional cases should the requirement for an assistant be waived.

In most cases the costs of the RTA assistant are funded by the Twinning contract. This has to be indicated in the Twinning work plan (Annex A1) and the corresponding estimated costs must be included in the project budget (Annex A3).

The BC may also consider ‘seconding’ the RTA assistant from their own administration rather than having an external recruitment under the Twinning contract. The advantage of this solution is to have a RTA assistant with ‘in house’ knowledge of the BC administration. In this case, the costs of the RTA assistant are not included in the Twinning contract.

RTA assistants funded by the Twinning contract must not have had, at least during the 6 months preceding their recruitment, any contractual relation with the beneficiary administration.

The recruitment procedure may be launched before the signature of the Twinning Contract but the RTA assistant may not start to work and corresponding costs will not be eligible before the start of the Twinning contract. A minimum of 3 candidates must be assessed/interviewed.

External recruitment of the RTA assistant must be in the form of a service contract to be awarded and concluded either by the MS Lead Partner or by the Contracting Authority (see section 3.9). The award and conclusion of this service contract are governed by the provisions of Annex A4 (contract award procedures). In all cases, the RTAs shall have a decisive say in the choice of their assistant and this obligation that cannot be subject to exception.

In case where the RTA assistant has to be replaced, a new recruitment procedure must be launched: it is not authorised to use the results of the initial recruitment procedure (e.g. list of pre-selected candidates).

## 3.8. Translation and Interpretation

As a matter of principle, the BC bears all the costs incurred for the implementation of  the Twinning project that are not included in the Twinning contract (see section 4). An exception may however be made for the costs of translation and of interpretation.

In this case, costs for these services will be included in the Budget of the Twinning contract (Annex A3) in relation to each activity for which they are required. The ceiling of EUR 10 000 per budget item must be respected in case of external services, unless lower ceilings are drawn up by the Contracting Authority in the BC.

Translation costs must be counted using the rates applicable in the BC.

Interpretation costs may be counted using the rates applicable at the place where the activity requiring interpretation takes place. For activities taking place in the MS it may however be economically advantageous to contract interpretation services in the BC (travel costs and per diems for the interpreter(s) must be taken into account in the cost comparison). In all cases, project partners are strongly encouraged to seek value for money.

The Contracting Authority in the BC will indicate the local price range applicable for translation and interpretation.

If the identified volume of translation and/or interpretation is considerable, it may be envisaged for reasons of cost-effectiveness, to recruit a full-time or part-time interpret/translator in addition to the RTA assistant. The provisions defined in section 3.7 that are applicable to the recruitment of RTA assistants funded by the Twinning contract shall be followed for the recruitment of the interpret/translator.

## 3.9. Equipment

3.9.1. Large Scale Equipment

Reference to equipment necessary for the implementation of the Twinning project must be mentioned in the Twinning work plan. This equipment, when needed, must not be financed by the Twinning budget. In certain cases, it may be possible that this procurement is financed with EU funds.

In all cases, it is the responsibility of the BC to secure financing for this equipment from a source of its choice and to ensure that the equipment is available when needed so as not to jeopardise the implementation of the Twinning project.

3.9.2. Office Equipment and supplies

The BC Twinning partner is solely and entirely responsible for providing all necessary office equipment to ensure effective working conditions for the project and, in particular, for the RTA.

The budget of the Twinning contract must not fund any office equipment (desktops, laptops, mobile, phones, faxes, scanners, CD-burners etc.)

In very exceptional cases and subject to due written justification, small items of essential supplies (e.g. small laboratory testing consumables or equipment) for a total cost of not more than EUR 5 000 may be funded by the Twinning contract to ensure that the implementation of the project can proceed smoothly. The contracting Authority must assess the proposed expenditure restrictively, in the light of its knowledge of the BC possibilities and on a case by case basis.

Any equipment purchased with project funds will become the property of the BC at the end of the project. Purchases must be transparent and must respect the provisions of Annex A4, in particular the rules of nationality and of origin applicable to the European Union programme funding the Twinning contract.

## 3.10. Private Sector Inputs

## 3.10.1. Tendering, procurement and contracting

Provisions detailed in the "Introductory Remarks" of Annex A4 apply.

## 3.10.2. Private Sector Sub-Contractors

Where a MS Partner is unable to carry out an activity necessary to the implementation of the Twinning project and provides adequate certification to that effect, this activity may be subcontracted. This could be the case for example of software design or development, for which private sector specialist input would be essential for the achievements of the Twinning project.

MS Partners are not allowed to subcontract key activities of the Twinning project, which must in all cases remain the sole prerogative of the public sector actors of the MS Partners.

All services to be subcontracted must be included in the Budget  of the Twinning contract with an annotation indicating clearly by which authorities these items will be contracted and paid.

Private sector experts included in the Twinning contract as described above must be budgeted based on their fees (invoices) and are not eligible for twinning management cost compensation.

- The selection of private sector sub-contractors must comply with the rules and procedures described in section 3.10.1 and defined in Annex A4.

- All invoices and supporting documents related to private sub-contractors input must be kept for expenditure verification and audit purposes.

## 4. 	Twinning Costs not covered by the EU

1.	All Twinning projects must be co-financed by the BC. The direct and indirect cost of the BC administration, civil servants and national private experts working for the project must be borne by the BC.

- Under IPA, costs for travel by BC officials from their capitals to a MS or between MS (e.g. in the framework of study visits) are not eligible. In other Twinning projects such costs may be eligible.

- Costs for large-scale equipment necessary for the implementation of the Twinning project must not be covered by the Twinning contract.

- The BC must provide free of charge the MS experts, including the RTA, with the requisite facilities for professional use. Accordingly the following costs are not eligible under the Twinning contract:

- adequately equipped office space

- telephone

- email services

- fax

- photocopiers,

- computer

- internet access

- secretarial support

- venues for conferences, training and workshops (except for kick-off and closure meetings - see section 9.4 of the Twinning Manual)

- access to information

- Duties, taxes and charges including VAT are not eligible under the Twinning contract, unless the MS Partner can demonstrate that it cannot be exempted or reimbursed, and under the condition that the European Union programme funding the Twinning contract authorises the reimbursement of such taxes (see article 14.2 of Annex A2).

For VAT on expenses incurred in the BC, certain beneficiary countries have a mechanism in place with the local Ministry of Finance to address this issue. MS Partners are advised to make careful enquiries before engaging in any purchase that may involve the payment of VAT or of any other duties, taxes and charges.

- MS expert fees or any other expenses related to MS experts input performed outside the BC are not eligible under the Twinning contract. These costs are deemed to be covered by the twinning management costs compensation.

EU funds must not be used to fund BC running costs. In the perspective of the long-term sustainability of the Twinning project and in order to ensure that systems are established which are commensurate with BC future funding capacity, BCs are expected to commit their own resources to Twinning projects (about sustainability, seesection 9.2 of the Twinning Manual).

## 5. 	Reporting requirements

### 5.1.	Reporting requirements for standard Twinning projects

Proper project reporting is essential to ensure effective follow-up of implementation, to properly evaluate the results and to ensure high quality for the project itself and for future projects.

Project reports must focus on the Twinning project but also place the contract in the context of related activities within the same programme and/or sector. Twinning reports should be a basis for inputs to sectoral or programme level monitoring reports, in particular highlighting issues that cannot be solved at the level of the Twinning project.

The MS Lead Partner must draw up Interim Quarterly Reports and a Final Report. The MS Project Leader is responsible for submitting these reports to the concerned authority. The BC Project Leader must be fully involved in the reporting process and should be given adequate time to put forward comments. The BC Project Leader must also co-sign each report before it is submitted by the MS Project Leader.

Interim Quarterly Reports and Final Report shall consist of a content section and of a financial section. Reports are drafted by the MS Project Leader and must be first submitted to the counterpart BC Project Leader, for comments (if any) and for co-signature, prior to formal submission to the designated authority. Reports must reflect not only the Project Leader’s own opinion on the progress of the Twinning project, but shall also be based on and reflect the information contained in the reports provided by the RTA, by the BC and by other sources (i.e. MS experts, training and seminars etc.) It is essential that the BC is fully involved in the preparation of each report, in order to ensure a comprehensive insight into project progress.

The reports must be submitted to:

| Reports to be submitted to: | IPA centralised / decentralised with ex ante control | IPA decentralised without ex-ante control | ENPI (Centralised) | ENPI (Decentralised) |
| --- | --- | --- | --- | --- |
| EU Delegation | X | Copy | X | Copy |
| Administrative Office/ Programme Administration Office | X (CFCE) | X | Copy | X |

Reports must be discussed in Quarterly Steering Committees, called by the Contracting Authority in agreement with the RTA. They must contain, as a minimum, the information detailed in the next sections. If minimum reporting requirements are not met, the Contracting Authority reserves the right to review or suspend funding of the Twinning project, after prior approval of this decision by the Commission Headquarters.

Reports must be submitted in accordance with the time limits detailed below. They are deemed to be approved by the Contracting Authority in the absence of any feedback within 45 days following their submission.

Report templates are available in Annex C4.

### 5.1.1. Interim Quarterly Reports

Throughout the duration of the Twinning project, at three-monthly intervals starting with the date of notification of the Twinning contract, the Project Leaders will prepare interim quarterly reports.

The first interim quarterly report covers generally a period of project implementation shorter than three months, due to the fact that the arrival of the RTA in the BC and the beginning of the work schedule do not coincide with the date of notification.

Interim quarterly reports are due during the month following the quarter under consideration: the first interim quarterly report is due in the fourth month following the date of notification of the Twinning contract.

# Theinterim quarterly reports must:

- Describe progress achieved in the implementation of the Twinning project during the period under consideration, making direct reference to the timetables and benchmarks as set out in the Twinning Work Plan, and highlighting any previously unforeseen activities or activities that have been cancelled.

- Update on the general environment for project implementation.

- Update on the assumptions and risks for project implementation.

- Make an overall evaluation of the progress achieved, including an explicit judgement on the likelihood of fully completing the project within the remaining time scale and budget. Specific reference should be made to the progress made towards the mandatory results and project purpose as outlined in the project fiche with measurement based on indicators set in the contract. The progress towards achieving target values of these indicators should be measured as well as the adequacy of the indicators.

- Provide recommendations.

The financial part of the interim reports, must document the actual expenditure in relation to budgeted expenditure. A list must be annexed that details each item of expenditure incurred in the period covered by the report, and indicating for each item: title/description, amount in local currency and in euro, relevant budget heading, reference of the justifying document.

### 5.1.2. Final Report

The MS and BC Project Leaders will jointly prepare, co-sign and submit to the designated authority a final report.

The final report shall be forwarded no later than three months after the implementation period (work plan) as defined in article 2 of the Special Conditions of the Twinning contract. This implies that the final report, the request for final payment and the expenditure verification report must be submitted at the latest during the last month before the end of the legal duration of the Twinning contract.

It will include:

- Executive summary of the Twinning project.

- Background information: description of the original situation in the relevant area of the BC administration before the project, indicating the gaps that the project intended to address; and listing objectives, purpose and mandatory results of the Twinning project.

- Implementation process: developments outside the project and project developments; any significant difficulties encountered.

- Achievement of mandatory results: if these have not been achieved a detailed explanation must be given on the underlying reasons and an action plan to complete the project must be submitted.

- Analysis of the long-term impact of the project, its sustainable results and identification of potential relevant follow-up actions, if applicable.

- Information on the steps taken to ensure the visibility of EU financing.

- Conclusions, recommendations to ensure sustainability of project results, including lessons to be learned for future Twinning projects.

- Proof of transfers of ownership (if applicable) and a final statement of all eligible costs of the Twinning project, plus a full summary statement of the Twinning project’s income and expenditure and payments received.

The final financial report must be accompanied by an expenditure verification report from a recognised, independent auditor, following the template in Annex A6 (see section 7.3 of the Twinning Manual).

If the MS fails to provide the Contracting Authority with a final report by the deadline specified above, and fails to provide an acceptable and sufficient written explanation of the reasons why this obligation could not be complied with, the Contracting Authority may terminate the Twinning Contract in accordance with section 6.7.2 of the Twinning Manual and with Article 12.2.a of Annex A2, and recover the not substantiated amounts already paid to the MS Partner.

5.2. Reporting requirements for Twinning light projects

There must be at least a start-up report covering the first two months of implementation the Twinning light contract (submitted during the third month) and a final report.

Reports must be endorsed and countersigned by the beneficiary, who may make additional comments.

Report templates are those applicable for standard Twinning projects.

Reports must be submitted as indicated in section 5.1.

# ANNEX A8
Mandate Junior Project Partners

# ANNEX 9 - CVs

Curriculum Vitae

Proposed position in the project:		Member State Project Leader (Lead Partner – Slovakia)

- Family name: 			Ondrus

- First name:				Branislav

- Date of birth:				26.3.1973

- Nationality:				Slovak

- Education

| Institution (date from - to) | Degree(s) or Diploma(s) obtained: |
| --- | --- |
| University of Economy of Bratislava 1991-1996 | Political Sciences, European Political Systems |

- Language Skills: Indicate competence on a scale of 1 to 5 (1 excellent - 5 basic)

| Language | Reading | Speaking | Writing |
| --- | --- | --- | --- |
| Slovak | 1 | 1 | 1 |
| English | 1 | 1 | 1 |
| Russian | 1 | 2 | 2 |
| German | 3 | 3 | 3 |

- Membership of professional bodies: N/A for high-ranking civil servants

- Other skills (e.g. Computer literacy, etc.): computer literacy, Lotus, ECDL

- Present position: State Secretary of the Ministry of Labour, Social Affairs and Family of the Slovak Republic (equivalent to Deputy to the Minister) in charge for employment and industrial relations

- Years within the firm: 16 years in social affairs: employment and industrial relations

- Key qualifications/skills (relevant to the assignment):

- More than 15 consecutive years of proven working in the field of labour market (employment/ALMP) and management of social policies, proven record of professional experience in the areas of labour law, employment and industrial relations;

- Professional level of English, Excellent management skills and leadership ability, education in political science related to employment, social dialogue and industrial relations, sound knowledge in Human Resources and Project management

- Proven experience as:

- Project Leader of Twinning project “Promoting social dialogue” in Serbia

- Project Leader of Twinning project “Development of Social Dialogue on Bi-partite Level” in Slovakia

- Project leader of “Increasing the capacity of the Organisation of Employers’ of FYROM on the way to EU”

- Team Leader of “European systematic approach for employers’ engagement to anticipate skills requirements and support quality assurance (QA) in VET”- project is aiming at employers’ engagement to anticipate skills requirements”

- Project manager of RELLMAS project – Regional and Local Labour Market Support in FYROM

- Project manager of “CompServ SME – Competencies Development through the Self-learning in Services SME for increasing employment rate and new jobs creation”

- In depth knowledge and understanding of the social policies, market-driven social reforms, labour and employment strategies, change management on state level, ministerial and inter-ministerial dialogue on social and labour policies,

- Proven experience in programme design (PCM, SWAP, Log frame analysis), team leader of various policy-making steering committees, development of social and labour policies and state reforms

- In depth knowledge in undertaking LM and ALMPM in order to provide recommendations and concrete proposals for its amendments in accordance with best EU practices;

- Directly in charge for employment issues at the Ministry and coordinating the works of the Central Office of Labour, Social Affairs and family in the area of implementation of ALMP measures through ESF

- Over 7 years of experience as a high ranked civil servant Social and employment expert at the Ministry of Labour, Social Affairs and Family of Slovakia and the Slovak Parliament - undertaking situation analysis of flexible forms of employment and developed comprehensive proposal for introduction of legislation and policies promoting social issues,

- Undertake situation analysis of informal economy and informal employment and develop and begin implementation of an Action Plan to promote work in the formal economy including fiscal, economic and social measures;

- Conducting analyses on representativeness issues and registration of trade unions and employers’ associations to  provide concrete proposals for changes of procedures in line with best EU practices;

- Implemented strategic public awareness campaigns on promotion of employment and industrial relations, employment flexibility and work performance, innovations at the workplace, participation and involvement of workers and partnership in the creation of better working conditions and equal opportunity and access to quality workplaces;

- PR campaigns on social development

- Over 10 years of experience in project management of EU funded initiatives/programmes in EU – regional policies on employment development linked to education, employment and social integration of marginalized groups,

- Over 10 years of experience in applying techniques related to project development / management (specifically LFA, SWOT, project fiche and/or ToR drafting, etc.) in EU funded projects

- Extensive experience in design, funding and implementation of national awareness and democratization campaigns in the social area including different stakeholders, e.g. NGO, CBOs, media, and in the field of advocacy and needs diagnostics;

- Capacity building in public bodies and ministries and development of strategies, management and human resource development, design and delivery of training/mentoring/tutoring and other forms of support in all aspects of organization at strategic and functional level, advocacy, internal governance, decision-making processes, accountability and networking;

- Specific experience in the region (most recent first)

| Country | Date from - Date to |
| --- | --- |
| Slovakia | 1995-till now |

- Specific experience abroad:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| United Kingdom | 1996 | Specialised training course for youth leaders and project managers |
| Germany | 1997 | Managed bilateral projects – youth employment, non-formal education |
| FYROM | Since 2009 | Planning of several strategic projects aiming at capacity building of state administration, self-government and social partners in labour law, youth unemployment and industrial relations. Specific measures towards accession to EU, policy formulation |

14.	Professional experience:

| Date: from (month/year) to (month/year) | 01/2012-ongoing |
| --- | --- |
| Location | Bratislava |
| Company / Organisation | Ministry of Labour, Social Affairs and Family of the Slovak Republic |
| Position | State Secretary General (Deputy to the Minister) on labour law, employment, social dialogue and industrial relations; |
| Job Description | - Leading working groups on labour law and employment gap analysis and recommendations as well as working committees of inter-ministerial communication on regional development and employment and social dialogue - Initiating Labour Law amendments in line with EU best practices proposed, including provisions on ALMP and ALMM - In charge for tri-partite social dialogue - Conducting a local, regional and nation-wide studies & analyses on ALMP with the active participation of the social partners and representatives of the industrial relations, - Coordinating the works of Central Office of Labour, Social Affairs and Family and MOLSAF on ALMP and ESF - Leading communication and work within the Tri-partite SEC (Social and Economic Council) - Collecting and advancing to the Government and the Slovak Parliament a number of recommendations for improvement of implementation/enforcement of measures aiming at LM and employment; - Leading the public awareness campaign of the Ministry on promotion of special ALMP measures, industrial relations, employment flexibility and work performance, innovations at the workplace, participation and involvement of workers and partnership in the creation of better working conditions and equal access to quality workplaces performed - Supervising the capacity building program for various stakeholders - development and implementation; - Maintaining the dialogue with the representatives of the trade unions and employers’ associations on employment and LM issues; trained in conducting social dialogue at the national level, as well as collective bargaining at branch and company levels, by the end of the execution of the measure; |

| Date: from (month/year) to (month/year) | 10/2012-ongoing till 12/2013 |
| --- | --- |
| Location | Bratislava |
| Company / Organisation | Ministry of Labour, Social Affairs and Family of the Slovak Republic in cooperation with RDA |
| Position | Team Leader |
| Job Description | EU-strategic project “European systematic approach for employers’ engagement to anticipate skills requirements and support quality assurance (QA) in VET”- project is aiming at employers’ engagement to anticipate skills requirements” - Supervision of the project - Policy development in the sector level (tourism and hospitality) - Coordination of works with the Ministry of Education - Involvement of social partners and planning common approaches for employment increase on skills development (focus on youth force) |

| Date: from (month/year) to (month/year) | 01/2010-12/2011 |
| --- | --- |
| Location | Bratislava |
| Company / Organisation | The Slovak Parliament |
| Position | Social Affairs Committee Chairman, MP |
| Job Description | - Undertaking Labour Law gap analysis in order to provide recommendations and concrete proposals for its amendments in accordance with best EU practices; - Undertake situation analysis of informal economy and informal employment and develop and begin implementation of an Action Plan to promote work in the formal economy including fiscal, economic and social measures; - Conduct an analysis on representativeness issues and registration of trade unions and employers’ associations to provide concrete proposals for changes of procedures in line with best EU practices; Delivery of Action Plan to promote work in the formal economy including fiscal, economic and social measures developed; |

| Date: from (month/year) to (month/year) | 1/2011-6/2012 |
| --- | --- |
| Location | Bratislava/Skopje |
| Company / Organisation | RDA |
| Position | Chief Supervisor |
| Job Description | Chief Supervisor of project: “Increasing the capacity of the Organisation of Employers’ of FYROM on the way to EU” - Building capacity of OEM - Trained staff on EU integration - Building partnerships - Labour law and protection of employees - Cooperation of SP at bipartite level - Networking and sustainability - Recommendations for follow up common projects with FYROM financed by Slovak Aid bilateral support in the social area |

| Date: from (month/year) to (month/year) | 1/2009-12/2009 |
| --- | --- |
| Location | Bratislava |
| Company / Organisation | Ministry of Labour, Social Affairs and Family of the Slovak Republic in cooperation with RDA |
| Position | Project Supervisor |
| Job Description | RELLMAS project – Regional and Local Labour Market Support in FYROM - Supervised the works and policies related to regeneration of local labour markets - Good practice examples in cooperation and involvement of social partners in employment issues, policy formulation - EU matters – Lisbon agenda, Employment Guidelines |

| Date: from (month/year) to (month/year) | 01/2008-12/2009 (24 months) |
| --- | --- |
| Location | Bratislava |
| Company / Organisation | Government of the Republic of Slovakia |
| Position | Director of the Government Press Office |
| Job Description | - Leading communication and dialogue referring to: - Social Policy and Employment – ALMP - the Tripartite Committee - PR and awareness raising towards social policy understanding: situation analysis on flexible forms of employment developed; Labour Law amendments in line with EU best practices proposed, including provisions on representativeness issues and registration of trade unions and employers’ associations; Action Plan to promote work in the formal economy including fiscal, economic and social measures developed; Public awareness campaign on promotion of industrial relations, employment flexibility and work performance, innovations at the workplace, participation and involvement of workers and partnership in the creation of better working conditions and equal access to quality workplaces performed |

| Date: from (month/year) to (month/year) | 10/2005 – 10/2007 |
| --- | --- |
| Location | Bratislava |
| Company / Organisation | Ministry of Labour, Social Affairs and Family of the Slovak Republic in cooperation with RDA |
| Position | Project manager |
| Job Description | 2-year EU-project “CompServ SME – Competencies Development through the Self-learning in Services SME” - Managed the project, - Coordinated works of the social partners and CSOs (training providers) - Capacity building of SME in competitiveness - Active labour market policy – new jobs creation within SME - Recommendations for innovative forms of employment in Slovakia - Trained staff - Planned sustainable actions for bringing innovation to SME |

| Date: from (month/year) to (month/year) | 01/2002-12/2007 |
| --- | --- |
| Location | Bratislava |
| Company / Organisation | TV media |
| Position | Expert on labour law, employment and industrial relations; /Editor and Project Director(TL of ESF funded project) |
| Job Description | - Conduct joint round-tables and workshops with decision-makers, trade unions, employers’ organisations, government actors and CSOs representing vulnerable groups to determine the position and measures for activation of vulnerable groups, including women, persons with disabilities and minority groups, within inclusive social dialogue; development of the social policy in Slovakia with focus on unemployment decrease, role of social partners in country development, discussed strategic planning for EU-funding for support to ALMP in Slovakia and best use of EU support for regions´ regeneration and employment increase - PR campaign on employment of young people, career development issues - Industrial relations topics, cooperation of state, self-govt. and CSOs - Media monitoring and watch on issues related to employment of young people in the regions |

| Date: from (month/year) to (month/year) | 12/2000 – 12/2001 |
| --- | --- |
| Location | Bratislava |
| Company / Organisation | Ministry of Labour, Social Affairs and Family of the Slovak Republic |
| Position | Team Leader |
| Job Description | Twinning project “Development of Social Dialogue on Bi-partite Level” in Slovakia - Managed the project with social partners - Transposition of directives - Managed discussions on social dialogue importance in social policy and job creation through ALMP - Trained tripartite representatives - Managed cooperation with the Slovak SEC - Assessment of progress |

| Date: from (month/year) to (month/year) | 01/1999-12/2002 |
| --- | --- |
| Location | Bratislava |
| Company / Organisation | Government of the Slovak Republic |
| Position | Social Affairs Expert labour law, employment, social dialogue and industrial relations; |
| Job Description | - Leading communication and work within the Tripartite SEC of Slovakia - Collecting and advancing to the Government and the national Assembly of the SR a number of recommendations for improvement of implementation/enforcement of the Law on the Social and Economic Council; - Leading the public awareness campaign of the Ministry of Social Affairs on promotion of industrial relations, employment flexibility and work performance, innovations at the workplace, participation and involvement of workers and partnership in the creation of better working conditions and equal access to quality workplaces performed - Conducting joint workshops with trade unions, employers’ organisations, government actors and CSOs representing vulnerable groups to determine the position and measures for activation of vulnerable groups, including women, persons with disabilities and minority groups, within inclusive social dialogue; |

| Date: from (month/year) to (month/year) | 01/2001-12/2001 |
| --- | --- |
| Location | Bratislava |
| Company / Organisation | European Socialist Party |
| Position | Member of the Presidium |
| Job Description | Analyses of Human Resources at Labour Offices, improvement and suggestions Building Strategy and Analyses of Education, co-operation with (National) Labour Offices in line with European , participation on EU projects, cooperation with social partners, organization of educational courses throughout the Slovak Republic |

| Date: from (month/year) to (month/year) | 01/1999-12/2001 |
| --- | --- |
| Location | Bratislava |
| Company / Organisation | Democratic Left Party |
| Position | Deputy Chairman |
| Job Description | - Situation analysis on flexible forms of employment developed; - Initiating Labour Law amendments in line with EU best practices proposed, including provisions on representativeness issues and registration of trade unions and employers’ associations; - Delivery of Action Plan to promote work in the formal economy including fiscal, economic and social measures developed; - Developed Strategy for active labour market policy and services - Working on policy recommendation related to re-qualification, workplace donations and other arrangements on the Labour Market |

| Date: from (month/year) to (month/year) | 01/1999-12/2000 |
| --- | --- |
| Location | Bratislava |
| Company / Organisation | Democratic Left Party |
| Position | Spokesperson |
| Job Description | - Analyses of Human Resources at Labour Offices, improvement and suggestions/recommendations for change management - Situation analysis on flexible forms of employment developed; - Initiating Labour Law amendments in line with EU best practices proposed, including provisions on representativeness issues and registration of trade unions and employers’ associations; - Delivery of Action Plans to promote work in the formal economy including fiscal, economic and social measures developed; - Working on policy recommendation related to re-qualification, workplace donations and other arrangements on the Labour Market |

| Date: from (month/year) to (month/year) | 01/1996-12/1998 |
| --- | --- |
| Location | TV |
| Company / Organisation | Expert on labour law, social dialogue and industrial relations/Key moderator on these themes |
| Position | - Industrial relations, social dialogue issues, social policy, PR campaign on employment of young people, education/training and career development - Developed a series of media products oriented on the support of the active participation of the Labour offices and self-governments on employment issues, social dialogue, communication with investors - Developed media products and TV campaign on the new forms of employment and needs of the regions in terms of social and economic conditions - Media monitoring and watch on issues related to employment of young people in the regions - Managed a team of 11 specialists on social policy issues |
| Job Description |  |

| Date: from (month/year) to (month/year) | 01/1995-12/1995 (24 months) |
| --- | --- |
| Location | Strasbourg |
| Company / Organisation | Council of Europe |
| Position | Expert labour law, employment services, non-formal education, social dialogue and industrial relations |
| Job Description | - Situation analysis on flexible forms of employment developed; - Initiating Labour Law amendments in line with European Policies and best practices proposed, including provisions on representativeness issues and registration of trade unions and employers’ associations; - Working on policy recommendation related to re-qualification, workplace donations and other arrangements on the Labour Market |

- Other relevant information (e.g. Publications, Patents, Other education, Seminars, lectures attended, Scholarships received):

- 1995 – Scholarship of the CoE, specialised English for project leaders in the social and education areas

- Specialised articles on social issues in magazines and national newspapers

CURRICULUM VITAE

Proposed position in the project: Junior Project Leader – Hungary

1.	Family name:	Komáromi

2.	First name: 	Róbert

3. 	Date and place of birth: 	22.07.1973 Paks

4.	Nationality: 	Hungarian

5.	Civil Status: 	married

Address (phone/fax/e-mail): Kendermag utca 45. 1162, Budapest, Hungary, +36-1-299-1090; +36-30-638-6873

6. 	Education:

| Institutions: | ELTE University, Budapest |
| --- | --- |
| Date: From (months/year) To (months/year) | September/1992 May/1998 |
| Degree: | Master degree in Sociology |

| Institutions: | ELTE University, Budapest |
| --- | --- |
| Date: From (months/year) To (months/year) | September/2000 May/2000 |
| Degree: | Certification in Labour Management |

| Institutions: | Hungarian Institute for Public Administration |
| --- | --- |
| Date: From (months/year) To (months/year) | September/1998 May/2000 |
| Degree: | Sociology, Ph.D. Programme |

| Institutions: | Budapest University of Economy and Public Administration |
| --- | --- |
| Date: From (months/year) To (months/year) | September/1999 May/2003 |
| Degree: | Master degree in European Studies |

| Institutions: | International Training Centre for Bankers |
| --- | --- |
| Date: From (months/year) To (months/year) | 2003 2003 |
| Degree: | Certification (Structural Funds in Practice) |

| Institutions: | Károli Gáspár University |
| --- | --- |
| Date: From (months/year) To (months/year) | September/2005 May/2007 |
| Degree: | Master degree in Supervision |

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Hungarian | Mother Tongue |  |  |  |
| English | 5 | 5 | 5 | 5 |
| French | 2 | 2 | 2 | 2 |

8.	Membership of Professional Bodies:

9.	Other skills (e.g. computer literacy, etc.):

In Windows environment strong knowledge of Word, Excel, Outlook, PowerPoint, SPSS etc.

10.	Present Position: Director General at National Labour Office (Hungary)

11.	Years of professional experience: 16 years

12.	Key qualifications:

- Proven professional record in the employment policy with more than 16 years of direct experience in the field

- Exceptional comprehensive knowledge of EU employment policy and related legislation

- Proven record in transposition of EU law in the social area, profound experience, outstanding professional background and relevant knowledge on all topics covered by this project (combination of research and practical experience)

- Excellent academic background related to the project content

- Direct experience and extraordinary skills and knowledge in management of large scale programmes/projects in the employment area – nationally and internationally

- Extraordinary leadership skills managing and leading big groups of experts, employees, proven ability for motivating people at work

- Excellent inter-communication, negotiation, presentation and mediation skills verified at different levels – nationally and internationally

- Proven ability to lead and work in multinational, cross-cultural teams of experts and well-known in Europe as one of good experts in employment and related social matters

- Proven language ability in English

13.	Specific experience in the region or else:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| United States, India, Luxembourg, Brussels/EC, The Netherlands | Since 1996 - ongoing | Presentations, speeches, trainings, internships, Expert work, lecturer , research works, etc. |

14.	Professional experience:

| Date: from (month/year) to (month/year) | 2010. – ongoing |
| --- | --- |
| Location | Kalvária tér 7., 1089, Budapest, Hungary |
| Company / Organisation | National Employment and Social Office |
| Position | Director General |
| Job Description |  |

| Date: from (month/year) to (month/year) | 01.2004. – 11.2010. |
| --- | --- |
| Location | Kalvária tér 7., 1089, Budapest, Hungary |
| Company / Organisation | National Employment and Social Office |
| Position | Director of Development |
| Job Description | Implementation of EU financed projects – Modernisation of the Public Employment Service Pre-accession Funds: PHARE Twinning Structural Funds: National Development Plan 2004-2006 and 2007-13 |

| Date: from (month/year) to (month/year) | 06. 2002. – 12. 2003 |
| --- | --- |
| Location | Alkotmány u. 3., 1051, Budapest, Hungary |
| Company / Organisation | Ministry of Employment and Labour Human Resource Development Operational Programme Managing Authority |
| Position | Programme Manager |
| Job Description | Implementation of the European Structural Funds in the co-operation with Intermediate Bodies Publicity, Technical Assistance, Employment policy |

| Date: from (month/year) to (month/year) | 05. 2000. – 06. 2002. |
| --- | --- |
| Location | Kossuth tér 5., 1051, Budapest, Hungary |
| Company / Organisation | Prime Minister’s Office |
| Position | Senior Adviser |
| Job Description | Employment and Social Policy |

| Date: from (month/year) to (month/year) | 08. 1998. – 05. 2002. |
| --- | --- |
| Location | Roosevelt tér 5., 1051, Budapest, Hungary |
| Company / Organisation | Ministry of Social and Family Affairs, |
| Position | Adviser |
| Job Description | Employment and Social Policy |

| Date: from (month/year) to (month/year) | 02. 1997. – 08. 1998. |
| --- | --- |
| Location | Kossuth L. u. 11., 7130, Paks, Hungary |
| Company / Organisation | Brain Bank Ltd., |
| Position | Managing Director |
| Job Description | Co-operation with municipalities to setting up and maintaining data bank |

| Date: from (month/year) to (month/year) | 06. 1995. – 02. 1997. |
| --- | --- |
| Location | Kossuth L. u. 11., 7130, Paks, Hungary |
| Company / Organisation | Dunaholding Paks Ltd., |
| Position | Salesman |
| Job Description | Factoring |

15	Others:

- Conferences, lectures

2009 Employment policy, Szent István University, Gödöllő, Invited Speaker

2004 “Integration or exclusion: changing structure at the employment of the mentally handicapped people” Conference, Debrecen, Invited Speaker

2004-2006 EU and Social Policy, ELTE University, Invited Speaker

2004 Sociology, Gabor Denes College, Szekszard, Invited Speaker

2003 – 2004 Structural Funds in Practice, Invited Speaker

Budapest College of Communication

Promei Kht.

Sokrates Academy

Tempus Foundation

Hajlektalanokert Foundation

2003 Disability and Social Policy, Conference, ELTE University, Budapest

Invited Speaker

2002 Bridging the Gap

The 30th International Conference on Social Welfare

Rotterdam, the Netherlands

Invited Speaker

- Researches

2003 Practice of the National Report’s to the European Social Charter

Research Leaders: Prof. György Könczei and Robert Komaromi

Organized by: ELTE University and National Employment Foundation

2001 People with Disability at Work at the TOP 200 National Companies

Research Leaders: Prof. György Könczei and Robert Komaromi

Organized by: ELTE University and National Employment Foundation

1999 International Economic Competition and the Welfare Systems

Views of the Economic Leaders

Organized by: SOCO

1996 Economic Change of Regime and the Chambers

Organized by the Hungarian Academy of Science

- Scholarships and international experiences

2008 Participation in the Technical Assistance to Support Employment Policy (phase II) project as sort term expert, Republic of Macedonia

2006 MTEC-Social Affairs/Employment Course, (24 September – 14 October) Clingendael Institute, Amsterdam Institute for Advanced Labour Studies, Tilburg University Utrecht, The Hague, The Netherlands

2003 1month Researcher` Grant Provided by the Hungarian Scholarship Board, Sacred Hearth University, Luxembourg

2002 2months Researcher` Grant Provided by the ELTE University Netherlands Institute of Care and Welfare, Utrecht, The Netherlands

2001 Study Tour to India, provided by the Grant of the Hungarian Scholarship Board, University of Delhi, Gokhale Institute of Politics & Economics, Pune, University of Mumbai

1999 – 2001 Participation in the “Support and Innovation Centres for the Social Sector in Central European Countries” project Organized by the Netherlands Institute of Care and Welfare. Workshops: Utrecht, Vilnius, Budapest, Bratislava

2000 Study Tour at the German Prime Minister’s Office, Berlin, Germany

1999 3months Researcher` Grant Provided by the Julius Rezler Foundation

Robert O. Anderson Schools of Management University of New Mexico, Albuquerque USA

1997 Grant Provided by the Julius Rezler Foundation

1996 Grant Provided by the Economy Leader's Round Table Foundation

- Publications

1. Hungarian

1.1 Articles in Professional Journals

Gellen, Marton – Komáromi, Róbert: Integration of employment and social service system and it’s experiences in the IT development. Munkaügyi Szemle, January 2009

The Netherlands: Public services on the market. Munkaügyi Szemle, January 2007.

Employment Integration of the Disability Employees. Esély. 2003. 5.

Some Question of the Part-Time Working System: The Netherlands. Munkaügyi Szemle. January 2003.

Keszi, Roland – Komáromi, Róbert – Könczei, György: Employment Policy at the 200 National Firms. Munkaügyi Szemle. November. 2003.

Keszi, Roland – Komáromi, Róbert – Könczei, György: Disability Employees at the 200 National Firms. Munkaügyi Szemle. December. 2002.

Survey of the Dutch Welfare, Regarding the Unemployment Benefit System. Munkaügyi Szemle. November. 2002.

Keszi, Roland – Komáromi, Róbert – Könczei, György: Main Employment Characteristics of the Disability Employees at the 200 National Firms. Szociális Munka. 2002. December.

Difficulties of the Premium Payment. MRP Hírfutár. December 1997.

1.2 Articles in Book

Könczei Gy. – Komáromi R. – Keszi R. – Vicsek L.: A fogyatékos és megváltozott munkaképességű munkavállalók foglalkoztatásáról a TOP 200 adatbázis alapján. In: Foglalkoztatást elősegítő munkaügyi kutatások. OFA Kutatási Évkönyv 3. Ed.: dr. Pongrácz László. Budapest, OFA, 2005.

Publicity at the Structural Funds. In: Inotai András (ed.): EU-studies. Volume III. Nemzeti Fejlesztési Hivatal. Bp. 2004.

Komáromi, Róbert – Lendvai, Noémi: „ … get voice and courage for themselves … „ Disability in the Social Policy. In: Zászkalicky, Péter – Vedres, Tamás (ed.) Disability in the border science of the education of the handicapped. ELTE Bárczi Gusztáv Gyógypedagógiai Főiskola, Bp. 2003.

Expereince of the employment of the people with disability.In: Fónai M. – Fónainé P. E. – Szabóné O. É. – Zolnai E. (ed.): Integration or exclusion? Debrecen Megyei Jogú Város Városi Szociális Szolgálat, Debrecen, 2004.

Compromise as an Identification Strategy, Social Psychology of the Second Economy. In: XXII. Országos Tudományos Diákköri Konferencia Társadalomtudományi Szekciója. VJRKTF és BME. Esztergom. 1995.

1.3 Translations

Kees Schuyt: Social Exclusion: the least, the last, the lost and the latest. Szociális Munka. December. 2002.

Original Edition: Kees Schuyt: ’Social Exclusion: the least, the last, the lost and the latest’ In: Bridging the Gaps, Essays on Economic, Social and Cultural Opportunities at Global and Local Levels, Netherlands Institute for Care and Welfare, Utrecht, 2002.

Frits Tjadens: Health care shortages: where globalisation, nurses and migration meet. Egészségügyi Gazdasági Szemle. 2003. május.

Original Edition: Health care shortages: where globalisation, nurses and migration meet. Eurohealth Vol. 8. No 3. Summer 2002.

1.4 Other reference

Roundtable discussion about disability – regarding the problems of employment. (Participant). Új Ifjúsági Szemle. autumn, 2004.

Faragó, József: Dosen’t Matter Who is the Owner. Népszabadság. Munkakör rovat. 2002. szeptember 17.

2. English

2.1 Articles in Book

Robert Komaromi – Noemi Lendvai: Annotated Bibliography, Hungary. In: Helmuth K. Anheiner – Sarabajaya Kumar (ed.): Social Sevices in Europe. Observatory for the Development of Social Services in Europe. 2003.

http://www.soziale-dienste-in-europa.de/Anlage25085/Bibliography_Social_Services_in_Europe_2003.pdf

CURRICULUM VITAE

Proposed role in the project:		Junior Project leader Czech Republic / Component leader 5

1.	Family name: 		KOLMEROVA

2.	First name: 		Vera

3. 	Date and place of birth: 		28/11/1959, Praha

4.	Nationality: 		Czech

5.	Civil Status: 		married

6. 	Education:

| Institutions: | Charles University, Prague, CR |
| --- | --- |
| Date: From (months/year)-To (months/year) | September 1979 - May 1983 |
| Degree: | PaedDr. – Doctor of Pedagogy |

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Czech | Mother Tongue |  |  |  |
| English | 5 | 5 | 5 | 5 |

8.	Membership of Professional Bodies:

9.	Other skills: MS Office, Text, Excel, PowerPoint, Adobe Acrobat

10.	Present Position: Director of Mediation and Counselling Department

11.	Years of professional experience: 25 years of professional experience in employment and education areas

12.    Key qualifications:

- 12 years of hands-on professional record in delivery services to public employment service customers (job-seekers, employers, public bodies), counselling and mediation

- 10 years leadership of Foreign Employment Unit at Ministry of Labour and Social Affairs responsible for Public Employment Service strategy in employment of foreigners (EU and non EU) in Czech Republic; management of team EURES Czech Republic which with European grants supports job mobility across Europe.

- Proven experience in communication policies in the LO of Czech Republic, elaboration of guideline for effective passing on information to customers

- 1 year leadership of Mediation and Counselling Department at Directorate General, which coordinates regional and local offices of Labour Office of the Czech Republic; agenda also involves areas in social system, cooperation with private agencies and EURES network.

- 1 year leadership of Adult and Tertiary Professional Education Unit at Ministry of Education, Youth and Sports, which coordinated adult education policy with focus on harmonisation of National System of Qualification and National system of occupation.

- 4 years inspection of quality of education in basic and secondary schools in Czech Republic

- 4 years managing education as deputy of school director at professional school in Praha - Jilove

- 5 years teaching of Czech Language and Physical training at High School

13.	Specific experience in the region or else:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| Poland | 1/2004 – ongoing | Czech – Poland cross border co-operations EURES, EURES-T Beskydy and EURES-TriRegio based on mutual governmental agreement with social partners involved |
| Slovakia | 07/2003 - ongoing | Cross border cooperation EURES, EURES-T Beskydy based on the Intergovernmental Agreement with social partners involved |
| Austria | 2010 - ongoing | PES co-operation in the job market policy in cross border region Czech - Austria |

14.	Professional experience:

| Date: from (month/year) to (month/year) | September 2013 – ongoing |
| --- | --- |
| Location | Czech Republic, Prague |
| Company / Organisation | Directorate General of Labour Office of the Czech Republic |
| Position | Director of Mediation and Counselling Department |
| Job Description | - Responsibility for processes of counselling, mediation, - Coordination of social system, - Cooperation with private agencies + their licences - EURES system |

| Date: from (month/year) to (month/year) | April 2012 - August 2013 |
| --- | --- |
| Location | Czech Republic, Prague |
| Company / Organisation | Ministry of Education, Youth and Sports |
| Position | Head of Adult and Tertiary Professional Education Unit |
| Job Description | - Strategy and policy of Adult education, - Recognition of qualifications, - National System of Qualification x National system of occupation (close cooperation with Ministry of Labour and Social Affairs), - National Qualification Framework, - Quality of Education – Rating (certification) of Education institutions |

| Date: from (month/year) to (month/year) | October 2002 - March 2012 |
| --- | --- |
| Location | Czech Republic, Prague |
| Company / Organisation | Ministry of Labour and Social Affairs |
| Position | Head of Foreign Employment Unit EURES Manager |
| Job Description | - Legal status of employment foreigners (EU and non EU), - Undeclared work, - Illegal work, - Monitoring of Labour Market, - Control system |

15. Others:

August 1998 – August 2002 School inspector at Ministry of Education, Youth and Sports

February 1994 – August 1998 deputy of High school director in Praha - Jilove

CURRICULUM VITAE

- Family name: Mr. Dr. BORBÉLY-PECZE – RESIDENT TWINNING ADVISER

- First names: Tibor, Bors

- Date of birth: 4th March 1976

- Nationality: Hungarian

- Civil status: married, with two children

- Education:

Planed position: RTA

| Institutions: | University of Godollo, Faculty of Arts and Economics, Gödöllő, Hungary |
| --- | --- |
| Date: From (months/year) To (months/year) | September 1995 May 1998 |
| Degree: | BA employment counsellor |

| Institutions: | Teachers Training College, Eger (1996-1999) |
| --- | --- |
| Date: From (months/year) To (months/year) | September 1996 May 1999 |
| Degree: | BA social teacher – school counsellor |

| Institutions: | Eotvos Lorand University, Budapest (1999-2001) |
| --- | --- |
| Date: From (months/year) To (months/year) | September 1999 May 2001 |
| Degree: | MA in Social Policy – specialization of employment policy |

| Institutions: | Semmelweis University, Faculty of Health Care, Budapest, Hungary |
| --- | --- |
| Date: From (months/year) To (months/year) | September 2006 May 2006 |
| Degree: | Specialisation in addiction counselling |

| Institutions: | Eotvos Lorand University, Faculty of Pedagogy and Psychology, Budapest, Hungary |
| --- | --- |
| Date: From (months/year) To (months/year) | September 2006 May 2010 |
| Degree: | Pedagogy, Ph.D. – thesis on lifelong (career) guidance policy development within education and employment policies |

- Language skills:

| Language | Reading | Speaking | Writing |
| --- | --- | --- | --- |
| Hungarian(C2 level) | mother tongue |  |  |
| English (C1 level) | excellent | fluent | fluent |
| French (A1 level) | basic | basic | basic |

- Membership of professional bodies:

Ongoing international activities (Europe and Overseas)

- ICCDPP-The International Centre for Career Development and Public Policy, Board Member (2010-ongoing) http://www.iccdpp.org

- EC: PES Senior Expert; 'PES to PES Dialogue' is the European Commission’s mutual learning support programme for public employment services (PESs) in the European Union (2011- ongoing)

http://ec.europa.eu/social/main.jsp?catId=964http://ec.europa.eu/social/main.jsp?catId=964

- EC: PES Senior Expert on public and private partnership among the employment services within the EU/EEA (PARES initiative of the EC, based on the ILO C No. 181 (1997), (2011-ongoing)  http://ec.europa.eu/social/main.jsp?catId=991&langId=en

Former international memberships

- ELGPN - European Lifelong Guidance Policy Network official representative of Hungary (http://ktl.jyu.fi/ktl/elgpn ) (2007-2012)

- ELGPN - Evidence-based LLG Policy and QA Work-package Leader (2011-12)

- EU Employment Observatory, MISEP- Mutual Information System on Employment Policy, Hungarian PES correspondent (http://www.eu-employment-observatory.net/en/about/misep.asp) (2004-2009)

- American Counselling Association (ACA) and the Division of National Career Development Association, VA (www.counseling.org) (2001-2002)

- Association for Public Policy Analysis and Management (APPAM) Washington DC, NW (www.appam.org) (2002-2003)

National memberships

- Hungarian Academy of Science (HAS) Section of Law and Economic, Committee on Human Resources Development (2012-)

- Hungarian Lifelong Guidance Council (NPT) founder, secretary of the council (2008-2012)

- Hungarian Teachers’ Association and the Division of National Adult Educators (2002-)

- Hungarian National Adults Education Institute, lifelong learning programs and institutes granting and authorization expert Budapest, Hungary (2002-2008)

- Hungarian School Counsellors’ Association, member of the governing body (2003-2004)

- National Mediator Association (www.partnershungary.hu) (2003-2006)

- “Kontakt" Foundation for career / vocational counsellors in Hungary, (www.palyanet.hu) (1999)

- Other skills: computer literacy, Android and Microsoft products

- Present position: Hungarian National Labour Office; Directorate for Employment, Senior Consultant

- Years within the firm at labour market and career guidance policy design and development: 16 years

Project leading experiences: 10 years with ESF national projects, 6 years with LLP projects, 10 years with LLL projects and policy developments

Experiences in policy design and implementation: 10 years with drafting background documents for national LLL Strategy of Hungary, National Strategy on Early-School Leavers (ESL) and National Reform Programme (NRP) for Europe 2020 Strategy (European Semester)

- Key qualifications:

- 15 years of experience in Lifelong Career Guidance (LLG) and PES development and education, including field work, research and methodological activities and management responsibilities

- 16 years of experiences in European public administrations

- 10 years experiences on project development and management

- 4 years experience in career guidance case/field experience and career counselling and of national employment services focusing all society segments

- independent report writing and analytical skills

- Project manager/Team Leader experience in building up and coordinating the Hungarian network of the national PES system, organizing the regional PES centres including strategy, organizational framework, legislative and operational background

- Strong research and methodological background in the field of employment and education policies and career guidance practice and policy

- Leadership role in large governmental projects, project leading experiences

- In-depth knowledge of state administration especially on employment policy and education

- Cross- policy knowledge on employment, health, education and vocational education policies

- Organisation development know-how of large government bodies

- 15 years of experience working in multi-cultural, multi-lingual environment (USA, EU)

- Expert works for the EuroGuidance Centre (www.npk.hu), Hungary, CEDEFOP, national VET Observatory (REFERNET) http://www.observatory.org.hu/, and TEMPUS Public Foundation, (Hungarian LLP Agency) (http://www.tka.hu/pages/main)

- strong understanding on post-communists countries public administration and local circumstances concerning EU project management

- regular professional activities in relevant European and international networks as WAPES, PES to PES, PARES, IAEVG, ICCDPP, ELGPN, EXPAK(Central-Europe), CPESSEC (Balkan Region)

- Specific consultancy experiences on career guidance and lifelong learning, employment policies:

| Country | Date from – Date to |
| --- | --- |
| China | August, 2014 Senior Non Key Expert China-Europe Public Administration Development Project (CEPA II) developed a manual for Chinese civil servant entry examination process http://cepa2.org/ |
| FYR of Macedonia (STE) | October, 2008, New Service Handbook development of the Macedonian PES |
| Slovakia-Hungary- Belgium PROGRESS (Key Expert) | 2008-2009 –LLG for job-seekers European Public Employment Services; (AFSZ, UPSVAR, FOREM, VDAB) http://internet.afsz.hu/resource.aspx?resourceID=full_kulfoldo_palyaor_llg_job_forjobseekers |
| Republic of Moldova (STE) | June, 2009 ILO CCE Sub-regional Office expert, service and ALMP development of the Moldavian PES |
| Austria-Slovakia- Hungary (KE) | 2009-2010 cross border improvement of national LLL strategies and LLG http://www.cbi-nlls.net/QIP/cbinlls.nsf/index?OpenFrameset |
| Croatia (IPA, Croatian PES) | June-July 2012, Short Term Expert on Croatian PES IPA project for national lifelong guidance policy and system development |
| Estonia INNOVE Foundation | June 2012 Short Term Expert on national education and guidance strategy of Estonia for 2013-2020 |
| European Lifelong Guidance Policy Network Work-package Leader; Work Programme designer | 2011-12; joint development of the European QA and evidence based policy framework on career guidance services with 14 EU/EEA and 3rd countries |

- Professional experiences

| Date from -Date to | Location | Company | Position | Description |
| --- | --- | --- | --- | --- |
| 01/2015 | Hungary/ EU28 | Ministry for National Economy, State Secretariat for Vocational, Adult Education and Employment | Senior Consultant | - involvement in the work of the European Association of Public Employment Service, PES reform and benchlearning activities, work of the European Employment Committee PES related activities, selected assessor of the benchlearning process in EU28 - managing the national PES MbO system - co-ordinating the Hungarian PES professional activities, service and ALMP developments - professional correspondences with OECD, ILO, WAPES |
| 01/2013- 12/2014 | Hungary | National Labour Office, Budapest | Senior Consultant | - Senior Expert on national LLL Programmes an PES developments, including profiling system design - Higher education, PES, national public administration curriculum developments - contribution to the new national Youth Guarantee, Early School Leaver and lifelong Learning strategies - PES modernisation: competency based matching system, PES 2020 etc. - design the Hungarian PES new activities in line with Europe 2020 developments (e.g. new youth guarantee programme, NSRF 2014-2020) - planer: MFF 2014-2020 ex-ante national criteria: profiling, IAP, partnership |
| 05/2012-12/2012 | Hungary/ EC DG. EAC. | National Labour Office/ European Lifelong Guidance Policy Network | Programme designer of the EU network 2013-14 Work Programme | - work together with 30 EU/EEA and 3rd countries and EC DG EAC and DG EMPL. for the development of the European Network 2013-14 Work Programme - drafting the Work Programme jointly with the Finnish Institute for Educational Research, University of Jyaskyla. - negotiate with the member countries representatives –delegated by the national ministries for education and or employment- also with the European stakeholders (e.g. Business Europe, ETUC, EC, agencies of the EC, ETF, CEDEFOP etc.) |
| 10/2008 –04/2012 | Hungary / EU (ESF) | Hungarian Public Employment Services (PES) / Hungarian National LLG / Council / ELGPN, ICDPP | Programme leader / secretary of the Hungarian National LLG Council / member of the managing board 2011-12 of ICDPP / state representative and Work Package (WP) leader of the ELGPN | - Programme Leader of the Development of the system of lifelong guidance in Hungary programme phase I. (2008-2010, 7,3M EUR, ESF, Social Renewal Operational Programme 2.2.2. ), the first national LLG programme: - Developing the concept paper - Managing the entire implementation process - Project Manager of Content and Methodology Development of the Career Guidance System of Hungary - Project Manager of developing and integrating the National Guidance Portal - Implementing, organizing & running 24 regional LLG offices/centers: - Strategy, business plan development - Functional and organizational design - Legislative background elaboration - Developing the cooperation model of the new LLCG offices and other stakeholders in and out the PES - Foundation of the National LLG Council - WP4 leader in the ELGPN (evidence based LLG and QA) |
| 09/2005 – 10/2008 | Hungary (ESF) | Hungarian PES National Employment Office & Ministry of Employment Policy and Labour | Employment Research programme leader | 'Modernisation of the Public Employment Service (PES)' prepared under the 'Service development, strategic planning, and research’ component of HRDOP Measure 1.2. (2M EUR) - project manager: " Employment policy researches, labour forecasting" - Designing the implementation plan for 14 Labour market (LM) research programmes - Monitoring the research programmes , evaluating the outcomes - Expanding synergies between the LM researches and PES service development - Engaged in the profiling and competency-based matching development components as a Key Expert - Preparing the dissemination plan of the project within the PES and national, regional levels |
| 09/2005-01/2007 | 11 EU countries | Taninfo Ltd. | Expert (part time) | EU Leonardo project team member, "DISCO" - Dictionary of Skills and Competencies aims a supporting the transparency and comparability of skills and competencies by providing a well-structured and proven multilingual terminology. (http://www.disco-tools.eu/) - Developing an EU based dictionary of competencies with a support of EU Training Village, CEDEFOP Greece - Testing the elaborated model - Evaluating the draft thesaurus |
| 02/2005-12/2006 | Hungary | Cultural Centre Budapest, U. of ELTE Faculty of Pedagogy and Psychology, U. of Pécs | Career guidance curriculum building expert (part time) | EU - Hungarian Republic Human Resource Development Operational Programme 3.5.4 measure: PALLÓ – „Ensuring the preparational, informational and supportive background of Life Long Learning in the cultural institutions project” as part of the “Improving the accessibility to adult education with the systemic involvement of the available cultural institutional system” programme - Curriculum development for LLG information providers containing: - Adult education guidance helper training - Developing a pilot component for the reintegration programme for older workforce and young adults after child-care allowance |
| 09/2003 – 08/2005 | Hungary | National Employment Office, Research Unit | Research fellow | - Field of focus: LLG policies and service developments of the PES - Analysis on career counselling policy of Hungary, EU and OECD countries - Analysis on state employment policy and the Hungarian Employment Service |
| 11/2002-06/2004 | Greece, Hungary, Germany, Czech Rep. | Taninfo Ltd. Hungary | Expert – Hungarian team leader (part time) | - EU Grundtvig2, project on career and school counselling and guiding: Good Case Practice exchange between the participating countries (http://www.taninfo.hu/softskills/) - Project manager, Hungarian team leader: - Active participation on country visits, - Preparing the country report - Responsibility for the hosted events, presentations etc. |
| 09/1999 – 08/2003 | Hungary | Capital Employment Office, Budapest | Professional employment counsellor | - Training leading activities (e.g. Job Club, group career counselling) - Group work counselling - Individual counselling - Usage of Choices ’96 & 2000 career guidance programmes http://www.bridges.com/us/prodnserv/choicescd_hs/index.html - Employment analysis of a branch office district - Programmes implementation of Active Labour Market Policy (ALMP) |

- Other relevant information (e.g., Publication)

Other project experiences

Front desk officer (60 rooms lodge) for CAMP USA programme for 4,5 months (2001), USA WI

Lecturing

- Lecturer in five different Hungarian universities/ colleges. (U. of ELTE, U. of Gödöllő, U. of Semmelweis, Wesley College, U. of Szeged, U. of Economics Budapest; King Zsigmond College)

- Subjects are: employment policy/ workaholism/ career guidance practice/ career guidance policy/ Human resource management

Professional References on-line:

- http://ktl.jyu.fi/ktl/elgpn

- http://english.employmentpolicy.hu/Engine.aspx

- http://internet.afsz.hu/engine.aspx?page=full_kulfoldi_palyaor_eu_magyar_llg_tanacs

- http://internet.afsz.hu/engine.aspx?page=full_tamop_222

- http://www.disco-tools.org/index.php?locale=hu_HU

- http://www.taninfo.hu/softskills/

- www.eletpalya.afsz.hu

In-service professional trainings

- 2004 University of Tampere, Finland e-learning, EU employment system ECTS 4 p. (English course)

- 2003 Summer University, Central European University (CEU SUN), Budapest mediation and

- arbitration (English course)

- 2002 Summer University, Central European University (CEU SUN), Budapest education policy (English course)

- 2003 public service administration, special state examination

- 2003 EUROASI – Addiction Severity Index survey

- 2003 Hungarian National Adult Education Institutes development and qualifying expert course

- 2001 journalist course

Personal professional website

http://www.borbelytiborbors.extra.hu/home.html; My LinkedIn profile , Research Gate and Google Scholar are also available on-line.

March, 2015

COMPONENT LEADERS, SHORT – TERM EXPERTS

CURICULUM VITAE

Proposed position in the programme:  Component leader 1

1. Family name: 			P A L I K O V Á

2. First names: 			Elena

3. Date of Birth: 			22nd October 1977

4. Nationality:	Slovak

5. Civil status:		             	married

6. Education:

| Institution | Comenius University, Bratislava, Slovakia, Faculty of Law |
| --- | --- |
| Date: from :to | September 1996 - June 2001 |
| Degree(s) or Diploma(s) | Master of Laws (academic diploma) |

| Institution | Comenius University, Bratislava, Slovakia, Faculty of Philosophy, Specialization: German and Promotion |
| --- | --- |
| Date: from :to | September 1996 – December 1997 |
| Degree(s) or Diploma(s) | Certificate |

7. Language skills: Mark native, 5=excellent, 4=good, 3=satisfactory, 2=fair, 1=weak for competence)

| Language | Reading | Speaking | Writing |
| --- | --- | --- | --- |
| English | 5 | 5 | 5 |
| German | 5 | 5 | 5 |
| Slovak | Mother language |  |  |

8.	Membership of professional bodies:

- Regular member of the Advisory Committee for Occupational Health and Safety (2004 -2009);

- Alternative Member of the Governing Board of the European Agency for Safety and Health at Work (2004 -2009, continuing);

- Alternative Member of the Governing Board of the European Foundation for the Improvement of Living and Working Conditions (2004 -2009, continuing);

- Member of Slovak National OSH Net.

- Irregular Member of Council working groups.

9.	Other skills:   Computer literacy (MS Office, Internet, Power Point, etc.), tourist – guide licence 
		      driving licence “B”

10.    Present position: 	Supreme State Counsellor

| Date | Since 2001 -ongoing |
| --- | --- |
| Institution/location | Ministry of Labour, Social Affairs and Family of the Slovak Republic, Department for EU relations and International Cooperation, Bratislava |
| Description | - Co-operation on carrying out the obligations in the former negotiation chapters: free movement of persons and social policy and employment; to comment the draft legislation in the area of labour law, employment and occupational health and safety and prepared in the form of acts and governmental regulations. - Preparation of the framework positions and instructions for the Social Questions WP sessions and Council of ministers meetings. To manage and perform the notification process within our Ministry responsibility. To take part in the European Commission expert working parties and a representation of the Slovak Republic in the EU agencies. |

- Years within the OSH and Labour law area:  13  (Since 2001)

12.	Key qualification: (Relevant to the programme)

Good knowledge and active practice of:

- Labour law relations in practice  - employment/antidiscrimination/OHS/labour market

- Proven record in drafting law for acquis transposition

- Experience in pre-accession process and approximation of law in social area - transposition and implementation of EU Directives

- Practical negotiation skills in terms of EU lobbying and EU negations in the decision-making bodies of European Community;

- Good knowledge of the labour market matters and employment policy – national and EU-level

- Cooperation of Slovak executive and national parliament in the EU matters;

- Preparing and evaluation of positions and statements for minister for the EPSCO Council;

- Overall view of primary and secondary EU legislation – labour law, employment and occupational health and safety;

- Proven twinning experience in twinning “IN” and “OUT”

- International and mainly European experience – working in multicultural, cross-beneficiary groups on legal matter.

- Specific experience/international work experience:

| ADEPT Course on “Social Affairs and Employment” | Clingendael, Hague, Holland EU - enlargement, Dutch Model, International Organisations, Human Rights in the EU, European Labour Law, Labour Market Policies |
| --- | --- |
| From: Till: | 2002 |
| Qualification obtained | Certificate |

| ADEPT Course on “How to operate in Brussels” | Hague, Holland Coordination of European Policies, Lobbying the European Union and Negotiation in the EU, Comitology, Project Cycle Management, SWOT analysis and strategic planning, EU decision –making procedure, Lisbon Agenda. |
| --- | --- |
| From: Till: | 2004 |
| Qualification obtained | Certificate |

| Course: “State, Executive and Ökonomie in Deutschland | Berlin, Germany Coordination of European Policies in Germany, Lobbying the European Union and Negotiation in the EU. |
| --- | --- |
| From: Till: | 2004 |
| Qualification obtained | Certificate |

14. Professional Experience:

| Project “Improved Labour Protection System in the Slovak Republic” | Bratislava, SR Improved Labour Protection System in the Slovak Republic – Legislation in the area of occupational health and safety, full and correct transposition of OSH Directives into National Legal Order of the SR. |
| --- | --- |
| From: Till: | 2001 – 2002 |
| Qualification obtained | Certificate |

| Matra project “Assessment and strategic analysis of the (financial) impact of occupational health and safety legislation on Slovak entrepreneurs.” | Bratislava, SR Expert preparation for the assessment and strategic analysis of the (financial) impact of occupation health and safety legislation in the Slovak Republic. |
| --- | --- |
| From: Till: | 2002 |
| Qualification obtained | Certificate |

| Course of Effective Communication skills | Bratislava, SR Presentation techniques, techniques how to deal with clients and public, effective team work, Telephone and PC communications skills, public and human relations. |
| --- | --- |
| From: Till: | 2005 |
| Qualification obtained | Certificate |

| Twinning Project MK/2006/IB/SO/01 “Review of the National Labour Legislation.” | Skopje, Macedonia (FYROM) Overall Objective of the project: To support the improvement of capacity of the country in reinforcing labour market and preparing for the accession to the European Union. Project purpose: To improve the capacity of the MoLSP in revising and enforcing the country’s labour legislation, in line with EU legislation and with the EU best practices, as appropriate. COMPONENT 1, COMPONENT 3: Improving the MoLSP capacity on issues linked with the EU labour legislation/activity as regards labour law implementation and occupational health and safety - Presentation and analytical description of respective EU Directives falling under subheading Health and Safety at Work and Labour Law, Support provision facilitating elaboration of ToC for Directives on Health and Safety at Work Setting up priorities for acquis transposition plan based on recommendations. Analysis of the existing implementing legislation and administrative guidance in the field of Labour Inspection. New beneficiary country OSH legislation was analysed and the table of concordance was evaluated as regards the binding provisions of EU legislation. COMPONENT 2: Assessment and reviews of country legislation on labour, employment and unemployment related insurance The assessment analysis of the existing employment legislation, especially the Law on Employment and Insurance in Case of Unemployment with a view to EU primary and secondary legislation, EU employment policy, ILO conventions and recommendations, European Social Charter in order to make concrete practical proposals for a further improvement and/or drafting of a new Employment Law. |
| --- | --- |
| From: Till: | 2008 - 2009 |
| Function | STE- component leader |

| Twinning Project “Health and Safety at Work”, IPA 2009, Croatia | Bratislava, SR Presentation techniques, techniques how to deal with clients and public, effective team work, Telephone and PC communications skills, public and human relations. |
| --- | --- |
| From: Till: | 2011-2012 |
| Function | STE |

15. Reference upon request

CURRICULUM VITAE

Proposed position in the project: Component leader 2

1.	Family name: 	KATUSCAK

2.	First name: 	Boris

3. 	Date and place of birth: 	02/10/1977, Banska Stiavnica

4.	Nationality: 	Slovak

5.	Civil Status: 	single

6. 	Education:

| Institutions: | University of Economics in Bratislava, Slovakia Dolnozemska cesta 1, |
| --- | --- |
| Date: From (months/year) To (months/year) | September 1998 May 2003 |
| Degree: | Dipl. Ing. (academic diploma) |

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
|  | Mother Tongue |  |  |  |
| English | 5 | 5 | 5 | 5 |

8.	Membership of Professional Bodies:

9.	Other skills: MS Office (Word, Excel, Power-point), ASU, Lotus Notes, Omega;

10.	Present Position: Advisor to Director General

11.	Years of professional experience: over 10 years of hands-on experience iun employment area

12.	Key qualifications: relevant to the project

- 9 years of professional experience in strategic management, steering,  coordination and supervision of labour offices (employment offices) in the area of employment services and  active labour market policy implementation;

- 6 years of proven experience in the management the implementation of new concept of employment services model in Slovakia and supervision of its implementation within 79 labour offices

- 10 years of professional experience in capacity building of the labour offices (employment centres) and relevant stakeholders to implement new active measures

- 9 years of professional experience in management of the national projects financed within the ESF and implemented on the national, regional and local level

- Managing the Grant management system co financed from the ESF for provision and delivery of  services including active labour market measures on national and regional level ( planning of the Calls for proposals, Guidelines, Operational Manuals, selection of grants, monitoring, reporting evaluation) and supervision of its implementation on the subordinated level

- 8 years of professional experience in communication and knowledge management strategies and guidelines for planning, monitoring and reporting the activities of the (Central office of labour, social affairs and family (COLSAF)

- 8 years of proven experience in change management policy provision to follow the common strategy to improve the services of the labour office for clients (implementation of Service model)

- Strong leadership and management skills ( coordination and management of 79 labour offices in different areas of employment policy)

- Legal expert in the field of harmonisation Slovak legislation with the EU Acquis in the field of free movement of workers within the HQ of Employment Service;

- In charge of setting up necessary structures with required administrative capacity fulfilling the preconditions for future integration of Slovakia in EURES network;

- Proven experience in capacity building of the employment office staff,  TNA, development of training plans, training materials and organising trainings for COLSAF staff dealing with new service model of the COLSAF;

- Proven experience in several twinning light projects implemented in the SK (SK06/IB/SO/01/TL -  “Strengthening of administrative structures for co-ordination of systems of social security in connection to the rulings of the European Court of justice”;   SR0110 01 01 0012 – “Free movement of workers and the co-ordination of social security schemes”; TWL-SR 0110/01/01/0012 “Strengthening the performance of Slovak Administrative Structure required for ‘Co-ordination of Social Security Schemes’; “Introduction of a Standard Classification of Occupations, preparation for participation in EURES” (SK99/IB/CO-01)

13.	Specific experience in the region or else:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| Hungary | 07/2003 – 12/2005 | Cross border cooperation - project focused on posting of workers in selected automotive companies |
| Poland | 1/2004 – 09/2008 | Slovak – Poland cross border cooperation based on mutual governmental agreement |
| Czech Republic | 07/2003 - ongoing | Cross border cooperation based on the Intergovernmental Agreement on mutual employment of workers |
| Austria | 2010 - 2012 | Forum for co-operation in the job market policy in cross border region Slovakia - Austria |
| Spain | 12/2001 – 06/2002 | SK/IB/99/CO-03 Twinning missions |

14.	Professional experience:

| Date: from (month/year) to (month/year) | September 2010 - ongoing |
| --- | --- |
| Location | Slovakia, Bratislava |
| Company / Organisation | Central Office of Labour, Social Affairs and Family |
| Position | State Advisor to Director General for Employment Policy |
| Job Description | - Strategic management, steering, coordination and supervision of employment offices in the area of employment services and active labour market policy; - Coordination the drafting of the Operational Programme documents and related measures to be financed on national, regional and local level - Member of the working group dealing with a redefinition of the concept of employment services model in Slovakia and supervision of its implementation within 79 labour offices - Development, testing, piloting and implementation of new active labour market measures based on the current needs of the market - Capacity building of the labour offices (employment centres) and relevant stakeholders to implement new active measures - Promotion of the measures implemented through the Operational Programme Employment and Social Inclusion on policy level ( awareness campaign for job seekers and employers, NGO, social partners and other project applicants - Preparation of internal standards and legislative instruments in the area of employment foreigners and citizens of EU member states - Implementation of the national legislation with the EU acquis in the field of free movement of workers - Coordination of conducting reports and analysis in the area of employment policies (implementation of active labour market measures, ad hoc operational analysis, regular analysis of the situation on the labour market; assessment and analysis of employment programmes); - Managing the national projects financed within the ESF - Strategic planning of EURES activities within EURES Grant; - Processing of presentations, processing of analysis, reports and other documents in the field of targeted policies within EU; - Development of procedures, manuals, guidelines, forms and other materials for implementation of free movement of workers legislation and EURES; - TNA, development of training plans, training materials and organising trainings for COLSAF staff dealing with new service model of the COLSAF; |

| Date: from (month/year) to (month/year) | January 2004 to August 2010 |
| --- | --- |
| Location | Slovakia, Bratislava |
| Company / Organisation | Central Office of Labour, Social Affairs and Family |
| Position | Head of Employment Service Dpt., EURES Manager for Slovakia (appointed since January 2004); |
| Job Description | - Responsible for coordination and management of employment services and active labour market measures on national level (79 labour offices) - Responsible for applying a legal, secondary and other regulations and acts related the provision of employment services, e.g. employment mediation, career guidance, employment plans preparations, training , re-training and other supported training programmes; - National co-ordination of the harmonisation of the national legislation with the EU acquis in the field of free movement of workers - Responsible for designing, testing, implementation of active labour market policy measures and methodology guidance within 79 labour offices - Planning, designing and multiyears budget allocations for delivery of employment services and active labour market measures within the Operational Programmes Employment and Social Inclusion - Approval of financial allocations for delivery of employment service within 79 labour offices - Setting up the Grant management system co financed from the ESF for provision and delivery of services including active labour market measures on national and regional level ( planning of the Calls for proposals, Guidelines, Operational Manuals, selection of grants, monitoring, reporting evaluation) and supervision of its implementation on the subordinated level - In charge of management, development, implementation, monitoring, reporting of national projects financed within the ESF: 15 National projects e.g Career guidance support; Support the Individual Actions plans; Information services assessable for all; Activation works for Inclusive Labour Market; etc. - Drafting reports, policy papers, employment incentives related to active labour market implementation - Management and coordination of the employment offices in the field of employment of foreigners, EU member states and the third countries; - Capacity building of the EURES Advisors and Assistants (development of the methodological tools; training needs analysis for EURES staff on local and regional level; development of the training curricula and delivery of training courses based on TNA ); - Management of EURES network compound of almost 100 EURES Advisers and Assistants on the territory of the Slovak Republic; - Alignment of the free movement of workers agenda with the national legislation and participation in EURES - In-depth analysis of the impact of the free movement of workers, especially regarding the administrative capacities of all institutions involved including the statistical monitoring of posted workers; - Carrying out the training needs analysis, preparing the training programmes (general and practical) and delivery of information sessions and targeted training - Overall management of the EC EURES grants (drafting the proposals, implementation of activities; management of the budget spending) - Representing of COLSAF at the EC working groups in free movement of workers - Development of number of booklets, manuals, working procedures, brochures, newsletters for different areas of free movement of workers and implementation of EURES network - Chief of mutual Slovak-Polish intergovernmental commission for cross-border cooperation in the field of labour and social policy – appointed by the State Secretary of the Ministry of Labour, Social Policy and Family; - Representative of the Employment Service at Inter-ministerial commission for migration - MECOMIC; - Member of Directive Board for migration and integration of foreigners of Migration Office of Ministry of Interior – appointed by the Vice – Prime Minister of Slovak Government; |

| Date: from (month/year) to (month/year) | July 2003 to December 2003 |
| --- | --- |
| Location | Slovakia, Bratislava |
| Company / Organisation | Central Office of Labour, Social Affairs and Family |
| Position | EURES Manager |
| Job Description | - Building and Introducing of EURES network in Slovakia at the accession of Slovakia to EU - Management the initial EURES network EURES of Advisers and Assistants at the whole territory of Slovakia - Managing the EC EURES grants - Representing of COLSAF at the EC - Preparation of administrative structures and procedures for participation in EURES - Organisation of innitial training for potential EURES managers - Counselling and providing specific information on free movement of workers in the EU, development of information on living and working conditions in the EU countries - Development of methodological tools in the area of employment for foreigners - Elaboration of the strategic documents for data collection and web site for EURES |

15. Others:

Organizing of 12 International Job Fairs for EURES with the participation of more than 350 employers from 20 EU/EEA countries;

Organizing of biggest job fair in Slovakia – JobExpo 2010, with participation of 150 employers and investors from SVK and Europe (www.jobexpo.sk)

Introducing the activity: Business breakfast with employers - to Local Labour Offices, activity was in last 3 years attended by more than 1500 employers;

Regular organization of multinational conferences on migration, cross-border cooperation, chairing these conferences;

CURRICULUM VITAE

Proposed role in the project:	Component leader 3

1.	Family name: 		GERŐ

2.	First name: 		George

3. 	Date and place of birth: 		05/02/1954, Budapest

4.	Nationality: 		Hungarian

5.	Civil Status: 		married

6. 	Education:

| Institutions: | Technical University of Budapest, Faculty of Transport Engineering, Branch of Information System Design |
| --- | --- |
| Date: From (months/year)-To (months/year) | Sep 1973 Jun 1978 |
| Degree: | Engineer MSc, information system design (academic diploma) |

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Hungarian | Mother Tongue |  |  |  |
| English | 5 | 5 | 5 | 5 |
| French | 3 | 3 | 3 | 2 |

8.	Membership of Professional Bodies:

9.	Other skills:

- Management

- Project management

- Process design and reengineering

- Advanced user level of MS Office suit

- Database design and development (MS Access)

- Presentation skills (oral and written)

- Driving licence and experience, category “B, C”

10.	Present Position: Head of IT Department at National Labour Office, Budapest

11.	Years of professional experience: 36 years

12.     Key qualifications:

- Public administration professional examination, Budapest, 2009

- Logistics management, Brussels, 1993

- Database management, database design, Brussels, 1993

- Business finance, Budapest, 1991

- Marketing management, Budapest, 1991

- HTML, PHP trainings, Budapest, 2005

Skills, experience:

- Management and business administration

- Development and implementation of IT applications; profound knowledge of IT systems and databases including employment systems operational within Hungarian PES

- Management of IT organisations

- Project management

- Business process planning

- Strategic planning

- Change management

- System design and analysis

- Effective decision making ability, flexibility, creativity and initiative spirit

- Motivation and team building skill

- Excellent written and oral communication skills

13.	Specific experience in the region or else: cooperation with Slovakia and Czech Republic; certain experience in West Balkans countries

14.	Professional experience:

| Date: from (month/year) to (month/year) | Jan 2013 - present |
| --- | --- |
| Location | Budapest, Hungary |
| Company / Organisation | National Labour Office, PES, Hungary |
| Position | Head of IT department |
| Main tasks and responsibilities | - Managing the IT department (60 people) - Participating in IT development projects - Representing the Office when negotiating with third parties - Taking the “single contact of Hungary” role in the European EURES interoperability project |

| Date: from (month/year) to (month/year) | Sep 2012 - Dec 2012 |
| --- | --- |
| Location | Budapest, Hungary |
| Company / Organisation | Kincsinfo, IT company of Hungarian State Treasury |
| Position | Project advisor |
| Main tasks and responsibilities | - Providing project management support services for complex development projects |

| Date: from (month/year) to (month/year) | Sep 2010 – Sep 2012 |
| --- | --- |
| Location | Budapest, Hungary |
| Company / Organisation | WebEye International Ltd. (Market leader multinational GPS technology provider for 14 countries in Europe) |
| Position | Head of International Business Extension |
| Main tasks and responsibilities | - Lobby and networking activities at multinational companies - Development and support of international company network - Development of yearly business planning and evaluation processes - Executive coaching activities |

| Date: from (month/year) to (month/year) | Dec 2007 – Sep 2010 |
| --- | --- |
| Location | Budapest, Hungary |
| Company / Organisation | National Office for Technology and Research (NKTH), Budapest |
| Position | Head of IT Department Vice president (of operational areas) |
| Main tasks and responsibilities | - Developing Office-wide operational processes and management procedures - Managing the IT department of the Office |

| Date: from (month/year) to (month/year) | Jan 2001 – Dec 2007 |
| --- | --- |
| Location | Budapest, Hungary |
| Company / Organisation | Gylen Consulting Ltd., Budapest |
| Position | Operation development and management consultant, interim manager |
| Main tasks and responsibilities | - Business process reengineering and organisational development (IT, logistics) - Management support – strategic planning, change management, operation development - Project management (IT, processes, organisation) Priority projects: Interchain (The Netherlands) Lagermax Group - DPD, AED, Spedíció, (Budapest) Timesped, (Budapest) Eurogate Group, (Budapest, London) Dunapack Plc, Budapest Waberer's / Deltasped Ltd., (Budapest) |

| Date: from (month/year) to (month/year) | Sep 1996 – Dec 2000 |
| --- | --- |
| Location | Budapest, Hungary |
| Company / Organisation | Hungarian Telecom (MATÁV), Budapest |
| Position | Project manager of “Invoicing of non-voice services” (BSS) Head of Program Office, Product Management Directorate |
| Main tasks and responsibilities | - Implementing Invoicing IT application as project manager - Develop and operate internal business processes for supporting the Product Development area of the company |

| Date: from (month/year) to (month/year) | Sep 1992 – Jul 1996 |
| --- | --- |
| Location | Brussels, Belgium |
| Company / Organisation | DHL WORLDWIDE EXPRESS |
| Position | Head of Eastern European IT Support |
| Main tasks and responsibilities | - Developing IT organizations for DHL companies - Managing IT projects in Eastern European countries - Planning and providing continuous training services for IT personnel - Managing and providing IT support services for the DHL companies in different Eastern European countries and for the European Headquarter - Integration testing activity in DHL's Strategic Program (testing activities in the UK and in the US) |

| Date: from (month/year) to (month/year) | Apr 1989 – Sep 1992 |
| --- | --- |
| Location | Budapest, Hungary |
| Company / Organisation | DHL WORLDWIDE EXPRESS |
| Position | Deputy Director of IT for Eastern Europe |
| Main tasks and responsibilities | - Developing the standard IT functionalities of the Eastern European Head Office - Supporting the establishment of IT functionalities in the Eastern European countries - Member of the management team of the Eastern European Head Office |

| Date: from (month/year) to (month/year) | Sep 1978 – Apr 1989 |
| --- | --- |
| Location | Budapest, Hungary |
| Company / Organisation | HUNGAROCAMION International Road Transportation Plc., Budapest, |
| Position | Head of Department, system analyst |
| Main tasks and responsibilities | - Development of IT applications for supporting the business processes of the company – as system designer and system analyst - Managing the Development Team (department) established for the transportation functionality development |

CURRICULUM VITAE

Proposed position in the project: 	Component leader 4

- Family name:			PAVLOVOVA

- First names:				Luba

- Date of birth:			25 October 1959

- Nationality:				Slovak

- Civil status:				Divorced

- Education:

| Institution [ Date from – Date to ] | Degree(s) or Diploma(s) obtained: |
| --- | --- |
| Technical University, Moscow, Russia,1979-1984 | MSc Diploma in Electronic Engineering (studies done in English & Russian languages) |
| Council of Europe (CoE) 1993-1994 | Long term training course on European institutions, project development and intercultural relations, Certificate issued by the CoE |
| Mobility International of the USA, July-August 1996 | Training on Leadership, Certificate of MI USA |
| Comenius University Bratislava, Post-graduate study, Centre of European studies, Slovakia 1997– 1998 | Post-graduate certificate on European Integration and EU Law |
| European Commission, Directorate –General EAC–“Education and Training”, Brussels, January -April 1997 | Training Certificate /Internship within Directorate General EAC- Community Programme and European Integration |
| European Institute of Public Administration, July 1999 | Certificate on Taiex Seminar on the European Union-“Institutions, Legal System, Policies, Enlargement” |
| OECD LEED Programme Trento, Italy, October 2006 | Certificate for professionals on Building Development Strategies For Cities And Regions (A capacity building training for policy-makers and practitioners) |
| European Consultants Organisation, 2006 | Certificate for professional Trainer of Trainers |
| European Commission, Directorate –General Enlargement, Brussels, March, 2008 | Training certificate – Twinning Projects in IPA countries, special training for EC Resident Twinning Advisers on accession process and sustainable development in candidate countries |

- Language skills: (Mark 1 to 5 for competence, where 5 is the highest)

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Slovak | Mother tongue |  |  |  |
| English |  | 5 | 5 | 5 |
| Bulgarian |  | 5 | 5 | 5 |
| French |  | 4 | 3 | 3 |
| Russian |  | 5 | 5 | 5 |
| Macedonian/Serbian/Croatian |  | 5 | 4 | 4 |

- Membership of professional bodies: Member of the Council of Europe Trainers and Consultants´ Pool, Strasbourg, France; Member of the Steering Committee of the European Social Inclusion Platform (ESIP); Member of the established Centre of Regional Competence AT-SK-HU-CZ (since Dec´2008), Member of the Supervisory Board of FYROMn Centre for Economic and Social Development (CESoR).

- Other skills:  (e.g. Computer literacy, etc.) PC skills – MS Windows (Word, Excel, Access, PowerPoint, Outlook), internet, Trados software translation tools; active driving licence

- Present position: Since 2004 Director and Chief Officer ALMPs of RDA, Bratislava Region

- Years of experience: more than 22 years of professional experience

- Key qualifications:

- Master Degree in engineering with a post-graduate qualification in “European Integration, EU-Law and Public Administration Reforms” and over 17 years of professional experience in Labour Market policies development and implementation, Active Labour Market Measures and procedures, HRD, LLL, labour market analyses and Active Employment Measures (AEM);extensive experience in labour law, in particular in pre-accession labour market contexts, in Slovakia and later in West-Balkans countries – i.a. assisted the Ministry of Labour of MK and Ministry of Labour of HR in drafting proposals for changes of relevant legal acts harmonised with the acquis

- Extensive experience in management of communication, awareness raising and information actions related to ALMPs, ALLMs, ESF and IPA

- Strong analytical, negotiation, organisational and communication skills based on long-standing experience as Expert and Project Coordinator in technical assistance, capacity building and twinning projects within public administration

- 7 years international experience in donor-funded projects in the fields of policy advice, legal and regulatory drafting, expertise for legal and regulatory documents linked to employment issues:

- Trained of end-users on policy planning at all levels and design of employment and other development and ALMMs  (1994, Romania)

- Support to Directorate for European Integration and Council of Ministers on AEMP and LLL(2006/2007, Romania)

- Strengthening social partnerships in employment policies in Romania (2006, Romania)

- Revised the Romania’s OP HRD and Programme Complement in line with requirements of the EU Regulation 1081/2006 on ESF for Active Employment Measures (2007/2008, Romania)

- Resident Twinning Adviser on Labour Law in Macedonia: Revising and enforcing the country’s labour legislation in line with acquis communautaire and with EU best practices; elaborating recommendations for the necessary implementing legislation, administrative guidance and institutional models; assisting the MoLSP in drafting proposals for relevant legal acts harmonised with the acquis(2008/2009)

- Advised MoL on sustainable implementation of EU acquis communautaire in  Macedonia (2009/2010)

- Worked on legal approximation – labour law, advice and support for elaboration of Tables of Concordance, and trained partners in the process of law drafting and skills development(2011/2012, Croatia)

- Policy advice to the Directorate for European Integration, Ministry of Civil Affairs, entities´ ministries on country’s involvement in new EU programmes focused i.a. on employment, based on EU regulations 2013/2014, Bosnia and Herzegovina)

Additionally, international experience in donor-funded projects in fields such as: Development of Youth Policy (2003, Azerbaijan), support in the implementation of the grant schemes for active employment measures (2007/2008, Romania), Creation of the Conditions for Using the Reform Tools of EU ECVET and EURES (2012/2013, Macedonia)

- 7 years experience in transitional economies providing policy advice and technical assistance to Ministries and public institutions as above, plus 5 years experience in technical assistance and twinning in Slovakia before EU accession (1998-2003)

- 5 years experienceof the above direct experience in supporting Ministries and public institutions to harmonise their employment and labour legislation with the EU Aquis (2008-2012), plus an additional 1.5 years in technical assistance in acquis transposition to Slovakia before accession (1998-2000)

- Hands-on experience in elaboration and putting in practical terms of Communication Strategies for state bodies (reference: Slovakia – Ministry of Labour, Croatia – Ministry of Labour, Macedonia – Ministry of Labour)

- Intimate knowledge of EU policies, directives, legislation and regulations related to employment gained by many years experience in acquis transposition and technical and legal advice based on EU regulations; as RDA Director in Slovakia, responsible for elaboration of stand points on EU social policy for Ministry of Labour on new legal acts related to employment and labour market reform

- More than 3 years’ experience within the Public Employment Service in Bratislava Self-governed Region in delivering Active Labour Market and Employment Measures (ALM-AEM); also, long-standing experience as Director of a Regional Development Agency and Chief Officer for ALMPs

- Extensive knowledge of Project Cycle Management, programming and decision-making processes of EU support programmes.

- Strong leadership skills; proven record in leadership and project management, excellent negotiation, presentation and communication skills (all levels: local/regional/national/ international)

- Experience as Expert and Project Manager/Coordinator in technical assistance, capacity building and Twinning projects within public administration.

- Long-term recognised experience in leading national & EU multi-national teams and local experts on EU complex projects; supervising and co-ordinating all technical aspects of project contracts; strong analytical, negotiation, mediation and communication skills

- Certified trainer in Change Management

- Excellent knowledge of Twinning philosophy and rules based on direct involvement in 6 TW OUT projects as RTA and STE/MTE

- Specific experience:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| Bulgaria | 02/2003-06/2003, 10/2004, 11/2005, 03/2006-09/2006, 2009-ongoing | Several projects aiming at BG authorities preparation for accession: capacity building, acquis, partnerships, sustainable development Developed Strategy for Sustainable Development of South-Central Region (ESF) |
| Azerbaijan | 06–10/2003 | Ministry of Education of Azerbaijan - development of youth education and employment policies from regional to national level, financed by Council of Europe |
| Romania | 04/1994, 04/2006- 07/2006; 05/2007-on going | TA and Twinning project on CBC capacity building (4 OP on CBC) |
| Bosnia and Herzegovina | 07/2006–10/2007 | Two Twinning light projects for DEI, Office of Govt. on EU integration (EU programmes in education & social areas) |
| Macedonia (FYROM) | 06/2008 – 09/2009 | RTA – Twinning project Review of the national labour legislation |
| Macedonia (FYROM) | 10-11/2009 | Slovak Aid: RELLMAS project aiming at local labour markets incl. measures for ethnic communities, preparation of study visit for FYROM officials to Slovakia (good practice experience with bringing closer the education to the needs of labour market) |
| Macedonia (FYROM) | 04 – 09/2010 | Slovak Aid project: training for municipalities and Economic Chamber of MK on partnership building and project development on HRD – LLL and AEM to be financed from IPA funding |
| Albania, Croatia | 02/2010 | Skills for Employability project for South East countries |
| Croatia | 10/2011-07/2012 | RTA – Twinning project Health and Safety at Work |
| Turkey | March 2010 | Skills for Employability - Forecasting of skills for employability and regeneration of the LM - project for South East countries financed by the British Council |
| Croatia | 2010-2011 | Twinning project for Ministry of Labour and Pension System in OHS |
| FYROM | 2012-ongoing | - Slovak Aid project COCURT: with OEM, CESOR and ESA (local) on ECVET, EURES and career guidance, (direct work with ESA offices in Skopje, Strumica, Veles, Stip a Bitola) - EU-funded project (LLP) EU.EM.NET on skills forecasting and engagement of employers in the process – sector of tourism & hospitality |

14.	Professional experience:

| Date: from (month/year) to (month/year) | 01/2004 – on-going |
| --- | --- |
| Location | Bratislava |
| Company / Organisation | RDA |
| Position | Director and Chief Officer for ALMPs |
| Job Description | Director of the Regional Development Agency, responsible for a variety of tasks: Coordination of RDA departments: staff management, team management;Coordination of activities with Ministry of Labour(MoL) on development and implementation of Employment Reforms and Employment and Labour Market Policies (ELMP); Drafting Active Employment Policies (AEPs), designed methodological guidelines for ALMMs; Elaboration of standpoints on EU social policy for Ministry of Labour on new legal acts related to employment and labour market reform and Bratislava Region and coordination and management of strategic projects on LLL&AEM and ALMM of Bratislava Region; Elaborated Employment Action Plan for Bratislava Region and worked on Cross-border Employment Strategy Bratislava – Vienna; Review of EU-best practices for regional socio-economic development within ESF, labour market policy development, strategic ALMM projects design & implementation;Capacity building of public sector in AELMP; regional, national and EU employment and labour market strategies; analysis of the labour market; Benchmarking setting for LLL and AEM projects and programmes and development of a Project Pipeline for Bratislava Region for the ESF –Active Employment Measures;Team leader/Project coordinator of more than 85 projects on ALMM, HRD & LLL. Since 12/2010 – consultancy to the Ministry of Economy, Labour and Entrepreneurship, Croatia;Building &strengthening social partnerships in employment policies;assessment report and recommendations for improving ESF procedures. |

| Date: from (month/year) to (month/year) | 3/2013-6/2014 |
| --- | --- |
| Location | Bosnia and Herzegovina - Sarajevo, banja Luka, Brcko |
| Company / Organisation | Directorate for European Integration |
| Position | Team Leader |
| Job Description | EU-project (framework contract) :Support to participation of Bosnia and Herzegovina in the new 2014-2017 cycle of EU Programmes (EUPs) with focus on Erasmus+, Horizon, EaSI programme Ensured mapping of EUPs; support to institutions to enable their participation in EUPs and strengthen their capacities; Policy advice on involvement in new EU programmes focused on employment and social innovation, education, research and technological development and SME support based on EU regulations: focus on EaSI Reg. No 1296/2013 (2014-2020); Managed meetings of BiH institutions; set up the methodology for and conducted trainings on EU programme on education (Erasmus+) and EaSI (Employment and Social Innovation). |

| Date: from (month/year) to (month/year) | 09/2012- 09/2013 |
| --- | --- |
| Location | Skopje, FYROM |
| Company / Organisation | Centre for Social and Economic Development |
| Position | Team leader |
| Job Description | Technical Assistance Project SlovakAid: „Creation of the Conditions for Using the Reform Tools of EU ECVET and EURES in Macedonia via Transfer of Slovak Experiences“ (SAMRS/2011/10/07) - Managed the project implementation and a team of 6 MS experts and 11 Macedonian experts; supervised the quality of products and outcomes; - Prepared and conducted training on ECVET (European Credit system in VET) for state officials and social partners; provided Slovak experience relevant for Macedonian conditions; |

| Date: from (month/year) to (month/year) | 11/2010-12/2011 |
| --- | --- |
| Location | Croatia, Zagreb |
| Company / Organisation | RDA for Ministry of Labour and Pension System, Croatia |
| Position | Resident Twinning Adviser (RTA) |
| Job Description | Twinning project “Health and Safety at Work”Managed the project of 1,254M Eur on-situ in Croatia ; Support for institutional building of 5 key state institutions, i.a.Ministry of Labour and Pension System (previous MELE), Consultation and involvement of 5 key CRO institutions for development of an effective occupational health and safety system in Croatia in line with the EU standards as well strengthening of the administrative capacities of mentioned CRO institutions related to health protection and safety at work, in line with the benchmark for Chapter 19 – Social Policy and Employment of the negotiations, in process of Croatia’s accession to the EU. Planned, designed and conduced training for groups of beneficiaries involving social partners in the process of law drafting and skills development in OHS sector; on-the-job training. Worked on legal approximation with the EU aquis – labour law, advice and support for elaboration of Tables of Concordance.Elaborated communication strategy for the Croatian beneficiaries on improving information services.Supported MLPS and other beneficiaries in elaboration of follow up project for Data Collector to be financed by ESF for Croatia.Developed strategic project under LLP on skills forecasting in OHS. Designed a common Communication Strategy and Road Plan for OHS – all beneficiaries, conducting TNA and training of beneficiaries staff, design and elaboration of the strategy development plan; elaborated reports and recommendations; Coaching and support – daily basis; Leader of team of 23 international experts (AT & SK) |

| Date: from (month/year) to (month/year) | 10/2009 -12/2010 |
| --- | --- |
| Location | Macedonia (FYROM) |
| Company / Organisation | Ministry of Labour and Social Policy, FYROM, |
| Position | Team Leader |
| Job Description | Programme-based approach: Technical Assistance Project SlovakAid: „ RELLMAS – Regional and Local Labour Market Support “ (SAMRS/2009/04/13) Elaborated regional and local labour market and employment analysis; Established partnerships at regional and local level and conducted training and education activities for selected representatives Elaborated local employment action plans at regional and local level and project pipeline based on the real needs of regions; Organized the Internships to Slovakia for selected participants aiming at labour market active policies examples and best practices sharing.Ensured institutional support for the implementation of EU acquiscommunautaire |

| Date: from (month/year) to (month/year) | 06/2008-09/2009 |
| --- | --- |
| Location | FYROM, Skopje |
| Company / Organisation | RDA for Ministry of Labour and Social Policy, Skopje |
| Position | Resident Twinning Adviser |
| Job Description | EC Twinning project “Review of the national labour legislation” - in consultation and involvement the Ministry of Labour and Social Policy of FYROM aimed at support for improvement of capacity of the country in reinforcing labour market and preparing for the EU-accession. Support state administration capacity in labour market and employment; Improving the capacity of the MoLSP in revising and enforcing the country’s labour legislation in line with acquis communautaire and with EU best practice on preparing for the accession to the EU; elaborated recommendations for the necessary implementing legislation, administrative guidance and institutional models;Defining the best institutional model for FYROM taking into account the country legal traditions and economic opportunities; Assisting the MoLSP in drafting proposals for changes of relevant legal acts harmonised with the acquis; Conducting TNA, design and elaboration of the implementation plan; reports and recommendations. |

| Date: from (month/year) to (month/year) | 07/2007 – 05/2008 |
| --- | --- |
| Location | Bucharest |
| Company / Organisation | RDA for Ministry of Labour, Family and Social Protection of Romania (MOLFSP) |
| Position | Key expert on Lifelong Learning |
| Job Description | Phare Project: Technical Assistance to support MOLFSP and Regional Intermediary Bodies in the implementation of the grant schemes for Active Employment Measures (AEM) & LLL for the qualification and re-qualification of the workforce by raising awareness, providing information and ensuring a transparent and competitive and effective process for projects appraisal and selection. Coordination of a team of 20 Local Experts. Undertaking a survey with a view to improving job quality and sustainability resulting from LLL and AEM grant projects and developing guidelines on EU best practices on market policy development and their application in the Romanian context. Training of potential grant beneficiaries in developing “winning” projects. Development of the campaign for promoting the grant scheme for ALMM and LLL. Utilisation of specific IT system for Structural Funds management. |

| Date: from (month/year) to (month/year) | 05/2007-06/2008 |
| --- | --- |
| Location | Bucharest |
| Company / Organisation | Ministry of Labour, Family and Social Protection of Romania (MOLFSP) |
| Position | Key expert on Labour market/LLL |
| Job Description | Phare Project: Technical Assistance to support MoLSSF and Regional Intermediary Bodies in the implementation of the grant schemes for Active Employment Measures (AEM) &LLL: Provided information and ensuring a transparent and competitive and effective process for projects appraisal and selection.Revised the Country OP HRD and Programme Complement in line with requirements of the EU Regulation 1081/2006 on ESF. Survey with a view to improving job quality and sustainability resulting from LLL and AEM grant projects and developing guidelines on EU best practices on market policy development and their application in the Romanian context. Trained of potential grant beneficiaries in developing “winning” projects.Developed of the campaign for promoting the grant scheme for ALMM and LLL. Utilisation of specific IT system for Structural Funds management. |

| Date: from (month/year) to (month/year) | 05/2007-6/2008 |
| --- | --- |
| Location | Bucharest |
| Company / Organisation | Ministry of Labour, Family and Social Protection of Romania (MOLFSP) |
| Position | Training coordinator on grant scheme and AEM |
| Job Description | Phare Project17M Euro: ‘Technical Assistance to support MoLSSF, NAE and final beneficiaries in the implementation of the grant schemes for active employment measures (AEM) mainly for youth, long-term unemployed and job seekers in rural areas and the implementation of the LLL grant schemes’. Co-management of the project and the training coordination; involved in: a) the campaign for promoting the grant scheme for ALMM and LLL;b)elaboration the evaluation methodology to be used for the grant scheme; c) revised all the“instruments” and procedures connected with the monitoring and contracting of the grant schemes, d) ensured effective training of project promoters in preparation of projects involving AEMs and LLL. |

| Date: from (month/year) to (month/year) | 04/2006-07/2006 |
| --- | --- |
| Location | Bucharest |
| Company / Organisation | Advisory Conciliation and Arbitrage Service, UK for Ministry of Labour, Family and Social Protection of Romania (MOLFSP) |
| Position | ESF/AEM Expert |
| Job Description | Twinning project- Supporting social dialogue and employment relations. Strengthening social partnerships in employment policies; Design of training programme for social partners (employers’ associations and trade unions on building capacity to implement Structural Funds, on EU good practices inALMM; Support the stakeholders in developing strategic projects in the area of AEMs and LLL to be financed by HRD OP.Elaboration of a guide book on EU best practices in AEM. Elaboration of ALMM and LLL projects for ESF funding. |

| Date: from (month/year) to (month/year) | 02-03/2006; 08-11/2006 |
| --- | --- |
| Location | Sarajevo, Banja Luka |
| Company / Organisation | Directorate for European Integration, Council of Ministers and Ministry of Civil Affairs |
| Position | STE/Training expert |
| Job Description | Two Twinning projects for the Directorate for European Integration, Office of Government of BiH and Ministry of Civil Affairs: 1) Support to the directorate for European integration and other relevant BiH institutions in preparations for participation in community programmes (LLL, YiA, CIP, Marco Polo, Daphne), and 2) Strengthening of State Level Institutions for co-ordination and preparation of BiH participation in European Community Programmes for LLL and Youth. Support to Directorate for European Integration and Council of Ministers on AEMP and LLL; Capacity building on public administration reforms. Since 2006 -On-going cooperation with BiH stakeholders in the area of ALMP/LLL– training and support for elaboration of proposals |

| Date: from (month/year) to (month/year) | 12/2005-10/2006 |
| --- | --- |
| Location | Slovakia |
| Company / Organisation | RDA for ECO, Brussels/ EUROFORMES |
| Position | ESF and Active Employment Measures Expert |
| Job Description | Regional expert within the project “Strengthening the regional and local capacities for management and implementation of Structural Funds assistance”.Coordinator of employment policy in Trnava Region; Policy advise on EU Regulations on Structural funds: 1081/2006 on ESF, 1080/2006 on ERDF, 1084/2006 on Cohesion fund and 1083/2006 on SF & CF incl. specialised training on EU Regulations for capacity building of state servants and public regional representatives; Design and implementation of tailor-made active labour market policies in the region; Capacity building of regional stakeholders with main focus on the ESF for potential final beneficiaries in Slovakia for the new programming period 2007-2013. TNA, Training programme designTraining of trainers, coaching on ALMM/LLL; Elaborated Manual for evaluation of ALMM projects. |

| Date: from (month/year) to (month/year) | 06/2003-12/2007 |
| --- | --- |
| Location | Slovakia |
| Company / Organisation | RDA for Employment Offices in Pezinok and Bratislava |
| Position | Expert on Active Employment and Labour Market Measures |
| Job Description | Responsible of Active Employment Measures, in charge of the following tasks within the Regional Public Employment Office: Responsible for the elaboration and implementation of of AEM and ALMM at regional level; Coordinator of the staff responsible to design projects in the area of AEM at regional level; Elaboration of special labour market policies and AEM schemes facilitating access to Education & Employment for disadvantaged groups, including young unemployed, Roma and long-term unemployed persons and unemployed women;Analysis of the local labour market needs, elaboration of recommendations and active labour market policies implementation and delivery; Encouraging partnerships with public and private organisations to improve employment opportunities for vulnerable target groups; cooperation with local employment pacts; Elaboration of projects on AEM and second chance education. |

| Date: from (month/year) to (month/year) | 07/2003 and 09/2003-10/2003 |
| --- | --- |
| Location | Baku, Ganja and Sheki regions |
| Company / Organisation | Ministry of Education Azerbaijan |
| Position | Consultant/Trainer |
| Job Description | Council of Europe funded project for capacity building in AZ education sector:Hands-on experience with the Ministry of Education of Azerbaijan- expert of the CoE/EC Partnership Agreement),Project “Development of Youth Policy from Regional to national Level”: developed education & training programme and strategic documents for AZ Ministry of Education. Training on sustainable programmes development for youth, on intercultural learning and on PCM and application preparation; Prepared handbook on financial opportunities for youth actions projects (CoE, EU, international donor foundations, EYC, bilateral support);Conducted specialised training on intercultural learning; |

| Date: from (month/year) to (month/year) | 12/2001 - 10/2003 |
| --- | --- |
| Location | Slovakia |
| Company / Organisation | Ministry of Labour and Employment of the Netherlands For the Slovak Ministry of Labour |
| Position | Twinning Project Coordinator |
| Job Description | EU Twinning “in” “Development of Social Dialogue on Bi-partite Level” project between the Ministry of Labour, Social Affairs and Familyof the Slovak Republic and the Ministry of Social Affairs and Employment of the Netherlands/ACAS, UK.Concepts creation aimed at employment development in Slovakia through AEM approach and active labour market policy; Supported and advised on legal aspects on Directives on consultation and information to workers; transposition of the relevant EU directives;Education reform for HRD (ALMM) – empowerment of social partners; education and training needs analysis for capacity building of social partners; ESF planning and programming activities for social partners involvement in the Active Labour and lifelong learning policy and measures. |

| Date: from (month/year) to (month/year) | 05/2000-11/2001 |
| --- | --- |
| Location | Bratislava, Zilina, Prievidza |
| Company / Organisation | Austrian Federal Environment Agency, Vienna for Slovak Ministry of Environment |
| Position | Twinning Project Coordinator |
| Job Description | EU Twinning “in” project between the Ministry of Environment of Slovakia and the Federal Environment Agency of Austria aimed at strengthening the institutions of Slovakia for ambient air protection. Capacity building of civil servants in environment area, including drafting legal provisions (acquis transposition);Training Needs Analysis and training design;Management of Grant Scheme and reports elaboration. *Klaus.radunsky@umweltbundesamt.at |

| Date: from (month/year) to (month/year) | 11/1998 – 06/2000 |
| --- | --- |
| Location | Bratislava |
| Company / Organisation | Office of the Slovak Government Institute for Law Approximation |
| Position | Team Leader |
| Job Description | EC funded TA – 2 projects for the Slovak Government aimed at preparation for EU-accession – Acquis transposition TL of the Central Translation Unit (CTU) within the Institute for the approximation of lawof the Office of the Government: Overall management and workflow coordination of the Unit ,Leading a team of 6 experts; Coordination of acquis transposition in the field of Social policyto improve the efficiency of law implementation in the social area in Slovakia; Training officials for transition from Phare to the EU structural funds and initiatives – ESF, Career development of staff – civil servants; Management of grant schemes& tenders |

| Date: from (month/year) to (month/year) | 01/1996-10/1998 |
| --- | --- |
| Location | Bratislava |
| Company / Organisation | Ministry of Education, Slovakia |
| Position | Responsible for European Integration Issues - Head of Sector Education and Training, Leading negotiation group of MoE, liaison with MOLSAF (education-skills-labour market) |
| Job Description | Supervising EU-integration process within the Ministry of Education, Implementation of the Europe Agreement concluded between Slovakia & EU;Chief negotiator with EC on education reforms and acquis implementation;Design National qualification framework and drafting the Ministry’s strategy on EU-integration with focus on HRD –ALMP/LLL, skills forecasting; In charge for EU programmes aiming at implementing LLL/AEM (youth, women) and for preparation of strategic materials for the Slovak Government on bringing closer education and labour market needs, design of LLL/AEM/NAPE (National Action Plan for Employment) -focus on vulnerable groups. Elaboration of Ministry’s education strategies & programming of EU fund and coordinator of education policy with Ministry’s subordinated organisations; |

| Date: from (month/year) to (month/year) | 01/1997-04 /1997 |
| --- | --- |
| Location | Brussels |
| Company / Organisation | European Commission, DG EAC |
| Position | EC expert |
| Job Description | Member of the EC team responsible for opening up of VET programmes to Slovakia, Romania, Bulgaria, Czech Republic, Poland and Hungary in the context of LLL/ALMMs: Elaboration of procedures for evaluation of projects AEM/LLL. Design of system for project implementation and coordination of activities with the ETF. Special internship with the EC in 1997 in LLL linked to the employment policies; since 1999 – EC expert for evaluation of projects aiming at vocational education and training in the context of LLL/ALMMs and expert on European education reforms – European qualification framework (EQF), ECVET- European credit system for VET, EQARF for VET (European quality assurance framework for VET); Expert work on HRD in the LLL context – areas of professional qualification and re-qualification |

| Date: from (month/year) to (month/year) | 04-12/1994 |
| --- | --- |
| Location | Romania |
| Company / Organisation | Intercultural Institute Timisoara |
| Position | Consultant on employment |
| Job Description | Grant Project on training and capacity building – second chance for socially excluded young people aged 16-25. Trained of end-users on policy planning at all levels and design of employment and other development and ALMMs and programmes for disadvantaged groups mainly targeted on Roma, young graduates without working experience, unemployed women, people 50+, etc.Designed of specialised training programmes for integration of disabled and socially excluded into the regular education system. |

| Date: from (month/year) to (month/year) | 04/-09/1995 |
| --- | --- |
| Location | Tunisia |
| Company / Organisation | International Activity Club |
| Position | Trainer Coordinator – Trainer of trainers |
| Job Description | Project aiming at developing mutual understanding and supporting young people capacity for business running (youth employment): - Elaborated complex training programme for Training of Trainers (common international groups involving Tunisian young leaders - future trainers) - Supported business development and young people start up |

| Date: from (month/year) to (month/year) | 1993-1995 |
| --- | --- |
| Location | Bratislava |
| Company / Organisation | State Institute for Youth Non-formal education |
| Position | Director General of International Cooperation Division |
| Job Description | Coordination/management of bilateral and multilateral international agreements; Coordination and management of programmes & projects aimed at fostering AEMP, continuing vocational training, LLL; Assessed labour market policy systems and programmes for better skills development for job acquisition by young people facing social problems and for disabled youth, capacity building of officials in AELMP, promoted EU best practices in ALMP. Building and strengthening social partnerships in LLL/AEM. Coordination of works for renewal of education system with the Ministry of Education. Leading education reforms in the area of non-formal education – “second chance” re-qualification programmes for young adults. |

| Date: from (month/year) to (month/year) | 9/1984 –12/1992 |
| --- | --- |
| Location | Bratislava |
| Company / Organisation | Slovak Academy of Science (SAS), |
| Position | Project coordinator |
| Job Description | Cooperation and coordination of projects with Russia - Dubna in the area of nuclear power stations, preparation of projects based on state requirements, measurements and scientific work. Responsible for drafting specialised HRD programmes for knowledge increase of the staff of the Institute/SAS. Training plan preparation. |

- Other relevant information (e.g., publications):

- Integration of disabled people in employment activities - problems, perspectives and challenges, 1995;

- Analysis of the employment potential of the Bratislava Self-Governing Region, co-author, 2005;

- Employment Action Plan for the Bratislava Self – Governing Region, co-author, 2005;

- Sustainable Jobs and Lifelong Learning 2008;

- Articles on ERDF, ESF and HR development in media, newspapers and magazines;

- Project Cycle Management Handbook for potential users of the structural funds, 2004;

- T-Kit on Project management – trans-voluntary services, CoE, 2003

- Methodology for evaluation of Phare grant schemes, Romania, 2007;

- Lifelong Learning & Clusters – planning LLL Clusters, 2009.

Curriculum Vitae

Proposed position in the project: STE

1.	Family name:		TKAC

2.	First names:		Vojtech

3.	Date of birth:		02/03/1949

4.	Nationality:		Slovak

5.	Civil status:		Married

- Education:

| Institution | Comenius University, Faculty of Law, Bratislava, Slovakia |
| --- | --- |
| Date: from (month(year): to (month/year) | 1967 – 1972 |
| Degree(s) or Diploma(s) obtained: | Master Degree in Law |

| Institution | Comenius University, Faculty of Law, Bratislava, Slovakia |
| --- | --- |
| Date: from (month(year): to (month/year) | 1980 |
| Degree(s) or Diploma(s) obtained: | Ph.D., Labour law |

7.	Language skills:  (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Reading | Speaking | Writing |
| --- | --- | --- | --- |
| English | 5 | 4 | 4 |
| French | 5 | 5 | 5 |
| Czech | 5 | 5 | 5 |  |
| Russian | 4 | 4 | 3 |  |

8.	Membership of professional bodies: Governing Body of ILO – member (observer) (1996 – 1998), International Social Security Association (1997-1999), Parliamentary Assembly of Council of Europe, Parliamentary Network of the World Bank, Organisation Committee for preparation of European Conference on Population (2005), Slovak Economic and Social Agreement Council (1990- 1993), Slovak Labour Law and Social Security Society Chairman

9.	Other skills: (e.g. Computer literacy, etc.)

PC skills – MS Windows (Word, Excel, Access, PowerPoint, Internet Explorer)

10.	Present position: Advisor of the Minister of Labour, Social Affairs and Family

11.	Years within the organisation (MOLSAF): 27 years of professional experience as lawyer in social area

- Key qualifications:

- Labour law and social security law, within the government sector in charge of labour, wage and social affairs legislation

- State plans of scientific research and state plan of economic research

- Issues of the automated system of legal information in the labour law and social security law

- Professional bargaining in the legislation sphere of labour and social security law, development of labour law legislation, etc.

- Work on social and economic reforms, creation of the basic documents for the democratic social legislation (comments on Labour Code, labour law in private enterprising, employment and working conditions, anti-discrimination and equal opportunities, collective bargaining, collective agreements, etc.)

- Preparation of the professional scientific analysis of the social reforms and labour law in the post-socialist countries for needs of EU

- Legislative works to prepare normative legal acts of a code character (Labour Code, social insurance, anti-discrimination and equal treatment, health and safety at work, work inspection, social assistance, complementary pension insurance, state and public service, adopting and ratification of the international documents of labour law Approximation of labour law and social security law in SR with EU law

- Preparation of prescriptive legal acts of the Slovak labour law and social security law, to launch the social-and-legal institutions in SR (Social Insurance Agency, National Labour Office, Economic and Social Agreement Council)

- Expertise for improving and influencing the labour law

- Negotiations within international labour law

- International regulatory legal acts

- Author of the essential reform document “The Concept of Social Sphere Transformation in the Slovak Republic

- Twinning experience in MK and SRB as legal expert in the social area

13.	Specific Countries experience - stays abroad and educational stays, Governing Body of ILO – member:

| Country | Date: from (month/year) to (month/year) |
| --- | --- |
| Poland (Faculty of law of University in Lodz) | February 1986 – March 1986 |
| Luxembourg | October 1990 |
| Switzerland (Geneva) | November 1990, 1992, 1996 – 1998 |
| Japan Institute of Labour (Tokyo) | July 1996 |
| Denmark (Copenhagen) | November 1999 |
| Finland (Helsinki) | October 2001 |
| Sweden (Stockholm) | October 2001 |
| Chile (Santiago de Chile) | November 2003 |
| Macedonia | 2008-2009 Twinning project on labour law – legal expert |
| Serbia | 2013-2014 Twinning project on social dialogue – legal expert |

14.	Professional Experience Record:

| Date: from (month/year) To (month/year) | October 2010 – October 2011 |
| --- | --- |
| Location | Bosnia I Herzegovina, Republika Srpska |
| Company | Ministry of Health and Social Affairs |
| Position | Labour Code Expert |
| Description | - Delivery of advise on labour law and EU laws and regulations within the project Support to social protection system in BiH, SlovakAid funded project - Analysis of the national legislation in the social field - Proposal for the strategic solution to the social area including antidiscrimination and equal opportunities issues - Transfer of knowledge and experience of the SR with the system of social protection at the local (municipal) level - Transfer of knowledge and experience of the SR in building personal capacities at the local (municipal) level |

| Date: from (month/year) To (month/year) | June 2008 –September 2009 |
| --- | --- |
| Location | Macedonia |
| Company | Ministry of Labour, Social Affairs Macedonia |
| Position | Labour Code Expert |
| Description | - Delivery of advise on labour law and EU laws and regulations within the project Review of the National Labour Legislation in Macedonia, twinning project - Labour law and social security law, collective bargaining, tripartite bargaining, general agreements, negotiations within international labour law, etc. - Twinning project – component 2- - Elaboration of tables of concordance for national law harmonization, assessment and reviews of country legislation - Analysis of the existing implementing legislation and administrative guidance - Elaboration of recommendations for effective institutional model - Training on issues covered by the project |

| Date: from (month/year) To (month/year) | September-December 2007 |
| --- | --- |
| Location | Bratislava, Nitra, Kosice, Banska Bystrica, Slovakia, Brno, Prague, Czech Republic |
| Company | Various universities |
| Position | Labour law and Industrial relations teacher and trainer |
| Description | - One of the pedagogic founders of the UPJS Faculty of Law in Kosice, leading the teaching of labour law and social security law, organising the theses, doctorate state examinations, final state examinations, expert supervisor of the scientific juniors within PhD studies, etc. - Submitting a draft recommendation of the Parliamentary Assembly of Council of Europe and its adoption in the form of Council of Europe Recommendation No. 1638 (2004) “Les tendances en nature de population en Europe et leursensibilité aux mesure des pouvoirs publics”, submitting a draft recommendation of the Parliamentary Assembly of Council of Europe “Demographic Challenges for Social Cohesion”, Doc. 10 371, 14 December 2004; - Participation in creation of the international standards for the international labour and social law in the conditions of International Labour Organisation, International Social Security Association, Council of Europe, external work on behalf of International Social Security Association, Parliamentary Assembly of Council of Europe, collaboration to develop the social concepts in the World Bank team (Albania, Bulgaria); |

| Date: from (month/year) To (month/year) | January 2007 – ongoing |
| --- | --- |
| Location | Bratislava, Slovakia |
| Company | Ministry of Labour, Social Affairs and Family of SR |
| Position | Counsellor of the Minister |
| Description | - Labour law and social security law, antidiscrimination, collective bargaining, Tripartite bargaining, general agreements - Negotiations within international labour law, etc. |

| Date: from (month/year) to (month/year) | September 1998 – June 2006 |
| --- | --- |
| Location | Bratislava, Slovakia |
| Company | National Assembly of the Slovak Republic |
| Position | Member of Parliament |
| Description | - Chairman of the Committee for Social Affairs and Housing - Labour Code Amendments - Delivery of studies and analyses |

| Date: from (month/year) to (month/year) | June1993 – October 1998 |
| --- | --- |
| Location | Bratislava, Slovakia |
| Company | Ministry of Labour, Social Affairs and Family of SR |
| Position | State Secretary / Minister of Labour, Social Affairs and Family |
| Description | - Presenting and managing the working teams to elaborate partial concepts within the scope of transformation of the social sphere in Slovakia in the field of the Concept of Employment Policy of the Slovak Republic, the State Policy Concept of the Slovak Republic in the Family Sphere, the Concept of Labour Price in the Slovak Republic, Concept of the Social Sphere Information System in the Slovak Republic, Concept of Education in Social Sphere in the Slovak Republic; - Presenting and direct management of the working groups for preparation of decisive legal regulations in the sphere of labour law and social security law in the Slovak Republic of a code type (preparation of the new Labour Code, laws on state and public service, work inspection, safety and protection of health at work, social insurance, complementary pension insurance, social assistance, state social support, etc.); - Author of the Concept of Social Sphere Transformation in the SR 1996;Member of Parliament |

| Date: from (month/year) to (month/year) | December 1987 – June 1993 |
| --- | --- |
| Location | Bratislava, Slovakia |
| Company | Professional offices in Czechoslovak trade union bodies - Czech and Slovak Trade Union Confederation, Federal Trade Union Central Office |
| Position | Legal expert, Head of legislation department of the Czech and Slovak Trade Union Confederation from 1990 until June 1993. |
| Description | - Representation of the trade union in Legislation Council of the Government, in Legislation Council Committee for Labour Law and Social Security, etc. - Collective bargaining issues - Labour code and industrial relations - Care of workers, labour law, leading the professional bargaining in the legislation sphere of labour and social security law, etc. - Participation in the social sphere legislative process in the field of labour law and social security law since 1990 up to now (member of Legislation Council of Federal Government of Czech and Slovak Federative Republic, member of tripartite bodies on a federation, chairman of the Constitutional Law Committee and chairman of the Committee for Social Affairs and Housing of National Council; - Elaboration of the Concept of Automated System for Legal Information in the Branch Labour Law and Social Security Law in 1980-ties of the last century; - Submitting the European Social Charter of Council of Europe to be ratified by National Council of the Slovak Republic (1998); - Participation in the legislation process in the sphere of labour, social and economic legislation in the conditions of Czech and Slovak Federative Republic in the period 1990 – 1992 in economic, political and social reforms; |

| Date: from (month/year) to (month/year) | 1972 – 1987 |
| --- | --- |
| Location | Bratislava, Kosice, Slovakia |
| Company | Comenius University, Faculty of Law, Kosice Branch, Faculty of Law of UPJS in Kosice |
| Position | Teacher, College lecturer (1982) |
| Description | Department of Labour Law and Agricultural-and-cooperative Law – scientific assistant, university pedagogue |

15.	Other Relevant Information

Scientific monographs published by foreign publishers

- TOMES, I. – TKAC, V.: Collective Bargaining and Collective Agreements, Theory, Practice, Models; published by Nakladatelstvi Prospektrum 1993, Prague, 280 p., ISBN 80 – 85431 – 66 – 1, author’s share 50 %.

Scientific monographs published by domestic publishers

- PALUS, I. – TKAC, V.: Social-and-economic Rights of CSSR Citizens, Praca 1998, Bratislava, 160 p., author’s share 50 %.

- TKAC, V.: Social Security in Private Enteprising, Nakladatelstvi Prospektrum 1991, Prague, 176 p. ISBN 80 – 85431 – 05 – x.

- TKAC, V.: Trade Union, Employers, Employee’s Councils (Europe, law and practice), Pressprint 2004, Kosice, 360 p., ISBN 80 – 89084 – 13 – 3.

Chapters in scientific monographs published by foreign publishers

- TOMES, I. – TKAC, V.: Collective Bargaining in The Czech and The Slovak Republic, IN:  Nuovi modelli di Dirittosindicalenell ’Europa Centrale (New Patterns of Collective Labour Law in Central Europe), published by Giuffre Editore 1996, Milano, Italy, p. 59 – 91”.

Chapters in scientific monographs published by domestic publishers

- TKAC, V.: Labour Law Issues of Project and Structural Works. In: SUCHOZA, J. -  TKAC, V.: Legal Aspects of Project and Structural Works, Anthology of Papers, published by Dom techniky CSVTS 1977, Prague, p. 53 – 88.

- TKAC, V.: Labour Law and Living Environment. In: SUCHOZA, J. – TKAC, V.: Legal Aspects of Project and Structural Works, Anthology of Papers, published by Dom techniky CSVTS 1977, Prague, p. 91 – 107.

- TKAC, V.: Criminal Law Implications of Breach of Duties at Project and Structural Works. In: SUCHOZA, J. – TKAC, V.: Legal Aspects of Project and Structural Works, Anthology of Papers, published by Dom techniky CSVTS 1977, Prague, p. 109 – 111.

- TKAC, V.: Labour Law Relations and Social Security. In: KNAPP, V. et al. Law and Information, Akademie 1989, Prague, 250 p. (p. 219 – 228).

- TKAC, V.: Application of the Automated Systems of Legal Information in State and Law Science, in Legal Education and Propaganda, In: KNAPP, V. et al. Law and Information, Akademie 1989, Prague, 250 p. (p. 264 – 280).

Specialised book works published by domestic publishers

- TKAC, V.: Labour Law in Personnel  Work, Praca 1979, Bratislava, 152 p.

- TKAC, V. – BRADLEROVA, L. – ZACHARIAS, J.: Labour Code (Commentary) I, published by Nakladateltsvi Prospektrum 1991, Prague, 335 p., ISBN 80 – 7107 – 023 – 8, author’s share 50 %.

- TKAC, V. – BRADLEROVA, L. – ZACHARIAS, J.: Labour Code (Commentary) II, published by Nakladateltsvi Prospektrum 1991, Prague, p. 335 - 613, ISBN 80 – 7107 – 023 – 8, author’s share 50 %.

- TKAC, V. – BRADLEROVA, L. – ZACHARIAS, J.: Labour Code (Commentary) III, published by Nakladateltsvi Prospektrum 1992, Prague, 288 p., ISBN 80 – 85431 – 51 – 3, author’s share 50 %.

- BRADLEROVA, L. – TKAC, V. –– ZACHARIAS, J.: Labour Code (Commentary), published by Nakladateltsvi Prospektrum 1994, Prague, 360 p., ISBN 80 – 7175 – 016 – 6, author’s share 33 %.

CURRICULUM VITAE

Proposed position in the project: STE

    - Family name:		LORENCIC

    - First name:	 		MERI

    - Date of birth:		15. 2. 1958

    - Nationality:	 		Slovene

    - Civil status:	  		Married

    - Education:

| Institution | Degree(s) or Diploma(s) obtained: |
| --- | --- |
| The Open University, Walton Hall, Milton Keynes, United Kingdom (2011) | Postgraduate level: The module “Development: context and practice” |
| The University of Edvard Kardelj in Ljubljana, Philosophic Faculty, (1990) | University Degree in Pedagogies (Academic study programme of 4 years plus 1 year for elaboration and defence of the degree dissertation; EQF level 7 |
| The University of Edvard Kardelj in Ljubljana, Pedagogic Academy, (1980) | Degree in Special Pedagogic and Institutional Education (Level 6) |

- Language skills:  (1 - excellent; 5 - basic)

| Language | Reading | Speaking | Writing |
| --- | --- | --- | --- |
| Slovenian | Mother tongue |  |  |
| English | 5 | 5 | 5 |
| Serbian/Croatian/Montenegrin | 5 | 5 | 5 |
| Macedonian | 5 | 3 | 4 |

- Membership of professional bodies:

Member of the WG responsible for the first Slovenian National Employment Action Plan (1999); Member of Adult Education Commission of the Council of Experts of Slovenia; Member of Slovenian Association for Career Guidance; Member of the Institute for research work and development in education

9.   Other skills: NVQ Advisor; Quality Assurance Advisor; Skills in Microsoft XP Professional package; PMC methodology;  Trained in “Impact

evaluation of technical cooperation and development projects and programmes” (ILO ICT)

10. Present position: Freelance Consultant, director

11. Years of experience: 34 years

12. Key qualifications:

Qualifications and skills

- Academic degree in education with more than 34 years of professional experience in the field of employment policy,  human capital development, life-long career guidance and social inclusion

- 18 years working at the Employment Service of Slovenia and over 6 years working in provision of technical assistance related to enhancing capacities of  Public Employment Services in Croatia, Serbia, Montenegro and FYRoM (over 6 years)

- 15 years of experience in an EU pre-accession assistance and its instruments (IPA, CARDS, PHARE); Good understanding of development concepts and rich experience in institutional capacity building for HRD policy makers and policy implementing institutions

- Good analytical skills and proven good drafting and reporting skills in English

- Good management and leadership skills, excellent team working and good organisational, communication and time management skills;

General professional experience

- Reach  experience in  HRD programmes identification, design, management, implementation, monitoring&   evaluation;

- Excellent training facilitation skills and reach experience in designing and delivering training of unemployed and employees aimed at enhancing their employability

- Responsibilities: Key expert responsible for Organisational Change Management of the Employment Service Agency (FYRoM); Leader of the component 2 of the EU funded project in the field of labour market & workforce development(Montenegro); ETF Country Manager for B&H; Team leader of the EU/CARDS funded project in the field of HRD & employment (Serbia)  leader of the Slovenian Government Programme “5000” /Second Chance/

Specific professional experience

- Rich  experience in designing, implementing, monitoring and  financing HRD interventions, including experience in analysis of employment/social inclusion/VET policy (Slovenia and the Western Balkan countries)

- Designing and conducting Functional review of Employment Service and Training Needs Analysis; drafting related reports, dissemination of results; translation of TNA results into the learning outcomes for training modules

- Good knowledge of EUROPE 2020 strategy and related Employment Guidelines and the EU policy in the field of social policy and education and training; good knowledge of IPA regulation and PRAG procedures.

- Experience in applying  PCM and  Log-Frame approach in drafting Terms of Reference for EAR/Delegation of EU for HRD projects; and in drafting

technical proposals

- Specific experience in the region:

| Country |  | Date from – Date to |
| --- | --- | --- |
| FYR of Macedonia |  | 2012-2013 |  |  |
| Montenegro |  | 2010 -2011 |  |  |
| Bosnia and Herzegovina |  | 2007 - 2009 |  |  |
| Serbia |  | 2003 – 2004, 2005, 2006 - 2008 |  |  |
| FYR of Macedonia |  | 2006 – 2008; |  |  |

- Professional experience:

| Date: from (month/year) to (month/year) | From 11/2013-ongoing |
| --- | --- |
| Location | Regional Development Agency Senec-Pzinok |
| Company / Organisation | Bratislava |
| Position | Employment Officer |
| Job Description | Implementing the life-long career guidance activities – training Conducting functional analyses of services in employment Transfer of know-how and experience from Slovene offices Liaison between Slovak and Slovene stakeholders in employment Analyses of HRD and of management practices, elaborated recommendations for improvement Preparation of specialised training programmes for “difficult” job seekers (in need of special psychological support and activation) Support to RDA Director in employment and HRD development programmes Drafting of methodologies in the field of employment policy and tailor-made training interventions |

| Date: from (month/year) to (month/year) | Part time from 2014 |
| --- | --- |
| Location | Ljubljana, Slovenia |
| Company / Organisation | Municipality of Maribor, Department for Youth |
| Position | Short-term expert |
| Job Description | Expert assistance in implementation of the URBACT project “My Generation at work”, which aims at fostering innovation, creativity and entrepreneurship and ICT among young people and encourage partnership among VET providers, university, innovation centre and other stakeholders in Maribor |

| Date: from (month/year) to (month/year) | 01/2012 - 10/2013 |
| --- | --- |
| Location | Skopje, FYR of Macedonia |
| Company / Organisation | Employment Service Agency of Macedonia |
| Position | Key expert – training coordination |
| Job Description | EU/IPA funded project: Further modernisation of Employment Service Agency (ESA). My tasks: (i) Conducting comprehensive analysis of existing work organisation, current business, capacity and performance and drafting the Functional Review; (ii) In close cooperation with the project team and stakeholders co-designing the organisational change management project through a strategic approach, with a clear and shared vision, taking into account the human and technical aspect of the change,; (iii) Improving planning, monitoring and reporting on ESA services (elaboration of guideliness, capacity building), with a great attention given to gender issues ; (iv) Conducting the Training Needs Assessment, processing data and drafting the TNA report, (v) Developing an overall Training programme for the ESA’s employees composed of training modules aimed at enhancing and advancing technical and individual working skills – defining learning outcomes upon the TNA findings; designing training modules materials and support documentation; drafting ToR for STE – trainers, organising, supervising and reporting on training delivery, designing evaluation forms and drafting reports (v) Delivery of coaching & training in new skills and behaviours for employees and management to implement change effectively. |

| Date: from (month/year) to (month/year) | 03/ 2013 |
| --- | --- |
| Location | Belgrade |
| Company / Organisation | National Employment Service of Serbia |
| Position | Senior expert |
| Job Description | - Delivering presentation on the TAIEX workshop: Working with vulnerable groups |

| Date: from (month/year) to (month/year) | 02/2010-01/2012 |
| --- | --- |
| Location | Monte Negro, Podgorica |
| Company / Organisation | Employment Agency of Monte Negro |
| Position | Key expert – leader of the project’s component 2 |
| Job Description | - EU/IPA-funded project “Labour Market Reform and Workforce Development”: My tasks: (i) Support the Ministry of Labour, PES, Ministry of Education, social partners and other stakeholders in defining policy for promoting local employment and HRD partnership and strengthening community based approach to design and implementation of local actions; (ii) Building up and capacity building of 4 local – cross sectorial partnerships for employment and HRD (iii) Designing and delivering training of the LPGs aimed at drawing up 4 municipal employment and HRD strategies and annual Action Plans addressing business environment, employment, education & training and social inclusion issues; (iv) Capacity building of MoL, PES and local actors for designing, monitoring, implementing projects applying PCM and LoG-Frame approach. (v) Supporting PES in preparing and conducting the grant scheme. (vi) Organising study visit to Slovenia and Austria; (vii) drafting technical reports. |

| Date: from (month/year) to (month/year) | 02 – 03/2011 |
| --- | --- |
| Location | Kosovo |
| Company / Organisation | GIZ, Germany |
| Position | Lead expert |
| Job Description | - Conceptualising and writing awarded technical proposal for the EU tender Teacher Training and Capacity Building of School Directors in Kosovo. Budget 3.5 mio EUR. |

| Date: from (month/year) to (month/year) | 07–11/2010 |
| --- | --- |
| Location | Torin, Italy |
| Company / Organisation | ETF – European Training Foundation |
| Position | Senior consultant |
| Job Description | Organising and providing expert input to the ETF peer learning study visit to Slovenia for the representatives of the Serbian Council for VET and Adult Education, their VET Centre and officials from the Ministry of Education of Serbia. Facilitating the study group work aimed at elaborating recommendations for further improvement of VET in Serbia and drafting the final report. |

| Date: from (month/year) to (month/year) | 04/2009-01/2010 |
| --- | --- |
| Location | Ljubljana, Slovenia |
| Company / Organisation | Ministry of Labour, Family and Social Affairs |
| Position | Senior expert |
| Job Description | - Drafting a policy note “A need for enforcing anticipation of skills needs at local levels in Slovenia” for MoLSFA. Cooperating with the London School of Economics in preparation of the bid for the study on labour market activation policies in the WB under PROGRESS (W. Bartlett). |

| Date: from (month/year) to (month/year) | 03/2006-03/2009 |
| --- | --- |
| Location |  |
| Company / Organisation | European Training Foundation (ETF) - an EU Agency |
| Position | Human Capital Development Specialist |
| Job Description | ETF COUNTRY TEAM MEMBER: Carried out content mid-term reviews of the EU CARDS Programme on employment and VET Serbia (2006- 2008). Drafting Terms of Reference for EU funded projects in VET and employment policy (Serbia, FYRoM). “GOVERNANCE AND ADMINISTRATIVE CAPACITY IN EMPLOYMENT/HRD, ETF Regional Project (2007 and 2008): Provided inputs to the project planning documents, designed the tool for countries’ self-assessment of their capacities for programming, managing, implementation and monitoring of employment/HRD policy and facilitating the countries’ reporting process (Serbia and FYRoM); delivering capacity building training in key indicators and elements for effective implementation of the employment/HRD policy and deployment of IPA and ESF assistance according to the elements of good governance (countries involved and benefited from the project events: Croatia, Serbia, fYRoM, Albania and Turkey) INSTITUTIONAL CAPACITY BUILDING, Serbia (2007): Designed and implemented capacity building training for national stakeholders for IPA programming (Comp I) in employment&HRD policy according to the strategic goals defined in Employment Strategy and NAPE, with the special focus on enforcing partnership between ministries and social partners and local ownership upon the interventions in HRD: employment, social inclusion and education&training. FYRoM (2007, 2008): prepared and carried out several events aimed at enhancing capacities of : (i) MoL, Ministry of Finance, PES for programming and implementing the OPHRD employment pillar (IPA IV Component); (ii) Ministry of Education, VET centre for OPHRD education&training pillar and (iii) institutions operating in the field of social inclusion, social protection for implementation of the OP HRD-social inclusion pillar. ETF REGIONAL PROJECT SOCIAL INCLUSION OF ETHNIC GROUPS IN EDUCATION AND TRAINING (2007-2009; Reviewed and provided inputs into the DG EMPL background studies on social inclusion and social protection (a part of the JIM process) for FYRoM and BiH; ETF COUNTRY MANAGER FOR BOSNIA AND HERZEGOVINA (2007-2008). My tasks: Planning the ETF activities in B&H; Drafting the ETF Country Plan for B&H 2007, 2008 and 2009 and the B&H Human Resource Development analysis (2008). Provided policy advice to the Ministry of Civil Affairs on VET reform process, adult learning and institutional settings and to the EC Delegation. Provided inputs to the EC Progress reports 2008 (DG ENLARG, DG EMPL). Contributed to the BIH education strategy “Strategic Directions for the Development of Education in Bosnia and Herzegovina, with the Implementation Plan 2008-2015« Leading the study “The role of Social partners in VET in LLL context in B&H” and carried out the related event with representatives of education, employment institutions and social partners. Led the ETF team responsible for drafting the feasibility study on adult learning in B&H on the request of the EC Delegation. Cooperating with other international organisations operating in B&H (OSI, UNICEF, the World Bank, DFID, OSCE, DVV) and NGOs. CONTRIBUTING TO THE ETF PUBLICATIONS (listed in the Bibliography), including In demand: Career Guidance in EU neighbouring countries (2009), |

| Date: from (month/year) to (month/year) | 01/2005 – 02/2006 |
| --- | --- |
| Location | Belgrade, Serbia + locations within Serbia |
| Company / Organisation | National Employment Service of Serbia |
| Position |  |
| Job Description | EU-CARDS project “Regional Socio-Economic Development Programme”, (3 pilot regions). My tasks: a) Capacity building of regional PES for designing and implementing local interventions; b) Enhancing PES cooperation with local providers; c) Delivery of training to PES employees on motivation and activation of unemployed persons (introducing life-long career guidance approach). |

| Date: from (month/year) to (month/year) | 10/2004-12/2005 |
| --- | --- |
| Location | Ljubljana, Slovenia |
| Company / Organisation | Employment Service Slovenia |
| Position | QA Manager and Projects Management |
| Job Description | My tasks: (i) Designing the awarded project “Innovative approach to the lecturing and learning for enhancement of IT skills and improved competitiveness of the unemployed persons in Podravje” based on blended learning (PHARE 2003) in partnership with the Slovenian Institute for Rehabilitation; (ii) Designing and managing the ESF/MoL awarded project “Information Centre for Job Seekers”. Delivering career guidance training for students and unemployed. Cooperation in elaboration of the faculty study programme Organiser of social network. Responsible for quality assurance (ISO standards and EFQM principles) and for self-evaluation targeting students, trainees, trainers and employees (elaborating a set of written questionnaires and processing of the collected data). |

| Date: from (month/year) to (month/year) | 04/2003 – 10/2004 |
| --- | --- |
| Location | Belgrade, Serbia |
| Company / Organisation | National Employment Service of Serbia |
| Position | Team Leader |
| Job Description | EC funded project “Support for Human Resources Development Measures for Unemployed and Redundant Employees in Serbia”, (2 M EUR): My tasks: (i) Planning and coordinating the work of a pool of long and short-term experts in a way to ensure high quality results in timely manner; (ii) Building capacities of the national level institutions responsible for HRD (MoL, MoES, Ministry of Economy, NES, VET Centre, Chamber of Commerce, Employers Association, Trade Unions) (iii) Facilitating the work/capacity building of the local partnership group for HRD and employment; (iv) Implementing Labour market survey and Training needs analysis targeting employers, results disseminated and considered in training development; (v) Facilitating elaboration of the district’s employment strategy; (vi) Designing and managing 2 grant schemes, 9 tenders, capacity building training provided for providers, 43 new trainings developed, 2.043 unemployed trained and 33% employed within 3 months after completion. (vii) Designed the monitoring system of training interventions. (viii) Provided policy advice and TA to the Serbian MoL in the preparation of the Programme of ALMMs for 2005 (ix) Designed and delivered a Capacity Building Plan for the staff of the NES Branch Office. (x) Organised and implemented the project conferences, workshops, round tables, seminars. |

| Date: from (month/year) to (month/year) | 01/2002- 03/2003 |
| --- | --- |
| Location | Slovenia, Maribor |
| Company / Organisation | DOBA EPIS |
| Position | Director of E&T programmes |
| Job Description | My tasks: (i) Coordinating and supervising the work of staff and external trainers; (ii) Developing new training programmes for companies (e.g. online training for Telekom Slovenia) and students/adults. (iii) Responsible for functioning of the Open learning centre; (iv) Introducing QA standards and procedures. |

| Date: from (month/year) to (month/year) | 03/2002- 06/2002 |
| --- | --- |
| Location | Slovenia |
| Company / Organisation | PCMG |
| Position | HRD expert |
| Job Description | Carrying out evaluation and providing expert opinion on implementation of the Dynamic Learning project carried out as a part of the Government Operational Programme for working at home and teleworking 2000-2002. |

| Date: from (month/year) to (month/year) | 01/2001-12/2001 |
| --- | --- |
| Location | Croatia |
| Company / Organisation | European Training Foundation (ETF) |
| Position | Employment/HRD expert |
| Job Description | ETF-funded project: “Vocational Education and Training against Social Exclusion”. My tasks: capacity building of a) the local partnership groups for designing, monitoring and implementing measures and programmes for socially excluded unemployed persons and b) the Employment Service staff for implementing Training Needs Analysis targeting employers and for developing CVT programmes based on TNA outcomes; c) co-drafting the reports; d) facilitator in the ETF workshop organised in Zagreb, Dec. 2001. |

| Date: from (month/year) to (month/year) | 01/1996 -12/2001 |
| --- | --- |
| Location | Slovenia, Ljubljana |
| Company / Organisation | Employment Service of Slovenia |
| Position | Adviser to the general director of ESS / Leader of the Government Programme “Programme 5000” |
| Job Description | Managing the ESS sector for education and training of the unemployed (annual budget varied from €11, 7 to €14, 4 million); My tasks: (i) Creating a network of E&T providers for unemployed. (ii) Developing operational and quality standards for design, selection and financing training programmes in close cooperation with Ministry of Education, (iii) Developing monitoring system and annually conducting descriptive outputs and outcomes evaluations; (iv) Introducing new measures and programmes, drafting reports on their implementation (vi) Member of the Steering Committee of the PHARE HRD Fund project (Slovenia, 1997) and the PHARE MOCCA project (Modernisation of Curricula, Certifications and Assessment in Vocational Education of Youth and Adults, 2000-2001); Cooperation in a Twinning Project “Support for Strengthening of Labour Market Organisations” (PHARE 1999), component “Preparation for participation in the ESF; Co-drafted the manual “Preparation for ESF” for ESS (2001); (vii) Member of the WG that drafted the Law on NVQ (2000). Leading the Government “Programme 5000” aimed at increasing educational attainment level of the unemployed and reducing the labour market skill mismatch. My tasks: (i) Led the Government WG composed of all key Slovenian institutions responsible for policy making and policy implementation in HRD (Ministry of Labour, Ministry of Education, Ministry of Economy, Ministry of Finance, ESS, Chamber of Commerce, Chamber of Crafts, Centre for VET, Adult Education Centre); (ii) Designed the Programme for several school years, organised supporting activities (scholarships, career guidance and counselling, etc) and ensure funding (annual costs amounted to 12.5 M€); (iii) Preparation of Special Guidelines to deliver VET programmes for adults/unemployed issued by the Minister of Education; iv) In cooperation with the Chamber of Crafts and employers piloted VET apprenticeship scheme for adults-unemployed; (v) Monitoring implementation and funding, reporting ; (v) Information and promotion campaign |

| Date: from (month/year) to (month/year) | 1984- 1995 |
| --- | --- |
| Location | Slovenia, Maribor |
| Company / Organisation | Employment Service of Slovenia - Regional Branch Office Maribor |
| Position | Counsellor |
| Job Description | My tasks: Organising, monitoring, promoting and reporting on training programmes for unemployed persons and cooperation with external training providers (1992-1995) Career guidance and counselling for young students and adults; deliver of lectures and individual counselling for pupils and their parents (1984-1991) |

| Date: from (month/year) to (month/year) | 1979 –1984 |
| --- | --- |
| Location | Slovenia |
| Company / Organisation | Reform School Logatec & Reform School Slivnica |
| Position | Tutor |
| Job Description | Tutor of the young people between 15 – 21 with the social and behaviour problems |

CURRICULUM VITAE

Proposed role in the project: STE

1.	Family name:	KELECINOVA

2.	First name:	DANICA

3. 	Date and place of birth:	10/7/1972Trnava, Slovakia

4.	Nationality:	Slovak

5.	Civil Status:	married

Address (phone/fax/e-mail):	danica.kelecinova@upsvr.gov.sk

6. 	Education:

| Institutions: | Trnava University in Trnava, Slovakia Hornopotočná 23 |
| --- | --- |
| Date: From (months/year)-To (months/year) | September 1995 June 2000 |
| Degree: | Mgr. (academic diploma) |

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Slovak | Mother Tongue |  |  |  |
| English | 4 | 4 | 4 | 4 |
| Russian | 4 | 4 | 4 | 2 |
| German | 2 | 4 | 3 | 3 |

8.	Membership of Professional Bodies: Association of Supervisors and Social Advisors (Slovakia)

9.	Other skills MS Office (Word, Excel, Power-point), SSZ, Lotus Notes, Omega, Cognos

10.	Present Position: Director of Information Systems Methodology for the Central Office of Labour, Social Affairs and Family

11.	Years of professional experience: 24 years

12.	Key qualifications:

- 24 years of professional experience in labour market field as a civil servant dealing with labour market/employment issues

- 12 years of proven experience in the management and leading people

- 12 years of professional experience in management of the national projects financed within the European Social Fund and implemented on the national level

- 9 years of professional experience in capacity building of the labour offices (employment centres) and relevant stakeholders to implement new active measures

- Excellent experiences in a field of informatics (labour market systems analysing, development, merging, testing and implementing) – one of designer of the IT system of COLSAF

- Strong leadership and management skills (coordination and management of 79 labour offices in different areas of employment and informatics)

- Experience in evaluation of active labour market policies

- The Whole professional career spent in labour market institutions on regional and national led meto better understanding of relationships, issues, possibilities, needs and challenges in this field

- Comprehensive knowledge of labour market policies, legislation and regulations

- Always eager to take on new challenges

13.	Specific experience in the region or else:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| Slovakia, Hungary, Austria | 2004 | Introduction and implementation of EURES (European Employment Services) |
| Slovakia, Hungary | 2010 - on going | Electronic Exchange of Social Security Information (EESSI) |
| Serbia | 2014 | Presentation of Slovak IT system of COLSAF – new generation |

14.	Professional experience:

| Date: from (month/year) to (month/year) | October 2013 - present |
| --- | --- |
| Location | Bratislava, Slovakia |
| Company / Organisation | Central Office of Labour, Social Affairs and Family |
| Position | Director of Information Systems Methodology for the Central Office of Labour, Social Affairs and Family |
| Job Description | -Responsible for managing, administration and development of the Information Systems in Central Office of Labour, Social Affairs and Family -Coordinating the project team leaders - -Adjusting the plans when needed -Making sure there is a smooth change over from the older systems to the new one -Creating reports and analysis in the area of employment policies (implementation of active labour market measures, ad hoc operational analysis, regular analysis of the situation on the labour market; and various statistic data on demand, by specific needs and on regular basis); -responsibility for information systems functioning -Participating on internal standards preparations -Responsible for data exchange between other institutions - responsible for strategic planning in IT field and course of future development -responsible for IT specific trainings after a new functionalities are implemented -Communication with external suppliers |

| Date: from (month/year) to (month/year) | October 2011 –September 2013 |
| --- | --- |
| Location | Bratislava, Slovakia |
| Company / Organisation | Central Office of Labour, Social Affairs and Family |
| Position | Head of the Methodology department |
| Job Description | Informatics systems Administrator of the Employment Services Section -defining the appropriate policies a related working instructions in compliance with relevant legislation, internal procedures and norms - Dealing with various methodology tasks and questions on a national level. |

| Date: from (month/year) to (month/year) | March 2008 – October 2011 |
| --- | --- |
| Location | Bratislava, Slovakia |
| Company / Organisation | Central Office of Labour, Social Affairs and Family |
| Position | Informatics systems Administrator of the Employment Services Section |
| Job Description | Informatics systems Administrator of the Employment Services Section |

| Date: from (month/year) to (month/year) | September 2000 – March 2008 |
| --- | --- |
| Location | Bratislava, Slovakia |
| Company / Organisation | The General directorate of National Labour Office in Bratislava |
| Position | Expert Methodologist |
| Job Description | Employment agency methodologist including available employment and social benefit agenda |

| Date: from (month/year) to (month/year) | April 1997 – August 2000 |
| --- | --- |
| Location | Trnava, Slovakia |
| Company / Organisation | Regional Labour Office in Trnava |
| Position | Professional methodologist |
| Job Description | Employment agency methodologist, design and administration of procedures, updating documentation according to new legislative regulation and needs. Consultancies with other institutions, solving various tasks and harmonizing methodologies |

| Date: from (month/year) to (month/year) | Mai 1991 – March 1997 |
| --- | --- |
| Location | Slovakia, Trnava |
| Company / Organisation | Office of Labour, Social Affairs and Family in Trnava |
| Position | Officer responsible for providing social assistance benefits |
| Job Description | Providing social assistance benefits for unemployed people and disadvantaged groups. Contact with client, consultations and offering a job positions. |

15.	Others:

15a.	Publications and Seminars:

- ITAPA - Information Technologies and Public Administration

- Congress ITAPA 2013: Putting IT together

- November 2013 Lecture - Information system employment services: first year in operation and what´s next?

- Congress ITAPA 2012: Focused on results

- October 2012 Lecture - Deployment of Information System of employment services for UPSVAR

15b.	References: upon request

CURRICULUM VITAE

Proposed role in the project:	STE

1.	Family name:	VIDO

2.	First name:	MARTIN

3. 	Date and place of birth:	7/2/1976 Nové Mesto nad Váhom, Slovakia

4.	Nationality:	Slovak

5.	Civil Status:	married

Address (phone/fax/e-mail):	martin.vido@upsvr.gov.sk

6. 	Education:

| Institutions: | The Jan Amos Komensky University Prague, Czech Republic, Roháčova 87 - Pedagogy and Andragogy focused on teaching adults |
| --- | --- |
| Date: From (months/year)-To (months/year) | September 2008 - June 2010 |
| Degree: | Mgr. (academic diploma) |

| Institutions: | Matej Bell University Banská Bystrica- Pedagogy |
| --- | --- |
| Date: From (months/year)-To (months/year) | September 2002 - June 1999 |
| Degree: | Bc. |

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Slovak | Mother Tongue |  |  |  |
| English | 4 | 4 | 4 | 3 |

8.	Membership of Professional Bodies:

9.	Other skills MS Office, UNIX/Linux (Word, Excel, Access, Power-point), SSZ, Lotus Notes, Omega, Cognos, Oracle DWH, CorelDraw, Windows based server administration, LAN/WAN, Client/Server

Programming skills: Oracle SQL, MS SQL, SQL report, Visual Basic, PHP, HTML

10.	Present Position: Team leader Cognos and Data warehouse team

11.	Years of professional experience: 19 years

12.	Key qualifications:

- 19 years of experiences in a field of informatics (labour market systems analyzing, development, merging, testing and implementing)

- 15 years of proven experience in evaluation of active labour market policies and statistics

- Most of the professional career spent in labour market institutions on regional and national level solving the labour market policy agenda

- Experience iun work with international teams, experience in twinning “in” projects

13.	Specific experience in the region or else:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| Hungary, Czech Republic, Austria | Since 2005 | Speaker at conferences, seminars and CBC-employment meetings |
| Serbia | 2014 | Presentation of the new IT system, explanation of issues, preparation of a common project with the Serbian Employment Service |

14.	Professional experience:

| Date: from (month/year) to (month/year) | June 2005 - present |
| --- | --- |
| Location | Bratislava, Slovakia |
| Company / Organization | Central Office of Labour, Social Affairs and Family |
| Position | methodologist and statistic officer |
| Job Description | -Responsible for periodical and ad-hoc statistic reports -Designing and administration of application programme equipment -Coordinating the project participants - -Creating reports and analysis in the area of employment policies (implementation of active labour market measures, ad hoc operational analysis, regular analysis of the situation on the labour market; and various statistic data on demand, by specific needs and on regular basis); -responsibility for Cognos IT system -Participating on internal standards preparations -Responsible for data exchange between other institutions -responsible for IT specific trainings after a new functionalities are implemented -Communication with external suppliers -IT Cognos, (ISSZ) community forum moderation and administration |

| Date: from (month/year) to (month/year) | October 2004–May 2005 |
| --- | --- |
| Location | Nové Mesto nad Váhom, Slovakia |
| Company / Organization | Office of Labour, Social Affairs and Family in Nové Mesto nad Váhom |
| Position | Department of Informatics, Statistics and Analyses |
| Job Description | - Administration of various IT Systems - Reports designing - Participating on labour market Analysis - periodic reporting and reporting on demands |

CURRICULUM VITAE

Proposed role in the project:	STE

1.	Family name:	CERNA

2.	First name:	Veronika

3. 	Date and place of birth:	05/08/1986

4.	Nationality:	Slovak

5.	Civil Status:	single

6. 	Education:

| Institutions: | University of Matej Bel, Faculty of Political Science and International Relations |
| --- | --- |
| Date: From (months/year)-To (months/year) | September 2001 - May 2006 |
| Degree: | Mgr. – academic diploma |

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Slovak | Mother Tongue |  |  |  |
| English | 4 | 4 | 4 | 5 |
| Spanish | 4 | 4 | 4 | 5 |
| German | 3 | 3 | 3 | 5 |
| Italian | 2 | 2 | 2 | 2 |

8.	Membership of Professional Bodies:

9.	Other skills (e.g. computer literacy, etc.):  MS Office (Word, Excel, Power-point), Lotus Notes

10.	Present Position: Advisor in the field of mass media policy

11.	Years of professional experience: 7,5 years

12.	Key qualifications:

- hands-on experience in elaboration of Communication Strategy and communication action plans for improving services in terms of providing targeted information to job-seekers, employers and other stakeholders

- Planning and conducting awareness raising activities

- Evaluation of communication strategies, plans and events

- Good understanding of PES functions and operation

- Campaign management

- international experience

13.	Specific experience in the region or else:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| Austria, Czech Republic, Germany, Hungary, Italy, Poland, Slovak Republic, Slovenia | 1/2011-10/2013 | Central European (CE) Knowledge Platform for an Ageing Society - Supporting demographic renewal through better conditions for families and improved reconciliation of working and family life; - Boosting employment – more jobs and longer working lives of better quality; - Raising productivity and economic performance through investing in education and research; - Receiving and integrating migrants into Europe; and - Ensuring sustainable public finances to guarantee adequate pensions, health care and long-term care. |

14.	Professional experience:

| Date: from (month/year) to (month/year) | July 2006 - ongoing |
| --- | --- |
| Location | Bratislava, Slovakia |
| Company / Organisation | Central Office of Labour, Social Affairs and Family |
| Position | Advisor in the field of mass media policy |
| Job Description | - Elaboration of policy papers in relation to COLSAF communication policy - Worked on COLSAF Communication Strategy, worked on action plan for improving services in terms of providing targeted information to job-seekers, employers and other stakeholders - Drafting press releases, news, and magazine articles - Developing media plans and policies - Directing public relations campaigns - Coordination of communication policy of COLSAF with the Ministry of Labour, Social Affairs and Family of the Slovak Republic - Design manuals preparation - Elaboration of proposal for ensuring quality of services and overall management in the COLSAF communication area |

- Others:

Co-organizing the biggest job fair in Slovakia – JobExpo 2014, with participation of 150 employers VET schools, EURES in EU MS and investors from Slovakia and Europe

CURRICULUM VITAE

Proposed role in the project:	STE

1.	Family name: 	Dr. Gellérné Lukács

2.	First name: 	Éva

3. 	Date and place of birth: 	05/01/1974, Veszprém

4.	Nationality: 	Hungarian

5.	Civil Status: 	Married

6. 	Education:

| Institutions: | University of ELTE, Faculty of Law, Budapest |
| --- | --- |
| Date: From (months/year)-To (months/year) | September 2004 September 2009 |
| Degree: | Ph.D. |

| Institutions: | Central European University, International Business Law, Budapest |
| --- | --- |
| Date: From (months/year)-To (months/year) | August 1997 July 1998 |
| Degree: | LLM. |

| Institutions: | University of ELTE, Faculty of Law, Budapest |
| --- | --- |
| Date: From (months/year)-To (months/year) | September 1992 May 2007 |
| Degree: | Dr. Jurist (lawyer) |

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Hungarian | Mother Tongue |  |  |  |
| English | 5 | 5 | 5 | 5 |
| German | 5 | 5 | 5 | 5 |
| French | 3 | 3 | 3 | 3 |
| Russian | 2 | 3 | 2 | 2 |

8.	Membership of Professional Bodies:

- International Federation for European Law (FIDE)

- Hungarian Association of Labour Law

9.	Other skills: MS Office (Word, Excel, Power-point), driving license

10.	Present Position: Senior Counsellor

11.	Years of professional experience: 15 years

12.	Key qualifications:

- 15 years of experience in international affairs in social area with focus on employment: negotiation, mediation, drafting of target-oriented documents, ability to channel different views, ability to reach consensus, ability to achieve the designated objective with mutual consent of the respective parties;

- 5 years leadership and management skills (as Head of Unit for legal approximation and as head of several working groups established for special purposes during the past 15 years);

- 15 years of experience as researcher, 5 years with a PhD title, ability to work on long-term projects aimed at producing focused outputs, either short or long versions of texts;

- European Law expert in the field of social policy, free movement of workers (persons), employment-related equal treatment issues;

- Participation in EU funded projects (projects of the European Integration Fund, of the European Commission);

- Proven experience in two twinning light projects.

13.	Specific experience in the region or else:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| Germany | 2003 – ongoing | Participation at the work of the German-Hungarian Mixed Committee on posting. |
| Austria | 2003 – ongoing | Participation at the work of the Austrian-Hungarian Mixed Committee on employment-related issues. |
| Slovakia | 2003 - ongoing | Participation at the work of the Slovak-Hungarian Mixed Committee on social policy and employment-related issues. |
| V4 countries | 2011 - ongoing | Participation of the work of the V4 cooperation in the field of human capacities. |

14.	Professional experience:

| Date: from (month/year) to (month/year) | November 1998 - ongoing |
| --- | --- |
| Location | Budapest, Hungary |
| Company / Organisation | Ministry of Employment and Social Affairs and its predecessors, at present Ministry of Human Capacities |
| Position | Senior Counsellor |
| Job Description | - Delegated member of the Hungarian government in the Administrative Commission for the Coordination of Social Security, - Delegated member of the Hungarian Government in the MISSOC group, - Representation of the Hungarian Government in the Advisory Committee on the Free Movement of Workers, - Delegated member of the Hungarian ILO Council dealing with ILO agreements, - Responsible for legal approximation in the field of human resources (social policy, employment related equal treatment, immigration-related equal treatment), - Responsible for EU-pilots and legal infringements in the above-mentioned fields, - Participation in the general law-making processes including employment issues related to foreigners and citizens of EU member states, - Coordination of expert opinions, reports and analysis in the area of social policy, human rights and equal treatment, - Processing of presentations, analysis, reports and other documents in the field of targeted policies within the EU Coordination with the Hungarian administrative bodies (ministries, public law bodies), - Coordination with administrative bodies in other MSs and third states, - Managing contacts with the European Commission, - Participation at SOLVIT mechanism.. |

15. Others:

STE experience also in twinning

Professional coordination of two PHARE twining-light programmes with the Netherlands on social security (prior to Hungary’s accession to the EU).

Recent key publications, lectures, projects

Author of the Hungarian Country Profile in the European Migration Network Study 2014, titled “Migrant Access to Social Security and Health Care”.

Web: http://ec.europa.eu/dgs/home-affairs/what-we-do/networks/european_migration_network/reports/results/2014/index_en.htm

Co-author of the Hungarian Country Profile for the FIDE 2014 conference, in the field of Union Citizenship (Union Citizenship: Development, Impact and Challenges) with a special focus on rights and equal treatment. (Éva Lukács, Tamás Molnár, Hungary. Citizenship within Directive 2004/38/EC – stability of residence for Union citizens and their family members In: Ulla Neergaard, Catherine Jacqueson, Nina Holst-Christensen (szerk.) Union Citizenship: Development Impact and Challenges. Konferencia helye, ideje: Copenhagen, Dánia, 2014.05.28-2014.05.31. Copenhagen: DJØF Publishing, 2014. pp. 603-641. ISBN 978-963-304-183-3.)

Éva Lukács, Free movement of persons – a synthesis, In Central and Eastern European Countries after and before the Accession, Volume I., page 51-101., University of ELTE, Budapest, 2011.

Web: http://jmce.elte.hu/docs/ConfDocVol1/EuropaiJogiTanulmanyok_8_2_0.pdf

Lecturer of the University ELTE, Faculty of Law, Specialist Training Institution Budapest (since 2000), main topics: Hungarian and International Social Security and Labour Law including equal treatment, Family Law, Free Movement of Persons.

Author of a monograph (Taking up employment in the European Union, 2004), more than 40 articles, chapters in books (both Hungarian and English) and lecturer at several forums both national and international.

Training

2004. Specialised examination of lawyers (full exam, A-B-C).

Acknowledgment

2004. Award given by the President of State for the Work performed for the Accession of Hungary to the European Union (Knights Cross – Award for Merit of the Republic of Hungary)

CURRICULUM VITAE

Proposed position in the project: STE

1.	Family name: 	Ignits

2.	First name: 	Györgyi

3. 	Date and place of birth: 	27/01/1980, Szekszárd, Hungary

4.	Nationality: 	hungarian

5.	Civil Status: 	married

6. 	Education:

| Institutions: | Lóránd Eötvös University, Faculty of Sociology |
| --- | --- |
| Date: From (months/year) To (months/year) | September 1998 June 2003 |
| Degree: | Academic diploma |

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Hungarian | Mother Tongue |  |  |  |
| English | 4 | 5 | 4 | 4 |

8.	Membership of Professional Bodies:

9.	Other skills: MS Office (Word, Excel, Power-point), SPSS statistical software, IBM Cognos datawarehosue

10.	Present Position: Deputy Head of Department of Statistics and Analysis, National Employment Service of Hungary

11.	Years of professional experience: over 6 years of practical experience in Statistics and Analysis, National Employment Service of Hungary

12.	Key qualifications:

Labour Market Information Management System

- 5 years of professional experience in the field of statistics and analysis regarding to the labour market and activities of public employment service, active labour market measures, earnings etc.

- Strong statistical skills in handling databases and analysis of several sources of labour market information including internationally comprehensive data also

- 5 years of operation and continuously developing the Labour Market Information System in the National Employment Office

- 5 years of operation and improve the Performance Management System in the Hungarian Public Employment Service

- 5 years of experience of coordinating and evaluation  researches in the field of active labour market policies, including effectiveness studies also

- 3 years of experience in time series analysis (seasonal adjustment of unemployment data in Hungary)

- 5 years of experience in the field of quantitative labour market prognoses in Hungary

- 2 years of experience of international benchmarking and bench-learning activities among Public Employment Services in the EU.

- Strong analytical skills in written as well as in spoken

- Experience of making presentations at national and international conferences and different target groups (nationally and internationally) in the field of labour market policies

13.	Specific experience in the region or else:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| Slovakia, Czech Republic, Belgium (Brussels), UK, Austria and Germany | Since 2008 – ongoing | Presentations at different events, e.g. conferences, workshops, seminars, open days, jobfairs, etc. |

14.	Professional experience:

| Date: from (month/year) to (month/year) | January 2008 - ongoing |
| --- | --- |
| Location | Hungary, Budapest |
| Company / Organisation | National Employment Service of Hungary |
| Position | January 2008 – January 2012: Labour Market Analyst of Department of Research and Analysis, National Employment Office January 2012 – ongoing: Deputy Head of Department of Research and Analysis, National Employment Office |
| Job Description | - Making labour market analysis in Hungary, writing monthly and yearly reports - handling databases (by using SPSS software) and analysis of several sources of labour market information including internationally comprehensive data also - Operating and developing the performance management system in the Hungarian PES, including evaluation of the performance indicators of the Hungarian PES - Continuous improvement and analyses the statistics regarding to the hungarian PES and related topics: labour market prognosis, structure of earnings survey, active labour market measures etc. - evaluate of the active labour market measures in Hungary (including effectiveness studies), - coordinating researches in the field of employment policy (active and passive measures, human services) in Hungary - coordinating the operating of the datawarehouse in the Hungarian PES - coordinating and analysis of customer satisfaction surveys in the hungarian PES - Operating and continuous improvement of the management information system of the Hungarian PES and Ministry of National Economy - Steering, coordination and supervision of Department of Statistics and Analysis in the National Employment Office, - Contribution to planning of Operational Programme documents in Hungary - cooperation with international organizations (OECD, ILO, EU) - Processing of presentations and analysis in the field of labour market policies, taking part of national and international conferences - Taking part in benchmarking and benchlearning activities among the Public Employment Services within the EU |

15. Others: references upon request

Curriculum vitae

Proposed role in the project:	STE

- Family name:		Turner

- First names:			Lubica

- Date of birth:			20/05/1953

- Nationality:			Slovak

- Civil status:			married

- Education:

| Institution [ Date from - Date to ] | Degree(s) or Diploma(s) obtained: |
| --- | --- |
| P.J.Safarik University 1972-1977 | MA in Education and Linguistics (academic diploma) |
| Nottingham Trent University/Roffey Park 1994 - 1995 | Certificate in Training and Development issued by Chartered Institute for Personnel Development, London (former IPD) |
| Thames Valley University, London 1997 - 1999 | International Assessor/Advisor in Training and Development Certificate International Certificate in Training, Learning and Development |
| MacKay Development Solutions, London, 2007 | Practitioner in the Art and Science of NLP |
| Results Coaching Systems, London 2007 | Intensive Coaching Skills Training |

- Language skills:  Indicate competence on a scale of 1 to 5 (5 - excellent; 1 - basic)

| Language | Reading | Speaking | Writing |
| --- | --- | --- | --- |
| English | 5 | 5 | 5 |
| Serbian/Croatian/Bosnian | 5 | 5 | 5 |
| Russian | 5 | 5 | 5 |
| French | 3 | 2 | 2 |
| Macedonian | 3 | 3 | 2 |

- Membership of professional bodies: Association for Management Training in the Slovak Republic

- Other skills:  (e.g. Computer literacy, etc.) MS Office, Windows XP, Novell GroupWise

- Present position:, Head of Unit for HRD / Chief Training Specialist in HRD

- Years of experience:   19 years of proven professional record

- Key qualifications:

- 19 years of proven record in training design and delivery in social area (capacity building, mediation and negotiation skills, communication skills) and extraordinary knowledge and professional skills in elaboration of training methodologies and evidence-based learning

- Extensive international experience in human resources management, development  of HR  policies, selection and recruitment processes, performance appraisal, career development and training development and delivery for HR managers and specialists

- Knowledge of EU-legal rules

- Excellent trainer recognised at EU-level

- Strategic planning, results based management, project management in EU projects; leadership;

- Sound experience in change management and organisational development including design, delivery and management of relevant capacity building programmes

- TNA and TOT (training of trainers); women’s empowerment and equal opportunities development;

- Extraordinary knowledge of West Balkans and proven language competencies in English,  Serbian and Russian

- Impressive international experience, result-oriented, ability to deliver training in mixed cross-cultural groups/teams

- Proven twinning experience in the Region

- Specific experience in the region:

| Country | Date from - Date to |
| --- | --- |
| Serbia | 2013-2014 (twinning) |
| Jordan | 2010 – 03/2012 |
| Croatia | 10/2012 – 5/2013 (twinning) |
| The Netherlands | 2004 - 2007 |
| Macedonia (FYROM) | 2002 - 2004 |
| Montenegro | 2000 - 2002 |
| Russia | 1990 - 1992 |
| Yugoslavia | 1980 - 1990 |

- Professional experience:

| Date: from (month/year) to (month/year) | 2009 – ongoing |
| --- | --- |
| Location | Slovakia and in Jordan (1st 2007-2009 and 2nd from 2010 till March 2012) |
| Company / Organisation | Regional Development Agency SP, Slovakia |
| Position | Head of Unit for HRD / Chief Training Specialist in HRD |
| Job Description | Elaboration of training offers and training programmes of RDA for 2007-13; train-the-trainers specialised trainings in the areas of OHS for occupational medicine doctors and safety specialists (coordinated works with the Slovak Ministry of Labour, Slovak Labour Inspectorate and Slovak Institute for labour Research), regional development and lifelong learning (focus on OHS area). Involved as key expert in EUGOH project – European Certificate for strengthening SMEs in the OHS area (2008-2009 – 2-year EU-funded project via LLP) Key expert on methodologies development – advanced learning and evidence-based learning. Developed specialised training for improving communication skills of state administration and business companies (top managers) Amann/Jordan: specialised technical assistance since 2010 to March2012 in HRD |

| Date: from (month/year) to (month/year) | 10/2011-05/2012 |
| --- | --- |
| Location | Zagreb/Croatia |
| Company / Organisation | Ministry of Labour and Pension System of Croatia |
| Position | Short term expert |
| Job Description | Responsible for evidence-based learning and training design and trainings delivery to 5 Croatian beneficiaries: - Ministry of Labour and Pension System of Croatia - Ministry of health - Croatian Institute for OHS (HZZZSR) - Croatian Health Insurance Institute (HZZO) - State Inspectorate And two social partners: - HUP – Hrvatska udruga poslodavaca - TU – Textile Elaborated specialised manuals and training materials upon needs of the social partners and state authorities |

| Date: from (month/year) to (month/year) | 2002 (one year) |
| --- | --- |
| Location | Slovakia |
| Company / Organisation | Ministry of Labour, Social Affairs and Family of the Slovak Republic |
| Position | Expert |
| Job Description | One year assignment aiming at providing technical assistance to the Swedish Working Authority for the Phare Twinning project in the area of health and safety (OHS); designed curricula and materials and conducted training of trainers related to issues of improving the enforcement of the EU legislation in Slovakia for selected Ministry staff. Elaboration of specialised evidence-based learning methodology for Ministry´s staff to be used for training of the OHS specialists in Slovakia (occupational medicine and safety specialists) |

| Date: from (month/year) to (month/year) | 2002 |
| --- | --- |
| Location | Slovakia |
| Company / Organisation | Prospecta (Open Society) |
| Position | Team Leader |
| Job Description | Image of Women Candidates in Media during Pre-Election Campaign Designed project, recruited project team, managed implementation and evaluation, wrote narrative and financial report, designed and implemented public relations strategy |

| Date: from (month/year) to (month/year) | 2002 |
| --- | --- |
| Location | Slovakia |
| Company / Organisation | Prospecta (Friedrich Ebert) |
| Position | Team Leader |
| Job Description | Role of Women in Regional Economic Development Designed project, recruited project team, managed implementation and evaluation, wrote narrative and financial report, designed and implemented public relations strategy |

| Date: from (month/year) to (month/year) | 2000-2002 |
| --- | --- |
| Location | Montenegro |
| Company / Organisation | ICMA |
| Position | Consultant/Trainer |
| Job Description | Local Government Development Conducted country-wide needs assessment, designed Training of Trainers, set up selection criteria and selected local trainers, recruited international trainers, designed and implemented ToT, wrote reports, provided consultancy for development of regional training centres and NGO capacity building |

| Date: from (month/year) to (month/year) | 2000-2002 |
| --- | --- |
| Location | Slovakia, Austria, Italy, Iceland |
| Company / Organisation | Technical University Kosice (Leonardo da Vinci) |
| Position | Project Manager |
| Job Description | Facilitation of Personal Development through Continuing Education FACE International steering committee member (Austria, Italy, Iceland, Slovakia); designed training curricula and materials for socially disadvantaged groups; delivered training; designed training evaluation |

| Date: from (month/year) to (month/year) | 2000-2001 |
| --- | --- |
| Location | Slovakia |
| Company / Organisation | Prospecta (USIA) |
| Position | Team Leader |
| Job Description | CEBWA Newsletter Designed 2-year project focused on OHS at work specifically for awareness raising on occupational medicine and safety issues at SME, recruited project team, raised funds, on-situ training on OHS in selected SME; managed publication, wrote narrative and financial reports |

| Date: from (month/year) to (month/year) | 1999-2000 |
| --- | --- |
| Location | Slovakia, UK, Netherlands, Czech Republic |
| Company / Organisation | Health and Safety Authority Kosice (for social partners) |
| Position | Project Manager |
| Job Description | Worker’s Involvement in Health and Safety – WISH International steering committee member (UK, the Netherlands, the Czech Republic, Slovakia); Two year (2.1. 1999 – 21.12.2000) EU-funded project aiming at providing expertise in training of trainers of occupational medicine doctors and safety specialists for the Health and Safety Authority in Kosice Region, Slovakia; developed trainer selection criteria based on EU best practice for incorporation of legislative knowledge into the practical enforcement of the EU directives in OHS area, designed curricula and training materials in the OHS area linked to EU legal rules incl. non-binding guides, practical training of the future trainers; coached pilot OHS workshops for a total number of 100 participants (doctors and safety specialists); participated in training evaluation & elaboration of recommendations for improvement of learning methodologies; wrote narrative and financial reports |

| Date: from (month/year) to (month/year) | 1999-2001 |
| --- | --- |
| Location | Slovakia |
| Company / Organisation | Technical Inspection Authority SR |
| Position | Team Leader |
| Job Description | TI SR Human Resources Development Designed 3-year project for 100 participants – specialists in occupational medicine and safety at work, including those representing social partners, prepared modular training curricula and related training materials, recruited of the future OHS trainers from state authorities and accredited Slovak OHS institutions/organisations, conducted training, managed training implementation and evaluation of training outcomes |

| Date: from (month/year) to (month/year) | 1998-2001 |
| --- | --- |
| Location | Slovakia, Ireland, Iceland, Norway |
| Company / Organisation | Greenfield Coordinators Wesport (Leonardo da Vinci) |
| Position | Team leader |
| Job Description | Communication, Education and Employment for Women through Information Technologies – CEEWIT International steering committee member; national team leader; developed project facilitating access to education and employment to disadvantaged groups of women from geographically remote areas; managed project implementation; managed evaluation of training; designed and implemented public relations strategy |

| Date: from (month/year) to (month/year) | 1998-1999 |
| --- | --- |
| Location | Slovakia |
| Company / Organisation | Constitutional Court of the Slovak Republic (for the European Commission) |
| Position | Project manager |
| Job Description | Strengthening Institutional Capacity of the Constitutional Court Managed implementation of 2 projects – IT enhancement and publication of a judicial journal |

| Date: from (month/year) to (month/year) | 1997-2000 |
| --- | --- |
| Location | Slovakia |
| Company / Organisation | ICMA |
| Position | Trainer / consultant |
| Job Description | Local Government Development Provided technical assistance for ICMA local government development program (Training of Trainers) and establishment of regional training centres; designed and implemented citizen participation and cross-sectoral cooperation program. |

| Date: from (month/year) to (month/year) | 1997-2000 |
| --- | --- |
| Location | Various locations |
| Company / Organisation | Prospecta (USIA, ILO, Open Society) |
| Position | Trainer/consultant |
| Job Description | Central European Business Women’ s Academy Co-founded network of women’s NGO from 8 Eastern European countries to promote women’s economic and political empowerment; designed and implemented three CEBWA Annual Workshops (Budapest, Slovakia, Belgrade); raised funds, wrote narrative and financial reports, developed and implemented public relations strategy |

| Date: from (month/year) to (month/year) | 1998 |
| --- | --- |
| Location | Slovakia |
| Company / Organisation | Prospecta (Open Society) |
| Position | Team leader |
| Job Description | Management Development in Women’s NGOs Designed project for 24 participants, training curricula and materials, recruited trainers, conducted training, managed training implementation and evaluation, wrote narrative and financial reports |

| Date: from (month/year) to (month/year) | 1996-1997 |
| --- | --- |
| Location | Slovakia |
| Company / Organisation | Prospecta (PHARE) |
| Position | Team leader |
| Job Description | Human Resources Development in Softip-East Designed 2-year project for 60 participants operational in the OHS area as safety specialists and doctors in occupational medicine, elaborated training curricula and learning materials, recruited trainers (State Labour Inspectorate, Ministry of Labour, Institute for Public Health, safety specialists at SME; conducted training on strengthening the capacity of OHS instoitutions and HRD of OHS specialists, managed training implementation and evaluation, wrote narrative and financial reports |

| Date: from (month/year) to (month/year) | 1996 |
| --- | --- |
| Location | Bratislava/London |
| Company / Organisation | British Council |
| Position | Trainer |
| Job Description | Strengthening Professional Capacity of the Slovak Parliament Office Designed training curricula and materials, delivered training to the Slovak Parliament Office staff |

| Date: from (month/year) to (month/year) | 1996 |
| --- | --- |
| Location | Slovakia |
| Company / Organisation | Prospecta (PHARE) Know How Fund |
| Position | Team Leader |
| Job Description | Women in Management Designed project, training curricula and materials, recruited trainers, managed training implementation and evaluation including budget and reporting, developed and implemented public relations strategy |

| Date: from (month/year) to (month/year) | 1995 |
| --- | --- |
| Location | Slovakia |
| Company / Organisation | Prospecta (PHARE) |
| Position | Team Leader |
| Job Description | - Management Development in SMEs Wrote project proposal; designed training curricula and materials, recruited trainers, managed project budget, implementation, reporting and evaluation, developed and implemented public relations strategy, trained 50 participants 2. Human Resources Managers Development Designed project, recruited trainers, managed project budget, implementation , reporting and evaluation, developed and implemented public relations strategy; trained 24 human resources managers from public and private organizations |

| Date: from (month/year) to (month/year) | 1994 – 1995 |
| --- | --- |
| Location | Slovakia |
| Company / Organisation | Know How Fund |
| Position | Lead Trainer |
| Job Description | Training of Management Trainers Instrumental in introducing management trainer profession in Slovakia; trained 120 management trainers; translated background materials, designed curricula and training materials; participated in programme evaluation |

15.	Others:

15a.	Publications and Seminars:

Publications

- Quick Guide for Elected Officials, ICMA Bratislava, 1997, co-author of a manual distributed to 30 thousand newly elected officials in Slovakia

- Social Skills Manual, TU Kosice, 2003, co-author of a manual for socially excluded long-term unemployed  (EU project FACE)

- Priručnik o vjestinama komuniciranja – for social partners and state institutions (OHS), 2012

- Training Skills Manual for social partners (evidence-based learning), 2012

Other Professional Experience

- 2007-2009 & 2010-3/2012	Amman	United Nations Relief and Works Agency, Head of HR, Recruitment & General Services 1st 2007-2009 and 2nd from 2010 till March 2012

As HRD Head - managed recruitment and selection of international and local staff in 5 UNRWA operations (Jordan, Syria, Lebanon, West Bank and Gaza), provided high level advice on HR issues; drafted policies and guidelines; managed implementation of e-recruitment system; designed evaluation metrics  and reporting system for managerial information; instrumental in 10% gender balance increase in senior level positions; implemented performance management of staff; as Head General Services managed annual budget (USD 2 million) for administrative support and facilities management of headquarters operations in 3 locations (Amman, Gaza and Jerusalem); managed over 70 staff.

- 11/2004 - 05/2007	The Hague	International Criminal Court, Selection and Development Officer

Managed recruitment and selection of professional category staff for the Office of the Prosecutor (OTP); provided advice to staff on human resources issues; instrumental in developing HR policies, revision of work surveys and job classification; managed full recruitment and selection cycle ensuring compliance with HR guidelines; identified training and development needs in OTP; managed implementation and evaluation of specialized training programs; established training companies database; designed and implemented induction programme in the Office of the Prosecutor; facilitated complex staff survey process for 300 OTP staff including preparation of action plan; designed and delivered Communication at Work series of workshops.

- 10/2002 – 11/2004	Skopje	Organization for Security and Cooperation in Europe, Training Coordinator

Established Mission Training Section, developed Mission training procedures and guidelines; conducted Annual Training Needs Assessment; designed, co-ordinated and evaluated Mission Training Program for 450 staff; planned and managed Mission training budget; designed and delivered over 10 training modules: Performance Appraisal, Management and Leadership, Customer Care, Team Building, Presentation Skills, Train the Trainers, etc.; designed, coordinated and supervised mission Induction Program; ensured training quality control; established database of external training providers; identified, hired and evaluated external training services; liaised with public administration representatives, local and international NGOs; provided technical assistance to Mission programs (Rule of Law, Public Administration Reform, Confidence Building) and other OSCE missions in the Balkans.

- 01/1996 – 09/2002, Kosice, Prospecta, Centre for Management Development, Executive Director

Co-founded non-profit organization; developed vision, mission, strategic and operational plan; conceptualized, developed and coordinated Management and Organizational Development/Women’s Development Programmes; recruited, selected and supervised 3 internal staff and 15 associates; designed and implemented over 30 national and international projects; raised funds, planned and managed project budgets; oversaw administrative and logistic support; drafted progress and final reports; liaised with donors and clients; established partnerships with local and international NGOs; created and promoted Central European Business Women’s Academy - regional network for the promotion of women’s economic and political empowerment; provided technical assistance on training and development of socially disadvantaged groups; designed training curricula and materials, conducted over 10 thousand training/participant days for private, public and NGO sectors; member of national project evaluation committee for PHARE grant programme; developed and implemented public relations strategy; presented at over 15 international conferences, seminars and workshops (UNECE, CIPE, CEBWA; Femisfera).

- 09/1998 – 11/1999	Kosice	Constitutional Court of the Slovak Republic, Head of International Department

Created the International Department at the invitation of the Court’s President; drafted operational procedures and guidelines; prepared job descriptions; supervised and coached 4 staff; planned and coordinated delivery of language services to the President and Judges including translation, editing and printing of documents and publications; developed conceptual plans and provided methodological directions for international co-operation; managed 2 EU funded projects for strengthening the Court’s activities (over 700 thousand EUR);  maintained contacts with governmental agencies, foreign Constitutional Courts and EU institutions; accompanied the President on his official visits abroad; planned and implemented international activities such as official government visits, international conferences and seminars.

- 07/1992 – 12/1995	Kosice	Kobexs.r.o., Sales and Marketing Direct

Set up private company providing interpreting and advertising services, organizational development consultancy; developed sales and marketing strategy; planned and managed financial flows; conducted clients needs assessments, prepared bids, negotiated with clients and suppliers; conducted long term customer care survey (mystery shopping) for a major wholesale chain; recruited, supervised and coached 3 staff and 18 associates.

- 04/1990 – 05/1992	Montinvest, Belgrade, site Lipeck, Russia, Head of Interpreting Section

Established Interpreting Section and supervised 4 staff; planned and coordinated the delivery of language services for a civil engineering company; instrumental in establishing a building site for over 1000 staff; liaised with local authorities on operational and administrative matters; assisted in business negotiations with local airport authority resulting in renting a fleet of aircrafts for transfer of workers between Yugoslavia and Russia; logistics and coordination of chartered air transport; interpreted at high level meetings.

- Vukovarska Gimnazija, Vukovar, Yugoslavia         Teacher

Designed curriculum and conducted language training for secondary school students (English and Russian).

- Trudbenik Belgrade, site Baghdad, Iraq Interpreter

Interpreted at meetings with the Contractor and external suppliers of services; translated design documentation and business correspondence.

CURRICULUM VITAE

Proposed role in the project:		STE

1.	Family name:		DOBESOVA

2.	First name:		Maria

3. 	Date and place of birth:		January 17, 1952, Slovakia

4.	Nationality:		Slovak

5.	Civil Status:		married

6. 	Education:

| Institutions: | University PJŠ Kosice, Slovakia |
| --- | --- |
| Date: From (months/year)-To (months/year) | 1970-1975 |
| Degree: | (MA) in psychology (academic diploma) |
| Institutions: | University PJŠ Kosice, Slovakia |
| Date: From (months/year)-To (months/year) | 1977-80 |
| Degree: | PhD. (organisational psychology) |
| Institutions: | Comenius University, Bratislava |
| Date: From (months/year)-To (months/year) | 1983-89 |
| Degree: | Ph.D (pedagogical psychology) |
| Institutions: | IPD U.K. |
| Date: From (months/year)-To (months/year) | 1993-95 |
| Degree: | Certificate - International Trainer (training, of managers/ToT) |
| Institutions: | Thames Valley University, London, U.K. |
| Date: From (months/year)-To (months/year) | 1998-99 |
| Degree: | Professional Certificate in assessing training skills |

Additional Trainings for Professionals:

2007       Co-Active Coaching Fundamentals, The Coaches Training Institute, ACTP

2005       Management Consulting Training Course, Japan International Cooperation Agency

2002	Gestalt in Organization, I-GAP, Prague, Czech Republic

2001	Gestalt Therapy, Slovakia

1997      Staff Consulting Skills, Designed Learning Inc., USA, Bratislava, Slovakia

1996      Training of local government representatives trainers, USAID and UN Centre for

Human Settlement, Zemplinska Sirava, Slovakia

1995      Identification and Analysis of Training Needs, Know-How Fund, Bratislava, Slovakia

1995      USAID Participant Training Program for SMEs, USA

1995      Managing People, the Open University, CUB Kosice, Slovakia

1994      Training of Management Trainers, Roffey Park, Management Institute, U.K

1994      Training of Management Trainers, Trent University, Nottingham, U.K.

1992     The Management of Change, Canadian Bureau for International Education, Modra, Slovakia

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Slovak | Mother Tongue |  |  |  |
| English | 5 | 5 | 5 | 5 |
| German | 5 | 5 | 5 | 5 |
| Russian | 5 | 5 | 5 | 5 |

8.	Membership of Professional Bodies: member of professional association of trainers

9.	Other skills (e.g. computer literacy, etc.):

10.	Present Position: RDA Adult Education Specialist/HRD

11.	Years of professional experience: 23 years of professional experience

12.	Key qualifications:

- Relevant academic and professional background

- Long-term proven record in training of various target groups including social partners representatives

- Proven record in TNA and training methodologies aiming at capacity building measures

- Excellent knowledge in training delivery, nationally recognised trainer

- Knowledge of EU-legal rules in the area of social dialogue and capability to provide tailor-made advise and education

- Excellent mediation and negotiation skills

- Extraordinary networking skills and knowledge, work with stakeholders at local/regional/national/international levels

- Knowledge of employment policy

- Long-term experience with including disadvantaged groups

- Direct twinning experience on work with state authorities and social partners in Croatia

- Work and training of women

- Experience in CSR

- International experience and excellent language skills

13.	Specific experience in the region or else:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| Serbia | 2014 | Twinning Project “Promoting social dialogue”/STE |
| Croatia | 10/2011-5/2013 | Twinning Project “Health and safety at Work”/STE |
| Czech Republic | Since 2000 | Several projects aiming at capacity building of various stakeholders |
| Ukraine | 2008 | ToT/Training delivery |

14.	Professional experience:

| Date: from (month/year) to (month/year) | 2013-2014 |
| --- | --- |
| Location | Belgrade, Serbia |
| Company / Organisation | RDA for the Ministry of Labour, Employment, Veteran and Social Policy of Republic of Serbia |
| Position | STE |
| Job Description | Works included: - Review of state of play in employment services and needs for training/capacity building - Identification of institutional model/s - Design of capacity building programme - TNA for ToT specialised training - HRD of social partners key representatives - Conduction of ToT - Training delivery for all three key players – social partners (employers´& employee´ representatives and civil servants) - Elaboration of modular training curricula - Design of training materials according to the topics - Elaboration of specialised training manuals for Serbian beneficiaries - Follow up planning for sustainable HRD |

| Date: from (month/year) to (month/year) | 10/2011-5/2013 |
| --- | --- |
| Location | Zagreb, Croatia |
| Company / Organisation | RDA for the Ministry of Labour and Pension System of Croatia |
| Position | STE |
| Job Description | TNA of Croatian state authorities and social partners involved in the project implementation: - Ministry of Labour and Pension System of Croatia - Ministry of health - Croatian Institute for OHS (HZZZSR) - Croatian Health Insurance Institute (HZZO) - State Inspectorate - HUP – Croatian Association of Emplyers - Trade Unions Association Elaboration of modular training curricula Design of training materials according to the topics Training delivery Elaboration of specialised handbooks for Croatian beneficiaries Follow up planning (planning project with social partners on skills forecasting at branch level) |

| Date: from (month/year) to (month/year) | 2005– ongoing |
| --- | --- |
| Location | Regional Development Agency SP, Slovakia |
| Company / Organisation |  |
| Position | RDA Adult Education Specialist |
| Job Description | - responsible for East Slovakia activities of the RDA in the area of social affairs, - strategic planning in training, - lifelong learning, - coordination of East team of experts - coordination of projects and training for social partners, self-government, CSOs and state authorities in East Slovakia - Labour market research. Identifying new employment opportunities. Consulting in the area of recruitment in the European labour market with special focus on Eastern Europe - Monitoring equality of opportunities in the labour market in Slovakia - development of partnerships with Ukraine - evidence-based learning - training of SME |

| Date: from (month/year) to (month/year) | 2000 – 2005 |
| --- | --- |
| Location | Bratislava |
| Company / Organisation | CRS - Centrum rozvoja samosprav (Local Government Development Centre), |
| Position | Trainer and consultant |
| Job Description | Capacity building for local representatives: mayors, city managers, economists, social partners representatives and other local professionals in cooperation with their respective associations |

| Date: from (month/year) to (month/year) | 1998 – 2004 |
| --- | --- |
| Location | Various locations in Slovakia and abroad |
| Company / Organisation | Freelance Trainer |
| Position | Trainer |
| Job Description | Freelance Trainer upon request of state, social partners and self-government administration on: - social matters - Mediation and negotiation - Capacity building for EU-funds - Training of trainers - Analysis in the social and education areas |

| Date: from (month/year) to (month/year) | 1977 – 1997 |
| --- | --- |
| Location | Kosice, Slovakia |
| Company / Organisation | DPMK, City Transport Company Kosice |
| Position | transport psychologist, manager of Department of organizational psychology, personnel manager |
| Job Description | - Managed Department and staff - Coordinated workflow - Planned skills needs - Designed modular training - Trained staff and cooperating stakeholders |

| Date: from (month/year) to (month/year) | 1996 – 2000 |
| --- | --- |
| Location | Kosice, Slovakia |
| Company / Organisation | LSGAC - Local Self-Government Assistance Centre (founded by USAID in Slovakia) |
| Position | Trainer and consultant |
| Job Description | - TNA, training delivery, - coaching and consulting, - searching and developing specialists, - business consultancy, |

| Date: from (month/year) to (month/year) | 1993 – 2004 |
| --- | --- |
| Location | Bratislava |
| Company / Organisation | City University Bratislava (The Open University U.K.) |
| Position | tutor |
| Job Description | - General Management, - Business Negotiation, - Internal and External Communication in Marketing, Organizational Development, - Management of Change |

| Date: from (month/year) to (month/year) | 1990 – 2001, since 2002 upon request |
| --- | --- |
| Location | Various locations in Slovakia |
| Company / Organisation | QUI SUM |
| Position | Trainer specialist |
| Job Description | - TNA, training delivery, - coaching and consulting, - searching and developing specialists, - business consultancy, - programs of manager education, - programmes for education of social partners - special management skills, - psychological development programs in small groups, - personal development plans, - advisory in managing companies |

- Others: elaborated specialised handbooks for ToT

CURRICULUM VITAE

Proposed position in the project: STE

1.	Family name:	Stefanik

2.	First name:	Miroslav

3. 	Date and place of birth:	31 July 1983 / Povazska Bystrica, Slovakia

4.	Nationality:	Slovak

5.	Civil Status:	Single

6. 	Education:

| Institution: | University of Economics in Bratislava |
| --- | --- |
| Date: From (months/year) To (months/year) | 01/10/2007 21/09/2010 |
| Degree: | PhD in Economic theory/Forecasting |

| Institution: | University of Essex |
| --- | --- |
| Date: From (months/year) To (months/year) | 01/11/2009 31/11/2009 |
| Degree: | Research stay at the ECASS centre |

| Institution: | Comenius University in Bratislava |
| --- | --- |
| Date: From (months/year) To (months/year) | 01/09/2003 31/08/2008 |
| Degree: | Master degree in Sociology |

| Institution: | Comenius University in Bratislava |
| --- | --- |
| Date: From (months/year) To (months/year) | 01/09/2002 01/06/2007 |
| Degree: | Master degree in Philosophy |

7. 	Language skills:  Indicate competence on a scale of 1 to 5 (1 - excellent; 5 - basic)

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Slovak | Mother Tongue |  |  |  |
| English | 5 | 5 | 5 | 5 |
| Czech | 5 | 5 | 5 | 5 |
| German | 3 | 4 | 3 | 3 |
| Polish | 3 | 3 | 3 | 3 |
| Macedonian | 3 | 3 | 3 | 2 |
| Russian | 2 | 3 | 2 | 2 |

8.	Membership of Professional Bodies: National Expert in the SkillsNet network administrated by CEDEFOP, Expert in the Centre for Social Dialogue administrated by the Confederation of Trade unions of the Slovak republic, Member of the Scientific Board of the Institute of Economic Research of the Slovak Academy of Sciences, Member of the Slovak Educational Research Association

9.	Other skills (e.g. computer literacy, etc.): Statistical software (Stata, SPSS, R) Econometrics Software (in particular EViews), Database software (SQL), MS Office, Basic web creating technologies, Policy analysis.

10.	Present Position: Analyst of the labour market, Department of the analysis and European Employment Strategy, the Ministry of Labour, Social Affairs and Family of the Slovak Republic (MB) Bratislava, Slovakia

11.	Years of professional experience:	more than 7 years of intensive experience

12.	Key qualifications:

- Proven 7 years of analytic skills related to labour market and educational policies gained through providing supporting analysis for several national as well as international policy documents and employment measures

- Long term focus on skills mismatch analysis on the labour market

- Monitoring and creation of indicators related in participation in international working groups focused on structural and employment indicators

- Extensive experience in monitoring and evaluation of active labour market measures (Internship programme, employment programmes financed through ESF)

- Evaluation of employment policy measures and interventions proved by several reports and underlined with a good methodological insight and strong data analysis skills

- Economic analysis including SWOT and Cost Benefit analysis

- Experience in evaluation of policy measures in order to stimulate social dialogue by enforcing social partners analytical strengths, preparation of expert statements and reviews

- Econometric model building; short-term and long-term economic forecasting based on macroeconomic approach;

- Excellent presentation skills proven during participation in various international projects

- Project management skills acquired by administrating and managing several research projects of national and international scale

- Skill needs forecasting using quantitative statistical data in combination with qualitative approaches

- Processing of individual data proved by a variety of outputs based on individual data analysis using most recent methods

- Data management skills using SQL and related programming tools to work with big databases

- Qualitative data methods including Focus groups and in depth interviews

- Advanced statistical methods from regression based model, logit, probit, log-linear modelling, factor and cluster analysis proved in a set of publications, reports and outcomes

- Experience in providing training on data management, policy analysis, monitoring and evaluation procedures

- Wide twinning experience in the targeted area (in Macedonia and Serbia)

13.	Specific experience in Eastern and South-Eastern Europe:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| Macedonia (FYROM) | 10/2011 – 06/2013 | EU funded Twinning project: SUPPORT TO THE NATIONAL EMPLOYMENT POLICY Social and economic analysis of the labour market; development of monitoring and evaluation system; training of the staff of the MLSP and ESA on their role in monitoring and evaluation; economic analysis of the working hours; cost benefit analysis; labour market forecasting system at the Ministry of Labour and Social Policy of FYROM |
| Georgia | 02/2013 | Delivery of training in data management procedures for Association of Private Employment Agencies of Georgia Administrated by the International Training Centre of ILO |

14.	Professional experience:

| Date: from (month/year) to (month/year) | 05/2012 – up to date |
| --- | --- |
| Location | Bratislava, Slovakia |
| Company / Organisation | Department of the analysis and European Employment Strategy, Social Affairs and Family of the Slovak Republic (MB) |
| Position | Expert and Data Analyst for Economic Modelling, Forecasts and Analyses |
| Job Description | Analysis and assessment of the active labour measures Economic analysis and research of informal economy aspects; Monitoring and evaluation of active labour market measures; Reporting and preparing analyses, mostly in the fields of labour market and macroeconomic analysis Economic analysis of national and regional employment policy Research activities in the fields of labour market, economic modelling Macroeconomic prognosis, analysis of structural unemployment Setting up models for socio-economic development |

| Date: from (month/year) to (month/year) | 10/2010 – 4/2012 |
| --- | --- |
| Location | Bratislava, Slovakia |
| Company / Organisation | Institute of Economic Research, Slovak Academy of Sciences |
| Position | Analyst/ part time - special contract |
| Job Description | Macroeconomic modelling of the labour market and aggregate demand in Slovakia Regional analysis – quantitative and qualitative of regional disparities Conducting economic and social policy research on commissioned projects; |

| Date: from (month/year) to (month/year) | 01/2009-09/2010 |
| --- | --- |
| Location | Bratislava, Slovakia |
| Company / Organisation | The Statistical Office of the Slovak Republic |
| Position | Head Advisor |
| Job Description | Analytical work on in-house data; financial flows analysis, Mathematical Economics, Econometrics and modeling Methodology of statistical surveying, Creation of new indicators, SDI monitoring |

| Date: from (month/year) to (month/year) | 06/2010-8/2012 |
| --- | --- |
| Location | Bratislava, Slovakia |
| Company / Organisation | Ministry of Labour Social Affairs and Family of the Slovak Republic |
| Position | Analytical expert |
| Job Description | Conducting economic and social policy analysis; labour market forecasting, wage settings and continuing vocational training; Participating in the development of the Strategy for Active Ageing |

| Date: from (month/year) to (month/year) | 01/2007-12/2007 |
| --- | --- |
| Location | Bratislava, Slovakia |
| Company / Organisation | Institute for Information and Prognosis in Education |
| Position | Statistician |
| Job Description | Survey data processing; economic and social policy analysis; labour force survey processing; |

15a.	Publications and Seminars:

List of selected publications in English:

STEFANIK, Miroslav. Looking at the development of returns to education in Slovakia after 1989. In Ekonomický časopis, 2012, Vol. 60, Issue. 4, p. 349-360. (0.274 - IF2011). (2012 - Current Contents, WOS, SCOPUS, EconLit)

STEFANIK, Miroslav. Internet job search data as a possible source of information on skills demand (with results for Slovak university graduates), In: Building on the skills forecasts: comparing methods and applications. CEDEFOP Conference proceedings, 2012. http://www.cedefop.europa.eu/EN/Files/5518_en.pdf

STEFANIK, Miroslav. Focused information on skills demand using internet job search data (with results for Slovak university graduates), Conference proceedings from the 11th Comparative Analysis of Enterprise Data & COST Conference 2012. http://doku.iab.de/fdz/events/2012/Stefanik.pdf

ŠTEFÁNIK, Miroslav. Changes in private returns to education caused by the tertiary education expansion in Slovakia. In Review of Applied Socio-Economic Research, 2011, vol. 1, no. 2, p. 167-177. ISSN 2247-6772.

STEFANIK, Miroslav. What can existing overeducation tell us about the situation in supply and demand of tertiary educated?. In Review of Applied Socio-Economic Research. 2011, Vol. I, Issue. I,  p. 11-28. ISSN 2247-6172.

STEFANIK, Miroslav. Slovak regional differences in the process of university graduates recruiting for a job. In Regional disparities in Central and Eastern Europe : theoretical models and empirical analyses : peer - reviewed international conference proceedings. Menbere Workie Tiruneh and Marek Radvanský (eds). - Bratislava : The institute of economic research of the SAS, 2010, p. 337-353. ISBN 978-80-7144-180-9.

STEFANIK, Miroslav. Labour market changes according to Slovak knowledge based economy needs. In “Europe in motion: society, labour market and sustainability in the age of migration.” Friedrich Ebert Stiftung e. V., Slovakia. Bratislava. 2009

List of selected publications in Slovak:

WORKIE TIRUNEH, Menbere - BUJŇÁKOVÁ, Tatiana - HORVÁT, Peter - LICHNER, Ivan -ŠTEFÁNIK, Miroslav. Predvídanie potrieb trhu práce v SR : teoretické východiská a empirické výsledky. (Forecasting of Slovak Labour Market Needs: Theoretical Assumptions and Empirical Results) Bratislava : Ekonomický ústav SAV, Ekonóm, 2012. s. 181. ISBN 978-80-7144-204-2

ŠTEFÁNIK, Miroslav. Problém prekvalifikovanosti ako indikátor situácie ponuky a dopytu na trhu práce (Overeducation as an Indicator of the Supply-demand Relations on the Labour Market). In Ekonomický časopis, 2010, Vol. 58, Issue. 4, p. 327-343. (0.237 - IF2009). (2010 - Current Contents, SCOPUS). ISSN 0013-3035.

ŠTEFÁNIK, Miroslav. Zmeny v ponuke vysokoškolsky vzdelaných pracovníkov na trhu práce z pohľadu potrieb znalostnej ekonomiky v Slovenskej republike (Changes in the supply of tertiary educated workers on the labour market, from the perspective of Slovak knowledge based economy): Thesis (PhD.). Bratislava : Národohospodárska fakulta Ekonomickej univerzity, 2010.

15b.	References (selected projects)

NEUJOBS – Employment 2025: How will multiple transitions affects the European labour market (7FP)

LM needs - Forecasting Slovak Labour Market Needs in the Medium Term - Up to 2025 (National project)

COST IS0701 - Comparative Analysis of Enterprise Data: Industry Dynamics, Firm Performance, and Worker Outcomes (COST)

CURRICULUM VITAE

Proposed position in the project: STE

1.	Family name: 	Kubisova

2.	First name:     	Maria

3. 	Date and place of birth: 	11 November, 1955

4.	Nationality: 	Slovak

5.	Civil Status: 	married

Address (phone/fax/e-mail): Clementisova 12, 036  01 Martin, Slovak Republic

- Education:

| Institutions: | Technical University of Kosice, Slovakia |
| --- | --- |
| Date: From (months/year) To (months/year) | 1975-1980 |
| Degree: | Academic diploma - engineering |
| Institutions: | University of Innsbruck, Austria |
| Date: From (months/year) To (months/year) | 2012 |
| Degree: | Certificate Educational programme in Competencies-based Advising, |
| Institutions: | Ministry of Construction and Regional development, Slovak republic |
| Date: From (months/year) To (months/year) | 2006 |
| Degree: | Certificate of Enlarging the regional and local capacities for management and realization of help from funds of EU |
| Institutions: | Nuremberg, Germany |
| Date: From (months/year) To (months/year) | 2003 |
| Degree: | Certificate of Trainer for Distant Consultancy |
| Institutions: | Comenius University and AIVD in Bratislava |
| Date: From (months/year) To (months/year) | 2000 |
| Degree: | Certificate of Trainer of Adult Education |
| Institutions: | ARBEITSGESTALTUNG KABA Uster, Switzerland |
| Date: From (months/year) To (months/year) | 1996 |
| Degree: | Certificate of the Trainer of Career Consultancy |
| Institutions: | Education centre in PovazskaBystrica, Slovakia |
| Date: From (months/year) To (months/year) | 1995 |
| Degree: | Certificate of trainer |
| Institutions: | Education centre in Povazska Bystrica |
| Date: From (months/year) To (months/year) | 1993 - 1995 |
| Degree: | Certificates of Manager course, Career consultant training, Personality development |
| Institutions: | OWZ Munich, Germany |
| Date: From (months/year) To (months/year) | 1992 |
| Degree: | Certificate of participation in 6 months course in charge of coordination and leading the training for novice trainers in marketing and management |
| Institutions: | IVAR, Martin, Slovakia |
| Date: From (months/year) To (months/year) | 1989 |
| Degree: | Certificate of Computer skills |

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Slovak | Mother Tongue |  |  |  |
| Czech | 5 | 5 | 5 | 5 |
| German | 5 | 5 | 5 | 5 |
| English | 5 | 5 | 4 | 4 |
| Russian | 5 | 5 | 5 | 5 |

8.	Membership of Professional Bodies:

9.     Other skills (e.g. computer literacy, etc.): (e.g. computer literacy, etc.):  Active professional use of office software – MS Word, Excel, PowerPoint, Internet and E-mail.

10.	Present Position: HRD Manager of Regional Development Agency Senec-Pezinok

11.	Years of professional experience: 25 years

12.	Key qualifications:

- 25 years of hands-on professional experience and knowledge of working in adult education area as a trainer and career counsellor (development of the strategies  and guidelines for career guidance to be implemented in all labour offices in Slovakia, redefining of the concept of the career guidance, development the system for career guidance for students and employers;  development of the group career guidance programmes, development and delivery of the assessment tools for counsellors;  development of methodologies and guidelines and other practical tools)

- professional experience in the employment services, also as a director of Office of Labour in Martin, Slovakia

- Working as an expert for solving the services of employment policy in Kirgizstan

- Expert in career counselling in Slovakia, based on Swiss and Austrian know-how, creator of methods developed further for Slovak conditions (project CVANU for NUCZV, several projects for Offices of Labour in Slovakia for their staff and unemployed, InfoKariera)

- 12 years of experience as trainer  for career guidance and adult training, organising and conducting trainings based on know-how from Switzerland (experiential learning methodology; delivery of career guidance for schools and employers; labour office staff trainer;

- Trainer, coach and methodologist in career counselling for various target groups (youth, schools, unemployed, 50+, etc)

- 10 years of professional experience in programming/implementation of HRD/ESF-funded projects, e.g.:

- EU – ESF project: National project - Improving the conditions for job-training for disadvantage people on the labour market

- EU – ESF project: National project -   Supporting the job training of juvenile delinquents in prisons

- EU – ESF National Project: Implementation of Evaluation of tools and training facilities for disabled people, to become job-ready

- EU – ESF National Projects: Support the employment scheme for handicapped people; Incentive Measures for  School Leavers; Activation works for Inclusive Labour Market;

- Setting up the Grant management system for the implementation of the ESF interventions for Employment service (national projects and grants – Employment and active labour market measures);

- 18 years of experience in design/delivery of active labour market programmes and measures (ALMPMs) e.g. developing and implementing training programs for job seekers – different target groups (women, young people, Roma’s, disadvantaged groups, etc. … delivery of on-the-job training courses based on the demand of employers;

- 18 years of experience in local labour market analysis and delivery of public employment services to unemployed and employers: e.g. analysis and research concerning special needs of women to return to the first labour market; analysis of the potential for business start ups; professional counselling for schools; developing and implementing training program for unemployed women  to qualify as assistants for elderly persons,

- Analysis  and provision of special support for juvenile seekers to provide support on finishing school, exploring skills and successfully enter the labour market

13.	Specific experience in the region or else:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| Austria, Luxemburg, Slovakia | 2011-2013 | Skills and Competences Assessment – New career guidance and counselling approach (SCAN), Leonardo TOI (partnership including social partners) |
| Macedonia (FYROM) | 12/2012 – till 11/2013 | Trainer of the OEM (Organisation of Employers of FYROM) staff and ESA staff (Employment Service Agency) |
| Italy, Greece | 09/2010 – 12/2012 | Leonardo da Vinci ‘Transfer of Innovation’ QUIGUS – ‘Trainer’ |
| Croatia | 01/2011 – 12/2011 | TW – Fostering effective employment of persons with disabilities into the labour rmarket |
| United Kingdom | 02/2010 – 09/2011 | Leonardo ‘Mobility’ VETPRO and PLM (K.A.B.A. Slovakia and ETS Ltd Lichfield, UK– ‘Coordinator and tutor’ |
| Italy | 04/2008 – 11/2008 | Vocational training course for ‘Naturalistic and Equestrian Tourist Guide’ – tutor for Promidea |
| Italy, France | 02/2006 – 12/2006 | Grundtvig – EUROVALIDITY – evaluation of the education of adults in France, Italy and Slovakia |
| Uster Switzerland | 03/1997 – 12/1997 | Training of job seekers - ARBEITSGESTALTUNG Uster Switzerland ( training and tutoring) |
| Kyrgyzstan | 02/1995 – 06/1995 | Support the PES - Project aimed on introduction of ALMP in Kyrgyzstan, in cooperation with GTZ, Eschborn, Germany |

14.	Professional experience:

| Date: from (month/year) to (month/year) | 1/2011- ongoing |
| --- | --- |
| Location | Bratislava |
| Company / Organisation | Bratislava Regional Development Agency Senec - Pezinok |
| Position | Senior Programme Manager – Training & Career development Specialist |
| Job Description | - Responsible for: - Training - TNA for labour offices staff for capacity building and skills acquisition, - Training methodologies and design - Training delivery to social partners and state authorities - Impact assessment - Individual action plans development for clients of labour offices - Coordination team of trainers - Delivery TOT (training of trainers) - Carrier guidance for different target groups - labour office clients - employment and labour market policy – implementation of the EU – ESF National Projects: Support the employment scheme for handicapped people; Incentive Measures for School Leavers; Activation works for Inclusive Labour Market; - implementation of social economy and inclusive employment measures - VET planning in the context of bringing closer the labour market and VET (skills for employability), - Development of training curricula, training delivery (adult’s trainings; training of trainers; in the employment and social policy area) |

| Date: from (month/year) to (month/year) | 1/2007-12/2010 |
| --- | --- |
| Location | Bratislava |
| Company / Organisation | K.A.B.A. Slovakia, non-profit organisation |
| Position | Director |
| Job Description | - Managing the national projects financed within the ESF: Increasing the qualification potential and availability of employees and persons entering the labour market; Increasing and improving Continuous Vocational Training to improve the adaptability of employees, etc… - Implementation of active labour market policy measures – designing, implementation, monitoring and evaluation - individual and professional guidance for the unemployed people; vocational guidance; employment schemes for school leavers; - Dealing with market analysis and delivery of services to unemployed and employers: e.g. analysis and research concerning special needs of women to return to the first labour market; analysis of the potential for business start ups; professional counselling for schools; developing and implementing training program for unemployed women to qualify as assistants for elderly persons, social assistance to mothers, juveniles by preparing and training them for the labour market; - Analysis and provision of special support for juvenile seekers to provide support on finishing school, exploring skills and successfully enter the labour market - drafting teaching and training materials for labour offices staff; - Development of innovative strategies and instruments to integrate people over 50 to the labour market and dissemination of good practice examples within the partners); |

| Date: from (month/year) to (month/year) | 1/2000-12/2006 |
| --- | --- |
| Location | Bratislava |
| Company / Organisation | National Labour Office of the Slovak Republic |
| Position | Director of Employment Services Department |
| Job Description | - Responsible for development and provision of carrier guidance in Slovakia – development of the strategies and guidelines for career guidance to be implemented in all labour offices in Slovakia; redefining of the concept of the career guidance, development the system for career guidance for students and employers; development of the group career guidance programmes; development and delivery of the assessment tools for counsellors; development of methodologies and guidelines and other practical tools - Setting up the Grant management system for the implementation of the ESF interventions for Employment service (national projects and grants – Employment and active labour market measures and Management of 4 Grant Schemes for Human Resources Development financed from ESF); - Implementation of, active labour market policy measures – designing, implementation, monitoring and evaluation - Dealing with individual and professional guidance for the unemployed people; vocational guidance; employment schemes for school leavers; - drafting teaching and training materials; - drafting the measures for the implementation of the National Employment Plan; |

| Date: from (month/year) to (month/year) | 11/1995-12/1999 |
| --- | --- |
| Location | Bratislava |
| Company / Organisation | Employment Fund of the Slovak Republic |
| Position | Head of Active Labour Market Measures Department |
| Job Description | - Drafting the national employment policy papers - Development of the client oriented approach in service delivery - Monitoring, evaluation and reporting about labour market situation - Coordination of the capacity building of the labour offices staff (internal and external training) - Implementation of innovative tools and methods in career guidance and consultancy services; - Development of the National Actions Employment Plans for job seekers - Development of policy and strategy for new concept of employment services models influenced by the relevant employment guidelines, job guidance, framework of common European labour market with the strong orientation to processes focus on individual measures; |

| Date: from (month/year) to (month/year) | 11/1991- 11/1995 |
| --- | --- |
| Location | Martin, Slovakia |
| Company / Organisation | Labour Office |
| Position | Director |
| Job Description | - Management and coordination of the staff and services of the labour office - Designing and implementation of the active labour market measures; - In charge of financial management of the APTP; - visibility actions and information campaign for labour office clients – unemployed and employers - Training needs assessment, delivery of labour office staff training; the trainers courses - Staff education and training |

| Date: from (month/year) to (month/year) | 07/1989 – 10/1991 |
| --- | --- |
| Location | Martin, Slovakia |
| Company / Organisation | IVAR – Institute of Education and Re-training in Martin |
| Position | Head of Pedagogic Division dealing with the development of the training and re-training courses; coordination of the delivery of the training courses with the district labour offices; methodology of the training course; planning and the implementation of the active labour market measures for the clients of the labour offices |
| Job Description |  |

| Date: from (month/year) to (month/year) | 11/1985-06/1989 |
| --- | --- |
| Location | Martin |
| Company / Organisation | ZTS Research and Development Institute |
| Position | Agent for technical information |
| Job Description | Coordination of the development projects |

| Date: from (month/year) to (month/year) | 10/1980-10/1985 |
| --- | --- |
| Location | Turany Slovakia |
| Company / Organisation | Drevina, state owned comany |
| Position | Manager for technical and organisational development |
| Job Description | Technical support of the services department |

15a.	Publications and Seminars: a range of contributions to specialised magazines of the Ministry of Labour and those related to adult education

CURRICULUM VITAE

Proposed position in the project: STE

1.	Family name: 	PALIK

2.	First name: 	Maros

3. 	Date and place of birth: 	3th May 1977, Kezmarok, Slovak Republic

4.	Nationality: 	Slovak

5.	Civil Status: 	Married

6. 	Education:

| Institutions: | Faculty of Law, Comenius University, Bratislava, Slovak Republic |
| --- | --- |
| Date: From (months/year) To (months/year) | September 1996 September 2001 |
| Degree: | Master of Law |

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Slovak | Mother Tongue |  |  |  |
| English | 4 |  | 4 | 4 |
| German | 4 |  | 4 | 4 |

8.	Membership of Professional Bodies: Member of the Slovak Bar Association

9.	Other skills (e.g. computer literacy, etc.): computer literacy (MS Word, MS Excel, MS Power Point, MS Outlook), driving licence (cat. B)

10.	Present Position: Chief lawyer for labour relations of RDA Senec-Pezinok

11.	Years of professional experience: 12 years

12.	Key qualifications:

- Civil law - labour law, employment law, collective bargaining law,  family law, contractual law

- 12 consecutive years of proven working experience  in the field of  labour law related to employment and working conditions,  working time,  collective bargaining, different type of work contracts

- Proven experience in representation in legal proceedings in employment and legal relations pursuant to the Labour Code

- Legal analysis to the draft labour law and legislation proposals drafting

- Proven experience in transposition of the labour law to the EU legislation (table of compliance; legal statements and analysis, legal agreements; comparative analysis and legislative proposals

- Representation in legal proceedings on responsibility for damage in the case of occupational accidents and occupational diseases

- Capacity building  expert –delivery of  trainings, lectures statements on labour and contractual law

- Twinning experience as STE – lawyer in Serbia

- Proven skills in working in cross-beneficiary, multicultural teams

13.	Professional experience:

| Date: from (month/year) to (month/year) | November 2006 – ongoing |
| --- | --- |
| Location | Slovak Republic, Bratislava |
| Company / Organisation | Regional Development Agency Senec-Pezinok (RDA) |
| Position | Chief lawyer for labour relations |
| Job Description | Legal assistance in the field of labour law: - legal analyses (legal opinions) for state and municipalities - Liaison with the Ministry of Labour, Social Affairs and Family (topics of cooperation: law analysis/labour code/occupational health and safety/employment/antidiscrimination and legal agreements drafting) as well as liaison with other state authorities and municipalities - Preparation of international contracts - Employment contracts and termination - Representing RDA at all legal matters in relation to the Labour Code - Training of state representatives and social partners representatives in understanding of new EU directives – impact on transposition - Legal assistance in company social dialog and collective bargaining, direct work with the social partners at national and regional levels - Legal advice to state/municipal and social partners’ representatives on legal proceedings on responsibility for damage in the case of occupational accidents and occupational diseases. - Elaboration of contracts pursuant to the Civil Code, - Protection of property rights (legal actions, representation in proceedings pursuant to the civil law). - Leading the RDA team of lawyers - STE: Twinning Project in Serbia with Ministry of Labour of Serbia in law transposition (2013-2014) |
| Date: from (month/year) to (month/year) | October 2006 – cont. upon request |
| Location | Slovak Republic, Bratislava |
| Company / Organisation | Law consultancy ltd |
| Position | Advocate |
| Job Description | Legal assistance in the field of labour law: - Elaboration of employment contracts and other contracts pursuant to the Labour Code, - Preparing of analysis and legal opinions in cases of Labour Law, - Preparing of internal organizational orders, - Legal assistance in company social dialog and collective bargaining, - Termination of employment, - Representation in legal proceedings in employment and legal relations pursuant to the Labour Code, and - Representation in legal proceedings on responsibility for damage in the case of occupational accidents and occupational diseases. Other legal assistance in: Legal assistance in the field of family law: - Dissolution of marriage, - Arrangement of rights to the minors, -Cancellation and settlement of estate by entirety of husband and wife, Legal assistance in civil and contractual law: - Representation of natural and legal persons, - Transfers of title to real estates and movables (purchase contracts, gift contracts, exchange contracts, etc.), - Elaboration of contracts pursuant to the Civil Code, -Protection of property rights (legal actions, representation in proceedings pursuant to the civil law). |
| Date: from (month/year) to (month/year) | May 2004 – September 2006 |
| Location | Slovak Republic, Bratislava |
| Company / Organisation | JUDr. Henrieta Danisova and Partners |
| Position | Lawyer |
| Job Description | - Elaboration of contracts and documents pursuant to the Labour Code - Preparing of analysis and legal opinions in Labour Law, - Elaboration of contracts and agreements, - Legal analysis (labour law), - Representation in legal proceedings, - Elaboration of documents in labour law and family law, transfers of title to real estates and movables (purchase contracts, gift contracts, exchange contracts, etc.), - Elaboration of contracts pursuant to the Civil Code. |
| Date: from (month/year) to (month/year) | January 2003 – April 2004 |
| Location | Slovak Republic, Bratislava |
| Company / Organisation | Slovak State Inspection |
| Position | Lawyer |
| Job Description | Preparing of administrative decisions Draft law preparation (inspection) Legal analysis Legal agreements |
| Date: from (month/year) to (month/year) | August 2001 – December 2002 |
| Location | Slovak Republic, Bratislava |
| Company / Organisation | Ministry of Defence of the Slovak Republic |
| Position | Department of International Relations - Internship Lawyer |
| Job Description | Preparing of foreign affairs documents (legal agreements and contracts, |
| Date: from (month/year) to (month/year) | January 1995 – July 2001 |
| Location | Slovak Republic, Bratislava |
| Company / Organisation | Vseobecna zdravotna poistovna (State Health Insurance Company) |
| Position | administrative worker, clerk |
| Job Description | support service in the administration matters; support for leading the office; organisation of meetings with state representatives, in particular with the Ministry of Labour, Social Affairs and Family and Ministry of Health of the Slovak Republic; logistical matters |

14.	Publications and Seminars:

A large number of seminars & workshops organized by the Slovak Bar Association – in the field of Labour Law, Civil Law, Family Law Civil Proceedings.

15.	References:

Ministry of Labour, Social Affairs and Family of the Slovak Republic (labour law/labour relations, legal analyses)

Magistrate Bratislava (civil law - contracts pursuant to the Civil Code; labour law relations and agreements)

Bratislava Self – Governing Region (legal analysis, contractual law)

Municipality of Bratislava - Petrzalka

Municipality of Bratislava - Dubravka

Domov socialnych sluzieb Rozsutec (labour law)

Domov socialnych sluzieb Plavecke podhradie (labour law)

Spolocnost pre rozvoj byvania Bratislava, n.o.

METRO Bratislava a.s. (legal assistance in labour law, contractual law, civil law)

METRO Investing s.r.o. (legal assistance in labour law, contractual law)

EXPA Group, s.r.o.

etc.

CURRICULUM VITAE

Proposed position in the project: 	STE

1.	Family name: 	KUBALOVA

2.	First name: 	Valeria

3. 	Date and place of birth:	4th June, 1961

4.	Nationality: 	Slovak

5.	Civil Status: 	Divorced

Address (phone/fax/e-mail): Drobneho 5, 841 01 Bratislava

6. 	Education:

| Institutions: | Matej Bell University, Faculty of Law, Banska Bystrica, Slovakia |
| --- | --- |
| Date: From (months/year) - To (months/year) | 09/2004 – 06/2008 |
| Degree: | University degree in Law (academic diploma) ; Master in Law |
| Institutions: | Carl Duisberg Geselschaft e.V. & Institute for European Politics, Slovak Rep. |
| Date: From (months/year) - To (months/year) | 3/2001 |
| Degree: | Certificate “EU Trainer” |
| Institutions: | ILO International Training Centre and European Training Foundation in Turin |
| Date: From (months/year) - To (months/year) | 11/1999 |
| Degree: | Certificate Special Preparatory Programme for the ESF, Training of the Training Managers for the National Training Institutions |

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Slovak | Mother Tongue |  |  |  |
| English | 5 | 5 | 5 | 5 |
| Russian | 5 | 5 | 5 | 5 |
| Croatian | 4 | 4 | 4 | 4 |
| Serbian | 4 | 4 | 4 | 4 |

8.	Membership of Professional Bodies: CEPAC Slovakia - Member of Governing Body from 1998 – 2003, Slovak Society for Evaluation – since 2008

9.	Other skills (e.g. computer literacy, etc.): Fully Computer literate: Microsoft Office, database and relevant graphics applications, etc.

10.	Present Position: Senior Programme Manager, Employment policy – evaluation and monitoring, strategic planning and active employment measures on both - programme and project level, social dialogue, Regional Development Agency Senec - Pezinok

11.	Years of professional experience: 22 years in public and private administration in the context of HRD & Education, Employment Policy – capacity building of state and public administration in the field of employment and social affaires

12.	Key qualifications:

- Over 22 years of professional experience in EU Employment, Labour Market Strategies, (capacity building of Employment Institutions for reforms of ALMPs, introducing new curricula, training of adults, industrial relation and social dialogue; youth employment, training of trainers, employment creation measures, LLL, social economy, VET), with  more than 15 year experience in different managerial and operational levels of Public Employment Services  and more than 10 years of managing the EC funded projects

- 15 year experience in working for and coordinating several Public Employment Services at various government levels as: Head of International Relations of the Ministry of Labour (1990-95), Deputy Head of Labour Market Policy Unit at the Employment Fund, Director of International Relations and Cooperation Department (1997-99) and Director of EU Policy and Programme Department (2000-2004) of the National Labour Office, Director of the National Training Institute for the ESF, Advisor to Director General for Employment at the Central Office of Labour (2004-2005) in Slovakia.

- Over 7 years of experience  in managing the inter-ministerial working groups in coordination of social security schemes ( in charge of preparation and negotiation of bilateral agreements on mutual employment and bilateral agreements on social security); social dialogue agenda

- Long experience in leading the negotiations on implementation of Aquis within the Chapters  “Free Movement of Workers” and “Employment and Social Policy”

- Development and implementation of the EU Employment, social inclusion,  VET and youth policy at national and local level in Slovakia, Belarus, Uzbekistan, Romania, BiH, Croatia, FYROM; Proven experience in introducing the European Employment Strategy into the Slovak Employment Service, Co-drafting the National Action Employment Plan,  National Action Inclusion Plan (including youth) - contact person for transposition of EU measures into chapter 2 Free movement of persons and chapter 13 Social policy and employment at the Employment Services

- Extensive knowledge of Public structures related to implementation of Employment policies financed under the ESF (day-to-day couching to Employment Services institutions, designing and establishment of MA/IBs structure and capacity building for the Ministry of Labour in Slovakia and Romania); capacity building and delivery of training through the National Training Institute for the ESF in Slovakia and establishment and training of eight Regional Advisory ESF Centres within the structure of Employment Services

- Management of the Public Employment Service Reform related to the ESF interventions, Management and Programming the HRD OP, Drafting OP Measures to support Employment; Experience in management and couching teams operating at different governmental levels to implement National Employment Strategies in Slovakia, Romania and Croatia;

- Sound experience in management and implementation of capacity building projects to Employment Institutions–  Support for the Ministry of Labour to prepare as Managing Authority for SOP HRD in Romania (first and second phase); Support the system of social protection in BiH; Fostering the effective inclusion of persons with disabilities into the labour market in Croatia Capacity building for PES staff (designing and implementation of the active labour market measures for job seekers, PCM, Call for proposal, financial management, monitoring, evaluation);Support the National Employment Policy  in FYROM (forecasting of the labour market including the future skill needs analysis for youth, development of monitoring and evaluation system of the employment policy);

- Practical skills in organisation and coordination of trainings, Training need analysis, delivery of seminars and workshops for civil servants with focus on labour market and employment, social dialogue (trainer at local, regional, national and European level)

- Long-term proven experience in designing, management, implementation, monitoring & evaluation of Active Labour Market Programmes; design &  implementation of the professional guidance for the unemployed; career guidance; employment schemes for school leavers; measures for registered employment, measures for youth,  disabled & socially excluded; developed the strategy for new concept of Employment Services models, HRD strategies on national, regional & local levels; social dialogue

- Long experience in participation in top-level conferences and workshops on employment policies and employment services models (DG Employment and DG Regio, ILO, World Association of Public Employment Services, OECD LEED Programme) and experience on international labour market of the countries involved (specifically including Turkey WLMP 2007-09; International PES conference on Undeclared work 2004-05; Accession countries PES Managers meetings and round tables  c/o DG Employment and DG Regio 2000-2004; international conference  The World of Labour 1997; WAPES 1997-99).

- Long-term work experience with design, preparation, management, monitoring and evaluation of grant schemes focused on employment and ALMPs

- Drafting more than 40 Call for Proposals for the ESF, capacity building and  training of trainers, training of project promoters, training of evaluators, building the ESF project pipeline on regional and local level - 800 project proposals in Slovakia and over 1500 project proposals in Romania)

- University Degree in Law; ILO Certificate for ESF: Training the Training Managers; EU Trainer Certificate

13.	Specific experience in the region or else:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| Macedonia (FYROM) | 09/2011 – 6/2013 | Twinning Project “Support to the National Employment Policy focused on the development of long-term forecasting of the labour market and monitoring and evaluation of employment programmes”. |
| Romania | 02/2007, 05/2007 – 11/2008 | Project “Support to the OP Human Resources Development” |

14.	Professional experience:

| Date: from (month/year) to (month/year) | 09/2011 – 06/2013 |
| --- | --- |
| Location | Skopje |
| Company / Organisation | Ministry of Labour and Social Policy |
| Position | Resident Twinning Advisor |
| Job Description | - Management of the Twinning Project ”Support to the National Employment Policy”, responsible for: - Development of the long-term forecasting of the labour market for the Ministry of Labour and Social Policy ; assessment of capacities and needs in terms of long-term forecasting; designing and set up of the Hermin model; analytical and forecasting capacity building of the Ministry’s staff and other stakeholders ( analytical and technical skills training, reinforcement of the interinstitutional cooperation (datasharing, quality and exchange of data within involved stakeholders; future skills need analysis for young people to match the LM) - Designing and introduction of the comprehensive monitoring and evaluation system for employment policy and programmes; policy and institutional framework for M&E System (development of manuals, guidelines, procedures for monitoring and evaluation, development of strategic and operational indicators for the National Action Employment Plan; reporting on the implementation of the National Action Employment Plan and Operational Plans, Outcome evaluation of some of the ALMM (methodology, implementation plan, interviews, data collection, evaluation, reporting) - Improvement of the capacities and skills of bodies, institutions and social partners to monitor and evaluate employment (development of the model of involvement of the social partners; training needs analysis, curricula development; technical and analytical skills training); |

| Date: from (month/year) to (month/year) | 1/2007 on going |
| --- | --- |
| Location | Bratislava |
| Company / Organisation | Regional Development Agency Senec - Pezinok |
| Position | Senior Programme Manager |
| Job Description | - Responsible for: - employment policy – evaluation and monitoring, strategic planning and active employment measures at programme and project level, socal dialogue agenda - Planning strategic projects in the area of HRD (ESF, Leonardo da Vinci, Progress); - analysis of the labour market (active labour market policy, monitoring and evaluation of labour market programmes - labour market analysis and active employment including cross-border employment measures planning Slovakia – Austria - social economy and inclusive employment measures - VET planning in the context of bringing closer the labour market and VET (skills for employability), - evaluation methodologies, - training of adults aged 50+ - training of trainers in the social policy area - RDA Key expert in the area of employment, EU social policy and elaboration of strategic projects for candidate and third countries in the social field aiming at active employment policy |

| Date: from (month/year) to (month/year) | 11/2007 – 12/2008 |
| --- | --- |
| Location | Slovakia, Bratislava |
| Company / Organisation | Bratislava School of Law |
| Position | International Programme Manager |
| Job Description | Coordination and management of the projects in the area of: Adult Education, Labour market and Social Protection; VET, Science and Research; multilateral projects financed under various EC funded programme. Responsible for: - National Panel Expert in Ex post evaluation of the EQUAL Community Initiative (2000-2006) - Impact on the functioning of the labour market and on the investment in human capital infrastructure through support to systems and structures (Thematic evaluation) – providing evaluation for all MS participating in EQUAL Community Initiative particularly in the employment, social inclusion and the equal opportunities and anti-discrimination policy areas - Management of the project funded under UNDP “The Slovak experience in the field of building national system of life-long learning for judges, prosecutors, advocates and other legal professionals in Belarus” – development of strategic document including the proposals and recommendations for improvement of Belarusian educational system for legal professionals; adjusting curricula and programmes of the Institute for Re-training and Upgrading Qualifications of Judges, Prosecutors and Legal Professionals - Management of the Slovak-Aid project “Support to System of Social protection” for the Ministry of Health and Social Welfare in Republic of Srpska in Bosnia and Herzegovina – analysis of social and labour legislation, development strategy for social welfare system, standardization of social services, training of trainers - Management of the project funded under UNDP “ Learning from the Slovak experience in development of the arbitration courts and alternative ways of dispute resolution for Uzbekistan” – harmonizing domestic business law with the relevant international and EU standards; development of the educational framework for advanced training and professional upgrading methods for arbitration judges; development of training curricula and delivery of training. - Implementation the project funded under the ESF “Increasing the quality of the Transfer of Knowledge Centre” - Implementation the Strategy of the development of the Creative Economy Centre (setting up the structure, designing the strategy, development the implementation models) - Capacity building of Transfer of Knowledge Centre (setting up the structure, units, selection the staff, Training needs analysis, development of new curricula or researchers and training package for different positions, delivery of training) - Implementation of the HRD component with the development, testing and training of the creativity of adults and job seekers - Participation in International Scientific Research Group focused on implementation of Bolonian educational standards into national Universities |

| Date: from (month/year) to (month/year) | 02/2008-11/2008 |
| --- | --- |
| Location | Romania, Bucharest |
| Company / Organisation | Archidata Italy |
| Position | Key Expert for Training |
| Job Description | Within the technical assistance of the project “Support for the MoLFEO to prepare as Managing Authority for SOP HRD in Romania” (second phase) responsible for: - Support the project portfolio development within all Priority Axis under SOP HRD for strategic projects and grants schemes for active labour market measures, social economy and partnership for local employment support schemes (strategy development of the measures, designing the local partnership approach, delivery of training for potential beneficiaries, monitoring indicators, evaluation methodologies and training of evaluators); - Preparation of 22 Call for Proposals under SOP HRD (strategic projects and grants schemes) – drafting of the Guideline for Applicants, Call for proposal package; - Preparation, management and delivery of training for over 2600 potential beneficiaries – writing quality proposal – (development of new curricula, training methodology, teaching materials, delivery of training, evaluation of training); - Support in development of evaluation methodology and selection criteria for MA SOP HRD evaluators of strategic and regional grants and delivery of training for 200 evaluators, TA support in designing structure and mechanism for evaluation of projects; - Assisting in capacity building of 8 Technical Secretariats of Regional Employment and Social Inclusion Pacts (introducing new curricula for adults, training and assisting/coaching to empower them to perform their job in partnership). Management and facilitation of social partnership in educational and training - Dissemination of the results of the Call for Proposals – best practices for Employment measures, Education, VET, Adult Education, Human Resources Development policies within the Priority Axis: projects on Transition from school to active life – 10 projects; Preventing and correcting early school leaving – 12 projects; - Support the MA SOP HRD in capacity building the institutional, administrative, programming, implementation, monitoring and evaluation structures necessary to effectively manage ESF after accession (training needs analysis, development the training strategy, Development of the methodology for project monitoring and evaluation on the project level, managing the training delivery for MA and IB staff) - Capacity building of multipliers for National Centre for Technical and Vocational Education Development (delivery of methodology and practical training for 150 evaluators |

| Date: from (month/year) to (month/year) | 02/2007 |
| --- | --- |
| Location | Romania, Bucharest |
| Company / Organisation | Eco 3, sprl. Brussels |
| Position | Short Term Training Experts |
| Job Description | Development of training material and training delivery in the position of Short term expert contracted within the technical assistance RO 2004/016-772.04.03 EUROPAID/1214669/D/SV/RO “Horizontal Training for Structural Funds”. Training topics: - Project development and implementation under the EU Structural Funds - Project identification and development (PCM, Analysis and identification of SF framework for the project application form, Partnership and networking, Information and publicity, Implications for FB, SF reporting requirements, Procedural guidelines for SF FB) - Project monitoring and evaluation ( Pre-implementation phase, SF project Management, Financial management, Monitoring and reporting, Evaluation, Control) |

| Date: from (month/year) to (month/year) | 11/2006 – 04/2007 |
| --- | --- |
| Location | Slovakia, Bratislava |
| Company / Organisation | Euroformes, sprl. Zilina |
| Position | Evaluation Expert |
| Job Description | Evaluation of the Transition Facility Programme (financed by EC through Phare ) – Interim Evaluation – Economic and Social Cohesion and Human Resources Development field under the implementation of the Ministry of Labour and Ministry of Education focused on introducing and implementation of Active Labour Market Policy, Education, VET and LLL and Equal opportunities: Drafting evaluation methodology, evaluation of 20 projects (Education, VET, LLL, economic and social cohesion), reporting, recommendations and corrective measure. |

| Date: from (month/year) to (month/year) | 11/2005 - 10/2006 |
| --- | --- |
| Location | Slovakia, Bratislava |
| Company / Organisation | Ministry of Labour, Social Affairs and Family of the Slovak Republic |
| Position | Deputy Team Leader, Technical assistance |
| Job Description | Technical Assistance project “Preparation for the Utilization of the ESF at Local and Regional Level (project pipeline development)” responsible for: - Management and the setting up of 8 Regional Advisory Centres for the ESF on regional level - Development of the project pipeline database - Training, consultancy and couching of the 400 Final Beneficiaries - future applicants for the ESF - project identification and project development - Consultancy to the 800 project proposals development; Evaluation and quality control reports to 800 projects - Programming of the OP Employment and Social Inclusion (input to individual Priority axis - axis Employment support, Lifelong Learning, Active Labour Market Policy, in particular – the framework for the implementation of the National Projects – Support the employment scheme for handicapped people; Incentive Measures for School Leavers; Activation works for Inclusive Labour Market, - Providing PCM training, evaluation and quality control reports of submitted developed projects ; Development of the methodology to the project monitoring and evaluation ; Providing training and drafting teaching materials for the final beneficiaries and MA staff on national and local level - Responsible for the establishment and training of 8 Regional Advisory Centres for the ESF in Slovakia and Staff Training (16 persons) - Development of manuals for the monitoring and evaluation procedures for the staff of 8 Regional Advisory Centres for the ESF - Management of project pipeline database under the SF |

| Date: from (month/year) to (month/year) | 05/2005 |
| --- | --- |
| Location | Romania, Bucharest |
| Company / Organisation | Euro Mediterranean Networks – EUROMED sprl |
| Position | Expert |
| Job Description | Initial training in European Affairs for Civil Servants from the Central Public Administration” - EuropeAid/117453/D/SV/RO. The main objective was to train the member of central state administration offices of Romania with the intention to provide the overall framework of individual EU policies and the experience of newly acceded countries (new EU Member States from 2004). Training and contribution to the booklet covered presentations and discussion on the following topics: - relevant acquis in employment and social affaires; harmonisation process in Slovakia - pre-accession period of EU technical assistance and lessons learned; transposition of EU measures into chapter 2 Free movement of persons and chapter 13 Social policy and employment - implementation of the European Employment Policy in Slovakia; challenges of the EES to employment and social system reform in Slovakia - how the Operational programme Human resources development reflects the EES and employment guidelines; National Action Plan for Employment in Slovakia; Practical case of the preparation of administrative structures for ESF; Administrative capacities for the management and implementation of ESF; Lessons learned and conclusions for Romania on its way in successful implementation of acquis and ESF - Contribution to the Handbook on EU Affaires – 15 pages |

| Date: from (month/year) to (month/year) | 09/2004 - 06/2005 |
| --- | --- |
| Location | Slovakia, Bratislava |
| Company / Organisation | ECO, sprl. Brussels |
| Position | Technical Assistance Expert |
| Job Description | Technical assistance for the Human Resources Grant Scheme – Flexibility of the Labour Market : - Management of the Grant Scheme - Preparation of the grant scheme package including the Applicants guidelines and consequent training of grant beneficiaries and future applicants - Co-ordination of the Evaluation, Selection, Reporting (training the Evaluation Committee staff, Development of the Manual for Technical and Financial Evaluation of the project proposals, drafting the Evaluation Report) - Monitoring of 70 grants within the Grant Scheme (February/March 2006). First part of the reform of the civil service - Assisting to 8 Regional Employment Plans Development Structures to design the active labour market measures within the priorities of the Employment Plans (particularly for measures focused on undeclared work, school leavers, early school leavers, measures for handicapped people, mediation services and vocational guidance) |

| Date: from (month/year) to (month/year) | 04/2004 11/2005 |
| --- | --- |
| Location | Slovakia, Bratislava |
| Company / Organisation | Central Office of Labour (equivalent: Central Employment Service) |
| Position | Advisor to Director General for employment and ESF |
| Job Description | Management of Human Resources Development programmes: - Setting up the Grant management system for the implementation of the ESF interventions for Employment service (national projects and grants –Employment and active labour market measures, VET, LLL); - Implementation of Employment support measures, active labour market policy measures, Education, Adult Education and VET policy – designing, implementation, monitoring and evaluation of the following measures for: individual and professional guidance for the unemployed people; vocational guidance; employment schemes for school leavers; targeted training for people over 50; drafting teaching and training materials; inclusion market for the handicapped people; - Managing the national projects financed within the ESF: Increasing the qualification potential and availability of employees and persons entering the labour market; Increasing and improving Continuous Vocational Training to improve the adaptability of employees; Development of innovative strategies and instruments to integrate people over 50 to the labour market and dissemination of good practice examples within the partners); - Development of policy and strategy for new concept of employment services models influenced by the relevant employment guidelines, cross-border monitor, migration flows, job guidance, framework of common European labour market with the strong orientation to processes according to individual measures, development of evaluation methodology and selection criteria - Capacity building of the Public Employment Services staff for the implementation the ESF - , organising and delivery of training for PES staff (Call for Proposal, PCM, evaluation, financial management, monitoring, evaluation) |

| Date: from (month/year) to (month/year) | 04/2002 – 03/2004 |
| --- | --- |
| Location | Bratislava, Slovakia |
| Company / Organisation | National Training Institute |
| Position | Director of National Training Institute |
| Job Description | Director of the National Training Institute for the ESF - Management of training and capacity building of the National Training Institute for the ESF - Policy formulation and identification for training policies and reforms - Training needs analysis for state, public administration and private sector- Development of training packages for Civil Servants on the way to EU and training delivery- Co-ordination of delivery of the ESF training modules - Development of the National Training Plan for the ESF, Monitoring and evaluation of the implementation of the National Training Plan |

| Date: from (month/year) to (month/year) | 01/2000 03/2002 |
| --- | --- |
| Location | Slovakia, Bratislava |
| Company / Organisation | National Labour Office (equivalent: Central Employment Service) |
| Position | Director |
| Job Description | - Director of EU Policy and Programme Department - Management of 4 Grant Schemes for Human Resources Development (administration, tendering, evaluation, selection procedures, grant contracts, monitoring, evaluation, reporting) based on PRAG + Practical Guide to contract procedures for EC external actions: - Implementation, monitoring and evaluation of the Phare project: SR 0107.02 – Grant Scheme for HRD through preventive and individual measure for the unemployed – 4 MEUR – 98 grants; Implementation, monitoring and evaluation of the Phare project: SK 0009.03 – HR Grant Scheme through Counselling and Training on regional and Local Level – 3 MEUR – 52 grants; Implementation, monitoring and evaluation of the Phare project: SR 2003-004-995-03-11 – HR Grant Scheme for Social Inclusion – 3,5 MEUR – 38 grants; Drafting the measures for the implementation of the National Employment Plan; Training delivery of the PCM modules - Member of the Evaluation Committee within 2 of them; Lecturer for the European Social Fund matters and other Structural Funds; Administration, updating evaluation criteria, managing the evaluation process, evaluation report drafting, preparation of the contracts, financial consultancy, monitoring, evaluation, reporting; Co-operation within Public Employment Services in EU and associated countries in various types of projects targeted on training, education, retraining, self-employment and other employment and labour market policy issues; Management, co-ordination and supervision of PHARE, CONSENSUS “Strengthening the performance of Slovak Administrative Structure required for ‘Co-ordination of Social Security Schemes’” (TWL-SR 0110/01/01/0012) and other foreign aid projects implemented by the NLO, Regional and District Labour Offices ; Negotiating within negotiation groups to bilateral screenings on “Employment and Social Affairs”, “Free movement of workers” and “Regional Policy”; - Responsible for the project Logistics of the international conferences, congresses, seminars and workshops related to employment and social policy issues, trainings for grant beneficiaries |

| Date: from (month/year) to (month/year) | 01/1997 - 12/1999 |
| --- | --- |
| Location | Slovakia, Bratislava |
| Company / Organisation | The National Labour Office (equivalent: Central Employment Service) |
| Position | Director |
| Job Description | - Director of Intern. Relations & Co-operation Department. - Management, co-ordination and implementation of international relations in the field of employment and social policy; - In charge of preparation and negotiation of bilateral agreements on mutual employment and bilateral agreements on social security - Leading the inter-ministries groups for preparation and unifying the legal statements on social security agreement executions - Leading the inter-ministries groups for preparation and unifying the legal statements on bilateral agreements on mutual employment - Management the Twinning Project “Introduction of a Standard Classification of Occupations, preparation for participation in EURES” (SK99/IB/CO-01); “Preparation of Slovakia’s Participation in the co-ordination of the social security schemes” (SR99/CO/03) - Management, implementation and monitoring of the Phare projects: “Guidance into the world of occupations” (Development of system to support the information, consultancy and advisory services and guidance for different target groups of jobseekers on the labour market, including youth ) - Management the project: “Modular distance training of professional occupation counsellors for European mobility (development of training materials for modular occupational counsellors, delivery of training for counsellors of labour offices) - Project “Gateway to Guidance” (verifying the possibilities of using the instruments of career guidance to manage the HRD in companies; developing the career guidance instruments and mediation services for the inclusion of unregistered jobseekers to the labour market |

| Date: from (month/year) to (month/year) | 09/1995 - 12/1996 |
| --- | --- |
| Location | Slovakia, Bratislava |
| Company / Organisation | Employment Fund |
| Position | Deputy Head of Labour Market Policy Unit |
| Job Description | Deputy Head of Labour market policy unit - Management, co-ordination, implementation, monitoring and evaluation of employment policy programmes on national, regional and local level. - Extensive cooperation with social partners (Confederation of Trade Unions and Tripartite Council) in public management to support financially the delivery of training programmes for Association of employers and Trade Unions |

| Date: from (month/year) to (month/year) | 04/1990 - 08/1995 |
| --- | --- |
| Location | Slovakia |
| Company / Organisation | Ministry of Labour, Social Affairs and Family |
| Position | Head of International Relations |
| Job Description | - Head of International Relations Unit, Deputy Director of International Relations Division - Responsible for multilateral co-operation of employment policy -ILO, UN, OECD, Council of Europe, ISSA, TACIS Countries (Ukraine, Russia) - Responsible for bilateral co-operation in the field of employment and social policy - Management, co-ordination and implementation of international relations in the field of employment and social policy; - In charge of preparation and negotiation of bilateral agreements on mutual employment and bilateral agreements on social security - Leading the inter-ministries groups for preparation and unifying the legal statements on bilateral social security agreements executions - Responsible for coordination of social security schemes and transfer of benefits ( bilateral agreements) - Designing and management the bilateral agreements within the cross-border cooperation in the field of active labour market policy – South Czechoslovakia – Hungary; South Czechoslovakia – Austria; North Czechoslovakia – Poland - Capacity building of staff responsible for new Phare National Programme focused on Employment and social affairs (setting up the structures – including units for monitoring and evaluation - within all 79 Labour Offices,) - Human Resources Development and capacity building of the Labour Offices staff financed under the support of the British Know How Fund (setting up the structures of the Labour Offices, development the strategy of the Labour Offices, training of the Directors of the Labour Offices) - Management the project focused on Designing the concept of the active labour market measures through the British Know How Fund (including job mediation services, professional guidance for jobseekers, setting up the job clubs activities, sheltered workshops, special measures for young people ) - Managing the multilateral projects in the field of labour market and social affairs. |

# CURRICULUM VITAE

Proposed position in the project:  STE

- Family name: 			PAVLOV

- First names:	 			Ilian

- Date of birth: 			06 November 1981

- Nationality:				Slovak

- Civil status:	 			Single

- Education:

| Institution [ Date from – Date to ] | Degree(s) or Diploma(s) obtained: |
| --- | --- |
| Secondary Grammar school, Bratislava, Slovakia, 1996 - 2000 | Graduation with excellent results. |
| Technical University in Sofia, Bulgaria, February 2000 – August 2000 | Scholarship form Ministry of Education in Slovakia based on tender organized by Slovak Academic Information Agency. |
| University of Economics in Bratislava, Faculty of Business Informatics. Slovakia, September 2001 – May 2006. | University degree with specialisation in Applied Informatics - title Dipl. Ing. (Engineer). |
| Ministry of Construction and Regional Development, Slovakia. June 2006 – October 2006. | Official Certificate in the field of EU cohesion policy, project management, specific activities in project realisation, case studies. |
| University of Economics Bratislava, Faculty of Economic Informatics, Slovakia, September 2006 – 2009. | Postgraduate study. Diploma of successful completion of Dissertation exams in the field of Business Informatics. |

- Language skills:  Indicate competence on a scale of 1 to 5 (5 - excellent; 1 - basic)

| Language | Reading | Speaking | Writing |
| --- | --- | --- | --- |
| Slovak | 5 | 5 | 5 |
| Czech | 5 | 5 | 4 |
| English | 5 | 5 | 5 |
| Bulgarian | 4 | 5 | 3 |
| German | 2 | 2 | 2 |
| Serbian/Croatian/Macedonian | 2 | 2 | 1 |

- Membership of professional bodies:

  - Member of the Balkan Agency for Sustainable Development

- Other skills:

- Excellent skills in the field of information technologies and software engineering. Good knowledge of software development methodologies and methods (structured and object oriented), computer networks, software products and related issues.

- Good organizational and presentation skills.

- Present position:

- IT specialist of the RDA Senec-Pezinok, providing IT and software solutions for public sector;

- Country manager of Taxback Ltd. for Slovakia and Czech Republic – company is global leader in the field of EU and non EU taxations systems and online tax support.

- Years of professional experience:

- 11 years – with the RDA Senec-Pezinok; responsible for IT projects management and implementation ICT projects and solutions

- 6 years experience in Sunrise systems - ICT.

- 8,5 years – Taxback, Ltd. responsible for IT business development of the company on Slovak and Czech markets.

- 3 years - University of Economics, Faculty of Business Informatics as a lecturer of Database systems and Computer Networks.

- Key qualifications: (Relevant to the project)

- University degree in the field of information technologies and software engineering.

- Postgraduate studies specialized on IT science.

- Practical experience in management and implementation of IT project on national and European level.

- Experience in Twinning projects, TW project “Health and Safety at Work” Croatia (Concept of Datacenter and statistical software for EU reporting).

- Knowledge of modern software products, software engineering methodologies, database systems and computer networks.

- Knowledge of software development life cycles.

- Knowledge of standards, requirements and metrics for software quality.

- Participation in projects on European level responsible for development of IT products and infrastructure.

- Good knowledge of the countries in West Balkans, practical experience working on projects based in Croatia, Bulgaria, Macedonia, Czech Republic and Austria; hand-on experience with implementation of international projects and abilities to work in a multi-national team,

- Excellent management and analytical skills.

- Good communication and negotiation skills.

- Specific experience in the region:

| Country | Date from – Date to |
| --- | --- |
| Croatia | Jan 2011 – June 2012 Regional Development Agency Senec - Pezinok (RDA SP) Twinning project “Health and Safety at Work” number: HR/2007/IB/OT/01 Short term IT expert |
| MK | Oct 2011 – Oct 2013 Project Cocurt aimed at preparation of Macedonian partners for implementation and pilot verification of reform tools (EURES and ECVET) for decreasing of unemployment rate in cooperation with public sector and employers. Implementation of employment portal. |
| UK, DE, BG, SK, MT, SP, PT, DK | 2008 – 2009 : Eufacinet project. Responsible for establishment of European database of facilitators, online community of practice, portal and DMS. |
| SK, DK, DE, IT, LT, PT, UK, MT | 2008 – 2009: Resyfac project. Preparation and implementation of Online Reference System for European Facilitators of Learning and partner’s collaboration tools. |
| SK, MK | 2008 - 2009: Rellmas project. Implementation of online portal for regional and local labour market support. |
| SK, CZ, AT, DE, BG, RO | 2007 - 2008: Eucerticon project. Technical expert accountable for development and implementation of collaboration platform and document management system on EU level. |
| SK, IE, BG | 2007: Taxback Ltd. Managing establishment of distributed CRM system, document management systems, reporting and statistical systems. |
| SK | 2006 – 2009: Lecturing on University of Economics in Bratislava, Faculty of Business Informatics. Lessons aimed at Database Systems (Oracle DB), Computer Networks. |
| SK, AT | 2005-2006: Over-regional strategy for employment between Slovakia and Austria. Development of portal solution and online dissemination tools. |
| SK | 2003 – 2012: Preparing analysis and conceptual designs of information systems. Management and implementation of IT projects for private and public sector. |

- Professional experience record:

| Date: | August 2003 – on going |
| --- | --- |
| Location | Bratislava, Slovakia |
| Company | Regional Development Agency Senec - Pezinok |
| Position | IT expert |
| Description | IT consulting for national and international projects. Designing agency information systems and technical infrastructure, development and maintenance. |
| Date: | January 2004 – on going |
| Location | Bratislava, Slovakia |
| Company | Taxback Ltd., Slovakia |
| Position | Country Manager for Slovakia and Czech Republic |
| Description | Accountable for technical development of the company, implementing of new processes, information technologies, reporting and statistics systems. Coordination and management of company employees and business development. Improvement of IT solutions for increasing efficiency and accountability of the company and its international branches. |
| Date: | September 2006 - May 2007 |
| Location | Bratislava, Slovakia |
| Company | Lenovo (International) B.V., o.z. |
| Position | IT and E-support |
| Description | Responsibility for the web content management necessary for technical support of the Lenovo international clients. |
| Date: | November 2005 – July 2006 |
| Location | Bratislava, Slovakia |
| Company | AJS Management |
| Position | Regional expert |
| Description | Supporting the Regional Development agencies in order to manage the implementation of the Phare grant scheme (2003-004-995-03-08): - Monitoring the implementation of the projects (activities, financial aspects, tenders, persons, changes on the project). - Training and educating the final recipients of the grants. |

- Other relevant information:

15a. Publications and Conferences:

- IT science articles for conferences and publications in Slovakia (Mladá veda 2006, Mladá veda 2007, ERIN 2008 – Education, Research, Innovation)

- Technical article for conference in Romania (IMT Oradea 2007)

- Technical article for conference in Bulgaria (MFT 2007)

- Member of project research team for Modernization of e-learning on University of Economics.

- Tutor of number of diploma theses in the field of information technologies.

CURICULUM VITAE

Proposed position in the project:  STE

1.	Family name:				MAJERČÁK

2.	First name:				Ivan

3.	Date of birth:				December 29th 1978

4. 	Nationality:				Slovak

5.	Civil status:				Married, two children

6.	Education and training:

| Institution | Date: from (month/year) to (month/year) | Degree(s) or Diploma(s) obtained: |
| --- | --- | --- |
| Faculty of Management, Comenius University, Bratislava | 9/1996 – 6/2001 | Mgr., Management of Information Systems |
| International Baccalaureate | 9/1994 – 6/1996 | IB Diploma |
| Courses, conferences and workshops focused on IT technologies and architecture (few examples listed): - Microsoft Professional Developer's Conference 2005 (Los Angeles) - Microsoft SharePoint Conference 2007 (Berlin), 2008 (Seattle) - MSDN, Technet and community events in Slovakia, Austria and CzechRepublic - MOC trainings such as Analyzing Requirements and Defining Microsoft .NET Solution Architectures, Microsoft SQL Server 2008 Integration Services etc. | 1999 – 2012 |  |
| Certificate in Advanced English, University of Cambridge Local Examinations Syndicate | 1995 |  |

7.	Language skills: (Mark native, 5=excellent, 1=weak for competence)

| Language | Reading | Speaking | Writing |
| --- | --- | --- | --- |
| English | 5 | 5 | 5 |
| Bulgarian | 4 | 5 | 3 |
| German | 4 | 3 | 2 |
| Slovak, Czech | Mother tongue |  |  |

8.	Membership of professional bodies: -

9.	Other skills: (e.g. Computer literacy, etc.)

Platforms:

- Windows Server (NT, 2000, 2003, 2008, 2012), Windows XP, Vista

- Security, Administration, Active Directory, Clustering technologies, UI Development

Development:

- Visual Studio Team System (MSF for Agile, Scrum),

- C#, VB.NET, PowerShell,

- ASP.NET, AJAX, SharePoint Development

- WCF, WWF,

- T-SQL, MS SQL Reporting Services, MS SQL Integration Services,

- Oracle 11g

- XML, XSLT, XPath,

- HTML, CSS, WAP,

- General overview of J2EE, BEA/Oracle products,

- UML, Microsoft Visio, Enterprise Architects,

- Microsoft Office Development

- PKI related technologies

Networking and protocols:

- WS-* protocols and specifications,

- TCP/IP networking essentials

Server products:

- Microsoft BizTalk Server 2002-2010,

- Microsoft SharePoint Portal Server 2003/2010,

- Microsoft Internet Information Server,

- Microsoft SQL Server 2000-2012

- Virtualization (HyperV, VMWare)

- Dot Net Nuke, Joomla

Software Engineering Methodologies:

- Siemens stdSEM/SEM NG, Chestra

- MSF, TOGAF

Microsoft Certificates:MCP (ID # 1327168) for following products:

- 70-668 PRO: Microsoft SharePoint 2010, Administrator

- 70-562 TS: Microsoft .NET Framework 3.5, ASP.NET Application Development

- 70-630 TS: Microsoft Office SharePoint Server 2007, Configuring

- 70-631 TS: Windows SharePoint Services 3.0, Configuring

- 70-630: Microsoft Office SharePoint Server 2007 – Configuration

- 70-631: Configuring Windows SharePoint Services 3.0

- Microsoft Visual Interdev 6.0

- Microsoft Frontpage 98

- Microsoft IIS 4.0

- Networking Essentials

- Present position:

  - IT Expert and IT Senior Architect

11.  Years within the firm:

- 14 years direct experience in the IT field; 5,5 years with the RDA Senec-Pezinok

12.  Key qualification: (Relevant to the project)

Long-term outstanding experience and excellent knowledge of:

- Proven professional knowledge in the area of IT strategies development, software engineering, systems integrations, networking, database development and administration,

- Software projects management and implementations proved by wide range of national projects for the Slovak government and projects for international companies,

- Creating feasibility studies (for public sector customers),

- Support of tenders (proposal writing, budgeting, presentations, contracts),

- Cost and effort estimation for projects, resource planning,

- Study of legislation related to current and upcoming projects,

- Managing and supervising junior architects (Solution Design Authority),

- Exploring technological trends for IT-wide usage,

- Project management/technical lead,

- Technology presentations for internal employees and customers,

- Excellent communication and language skills and skills for team work in international environment,

- Knowledge of the region.

13.	Specific / international work experience:

| Country | Date: from (month/year) to (month/year); Description |
| --- | --- |
| Croatia | REGIONAL DEVELOPMENT AGENCY SENEC PEZINOK (RDA SP) “HEALTH AND SAFETY AT WORK” TWINNING NUMBER: HR/2007/IB/OT/01 – Concept of IT system in OHS SHORT-TERM IT EXPERT |
| Slovakia | Freelancing Solution Design Architect (Focuson .NET, MS SQL, DOT NET NUKE, MS SQL REPORTING SERVICES, VIRTUALIZATION, Oracle) SDA for numerous projects in government and academicsector (subcontractor for SIEMENS/ATOS and SCHOOL OF ECONOMICS AND MANAGEMENT IN PUBLIC ADMINISTRATION) |
| Ireland | IS for Horse Racing Ireland Name of Project: Race Management System Position: solution architect, technical PM, technology expert for Microsoft Office SharePoint 2007 |
| Ireland | Solution Architecture for Siemens Ireland Name of Project: SIRENE – architecture of one of the main subsystems in Schengen IS project (project at tender stage) Position: solution architect |
| Slovakia | Portal project for Ministry of Education Name of Project: Portal of Research and Development Potential (http://www.veda-technika.sk) Position: solution architect, PM, technology expert for Microsoft Office SharePoint 2007 Team under supervision: 7 developers |
| Slovakia | IS for Ministry of Justice Name of Project: eServices for Business Register Position: solution architect, technology expert for Microsoft BizTalk Server 2006 |
| Slovakia | IS for School of Economics and Management in Public Administration Name of Project: AIS - Academic Information System and Portal Position: solution architect, PM (private, non-profit activity) |
| Austria | Cooperation in Microsoft Support Center providing support for Siemens units internationally Development of system architecture, design and solutions for world-wide customers |

- Professional Experience Record:

| Date: | January 2004 – on going |
| --- | --- |
| Location | Bratislava office, Slovakia |
| Company | Regional Development Agency Senec - Pezinok |
| Position | IT expert |
| Description | Designing IT solutions for the public sector; improvement of the technical infrastructure |

| Date: | June 2001 – continue |
| --- | --- |
| Location | Bratislava, Slovakia |
| Company | Siemens Program and System Engineering |
| Position | IT Senior Architect |
| Description | Creating Enterprise Solution Architecture for public sector projects. |

| Date: | 1997-1999 |
| --- | --- |
| Location | Bratislava |
| Company | Gratex international, s.r.o. – IT division, WEB Development department |
| Position | IT – SW Developer |
| Description | Web development of e-zone and e-commerce solutions (e.g.: http://www.inzine.sk (1st Slovak e-zine), http://www.realshop.sk (largest Slovak Internet shopping mall)) |

| Date: | 1996-1997 |
| --- | --- |
| Location | Bratislava |
| Company | Trex, s.r.o. |
| Position | IT – SW Telecommunications officer |
| Description | Novell / Windows NT network administration, intranet development, support. Web designer and developer, network administrator, technical support |

15.  Others:

Organizational skills:

- Management – Master’s degree in management with focus on Management of Information Systems. Practical experience from team leading of department within Siemens PSE (up to 15 members).

- Good knowledge of economics, accounting and personal management methods.

- Practical experience from project leadership, especially for state and public administration institutions (Government Office of Slovak Republic, Ministry of Justice Slovak Republic, Ministry of Education) with budget up to 300.000 EUR.

International Conferences Contributions:

- Several conferences for Siemens employees and its customers

Others:

- Microsoft Certified Professional Certificate (ID # 1327168)

- Driving licence: class B

| Europass Curriculum Vitae |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Personal information |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| First name(s) / Surname(s) | Tea Sturua |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Address(es) | Javakhishvili str. 51, Tbilisi Georgia |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Telephone(s) | Mobile: 599 97 62 88 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E-mail | tsturua@ssa.gov.ge |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of birth | 28.10.1966 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Gender | female |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Proposed position in the project | Project Leader (counterpart) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Work experience |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 25.01.2013 - present | Head of Department Employment Programs Department The Ministry of labour, Health and Social Affairs of Georgia The Social Service Agency Department management, coordination of the territorial units |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2008 – 05.2014 2005 -2008 2004 – 2005 2003 – 2004 2004-present | International Investment Company CPG Project Manager Investment projects Management, preparation of new investment proposals Deputy Director State Programs management department Social Service Agency In 2005, employment promotion programs for unemployed people, coordinate and administer state programs for people with disabilities in 2006, professional training and retraining of the unemployed 2005-2006. administer and coordinate state programs for people with disabilities in 2007, 2007, State of temporary employment. Administration and coordination of programs, 2007 "good beginning", Conduct program administration. Social support program for families below the poverty line. Head of employment programs division Ministry of labour Health and Social affairs Developing State Employment support services and monitoring of these programs implementing structural units Monitor Administration of The World bank Agricultural Projects Project Management and Monitoring Founder, Project author, Project manager Georgian Culture Inside and outside of the country Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2000-2003 | Ltd “Faithful friend” Director Company Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1998 – 2000 1995 – 1998 1994-1995 | Manager Consultant Ltd “ivermedi” Doctor Anaesthesiologist No. 4 Hospital anaesthesiology Section Doctor –intern Clinical Hospital No. 1, Anaesthetic Department |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Education and training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1987 - 1994 | Anaesthesiologist Master’s Diploma Tbilisi State Medical Institute, Tbilisi (Georgia) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1996- 1998 | Ecologist-expert State Institute of Ecology, Tbilisi (Georgia |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2007 – 2008 | Social Policy and Social Work Iv. Javakhishvili. State University |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Personal skills and competences |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mother tongue(s) | Georgian |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Other language(s) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Understanding |  |  |  |  |  |  | Speaking |  |  |  |  | Writing |  |
|  |  | Listening |  |  |  | Reading |  |  | Spoken interaction |  | Spoken production |  |  |  |  |
| English |  |  | C1 |  |  |  | C1 |  |  | C1 |  |  | C1 |  | C1 |
| Russian |  |  | C2 |  |  |  | C2 |  |  | C2 |  |  | C2 |  | C2 |
|  | (*) Common European Framework of Reference for Languages |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Communication Skills | Good communication skills gained through experience in public and privet service |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Organisational skills and competences | Co-ordination and administration of people, planning, management, motivation, team –work, organization of meetings, seminars, negotiations, working groups, drafting, work in national administration, work with Eurostat, EC, projects, program negotiation and monitoring-acquired on the job, during studies and training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Job-related skills | Mentoring skills, good command of reporting, drafting, analysis, negotiations, presentation, work in multicultural environment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Computer skills and competences | Command of MS Word, MS Excel, MS Power Point, HTML, MS Access, MS Project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Europass Curriculum Vitae |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Personal information |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| First name(s) / Surname(s) |  | Maia Asatiani |  |  |  |  |  |  |  |  |  |  |  |  |
| Address(es) |  | Chubinashvili str.27, Tbilisi Georgia |  |  |  |  |  |  |  |  |  |  |  |  |
| Telephone(s) |  | 0322 91 12 72 |  |  |  |  | Mobile: |  |  |  | +995 77 57 44 09 |  |  |  |
| E-mail |  | masatiani@ssa.gov.ge |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of birth |  | 21.09.1984 |  |  |  |  |  |  |  |  |  |  |  |  |
| Gender |  | female |  |  |  |  |  |  |  |  |  |  |  |  |
| Proposed position in the project |  | RTA Counterpart |  |  |  |  |  |  |  |  |  |  |  |  |
| Work experience |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 25.01.2014 - present |  | IR Specialist The Ministry of labour, Health and Social Affairs of Georgia The Social Service Agency - Policy analysis, proposals, regulatory included, - Monitoring labour market trends, reporting, - Evaluation, co-operation with PES regarding labour market trends and monitoring of active - labour market policy measures. - Co-operation with public sector institutions, NGOs, research projects, including cooperation - in the World Bank research project, - Co-ordination of the EU related issues, preparation of national positions, meetings |  |  |  |  |  |  |  |  |  |  |  |  |
| 06.2012 – 06.2013 06.2009 -06.2011 06.2007 – 06.2009 09. 2006 – 06. 2007 2005-2006 |  | The School of Social Sciences, Assistant University of Georgia Administrative, translate, Academic Organisational Tasks Administrative assistant HeidelbergCement Caucasus Administrative, translate, Organisational Tasks Rector’s Office Manager University of Georgia Administrative, translate, Academic Organisational Tasks Liaison Officer Georgian Forecast Relation with WTO, receiving Information from WTO, analyse Teacher of English 29 Public School |  |  |  |  |  |  |  |  |  |  |  |  |
| Education and training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 02.2005 – 12.2008 |  | Politics and International Relations Master’s Diploma University of Georgia, Tbilisi (Georgia) |  |  |  |  |  |  |  |  |  |  |  |  |
| 09. 2002- 06.2006 |  | Humanitarian Faculty Translator Interpreter (English – Russian) Georgian Technical University, Tbilisi (Georgia |  |  |  |  |  |  |  |  |  |  |  |  |
| Personal skills and competences |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mother tongue(s) |  | Georgian |  |  |  |  |  |  |  |  |  |  |  |  |
| Other language(s) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Understanding |  |  |  |  | Speaking |  |  |  |  | Writing |  |
|  |  |  | Listening |  | Reading |  |  | Spoken interaction |  | Spoken production |  |  |  |  |
| English |  |  |  | C2 |  | C2 |  |  | C2 |  |  | C2 |  | C2 |
| Russian |  |  |  | C2 |  | C2 |  |  | C2 |  |  | C2 |  | C2 |
|  |  | (*) Common European Framework of Reference for Languages |  |  |  |  |  |  |  |  |  |  |  |  |
| Communication Skills |  | Good communication skills gained through experience in public and privet service |  |  |  |  |  |  |  |  |  |  |  |  |
| Organisational skills and competences |  | Co-ordination and administration of people, planning, management, motivation, team –work,organization of meetings, seminars, negotiations, working groups, drafting, work in nationaladministration, work with Eurostat, EC, projects, program negotiation and monitoring-acquired on the job, during studies and training |  |  |  |  |  |  |  |  |  |  |  |  |
| Job-related skills |  | Mentoring skills, good command of reporting, drafting, analysis, negotiations, presentation, work inmulticultural environment |  |  |  |  |  |  |  |  |  |  |  |  |
| Computer skills and competences |  | Command of MS Word, MS Excel, MS Power Point, HTML |  |  |  |  |  |  |  |  |  |  |  |  |

Annex 3

| Europass Curriculum Vitae |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Personal information |  |  |  |  |  |  |  |  |  |  |  |  |
| First name(s) / Surname(s) |  | Danica Lehocka |  |  |  |  |  |  |  |  |  |  |
| Address |  | J. Nalepku 32,821 01 Bratislava (Slovakia) |  |  |  |  |  |  |  |  |  |  |
| Mobile |  | +421 949 285 323 |  |  |  |  |  |  |  |  |  |  |
| E-mail(s) |  | danica.lehocka@employment.gov.sk |  |  |  |  |  |  |  |  |  |  |
| Nationality |  | Slovak |  |  |  |  |  |  |  |  |  |  |
| Date of birth |  | 21/07/1974 |  |  |  |  |  |  |  |  |  |  |
| Gender |  | Female |  |  |  |  |  |  |  |  |  |  |
| Desired employment / Occupational field |  | Research, Education |  |  |  |  |  |  |  |  |  |  |
| Work experience |  |  |  |  |  |  |  |  |  |  |  |  |
| Dates |  | 01/07/2010 → ongoing |  |  |  |  |  |  |  |  |  |  |
| Occupation or position held |  | State Counsellor for Employment, Director for Employment Section |  |  |  |  |  |  |  |  |  |  |
| Main activities and responsibilities |  | Management and coordination of the Employment Section dpt. including the Labour Law department dealing with industrial relation, labour conditions, collective bargaining, social dialogue Legislative works to prepare normative legal acts of a code character (Labour Code, health and safety at work, work inspection, state and public service; adopting and ratification of the international documents of labour law Approximation of the Labour Law, member of the working group for EMCO Negotiation within the ILO, EU related to employment related issues, representation of the Ministry to EU Summits Correper groups member dealing with the position of Slovakia to EU Council Reporting and preparing analyses for monitoring and evaluation mostly in the fields of employment policy and labour market Cooperation in development of the methodology for mid-term evaluation of the national labour market programmes co-financed through the European Social Fund Analytic work on: Preferences towards different educational groups on the Slovak labour market Vocational training provision in Slovak firms using CVTS 2005 micro data Analysis related to overeducation as an indicator of the supply-demand relations on the labour market |  |  |  |  |  |  |  |  |  |  |
| Name and address of employer |  | Ministry of Labour, Social Affairs and Family of the Slovak Republic Spitalska 4-6, 81643 Bratislava (Slovakia) |  |  |  |  |  |  |  |  |  |  |
| Type of business or sector |  | State administration |  |  |  |  |  |  |  |  |  |  |
| Dates |  | 01/1/2005 → 30/06/2010 |  |  |  |  |  |  |  |  |  |  |
| Occupation or position held |  | Director of the Employment Department |  |  |  |  |  |  |  |  |  |  |
| Main activities and responsibilities |  | In charge of individual and collective labour law regulation (Labour code, collective labour law, social dialogue, wage and remuneration regulation), Preparation and authorization of the official standpoints on various labour law issues, Representation of the Slovak Republic in the EU working groups (posting of workers, EWC, general directors in industrial relations) Analysis of activities in the fields of labour market, human capital and educational studies Cooperation in creating methodology to forecast Slovak labour market needs. In charge of the preparation of Employment Strategies, Operational Programmes for Human Resources Development and Social Inclusion Management of Labour Offices of the Slovak Republic |  |  |  |  |  |  |  |  |  |  |
| Name and address of employer |  | Central Office of Labour, Social Affairs and Family Spitalska 6, 81643 Bratislava (Slovakia) |  |  |  |  |  |  |  |  |  |  |
| Type of business or sector |  | Public administration |  |  |  |  |  |  |  |  |  |  |
| Dates Occupation or position held |  | 01/01/1998 - 30/12/2004 Head of Unit for Social Dialogue |  |  |  |  |  |  |  |  |  |  |
| Main activities and responsibilities |  | Management of the social dialogue development Analysis of the labour market and industrial relations, analytical research of the related issues Analysis of the changes of the labour market Delivery of training and social partners Communication with a public and media Applied economic and labour market research Skills demand – comparing methods and applications |  |  |  |  |  |  |  |  |  |  |
| Name and address of employer |  | Social Dialog Centre |  |  |  |  |  |  |  |  |  |  |
|  |  | Pekná cesta 6, 830 04 Bratislava (Slovakia) |  |  |  |  |  |  |  |  |  |  |
| Type of business or sector |  | Public administration |  |  |  |  |  |  |  |  |  |  |
| Education and training |  |  |  |  |  |  |  |  |  |  |  |  |
| Dates |  | 01/10/2007 - 21/09/2010 |  |  |  |  |  |  |  |  |  |  |
| Title of qualification awarded |  | PhD. (Third level of tertiary education) |  |  |  |  |  |  |  |  |  |  |
| Principal subjects / occupational skills covered |  | Economic theory/Forecasting, PhD. thesis: Changes in the supply of tertiary educated workers on the labour market, from the perspective of Slovak knowledge based economy. |  |  |  |  |  |  |  |  |  |  |
| Name and type of organisation providing education and training |  | Economic University in Bratislava (Faculty of National Economy) Dolnozemska cesta 1, 852 35 Bratislava (Slovakia) |  |  |  |  |  |  |  |  |  |  |
| Level in national or international classification |  | ISCED 6 |  |  |  |  |  |  |  |  |  |  |
| Dates |  | 01/09/1993 - 31/08/1997 |  |  |  |  |  |  |  |  |  |  |
| Title of qualification awarded |  | Mgr. (second level of tertiary education) |  |  |  |  |  |  |  |  |  |  |
| Principal subjects / occupational skills covered |  | Sociology Master thesis: Labour market requirements on employees in a knowledge society. |  |  |  |  |  |  |  |  |  |  |
| Name and type of organisation providing education and training |  | Comenius University in Bratislava (Philosophical Faculty) Gondova 2, 818 01 Bratislava (Slovakia) |  |  |  |  |  |  |  |  |  |  |
| Level in national or international classification |  | ISCED 5 |  |  |  |  |  |  |  |  |  |  |
| Personal skills and competences |  |  |  |  |  |  |  |  |  |  |  |  |
| Other language(s) |  |  |  |  |  |  |  |  |  |  |  |  |
| Self-assessment |  |  | Understanding |  |  |  | Speaking |  |  |  | W r i t i n g |  |
| European level (*) |  |  | Listening |  | Reading |  | Spoken interaction |  | Spoken production |  |  |  |
| English |  |  | C1 | Proficient user | C1 | Proficient user | C1 | Proficient user | C1 | Proficient user | C2 | Proficient user |
| German |  |  | B2 | Independent user | B2 | Independent user | A2 | Basic User | B1 | Independent user | B1 | Independent user |
| Czech |  |  | C2 | Proficient user | C2 | Proficient user | C2 | Proficient user | C2 | Proficient user | C2 | Proficient user |
|  |  | (*) Common European Framework of Reference (CEF) level |  |  |  |  |  |  |  |  |  |  |
| Social skills and competences |  | Good communication skills and adaptability to new environments, gained also through my work experience abroad. I am able to learn very quickly. |  |  |  |  |  |  |  |  |  |  |
| Technical skills and competences |  | I am quite skilled in work with IT and office equipment, such as IT networks components, computers, printers, and so on. |  |  |  |  |  |  |  |  |  |  |
| Computer skills and competences |  | Very good command of Microsoft Office tools (Word, Excel, PowerPoint, and Access) Statistical software: Advanced command of SPSS, Intermediate in STATA, beginner in R statistical software. Basics in SQL. Operational knowledge of HTML and basic web creating technologies. Experience in creating web questionnaires. Excellent level of internet usage. |  |  |  |  |  |  |  |  |  |  |
| Artistic skills and competences |  | I play acoustic guitar. |  |  |  |  |  |  |  |  |  |  |
| Driving licence(s) |  | B, B1, BE |  |  |  |  |  |  |  |  |  |  |
| Additional information |  | List of publications in English |  |  |  |  |  |  |  |  |  |  |

Other short term experts – back up (reserve)

CURRICULUM VITAE

Proposed role in the project:	STE

1.	Family name:	ZEMKO

2.	First name:	Róbert

3. 	Date and place of birth:	23/3/1968 Šurany, Slovakia

4.	Nationality:	Slovak

5.	Civil Status:	Married

Address (phone/fax/e-mail): 	robert.zemko@upsvr.gov.sk

6. 	Education:

| Institutions: | Slovak University of Technology In Bratislava, Faculty of Electrical Engineering - Radio electronics |
| --- | --- |
| Date: From (months/year)-To (months/year) | September 1987 - June 1993 |
| Degree: | Academic diploma in engineering |

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Hungarian | Mother Tongue |  |  |  |
| Slovak | 5 | 5 | 5 | 5 |
| German | 2 | 3 | 2 | 2 |
| English | 4 | 4 | 3 | 4 |

8.	Membership of Professional Bodies:

9.	Other skills (e.g. computer literacy, etc.): WINDOWS, Microsoft Office, Windows Server, Programing in: SQL, HTML, PHP, C++, Visual Basic, FoxPro, Databases in MySQL, Oracle

10.	Present Position: IT system methodologist

11.	Years of professional experience: 21 years

12.	Key qualifications:

- 21 years of working experience on labour market offices

- 2 years of experience in the Central Office of Labour, Social Affairs and Family – methodologist of IT systems

- Managing and communication skills (managing of 79 labour offices in different areas of employment and informatics)

- Experience in working in international teams, presentation and explanation skills

13.	Specific experience in the region or else:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| Hungary | 2007-2011 | EURES-T-DANUBIUS cross-border partnership to resolve the temporary and permanent employment problems |
| Czech Republic | 2005 - | Cooperation on matters relating to PES systems and services |

14.	Professional experience:

| Date: from (month/year) to (month/year) | October 2012 - ongoing |
| --- | --- |
| Location | Slovakia - Bratislava |
| Company / Organisation | Central Office of Labour, Social Affairs and Family |
| Position | Methodologist on Department of Information Systems Methodology |
| Job Description | - Analytical and evaluation activities - Specialised work in a field of civil state service - Elaboration and participation of program on documentation (reports, analyses, guidance) - Coordination of complex IT systems in field of statistics - Solving various problems in area of labour market and statistics - Communication with external suppliers - Participating on internal standards preparations - Managing and administration of IT core Systems in Central Office of Labour, Social Affairs and Family - Cooperation and project preparation on national and multinational level - Operative work when needed. - Lecturing and consulting - Moderation of discussion forum about IS questions. - evaluation of outcomes and preparation of background papers for decisions provided by national state institution - coordination of parts of complex systems in national state institution - testing new functionalities and providing feedback to suppliers - implementing new modules and functionalities to existing IT systems - organising training days over the country and lecturing actual themes |

| Date: from (month/year) to (month/year) | December 1993 – October 2012 |
| --- | --- |
| Location | Slovakia – Nové Zámky |
| Company / Organisation | Office of Labour, Social Affairs and Family |
| Position | data analyst and statistics |
| Job Description | - software and hardware solutions - data collection, analysing and processing - developed strategic papers in relation to IT system/s - security of data - systems compability |

15.	Others:

- Programming application programme equipments - the applications used on Labour, social affairs and family offices: program PCS (Professional consulting services) a IPS (Professional information-consulting services)

- Lecturing and teaching - informatics

15a.	Publications and Seminars:

15b.	References:

CURRICULUM VITAE

Proposed role in the project:	STE

1.	Family name:	GROSCH

2.	First name:	Peter

3. 	Date and place of birth:	28/1/1968 Nové Zámky, Slovakia

4.	Nationality:	Slovak

5.	Civil Status:	Married

6. 	Education:

| Institutions: | Technical University of Košice, Slovakia, |
| --- | --- |
| Date: From (months/year)- To (months/year) | September 1986 June 1991 |
| Degree: | Academic diploma in IT |

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Hungarian | Mother Tongue |  |  |  |
| Slovak | 5 | 5 | 5 | 5 |
| English | 4 | 5 | 4 | 3 |

8.	Membership of Professional Bodies:

9.	Other skills (e.g. computer literacy, etc.): WINDOWS, LINUX, Microsoft Office, Windows Server,

Programing skills: SQL, HTML, JavaScript, PHP, C++, Visual Basic, FoxPro, Databases in MySQL, Oracle

10.	Present Position: IT system methodologist

11.	Years of professional experience: 23 years

12.	Key qualifications:

- 23 years of working experience on labour market offices

- 15 years head of informatics department

- 3-year of experience directly with the Central Office of Labour, Social Affairs and Family – methodologist of IT systems

- 2 years of practice in the position of IT specialist in Social Insurance Agency in Nové Zámky

- Excellent knowledge in ICT with focus on needs of PES

- Ability to work in an international environment

13.	Specific experience in the region or else:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| Hungary | 2007-2011 | EURES-T-DANUBIUScross border partnership to resolve the temporary and permanent employment problems |
| Poland | 2006 - 2007 | EQUAL - Enhancing access to employment and the sustainable inclusion in the labour market |
| Netherland | January 2003 - April 2005 | Matra project – Development of client centred and self-service career guidance services in Labour Office |

14.	Professional experience:

| Date: from (month/year) to (month/year) | October 2011 - ongoing |
| --- | --- |
| Location | Slovakia - Bratislava |
| Company / Organisation | Central Office of Labour, Social Affairs and Family |
| Position | IT methodologist |
| Job Description | - Creation and participation on methodologies, documents, standards, manuals, FAQ, procedures - Introduction, Implementation and testing of the IT systems - Coordination and making guidelines for labour market offices in a field of new internal applications and application program interfaces. - Cooperation and collaboration in new projects on a national and international focus - partnership in field of programming with other state institutions |

| Date: from (month/year) to (month/year) | June 1991 – October 2011 |
| --- | --- |
| Location | Slovakia – Nové Zámky |
| Company / Organisation | Office of Labour, Social Affairs and Family |
| Position | Head of Informatics department |
| Job Description | - administration of system maintenance, Database system maintenance and maintenance of the database environment - administration of the internal labour office applications and their connected databases - installation and configuration of organisation servers and user working stations - Reinstalling and updating the core systems. - Operative diagnosing and fixing running systems - providing all systems including user working stations be functional - managing compatibility in IT infrastructure between various devices and parts of infrastructure - Creating a periodic situation reports and labour market analysis. Creating short term and long term labour market predictions and statistic exports - coordination of department activities |

15.	Others

- Programming the applications used on Labour, social affairs and family offices: program PCS (Professional consulting services) a IPS (Professional information-consulting services)

Regular organization of multinational conferences on migration, cross-border cooperation, chairing these conferences;

- Lectoring and teaching - informatics

OPIS (Operational programme Information society) –Code list systems in RSD DSD IT systems – starting in 2012 - ongoing

CURRICULUM VITAE

Proposed role in the project:		STE

1.	Family name: 		Beran

2.	First name: 		Jiří

3. 	Date and place of birth: 		10.1.1969, Strakonice

4.	Nationality: 		Czech

5.	Civil Status: 		Married

Address (phone/fax/e-mail): Průběžná 44,České Budějovice 370 04, Czech Republic

jiri.beran@cb.mpsv.cz

6. 	Education:

| Institutions: | Faculty of Health and Social Studies of South Bohemian University |
| --- | --- |
| Date: From (months/year) To (months/year) | 9.1990 6.1994 |
| Degree: | Mgr. |

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Czech | Mother Tongue |  |  |  |
| English | 4 | 5 | 4 | 4 |
| German | 3 | 4 | 3 | 3 |

8.	Membership of Professional Bodies:

9.	Other skills (e.g. computer literacy, etc.): driving license group B, PC skills, Microsoft Office (exam ECDL), lecturing and presentation skills

10.	Present Position: Head of Section of labour market, analyst of labour market

11.	Years of professional experience: 20 years

12.	Key qualifications: reliability, experience

- excellent knowledge in statistics, data analysis and  data processing in the labour market

- proven record as analyst of the labour market

- Evaluation skills of projects and project outcomes

- Knowledge of instruments of active labour market measures

- Wide experience at local and central level in relation to employment policy

- International experience and project management skills

13.	Specific experience in the region or else:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| Slovakia, Brussels, Hungary, Austria | Since 2000 | Project in Equal, for CBC on labour market, conferences, seminars, working meetings |

14.	Professional experience:

| Date: from (month/year) to (month/year) | 1.4.2011 – up to now |
| --- | --- |
| Location | Czech Republic, České Budějovice |
| Company / Organisation | Labour Office of Czech Republic |
| Position | Head of section of labour market, analyst of labour market |
| Job Description | Processing of monthly statistics on the labour market situation, the processing of ad hoc statistical data. Management of the labour market section. |

| Date: from (month/year) to (month/year) | 1.1.2007 – 31.3.2011 |
| --- | --- |
| Location | Czech Republic, České Budějovice |
| Company / Organisation | Labour Office in České Budějovice |
| Position | Head of section of labour market, analyst of labour market |
| Job Description | Processing of monthly statistics on the labour market situation, semi-annual and annual analyzes of the situation and developments in the labour market, processing ad hoc statistical data. Management of the labour market section. |

| Date: from (month/year) to (month/year) | 1.8.2000 – 31.12.2006 |
| --- | --- |
| Location | Czech Republic, České Budějovice |
| Company / Organisation | Ministry of Labour and Social Affairs |
| Position | Regional worker, project manager |
| Job Description | Participation in the preparation and drafting program documents in the Czech Republic implementation of monitoring projects implemented under the pre-accession programs Phare and Equal, formal and substantive evaluation of submitted projects. |

| Date: from (month/year) to (month/year) | 1.6.1996 – 31.7.2000 |
| --- | --- |
| Location | Czech Republic, České Budějovice |
| Company / Organisation | Labour Office in České Budějovice |
| Position | Officer for Active Politic of Employment |
| Job Description | Instruments of Active policy of employment - community service, ensuring agenda of work permits to foreign countries (mainly in Germany and Switzerland), participation in the testing of the new software system for labour office, working group members for testing new software. |

| Date: from (month/year) to (month/year) | 15.9.1994 – 31.5.1996 |
| --- | --- |
| Location | Czech Republic, České Budějovice |
| Company / Organisation | Faculty of Health and Social Studies of SBU |
| Position | Assistant |
| Job Description | Ensuring the Centre's activities to help children, adults and the elderly, the clinical work of the faculty, teaching a selected subjects, organization and delivery of care services for seniors in cooperation with other involved bodies in České Budějovice. |

15.	References: upon request

CURRICULUM VITAE

Proposed role in the project:	STE

1.	Family name: 	KALMAR

2.	First name: 	Andras

3. 	Date and place of birth: 	23/07/1977, Ajka

4.	Nationality: 	Hungarian

5.	Civil Status: 	married

6. 	Education:

| Institutions: | Corvinus University of Budapest, Hungary Fővám tér 8. |
| --- | --- |
| Date: From (months/year)-To (months/year) | September 2009 May 2011 |
| Degree: | Post-graduate human management expert |

| Institutions: | Corvinus University of Budapest, Hungary Fővám tér 8. |
| --- | --- |
| Date: From (months/year)-To (months/year) | September 1996 June 2001 |
| Degree: | Academic diploma – social sciences |

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Hungarian | Mother Tongue |  |  |  |
| English | 5 | 5 | 5 | 5 |

8.	Membership of Professional Bodies:

9.	Other skills: MS Win 8, ECDL 7 modules, brochure design editing video materials and pictures

10.	Present Position: Resident Twinning Advisor

11.	Years of professional experience: 11 years

12. Key qualifications:

- 11 years of professional experience in strategic management,  development and co-ordination of county and regional labour centres as regards the development of services

- 5 years of experience of co-ordinating, integrating and standardising services and labour market measures for 174 local offices

- 11 years of professional experience in managing activities with relevant stakeholders connected to labour market services on local and regional level

- 8 years of professional experience in management of national European funding mechanisms on local and national level

- 8 Managing of EU Progress programmes on regional and national level (planning, reporting, managing, monitoring) and supervision of its implementation on the subordinated level

- 11 years of professional experience in knowledge management and training activities as regards the development of PES services

- 8 years of experience in developing strategies and rules of procedures of services on local, regional and national level

- 11 years of confirmed management and specialisation on communication and promotion activities as regards employment services

- Strong leadership and management skills ( coordination and management of 19 county labour offices and 174 local offices as regards to European Employment Services)

- 11 Managing pre-accession bilateral and post-accession international and cross-border co-operations

- International experience in developing service portfolio as regards services to employers

- Proven twinning record as RTA in Macedonia (FYROM)

- Excellent skills in working with multinational teams, experience as trainer in Training of Trainers

13.	Specific experience in the region or else:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| Slovakia | 04/2007 – 02/2014 | Cross border cooperation - EURES-T co-operation with Slovakia, mobility services |
| Austria | 01/2009 – 02/2014 | Cross border cooperation - EURES-T co-operation with Austria, mobility services |
| Romania | 03/2010 – 02/2014 | Cross border cooperation - EURES-T co-operation with Romania, mobility services |
| Turkey | 10/2010 | INT MARKT 42098 (EURES as a tool to promote free movement of workers in Europe) |
| Turkey | 02/2011 | INT MARKT42887 (Workshop on Flexibility of Labour Markets) |
| Serbia | 10/2013 | INT MARKT 53119 (Workshop on Preparations necessary to Join the EURES Network) |
| FYROM-Macedonia | 02/2014 – ongoing | MK10/IB/SO/01 (Strengthening the capacities for effective implementation of the acquis in the field of freedom of movement of workers) |

14.	Professional experience:

| Date: from (month/year) to (month/year) | 2014 till 4/2015 |
| --- | --- |
| Location | Macedonia (FYROM), Skopje |
| Company / Organisation | Employment Service Agency |
| Position | Resident Twinning Advisor |
| - Job Description | - Implementation of the twinning project: “Strengthening the capacities for effective implementation of the acquis in the field of freedom of movement of workers, MK10/IB/SO/01” - assessment of the legal framework in the field of free movement - trainings organized for colleagues in the public administration working connected to labour mobility - organizing awareness rising events for the target groups |

| Date: from (month/year) to (month/year) | 03/2012 – 02/2014 |
| --- | --- |
| Location | Hungary, Budapest |
| Company / Organisation | National Employment Service |
| Position | Manager of EURES department, Assistant to HoPES |
| Job Description | - assisting the Head of the National Employment Service at European and international affairs in line with the EU 2020 employment strategy - keeping touch with EU/EEA member states regarding employment policy - coordinating the work of 30 national EURES advisors and 174 assistants - organising the service delivery to employers and jobseekers in connection to labour mobility (international recruitments, job fairs and public fora) - developing connections with pre-accession countries and participate in bilateral projects |

| Date: from (month/year) to (month/year) | 05/2011 – 02/2012 |
| --- | --- |
| Location | Sweden, Stockholm |
| Company / Organisation | Arbetsförmedlingen, (AMO Solna) |
| Position | EURES advisor |
| Job Description | - managing EURES activities in 7 local offices of the job centre - developing the service portfolio for employers in the region to help them find competences they need from other Member States - Organisation of recruitment projects across the EU Member States |

| Date: from (month/year) to (month/year) | 01/2008 - 05/2011 |
| --- | --- |
| Location | Hungary, Budapest |
| Company / Organisation | National Labour Office |
| Position | EURES manager |
| Job Description | - managing and developing the EURES network in Hungary - developing the service portfolio regarding migration for employers and jobseekers - cooperation with EURESco and the member states as well as partner organisations - integration of EURES into the Public Employment Service |

| Date: from (month/year) to (month/year) | 07/2003 - 12/2007 |
| --- | --- |
| Location | Hungary, Budapest |
| Company / Organisation | Central Trans-Danubian Labour Centre |
| Position | EURES advisor |
| Job Description | - providing services to employees and employers in the field of free movement of workers - managing the work of 24 EURES assistants in the region, event organisation, recruitments - management of bilateral agreements |

15. Others:

Organisation of large scale international recruitments and events of public interest (e.g. International Job Fairs, Road Shows etc.), up to visitors of 8000 jobseekers

Participation in the EC's projects (Your First Job Abroad, What Social Europe can Do for You) as national coordinator and in specialized working groups aiming development of services

Development of various employment service portals (www.eures.hu, www.eures-t-danubius.eu, www.eures-pannonia.hu, www.twinningsweden.eu (password: Skopje)

# CURRICULUM VITAE

Proposed position in the programme: STE

| 1. Family name: | NADAZDYOVA |
| --- | --- |
| 2. First names: | Maria |
| 3. Date of birth: | 16/06/1955 |
| 4. Nationality: | Slovak |
| 5. Civil status: | Single |

##### 6. Education:

| Comenius University, Faculty of Philosophy, Bratislava | 1973 1978 | Diploma (1978); Specialisation : Pedagogical Psychology, English Language |
| --- | --- | --- |
| Comenius University, Faculty of Philosophy, Bratislava | 1980 | Degree in Pedagogical Psychology (PhDr) |
| Institute for Further Training of Teachers, Bratislava | 1988 | Certificate, Postgraduate further training “Communication in teaching process” |

##### 7. Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | reading | speaking | writing |
| --- | --- | --- | --- |
| Slovak | Mother-tongue |  |  |
| English | 5 | 5 | 5 |
| French | 2 | 2 | 2 |
| Czech | 5 | 5 | 5 |
| Russian | 2 | 3 | 1 |

8. Membership of non-professional bodies:

- Other skills:   (e.g. Computer literacy, etc.), Computer literate (ECDL)

##### Present position: State Counsellor

##### Previous position

Foreign Aid Coordination Department, Director/Senior Program Officer, Ministry of Labour, Social Affairs and Family of the Slovak Republic: responsible for coordination of pre-accession, Transitional Facility and bilateral aid projects and developing participation in the European and multilateral  projects (including Twinning and TA projects in Candidate Countries and those covered by different financial instruments of the EU)

##### Years of experience: 21

##### 12. Key qualifications and experience

- EU policies and standards – EU decision making process, social policy, employment, non-discrimination, labour law;

- Excellent knowledge of EU law on anti-discrimination and equal treatment – directives 2000/43, 2000/78, 2006/54, its transposition and enforcement in practice

- Twinning experience -  work experience and activity on legal transposition of above-mentioned directives and capacity building of the Depart. Of Equal Opportunities of the Macedonian Ministry of Labour and Social Policy; proven record in training on anti-discrimination in FYROM & Serbia

- local social and economic development – needs identification, public policies evaluation;

- interview conducting, team leading, awareness raising campaigns, development of inquiry tools and methods for different target groups;

- training needs analysis, lecturing and training provision on social policy issues, EU affairs and human resources development;

- good knowledge of civil and public service based on long-term expert and management practice;

- communication skills and work experience in multicultural and multilingual environment (EU, OECD, ILO, COE);

- social services – systems and reforms, people with disabilities; social inclusion processes – elimination of poverty and social exclusion;

- international relations, development and cooperation programs, EU financial instruments and programmes, European construction; institutional and capacity building, project development and management;

- Specific international experience:

| Country | Date | Domain |
| --- | --- | --- |
| Norway | 1992 | Participation in bilateral project aimed at exchange of know-how on social services reforms for people with disabilities, deinstitutionalisation of services and development of community based services, awareness raising activities of different actors to help promote and achieve the goal. |
| United Kingdom | 1994 | Study of new trends and development of innovative social services for people with complex special needs/disabilities, identification of key players necessary for successful implementation of change strategy in social services domain, communication and awareness raising strategies. |
|  | 1998 | Design of and participation in Phare project on Social work education – background study for introduction of new curricula and quality standards in social work education and practice in Slovakia. |
| USA | 1996 | Study visit/tour on new trends and strategies in integration of socially excluded and marginalised groups – low qualified, people with disabilities into mainstream policies and their participation in open labour market; social services reform, community planning; social security reform – federal and state level involvement, institutional coverage, law drafting; participation in numerous governmental and non-governmental training programmes on change management in community-based services and person centred planning. |
| Netherlands | 1997 | Participation in Phare Project and related training on social security and social services reform and Project on employment of people with disabilities |
|  | 1998 | Study of best practices in training of civil servants (focus on social work training and social work provision) as a background study for introduction of new curricula and quality standards in civil servants training and social work education and practice in Slovakia |
| Germany | 1999 | Design of and participation in Phare Project and training in development of new education and training programmes for the whole social and employment sphere in the Slovak Republic (civil and public servants), cross country comparative study on training programmes of civil and public servants in social and employment sphere (selected EU Member States) |
| European Union | 2001-2006 | Permanent representation of the national administration in the EU working structures (European Union, Council of the EU) in the following areas: social policy, employment, labour law, non-discrimination and equal opportunities, social inclusion and disability, public health, free movement of labour, recognition of professional qualifications, Lisbon Strategy |
| Macedonia | 2007 - 2009 | Twinning project on Review of the National Labour Legislation in Macedonia (responsible for non-discrimination legislation, training needs and training component, delivery of training for participating civil servants and social partners) |
| Serbia | 2009 | Slovak Aid Project National Convention on the EU in Serbia - participation in the Social dialogue WG delivering Labour Market experiences of the Slovak Republic |
| Kosovo | 2008 | Project FRIDOM - DFID/Department for International Development UK (Reference No. CNTR 06 7624), implementation phase and desk research for comparative analyses on Functional Review and Governmental Institutional Design for Kosovo (comparative analyses - Slovak Republic complement) |
| Macedonia | 2010 onwards | Slovak Aid Project Improvement of Business Environment and Labour Market in Macedonia by Successful Know-how Transfer from Slovakia |
| Macedonia | under development | Twinning project on Support to the National employment Policy (training needs analysis, development of training courses and delivery of trainings) |
| Albania | 2010 onwards | EBRD funded Consultancy project: Albania – Utilities Public Procurement Reform Project (complete project development and management, including capacity building /training component) |

##### Professional experience:

| Date | 2011 - ongoing |
| --- | --- |
| Location | Bratislava |
| Company | Ministry of Labour, Social Affairs and Family of the Slovak Republic |
| Function | State Counsellor |
| Description | Preparation of Slovak Presidency in EU, employment policy coordination, work on anti-discrimination and equal opportunities issues within the scope of the Ministry, drafting strategic papers for the Slovak Govt on anti-discriminatory matters, support to legal dept on law amendments, on-service training of new colleagues on above |

| Date | March 2008 - 2010 |
| --- | --- |
| Location | Bratislava |
| Company | Regional Development Agency Senec - Pezinok |
| Function | Senior Programme Manager on Employment Policy |
| Description | Design, development, and implementation of strategic programmes – active employment measures, monitoring and implementation of programme initiatives and projects in social policy and employment including globalised labour market, non-discrimination, social lifelong learning, adult training, promotion of human capital, transfer of best practices to countries in transition and horizontal EU issues. . |

| Date | August 2006/October 2007 |
| --- | --- |
| Location | Bratislava |
| Company | Ministry of Labour, Social Affairs and Family of the Slovak Republic – PHARE and Transition Facility/Foreign Aid Coordination Department |
| Function | Director |
| Description | Coordination, development and management of the European and international/bilateral projects related to employment, labour law, health and safety at work, civil service, social inclusion and poverty reduction, gender equality, free movement of labour and European Social Fund issues |

| Date | February 2006/August 2006 |
| --- | --- |
| Location | Bratislava |
| Company | Ministry of Labour, Social Affairs and Family of the Slovak Republic – European Affairs and International Relations Division |
| Function | Director General |
| Description | Development and coordination of the EU and international affairs, relations with international bodies and agencies, bilateral and multilateral cooperation in employment, social policy, non-discrimination and free movement of labour field, representing the Ministry at various high level events and meetings, drafting and defending national positions and policies in the above mentioned area of the Ministry’s activity in relation to the European Union, the Council of Europe, OECD, ILO, WTO, UN, reporting on transposition and implementation of legally binding and non-binding international standards into national legislation and practice. |

| Date | August 2001/January 2006 |
| --- | --- |
| Location | Brussels |
| Company | Permanent Mission/Permanent Representation of the Slovak Republic to the EU - Ministry of Foreign Affairs of the Slovak Republic |
| Function | Diplomatic post - Counsellor |
| Description | Representing the Slovak national administration to the EU institutions in the following areas of activity: social policy, employment, working conditions, health and safety at work, non-discrimination, equal opportunities, public health (2001-2004), free movement of labour, ESF, recognition of professional qualifications (2001-2003), Lisbon Strategy; drafting and defending national positions regarding the EU policy and Community law proposals and amending them. |

| Date | April 2000/July 2001 |
| --- | --- |
| Location | Bratislava |
| Company | Ministry of Labour, Social Affairs and Family of the Slovak Republic – Social Assistance Division |
| Function | Director General |
| Description | Development and implementation of national policies and legislation in the area of social policy – covering e.g. social inclusion, elimination of poverty and social exclusion, promotion of labour market and employment opportunities for vulnerable groups (e.g. people with disabilities, long-term unemployed, low qualified, ethnic groups, 50+), social benefits for people in material needs, social services, integration of people with disabilities, social care for elderly. Active participation in drafting of pre accession strategic and policy documents, screening of the national legislation and acquis communaitaire transposition, pre-accession national administration team member - head of Social Policy and Employment Chapter, member of Free Movement of Persons Chapter. |

| Date | August 1998/March 2000 |
| --- | --- |
| Location | Bratislava |
| Company | Ministry of Labour, Social Affairs and Family of the Slovak Republic - Human Resources and Personnel Policy Division |
| Function | Expert – development policy officer in charge of Human Resources Development |
| Description | Development of strategies and policy documents on new training programmes for civil and public servants in social policy and employment domain and conducting short-term and medium term training needs analyses in the sector; trainer of trainers programmes; Active participation in drafting of pre accession strategic and policy documents, screening of the national legislation and acquis communaitaire transposition, pre-accession national administration team member - head of Social Policy and Employment Chapter, member of Free Movement of Persons Chapter. |

| Date | August 1996/July 1998 |
| --- | --- |
| Location | Bratislava |
| Company | Ministry of Labour, Social Affairs and Family of the Slovak Republic – Social Affairs Division, Change Strategy Department (reform of social services in practice) |
| Function | Director |
| Description | Development, promotion and implementation of change management measures and procedures in the sector of social services – development and promotion of regional and local development plans, identification of key players and building of regional and local coalitions capable of bringing sustainable change to social services structures and institutions; conducting training needs analyses, developing and delivering training programmes for both public and NGO sector at national level. |

| Date | May 1994/July 1996 – April 1992/April 1993 |
| --- | --- |
| Location | Bratislava |
| Company | Social Services Care Centre |
| Function | Policy Development Officer – Director |
| Description | Development and promotion of new policies for vulnerable and marginalised groups - community based services, deinstitutionalisation, human rights based disability policy, regional and local team building, leading national development team in social services sector for people with disabilities and elderly; training needs analysis, development and delivery of tailor-made training programmes for different target groups of key actors. |

| Date | March 1993/April 1994 |
| --- | --- |
| Location | Bratislava |
| Company | Care Services Home for elderly and Residential Care Services Home for young people with physical disabilities |
| Function | Deputy Director, Special Teacher and Social Worker |
| Description | Social work and care provision |

| Date | September 1985/March 1992 |
| --- | --- |
| Location | Bratislava |
| Company | Vocational secondary school |
| Function | Deputy Director/Deputy Head Teacher |
| Description | Management of residential school home, vocation counselling, students personal development and achievement counsellor, adult training, English teacher |

| Date | September 1978/August 1985 |
| --- | --- |
| Location | Bratislava |
| Company | Psycho-diagnostics |
| Function | Head of Department |
| Description | Research, development, construction, testing, marketing and production of standard achievement tools/tests – psycho diagnostic and didactic tests applicable in different education and training situations including adult training for socially and ethnically disadvantage groups; training needs analysis, national surveys of educational achievements, comparative analysis, educational/training goals and policy assessment. |

Publications (selected):

- Current trends of women employment in the Slovak  republic, RILSAF, Bratislava 1997

- Roma  minority position on the labour market, RILSAF, Bratislava 1998

- Education, training and employment in Slovakia (country study, in collaboration), International Labour Office, Budapest 1999

- Training against social exclusion, Education and Training Foundation ( in collaboration), European Training Foundation, Turin 2000

14. References: obtainable from the following

Mrs. Maria Janusova – Head of Employment Strategy Branch of Labour Department of Ministry of Labour, Social Affairs and Family of the Slovak republic

Mrs. Daniela Kalužná – Advisor of the Permanent Mission of the Slovak Republic in OECD

Ms Luba Pavlovova, RDA Director, Bratislava

Mrs. Martina Lubyova – Officer of International Labour Office, Subregional Office for Eastern Europe and Central Asia.

Mrs. Zuzana Harmathova – Official of DG Employment and Social Affairs of EC

CURRICULUM VITAE

Proposed position in the project: STE

1.	Family name: 	Schaumannová

2.	First name:	Helena

3. 	Date and place of birth: 	16th December 1969, Ostrava

4.	Nationality: 	Czech

5.	Civil Status: 	married

Address (phone/fax/e-mail):

Volgogradská 71, Ostrava – Zábřeh, 700 30, Helena.schaumannova@ot.mpsv.cz, 950143252

h.schaumannova@seznam.cz, +420603216771

6. 	Education:

| Institutions: | Masaryk University Brno, Faculty of Social studies, Czechoslovakia |
| --- | --- |
| Date: From (months/year)-To (months/year) | 09/2001 – 01/2005 |
| Degree: | University degree (academic diploma) - Master |
| Institutions: | Silesian University Opava, Faculty of Philosophy and Science, Czechoslovakia |
| Date: From (months/year)-To (months/year) | 09/1997 – 06/2000 |
| Degree: | University degree (academic diploma) - Bachelor |

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Czech | Mother Tongue |  |  |  |
| English | 4 | 5 | 4 | 4 |
| Russian | 3 | 3 | 3 | 2 |

8.	Membership of Professional Bodies:

9.	Other skills (e.g. computer literacy, etc.):

Microsoft Office package (Word, Excel, Power Point), internet, Moodle, Benefit, Monit

10.	Present Position: Senior manager of the EU projects department – Labour office of ČR – Regional unit in Ostrava (management and implementation of ESF projects – Human Resources and Employment Operational Programme - OPLZZ)

11.	Years of professional experience: 18 years of professional experience in public and private administration in the Employment Policy, Education, Human resources and Research; 8 years of professional experience in evaluation, creation and implementation EU projects aiming at HRD

12.	Key qualifications:

- 12 years of professional experience in Employment Strategies, Labour Market policies and controlling of public resources  - cooperation with employers, provision and execution of  control mechanism for start-ups;  partnership networking of the NGO and private sector the local level

- 8 years of professional experience in evaluation of EU projects (cooperation with Public Employment and Education Services) – e.g. Human Resource Development Operational Programme (2004 – 2006);  Human Resources and Employment Operational Programme (2007 – 2013); Industry and Innovation Operational programme (2009 – 2012); Education for Competitiveness Operational Programme (2008 – 2012); Cross-board cooperative Operational Programme Czech Republic – Poland (2006 – 2013

- 7 years of creation and management of  EU projects (cooperation with Public Services, Non-profit organizations, Research institutes and Universities): Human Resources and Employment Operational Programme (2008 – 2013); Education for Competitiveness Operational Programme (2008 – 2012); Cross-border cooperation Operational Programme Slovak – Czech Republic (2008 – 2012)

13.	Specific experience in the region or else:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| Slovakia | 09/2008 – 05/2011 | Project “Diagnostic of knowledge and skills of the students in the Czech-Slovak border region focusing on development of the students” |

14.	Professional experience:

| Date: from (month/year) to (month/year) | 06/2013 - ongoing |
| --- | --- |
| Location | Ostrava |
| Company / Organisation | Labour Office of the Czech Republic – Regional Unit in Ostrava |
| Position | Manager of EU projects’ department |
| Job Description | - Management of projects - Human Resources and Employment Operational Programme (employment regional projects) - Management of projects teams - Setting up the grant management of the ESF co-financed projects ( grants scheme, procedures, guidelines, call for proposals, rues for monitoring and evaluation) - Coordination and creation of regional employment projects - Cooperation with other public services - Management of public procurement |

| Date: from (month/year) to (month/year) | 03/2008 - 2012 |
| --- | --- |
| Location | Ostrava |
| Company / Organisation | University of Ostrava Methodology and Evaluation center (NNO) |
| Position | Project manager |
| Job Description | - Management of EU projects (education, research, employment, cross-boarder cooperation projects) - Management of projects team - Coordination and creation EU projects - Cooperation with non-profit organisation and research institutes - Marketing of projects - Controlling of project outputs - Management of public procurement |
| Date: from (month/year) to (month/year) | 04/1995 – 2007 |
| Location | Ostrava |
| Company / Organisation | Labour office in Ostrava |
| Position | Controller |
| Job Description | - Controlling of labour law in employers companies; - Financial controlling of the resources for ALPM - employers |

CURRICULUM VITAE

Proposed position in the project: STE

1.	Family name: 	Balaban

2.	First name: 	Gabor

3. 	Date and place of birth: 	07/08/1975, Miskolc

4.	Nationality: 	Hungarian

5.	Civil Status: 	single

6. 	Education:

| Institutions: | University of Miskolc, Faculty of Economics (Miskolc) |
| --- | --- |
| Date: From (months/year) To (months/year) | September/2010 ongoing |
| Degree: | BA in Management Sciences |

| Institutions: | University of Miskolc, Faculty of Arts (Miskolc) |
| --- | --- |
| Date: From (months/year) To (months/year) | September/1996 May/ 1998 |
| Degree: | Secondary school teacher in social sciences (MA level) |

| Institutions: | University of Miskolc, Faculty of Arts (Miskolc) |
| --- | --- |
| Date: From (months/year) To (months/year) | September/1994 May/ 1998 |
| Degree: | Sociologist (MA level) |

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Hungarian | Mother Tongue |  |  |  |
| German | 3 | 3 | 3 | 2 |
| French | 2 | 2 | 2 | 2 |
| English | 5 | 5 | 5 | 5 |

8.	Membership of Professional Bodies: -

9.	Other skills: MS Office (Word, Excel, Power-point), SPSS (Statistical Package for the Social Sciences) User of social media and web 2.0 applications; grant management systems (SWIM, ECAS, EMIR), Adobe Photoshop (graphical design)

10.	Present Position: EURES reform coordinator (EURES National Co-ordination Office)

11.	Years of professional experience: 15 years

12.	Key qualifications:

- 12 years of proven experience in the development and implementation of business and workforce development projects (financed by ERDF and ESF),

- Experience in preparation of business plans, HR development and marketing plans for SMEs, NGOs,

- Experience in elaboration, coordination, monitoring and evaluation of labour market and social economy projects;

- 4 years of experience in implementation of international projects (INTERREG HUSKUA)

- 12of proven experience in planning and implementation of rural development programmes and projects for (SAPPARD, LEADER and ERDF fund programmes),

- 7years of experience in small-group trainings and holding presentation

- Evaluating the quality and accessibility of results of the “FORRÁS- regional Program for developing vocational guidance service” (PHARE- HU0008-02-01-0073)

- 8 years proven experience in planning and managing public procurement processes for acquisition of labour market services and for infrastructural investment

- First-hand experience in Project Cycle Management (PCM) and project developing techniques,  good knowledge of European policy documents and initiatives

13.	Specific experience in the region or else:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| Hungary, Sátoraljaújhely | November 2010- April 2013. | “Research on exploitation of hydropower potential in the cross border (Slovakia- Hungary) rivers HUSK/0901/1.2.1/0220” (beneficiary: Foundation for Zemplén Regional Enterprise Promotion, ZRVA), professional contribution in the expert team for the Feasibility Study |
| Hungary, Budapest | 2014 | EURES-T Pannónia and EURES-T Danubius Activity Plans 2013-2014. - cross border cooperation for easing the employment problems in the cross border regions. |

14.	Professional experience:

| Date: from (month/year) to (month/year) | 2014 - ongoing |
| --- | --- |
| Location | Hungary, Budapest |
| Company / Organisation | National Labour Office of Hungary (Budapest) |
| Position | EURES reform coordinator (Civil servant) |
| Job Description | - Co-ordination and organization of the reform of the national EURES-network - Preparation of international grant applications in the field of employment and social policy - Managing procurement processes according to EURES reform activities with involvement of social partners, - Communication with the representatives of PES and with other partner organisations, - Building new EURES partnerships, planning new EURES activities - Preparing Activity plan and Final Activity reports according to EURES reform, - Creating and holding presentation in EURES reform related topics, events, - Participating in the events organised by the Commission and the European EURES Network, contribution in the international activities of EURES Network, - General EURES advisory duties at the national EURES costumer service |

| Date: from (month/year) to (month/year) | 2013 |
| --- | --- |
| Location | Hungary, Budapest |
| Company / Organisation | Labour Centre of the Budapest Metropolitan Government Office |
| Position | Project mentor in SROP 2.1.6 “I learn again” |
| Job Description | - Counselling for the involved target group, coordination of the implementation of programmes financed by the European Social Fund - Preparation of progress report for the programme - Financial management and administration |

| Date: from (month/year) to (month/year) | 2007 - 2012 |
| --- | --- |
| Location | Hungary, Miskolc |
| Company / Organisation | SPEKTRUM-3 Business and Rural Development, Consulting and Human Service Nonprofit Ltd. |
| Position | Senior project manager |
| Job Description | - Planning, managing and coordinating regional and/or local projects for infrastructure development and capacity building granted by EC, - Consultancy for SMEs and local municipalities according to employment, HR and organisation development issues, - Development of equal opportunity situation analyses and environmental sustainability measures |

| Date: from (month/year) to (month/year) | 2002 - 2010 |
| --- | --- |
| Location | Hungary, Miskolc |
| Company / Organisation | SPEKTRUM-3 Business and Rural Development, Consulting and Human Service Nonprofit Ltd. |
| Position | Teacher, trainer |
| Job Description | - Teaching economics and urban sociology in vocational training programmes of the Hungarian Chamber of Commerce - Creating non- formal education programme for PCM and public procurement process |

| Date: from (month/year) to (month/year) | 2007 - 2012 |
| --- | --- |
| Location | Hungary, Miskolc |
| Company / Organisation | SPEKTRUM-3 Business and Rural Development, Consulting and Human Service Nonprofit Ltd. |
| Position | Public procurement expert |
| Job Description | - Managing EU threshold reaching and national procedures, mainly all types (negotiated and accelerated, restricted and open etc.) of procedures for both Tenderers and Contractor Authority - On the behalf of Contractor Authority conducting approx. 100 procedures for constructing works, approx. 50-50 procedures for public supplies and for public services, - Compiling Tender documentations and Contract Notices, - Providing Tenderers with additional information in the tender period, - Transacting tender opening procedures, - Evaluating tenders, transacting negation procedures, - Administration of all proceeding action according to Act of Public Procurement - Representing the contract authority on the individual review procedure. |

| Date: from (month/year) to (month/year) | 1999 - 2007 |
| --- | --- |
| Location | Hungary, Miskolc |
| Company / Organisation | SPEKTRUM-3 Business and Rural Development, Consulting and Human Service Nonprofit Ltd. |
| Position | Junior project manager (JPM) |
| Job Description | - Coordination and management of the projects financed by IPA (SAPPARD, PHARE), - Organising project events and providing information for partners, - Junior expert in the project: “Developing vocational training programme for rural development (PHARE HU9705-0203-0014)” and “Improving the quality of the rural tourism infrastructure in Hejce- Regéc- Novajidrány (PHARE HU9705-0302-00149)” - Project planning, community development |

15. Others:

2002. Julius Rézler scholarship - Indiana University, USA - Research and study in the field of sociology organisations

2000. EURODYSSE scholarship – Délemont, Canton Jura, Switzerland- Experience in the field of international market research and investment incentives. Organising business events, conferences and meetings with the participation of high- level public actors and diplomats.

CURRICULUM VITAE

Proposed position in the project: STE

1.	Family name: 	SZIKLAI

2.	First name: 	Istvan

3. 	Date and place of birth: 	04/07/1972, Gyula, Hungary

4.	Nationality: 	Hungarian

5.	Civil Status: 	married

6. 	Education:

| Institutions: | University of Eotvos Lorand, Faculty of Social Sciences, Budapest, Hungary |
| --- | --- |
| Date: From (months/year) To (months/year) | 01/09/1999 15/05/2005 |
| Degree: | Ph.D in Sociology (Social Policy) |

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Hungarian | Mother Tongue |  |  |  |
| English | 5 | 5 | 5 | 4 |

8.	Membership of Professional Bodies:

- Founder and member, Social Workers’ Democratic Trade Unions 2000 –

- Member, Hungarian Board of the International Committee on Social Welfare (ICSW) 1999 – 2002

- Member of Board, Hilscher Rezso Social Policy Association, Hungary 1997 – 2002

- Member, Hilscher Rezso Social Policy Association, Hungary 1993 –

9.	Other skills: MS Office (Word, Excel, Power-point, etc.), SPSS(a tool for statistical analyses)

10.	Present Position: Senior expert on employment, implemented several employment and social service projects co-financed by the EU Structural Funds in Hungary

11.	Years of professional experience: 14 years

12.	Key qualifications:

- 12 years of proven experience in the development and implementation of equal opportunity developments (both horizontal and targeted)

- 10 years of professional experience in strategic management, steering,  coordination and supervision of projects, programmes in the field of labour market and social services;

- 7 years of experience in conducting research, holding presentation for large audience

13.	Specific experience in the region or else:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| Hungary | Ongoing | See professional expertise |

14.	Professional experience:

| Date: from (month/year) to (month/year) | August 2009 - ongoing |
| --- | --- |
| Location | Budapest, Hungary |
| Company / Organisation | Public Employment Centre, National Labour Office of Hungary |
| Position | Senior expert on Employment, Social and Equal Opportunity Issues |
| Job Description | 1. Harmonisation of the employment and social services, benefit system 2. Strategic planning, and supporting the implementation of the developments co-financed by the EU 3. Quality controlling of the EU co-financed projects |

| Date: from (month/year) to (month/year) | August 2009 - ongoing |
| --- | --- |
| Location | Budapest, Hungary |
| Company / Organisation | Eotvos Lorand University, Faculty of Social Sciences |
| Position | Assistant professor |
| Job Description | 1. Giving lectures on introduction to social policy, teaching several course related to EU social policy, the EU Structural Funds, the labour and social policy, comparative social policy 2. Organising (facilitate, moderate, etc.) the PhD students on social policy and social work (including the establishment of international relationships |

| Date: from (month/year) to (month/year) | Aug / 2006 → Jul/ 2009 |
| --- | --- |
| Location | Budapest, Hungary |
| Company / Organisation | Hungarian National Development Agency, Managing Authority of Human Resource Programmes |
| Position | Senior expert on Social and Equal Opportunity Issues |
| Job Description | 1. Expertise on social policy, exclusion – inclusion politics and practice 2. Forecasting, planning and follow up (evaluation) the main (driving) forces of changes ahead (especially demography, employment, need for social protection, etc.) 3. Expertise on the equal opportunities (not only gender but Roma and Disability issues as well) horizontal issues (especially measuring, implementation, evaluation) |

| Date: from (month/year) to (month/year) | Apr / 2001 → Dec / 2006 |
| --- | --- |
| Location | Budapest, Hungary |
| Company / Organisation | Ministry of Health, Social and Family Affairs (former Ministry of Youth, Family and Social Affairs and Equal Opportunities) |
| Position | civil servant, Deputy head of department from Sept of 2004 |
| Job Description | 1. co-ordinating and strategic planning (involving strong partnership) of programmes in the field of social inclusion and equal opportunities, particularly those (possibly) co-financed by the EU Structural Funds from 2007 2. supervising the implementation of the first National Development Programme’s (2004-2006) measures fighting against poverty and social exclusion 3. Monitoring and evaluation of the implementation of the first National Action Plan on Social Inclusion (2004-2006) 4. Active participation in modernising the (statistical) methodology as well as strengthening policy capacity and analyses used in the field of social policy 1. Expertise on social policy, exclusion – inclusion politics and practice 5. Forecasting, planning and follow up (evaluation) the main (driving) forces of changes ahead (especially demography, employment, need for social protection, etc.) 6. Expertise on the equal opportunities (not only gender but Roma and Disability issues as well) horizontal issues (especially measuring, implementation, evaluation) |

15. Others:

- experienced in project development and implementation,

- well practised in giving lectures, holding and writing speeches, presentations;

- openness and committed to basic human rights, values;

CURRICULUM VITAE

Proposed position in the project: STE

1.	Family name: 	Tamajka

2.	First name:     	Milos

3. 	Date and place of birth: 	3 March, 1976

4.	Nationality: 	Slovak

5.	Civil Status: 	married

Address (phone/fax/e-mail):  Slovak Republic 106 Vodarenska Street Piestany, 921 01, Slovakia, Tel: +421-907-551-734,    email: milos.tamajka@upsvar.gov.sk

6. 	Education:

| Institutions: | City University, Trencin, Slovakia |
| --- | --- |
| Date: From (months/year) To (months/year) | 09/1999 – 05/2005 |
| Degree: | - Academic diploma - Master of Business Administration (M.B.A.) |

| Institutions: | Hotel Academy, Piestany, Slovak Republic School |
| --- | --- |
| Date: From (months/year) To (months/year) | 09/95 – 06/98 |
| Degree: | - Degree of the Higher education of Hotel management and Tourism |

| Institutions: | White &Case, Bratislava |
| --- | --- |
| Date: From (months/year) To (months/year) | 2005 01/2005 012/2005 |
| Degree: | Certificate of ‘Trainer of Communication Strategy” |

| Institutions: | BALA, ltd. |
| --- | --- |
| Date: From (months/year) To (months/year) | 02/2007 -09/2007 |
| Degree: | Certificate Modul Advanced Communication |

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Slovak | Mother Tongue |  |  |  |
| Czech | 5 | 5 | 5 | 5 |
| German | 3 | 3 | 3 | 3 |
| English | 5 | 5 | 5 | 5 |
| Russian | 5 | 5 | 5 | 5 |

8.	Membership of Professional Bodies:

9.	Other skills (e.g. computer literacy, etc.): (e.g. computer literacy, etc.):  Active professional use of office software – MS Word, Excel, PowerPoint, Internet and E-mail.

10.	Present Position: Director of Department of Employment Services, District Labour Office

11.	Years of professional experience: 14 years; more than 8 years at Employment Service

12.	Key qualifications:

- 9 years of professional experience in programming/implementation of ESF co-financed projects, e.g.:

- HRD projects: National projects - training, re-training, direct support of investors; business start ups; Internship support for young people;  Employment schemes for school leavers; Targeted training for known employer; etc. Career guidance support; Support  the Individual Employment Actions plans; Activation works for Inclusive Labour Market;

etc;….

- Over 8 years of experience in design/delivery of active labour market programmes and measures (ALMPMs) e.g. piloting, testing of new active labour market measures based on the needs of the clients of the (especially for disadvantaged target groups, measures for reconciliation of the family life; special inclusion measures to include the Roma’s into the labour market; handicapped people; targeted measures for employers  on the regional level

- Proven experience in change management policy provision to follow the common strategy to improve the services of the labour office for clients (implementation of Service model for labour offices – 6  years), negotiation and cooperation with local government, state government, tripartite institutions, politics, business community on the national and regional level ; Proven experience in managing the local Socio-Economic Council dealing with the social partners related to employment policy in the region

- Proven experience  in management of the Grants within the implementation of the ESF interventions  - Call for proposals based on the needs of employers and local NGO actors; procedures and guidelines related to the selection, implementation, monitoring and control of the grant projects

- 10 years of experience as  expert for  communication strategy (drafting and the implementation of the communication strategies

13.	Specific experience in the region or else:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| Macedonia (FYROM) | 12/2012 – 11/2013 | Trainer of the OEM (Organisation of Employers of FYROM) staff and ESA staff (Employment Service Agency) |
| Czech Republic, Hungary | From 2005 | Common projects in employment, seminars, CBC, conferences, working meetings and expert consultations |

14.	Professional experience:

| Date: from (month/year) to (month/year) | 1/2010- ongoing |
| --- | --- |
| Location | Piestany, Slovakia |
| Company / Organisation | Office of Labour, Social Affairs and Family |
| Position | Director of Office of Labour, Social Affairs and Family, Piestany |
| Job Description | - In charge of management and coordination of operations within the labour office including the 3 local offices; - Planning, designing, budget allocations for delivery of employment services and active labour market measures based on the needs of the local labour market and their implementation - Management of national projects financed through the ESF - Piloting, testing of new active labour market measures based on the needs of the clients of the (especially for disadvantaged target groups, measures for reconciliation of the family life; special inclusion measures to include the Roma’s into the labour market; handicapped people; targeted measures for employers - Participation of the drafting of the OP measures for programmes and measures on regional and local level - Managing the local Socio-Economic Council dealing with the social partners related to employment policy in the region - responsible for applying the change management within the local office to follow the common strategy to improve the services of the labour office for clients |

| Date: from (month/year) to (month/year) | 2/2005 -12/2009 |
| --- | --- |
| Location | Piestany, Slovakia |
| Company / Organisation | Office of Labour Social Affairs and Family |
| Position | Head of Active Labour Market Unit |
| Job Description | - In charge of applying a legal, secondary and other regulations and acts related the provision of employment services, e.g. employment mediation, career guidance, employment plans preparations, training , re-training and other supported training programmes; implementation of active labour market policy measures - Designing and planning of the ALMM based on the regional needs; pilot testing of the new measures in cooperation with local stakeholders - In charge of the national projects financed within the ESF: Tourism support in the region through investments into balneology (training, re-training, direct support of investors; business start ups); Internship support for young people; Employment schemes for school leavers; Targeted training for known employer; etc. - Management of regional Grant Schemes for OP Employment and Social Inclusion financed from ESF) – development of the Call for proposals based on the needs of employers and local NGO actors; development of procedures and guidelines related to the selection, implementation, monitoring and control of the grant projects - Cooperation in labour market analysis development based on the operational needs; - Development the innovative instruments – “turism nature projects” for balneology in the region; integrate people over 50 to the labour market and dissemination of good practice examples within the partners); - Monitoring the implementation of active labour market measures and participation in evaluation of active measures delivered by the office |

| Date: from (month/year) to (month/year) | 9/2003 -1/2005 |
| --- | --- |
| Location | Piestany, Slovakia.UKRO, ltd. of the National |
| Company / Organisation | Slovenska sporitelna - bank |
| Position | HRD Manager |
| Job Description | - Processing loans for local businesses - Consulting about investments to clients - Communication strategy for VIP clients - Performing a variety of clients requests related to local business support as assigned |

| Date: from (month/year) to (month/year) | 03/2000 -08/2001 |
| --- | --- |
| Location | Dubai, United Arab of Emirates.UKRO, ltd. of the National |
| Company / Organisation | Jumeirah International - Emirates Tower Hotel |
| Position | HRD Manager |
| Job Description | - Assisting restaurant manager in the day-to-day operations - Supervising of staff - Dealing with customers’ complains - Preparation of the documents for recruitment of the staff |

CURRICULUM VITAE

Proposed position in the project: STE

1.	Family name: 	Kralikova

2.	First name: 	Patricia

3. 	Date and place of birth: 	20 September, 1980

4.	Nationality: 	Slovak

5.	Civil Status: 	married

Address (phone/fax/e-mail): 916 41 Dolné Srnie 467, patricia.kralikova@upsvar.gov.sk; Slovak Republic

6. 	Education:

| Institutions: | Slovak Agricultural University Nitra Faculty of Gardening |
| --- | --- |
| Date: From (months/year)- To (months/year) | 1999 – 2004 09/1999 10/2004 |
| Degree: | Academic diploma – engineer – relevant to Master |

| Institutions: | Ernst &Young Business School |
| --- | --- |
| Date: From (months/year)- To (months/year) | 20 – 24 June 2011 |
| Degree: | EURES Final Training Course, Bucharest |

| Institutions: | TM CONSULTING, s.r.o., Nitra |
| --- | --- |
| Date: From (months/year)- To (months/year) | 4 – 6 October 2010 |
| Degree: | Certificate of Participant of the Presentation Skills |

| Institutions: | CONSTANTINE THE PHILOSOPHER UNIVERSITY IN NITRA |
| --- | --- |
| Date: From (months/year)- To (months/year) | 07 – 10/ 2008 |
| Degree: | Certificate of Participant for Development of job skills |

| Institutions: | ARBEITSGESTALTUNG KABA Uster, Switzerland |
| --- | --- |
| Date: From (months/year)- To (months/year) | 1996 02/1996 012/1996 |
| Degree: | Certificate of ‘Trainer of Career Consultancy’ |

| Institutions: | KING STREET COLLEGE, London |
| --- | --- |
| Date: From (months/year)- To (months/year) | 03/2006 -09/2006 |
| Degree: | Diploma in English as a foreign language (Level: Upper-Intermediate) |

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Slovak | Mother Tongue |  |  |  |
| Czech | 5 | 5 | 5 | 5 |
| German | 3 | 3 | 3 | 3 |
| English | 5 | 5 | 5 | 5 |
| Russian | 5 | 5 | 5 | 5 |

8.	Membership of Professional Bodies:

9.	Other skills (e.g. computer literacy, etc.): (e.g. computer literacy, etc.):  Active professional use of office software – MS Word, Excel, PowerPoint, Internet and E-mail.

10.	Present Position: Director of Department of Employment Services, District Labour Office

11.	Years of professional experience: over 14 years

12.	Key qualifications:

- 10 years of professional experience in programming/implementation of HRD (ESF co-financed) projects, e.g.:

- ESF projects: National projects - Career guidance support; Support  the Individual Actions plans; Information services assessable for all; Activation works for Inclusive Labour Market;

- ESF projects: National projects -   Increasing the qualification potential  of  employees  and persons entering the labour market; Employment schemes for school leavers; Improving Continuous Vocational Training to improve the adaptability of employees, Targeted training for known employer; Support the Internships programmes you young people;  etc…

- 10 years of experience in design/delivery of active labour market programmes and measures (ALMPMs) e.g. designing, testing and implementation of  variety of active measures for job seekers, employers and different target groups on the local and regional level

- 10 years of experience of development and provision of carrier guidance in Slovakia –  development and provision of carrier guidance and mediation – development of the strategies  and guidelines for career guidance;  redefining of the concept of the career guidance, development and delivery of the assessment tools for counsellors;

- 5 years of experience as trainer for  adult,  drafting training curricula, organising and conducting trainings; delivery of training courses for labour offices staff  based on the training needs analysis

- Proven experience  in management of the grants within the implementation of the ESF interventions for delivery of employment service and active labour market measures (development of the grant schemes,  Call for proposals and related operational guidelines compliant with ESF rules)

13.	Specific experience in the region or else:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| FYROM | 12/2012 – 11/2013 | Trainer of the OEM (Organisation of Employers of FYROM) staff and ESA staff (Employment Service Agency) |
| Czech Republic, Hungary, Poland | Since 2008 | Conferences, training, seminars, common projects and know-how transfer in employment area |

14.	Professional experience:

| Date: from (month/year) to (month/year) | 1/2011- ongoing |
| --- | --- |
| Location | Nové Mesto nad Váhom, Slovakia |
| Company / Organisation | Office of Labour, Social Affairs and Family |
| Position | Director of Department of Employment Services |
| Job Description | - In charge of management and coordination of supported labour market measures and delivery of supported services for job seekers and employers on the regional level - Participation of the drafting of the OP measures for programmes and measures on regional and local level - Member of the working group dealing with a redefinition of the concept of employment services model in Slovakia - In charge of development and provision of carrier guidance and mediation (member of a team on regional level) – development of the strategies and guidelines for career guidance; - redefining of the concept of the career guidance, development the system for career guidance for students and employers; - Elaboration of programmes for career guidance services and self-help programmes for the labour office clients delivery of the assessment tools for counsellors - Managing the national projects financed within the ESF: Career guidance support; Support the Individual Actions plans; Information services assessible for all - Cooperation in implementation of active labour market policy measures |

| Date: from (month/year) to (month/year) | 2/2008 -12/2010 |
| --- | --- |
| Location | Nové Mesto nad Váhom, Slovakia |
| Company / Organisation | Office of Labour Social Affairs and Family |
| Position | Head of Active Labour Market Unit |
| Job Description | - Designing and planning of the ALMM based on the regional needs; pilot testing of the new measures in cooperation with local stakeholders - Managing the national projects financed within the ESF: Increasing the qualification potential of employees and persons entering the labour market; Employment schemes for school leavers; Improving Continuous Vocational Training to improve the adaptability of employees, Targeted training for known employer; etc… - Implementation of active labour market policy measures – designing, implementation, monitoring and evaluation - Monitoring the implementation of active labour market measures and participation in evaluation of active measures delivered by the office - Cooperation in labour market analysis based on the operational needs; - drafting teaching and training materials for labour offices staff – staff training; - Development the innovative strategies and instruments to integrate people over 50 to the labour market and dissemination of good practice examples within the partners); - Implementation of the Grant management scheme for the implementation of the ESF interventions for Employment service (national projects and grants – Employment and active labour market measures; - Management of regional Grant Schemes for OP Employment and Social Inclusion financed from ESF); |

| Date: from (month/year) to (month/year) | 9/2004 -1/2008 |
| --- | --- |
| Location | Nové Mesto nad Váhom, Slovakia.UKRO, ltd. of the National |
| Company / Organisation | LUKRO, ltd. |
| Position | HRD Manager |
| Job Description | - In charge of staff recruiting for different companies within the holding - In charge of preparation of the job specification; testing the candidates competences and skills; recruiting process - Co-operation with the labour office in terms of on-the-job training for newly contracted staff |

CURRICULUM VITAE

Proposed position in the project: STE

1.	Family name:	SIMOVA

2.	First name:	Zdenka

3. 	Date and place of birth:	2nd April 1967, Vysoke Myto

4.	Nationality:	Czech

5.	Civil Status:	Married

Address (phone/fax/e-mail): + 420 950 172 420, zdenka.simkova@uo.mpsv.cz

6. 	Education:

| Institutions: | University of Cambridge ESOL Examinations |
| --- | --- |
| Date: From (months/year)- To (months/year) | 01/2013 01/2013 |
| Degree: | Preliminary English Test Certificate (PET) |
| Institutions: | University of Pardubice |
| Date: From (months/year)- To (months/year) | 09/2005 06/2008 |
| Degree: | Bachelor / Bc. |
| Institutions: | Czech Association for Cybernetics and Informatics |
| Date: From (months/year)- To (months/year) | 06/2005 08/2005 |
| Degree: | Certificate European Computer Driving Licence |
| Institutions: | SC C spol. s r.o., Prague |
| Date: From (months/year)- To (months/year) | 06/1995 06/1995 |
| Degree: | Statistics Methods Certificate |

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Czech | Mother Tongue |  |  |  |
| English | 4 | 4 | 4 | 4 |
| Russian | 3 | 4 | 3 | 3 |
| Slovak | 3 | 5 | 2 | 1 |

8.	Membership of Professional Bodies:

9.	Other skills (e.g. computer literacy, etc.):

Fully Computer literate: Microsoft Office, database and relevant graphics applications, ArcGIS, etc.

10.	Present Position: Statistical and analytical department, Labour Office, Czech Republic

11.	Years of professional experience: 21 years in employment services (19 years as a manager of labour market in the context of analysis, statistics and cooperation with employers; 7 years as an information technology operator).

12.	Key qualifications:

- Over 21 years of professional experience at Employment Service.

- Processing of Labour Market development forecast in Usti nad Orlici district.

- Managing, organising and responsibility for work of Labour Market Compartment.

- Analysis of particular Labour Market factors, processing of the analysis results including creating of precautions meeting the Labour Office, Pardubice Region and Employment Service Management needs.

- Performing analysis and statistical records for Labour Market analysis and employment development, processing of monthly statistical statements and other statistical reports.

- Monitoring of employers and database updating.

- Surveillance and evaluation of employers’ fulfilment of obligation to employ reduced working ability citizens in obligatory percentage.

- Cooperation with all the special compartments of the Labour Office and with other Public Administration Authorities.

- Experienced in ESF financed project  - Guarantor of “Vzdělávejte se pro růst!” project in Usti nad Orlici district 08/2011 – 01/2012

- Processing of reports for Regional Coordination Group in Usti nad Orlici district.

- Cooperation in development of Employment Information Systems.

- Testing and verifying of OKpráce and OKcentrum applications of OKsystem s r.o. company.

- Member of OK práce Modul Working Groups established by Ministry of Labour and Social Affairs (MLSA) serving to the development of the Information System of the Employment Offices. Working Group for Vacancies and Labour Market Monitoring (2003 – 2011) and Statistics Working Group (2002 – 2011).

- Creating of Employment Maps using MS Map and ArcGIS.

- Verifying of contracts of ALAMPs in Usti nad Orlici district.

13.	Specific experience in the region or else:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| Slovakia | 09/2008 – 12/2011 | Cross border project : New IT skills for local self-government regions” |

14.	Professional experience:

| Date: from (month/year) to (month/year) | 04/2011 – ongoing |
| --- | --- |
| Location | Pardubice, Czech Republic |
| Company / Organisation | Czech Republic Labour Office – Regional Subsidiary Pardubice |
| Position | Labour Office Employee – Labour Market Manager |
| Job Description | - Systemic processing of labour market and employment development data based on labour market monitoring in Regional Subsidiary Pardubice´s district. - Processing standard and non-standard statistics and analysis meeting both Labour Office and public´s need. - Processing and updating of an employer’s database and database of employment development based on labour market development in Usti nad Orlici district or in Regional Subsidiary Pardubice district. - Guarantor of “Vzdělávejte se pro růst!” project in Usti nad Orlici. - Ensuring consultant and information service for employers. - Deputy Officer of surveillance and evaluation of employers´ fulfilment of obligation to employ reduced working ability citizens in obligatory percentage. - Verifying of contracts of ALAMPs in Usti nad Orlici district. |

| Date: from (month/year) to (month/year) | 12/1992 – 03/2011 |
| --- | --- |
| Location | Usti nad Orlici, Czech Republic |
| Company / Organisation | Labour Office Usti nad Orlici |
| Position | Labour Market Compartment Manager |
| Job Description | - Processing of labour market development prognosis in Usti nad Orlici district. - Managing, organising and responsibility for Labour Market Compartment. - Analysis of particular labour market factors, processing analysis results including creating of precautions meeting the Labour Office, Pardubice Region and Employment Service Management needs. - Performing analysis and statistical records for labour market analysis and employment development, processing of monthly statistical statements and other statistical reports. - Monitoring of employers including database updating. - Surveillance and evaluation of employers’ fulfilment of obligation to employ reduced working ability citizens in obligatory percentage. - Cooperation with all the special compartments of the Labour Office, with other Employment Offices and with other Public Administration Authorities. |

| Date: from (month/year) to (month/year) | 06/2004 – 06/2011 |
| --- | --- |
| Location | Usti nad Orlici, Czech Republic |
| Company / Organisation | OKsystem spol. s r.o. |
| Position | Verifier of OKprace and OKcentrum information systems |
| Job Description | - Testing and verifying software – verifying functions of the new versions and its comparing to the previous ones. - Suggesting of possible changes of the system. - Practical verifying of coincidence of user´s manual and the software. |

| Date: from (month/year) to (month/year) | 07/1985 – 11/1992 |
| --- | --- |
| Location | Usti nad Orlici, Czech Republic |
| Company / Organisation | Elitex, s.p. / Rieter Elitex, a.s. |
| Position | Information Technology Operator |
| Job Description | - Ensuring of EC1021 functioning (keeping the program flowing) |

CURRICULUM VITAE

Proposed position in the project: STE

1.	Family name:	MAREK

2.	First name:	JAN

3. 	Date and place of birth:	7th Dezember 1954, Nizkovice, Czech Republic

4.	Nationality:	Czech

5.	Civil Status:                          	Married

Address (phone/fax/e-mail):    Slovanská 886, 684 01 Slavkov u Brna, Czech Republic

+420 603 824 989, e-mail: ing.janmarek@volny.cz

6. 	Education:

| Institutions: | University of Economics, Prague, Faculty of Business Administration Czech Republic |
| --- | --- |
| Date: From (months/year) To (months/year) | 10/1976 -07/1980 |
| Degree: | University degree in Economics, Ing. |

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Czech | Mother Tongue |  |  |  |
| Slovak | 5 | 5 | 5 | 5 |
| German | 4 | 4 | 4 | 4 |
| Russian | 4 | 4 | 4 | 3 |
| English | 4 | 4 | 3 | 4 |

8.	Membership of Professional Bodies:

The Council for the Development of Human Resources in the South Moravian Region

Chamber of specialists for crisis management and insolvency in the Czech Republic

9.	Other skills (e.g. computer literacy, etc.):

- User Windows - Word, Excel, Power Point, etc. Standard work with the Internet, electronic mail, mobile communications. Ability to work independently with specialized databases and information systems for businesspeople

- Lecturing experience in lecturing Banking and International Banking under the Banking Institute College of Prague (until 2012 a member of the Academic Board). I am a certified teacher of adult education (AIVD in cooperation with the Palacky University in Olomouc).

- Driving Licence A, B, C, T, each year as a driver around 30,000 km.

10.	Present Position:      Labour Office in Vyškov, Director

11.	Years of professional experience: 33 years of experience in employment area (public and business)

12.	Key qualifications:

- More than 33 years of professional experience in comprehensive management of separate organizational units of the state, ensuring the state employment policy and non-insurance social welfare in the administrative district and to the extent applicable laws.

- Proven skills in negotiation and cooperation with local government, state government, tripartite institutions, politics, business community; negotiations with foreign investors.

- More  than 20 years of professional experience as change management expert  a specialist in the teams MLSP (acts as coordinator of activities in the field of standardization activities and streamlining the organizational structure of work within the employment service)

- 22 years of experience in design/delivery of active labour market programmes and measures (ALMPMs)  - policy design of the active labour market measures reflected the needs of the local labour market; piloting of measures, testing, implementation on regional and local level; Conceptual management and targeted implementation of active employment policy (ALMPMs) on the most vulnerable groups in the labour market. Working with ethnic minorities. Targeted implementation of European resources at the local level. Cooperation with headquarters in the creation of new programs in the field of active employment policies and their successful implementation.

- 10 years of professional experience in programming/implementation of HRD (ESF co-financed) projects, e.g.: national projects:

- Project “The Educate!" (06/2009 – 12/2010) - aimed at employers who due to the global financial crisis and economic recession had to cut production at its plants, and for their employees. The project employers to raise funds for the implementation of training courses for their employees, who are vulnerable to the negative effects of organizational changes in the company as a result of the crisis. Employees are then given an opportunity to participate in further education, improve their professional knowledge, skills and competencies in the general Education and employers gain space for more efficient staffing solutions company situation during the crisis. Project was highly rated and in the EU.

- Project “The Educate for growth" (05/2011 – 07/2013) focused on s the support of employers, who managed to overcome the economic recession and currently pursues its sectors for growth as a significant share of GDP.

- Project “The Educate for stability" (09/2012 – 08/2015) - to promote the maintenance of jobs for those employers who, in the context of the economic downturn in the Czech Republic are in temporarily difficult economic situation and temporarily unable to assign work to employees in the agreed scope.

- Excellent managerial skills and long lasting experience managing the staff in employment services. The complex knowledge of economics and finance. Human Resources. Crisis management. Experience in European projects. Project management. Training and teaching skills.

- Proven 14 years of experience in management of the Grants corresponding long-term experience with the implementation of ESF projects, their monitoring and evaluation. Experience with the analysis of the labor market at both the regional and national level. Successful application of components ALMPMs to work with both the unemployed and the employers.

13.	Specific experience in the region or else:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| Austria | 05-06/2010 | LdV – Intership at AMS Wien |
| Austria | 02-04/2011 | LdV – Intership at AMS Niederösterreich |
| Germany, France | 10/2006 | Twinning Light Project (Bundesagentur für Arbeit, Zentrale Nürnberg) |
| Italy - Sicily | 10-11/2012 | LdV |
| Slovakia | Regularly since 2000 | Common meetings and actions in employment area |

14.	Professional experience:

| Date: from (month/year) to (month/year) | 10/2000 – 09/2010, 08/2012 -ongoing |
| --- | --- |
| Location | Vyškov |
| Company / Organisation | Úřad práce / Labour Office |
| Position | Director |
| Job Description | Main activities and responsibilities - Comprehensive management of separate organizational units of the state, ensuring the state employment policy and non-insurance social welfare in the administrative district Vyskov and to the extent applicable laws. Negotiation and cooperation with local government, state government, tripartite institutions, politics, business community. Negotiations with foreign investors. Working in specialist teams MPSV (acts as coordinator of activities in the field of standardization activities and streamlining the organizational structure of work), international cooperation (Austria, Germany, Slovakia, Hungary, Slovenia) incl. participation in projects and internships. The work of the Council for the Development of Human Resources South Moravian Region. |

| Date: from (month/year) to (month/year) | 10/2010 – 07/2012 |
| --- | --- |
| Location | Brno |
| Company / Organisation | Úřad práce /Labour Office |
| Position | Country manager |
| Job Description | Main activities and responsibilities Comprehensive management of separate organizational unit within the Office of the works of the Czech Republic, the governmental policy of employment and social support in the administrative district of the South Moravian Region and to the extent applicable laws. Negotiation and cooperation with local government, state government, tripartite institutions, politics, business community. Negotiations with foreign investors. The work of the Council for the Development of Human Resources South Moravian Region and in specialist teams of Ministry of Labour and Social Affairs of the Czech Republic. |

| Date: from (month/year) to (month/year) | 02/2000 – 09/2000 |
| --- | --- |
| Location | Prague, Veselí nad Moravou |
| Company / Organisation | Z – GROUP, Inc. |
| Position | Senior Manager – Financial Area |
| Job Description | Solution funding and restructuring of holding company with a turnover of over 12 billion CZK. Negotiations with major creditors, with the banks. Solution specialized and complex tasks under the direct control of the President of the Board. Leading a team of specialists crisis management. |

| Date: from (month/year) to (month/year) | 08/1992 – 01/2000 |
| --- | --- |
| Location | Brno |
| Company / Organisation | Investment and Postal Bank. Inc. |
| Position | Head of banking transactions. Deputy Director of the Regional Branch Brno |
| Job Description | Complex and complicated banking transactions (credit and financial transactions). Business and legal proceedings related thereto. Methodical and efficient management of the South Moravian branch networks in the business area. From the position of DD then the responsibility for the introduction of retail stores in the region, including construction of a new organizational structure and its management. Leadership and management of large teams of different collaborators. |

| Date: from (month/year) to (month/year) | 08/1980 – 07/1992 |
| --- | --- |
| Location | Valašské Meziříčí, Nížkovice |
| Company / Organisation | Agricultural cooperative (ZD) Podlesí Valašské Meziříčí, ZD Nížkovice |
| Position | Economist and Trade Deputy – Agriculture and business |
| Job Description | economy, business - a comprehensive management teams of various sizes in the economic and commercial fields. |

15.	Others:

Practical and verifiable experience in the successful management of different types of teams of various sizes (5-1,500 people). The ability to self-determination and teamwork. Ability to coordinate and unite to find solutions in difficult situations and specifically to motivate employees.
Europass Mobility (CZ/00/2010/0290/002/AT/10) - Internship at AMS Wien
Europass Mobility (No. CZ/00/2008/1218/003/AT/10)-Internship at AMS Österreich
Twinning Light PROJECT - an international project incl. internships (F, D) organized by the MLSA, NVF and headquarters Bundesagentur für Arbeit Nuremberg
Media training for executives (MLSA)
Financial control (MLSA).
Finanzkontrolle (Office of the Canton of Zürich).
Lecturer adult education (AIVD in collaboration with the University Palacky Olomouc)
GUSTAV KÄSER TRAINING (four semesters, managerial skills, Prague)
INVENTA PROGRAM MANAGER (Corporate finance - lecturer Mark Rooney, USA)
etc

16.	Publications and Seminars:

Lecturing experience in lecturing Banking and International Banking under the Banking Institute College of Prague (until 2012 a member of the Academic Board). I am a certified teacher of adult education (AIVD in cooperation with the Palacky University in Olomouc).

Lectures in the Austria-Czech Academy of Experts EXPAK (2002-2013). Articles in professional journals (ANDRAGOGIKA, South Moravian Lobbying), frequent appearances in the media (television, radio, newspapers)

17.	References:

References supplied upon request.

# CURRICULUM VITAE

Proposed position in the project: STE

1. Family name:  	Mateřanková

2. First name: 	Jarmila

3. Date, place of birth:	10.11.1954, Opava

4. Nationality:	Czech

5. Civil status: 	married

Address:  	Mrs. Jarmila Mateřanková, Přemyslovců 30a, 747 07  Opava 7, Czech Republic

Tel. :  	+420950142300; +420775630550, Fax: +420950142302; EMail:Jarmila.Materankova@op.mpsv.cz

6. Education:

| Institution | Vysoká škola báňská Ostrava, Czech Republic (Mining University) |
| --- | --- |
| Date: from (month/year): to (month/year) | 9/1974 6/1979 |
| Degree(s) or Diploma(s) obtained: | University degree in computer science |
| Institution | Gymnasium Opava, Czech Republic |
| Date: from (month/year): to (month/year) | 9/1970 6/1974 |
| Degree(s) or Diploma(s) obtained: |  |
| Institution | Státní jazyková škola při Obchodní akademii v Opavě |
| Date: from (month/year): to (month/year) | 1995 |
| Degree(s) or Diploma(s) obtained: | state exam in English language |

7. Language skills:

| Language | Reading | Speaking | Writing |
| --- | --- | --- | --- |
| English | 5 | 4 | 5 |
| Russian | 4 | 3 | 3 |
| German | 3 | 2 | 2 |

8. Membership of the Professional Bodies:

- Advisory Board of the Regional Labour Office in Ostrava

- Steering Committee for the Strategic Planning of the City of Opava

9. Other skills:  fully computer literate

10. Present position: Head of Local Labour Office in Opava

11. Years of professional experience:   33 years altogether, 23 years in Czech public employment services

12. Key qualifications:

- 23 years of experience in labour market analysis, with the background of master degree in mathematical statistics, probability, operation research and programming

- 25 years of experience in managing positions, with up to 150 subordinates, and the budget of 1 billion CZK

- 11 years of experience in active labour market policy implementation, incl. ESF financed projects,  in the region heavily hit by extremely high rate of unemployment and long-term unemployment; namely experience in subsidies for creating new jobs for unemployed within the firms, start up subsidies for unemployed to become new entrepreneurs, subsidies for municipal work as a tool for combating long term unemployment, subsidies for creating and maintaining sheltered work for disabled, special programmes for school leavers, implementation of successful training programmes, like Get trained!

- 5 years of experience as a lecturer on labour market issues, proven by Ministry of Labour and Social Affairs

- 5 years as a member of the Czech Ministry of Labour and Social Affairs working group for labour market monitoring, analysis and statistics

- 15 years - proven professional record and hands-on experience as trainer/teacher on social matters/employment/labour market (in university, specialised training courses, etc.)

- strong analytical skills, proved by frequent contracts with top Czech labour market research institutions, like Masarykova univerzita (Masaryk University), Výzkumný ústav práce a sociálních věcí (Research Institute of Labour and Social Affairs)

- ability to work in multinational teams and strong language capacity in English

13. Specific experience in the region or else:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| Czech Republic (Poland, Italy, Latvia, Belgium, Slovenia, Slovakia) | 2011 - 2013 | Learning from Experience of PES Practitioners in EU (National Training Fund) |
| Czech Republic, Prague | 2008 | Evaluation of ALMPs in the Czech Republic (National Training Fund) |
| Czech Republic, North Moravian-Silesian Region | 2000 - 2003 | Cross Border Cooperation – CBC projects |
| Czech Republic, North Moravian-Silesian Region | 2000 - 2004 | Implementation of Phare/Palmif programme in the region |

14. Professional Experience Record:

| Date: from (month/year) to (month/year) | 4/2011 ongoing |
| --- | --- |
| Location | Prague, Czech Republic |
| Company | Labour Office of the Czech Republic |
| Position | Director of the Labour Office in Opava |
| Description | Responsible for local public employment services and social benefits, consultancy, career guidance; both for demand and supply sides, mediation of employment, cooperation with employers and municipalities. Participation in EURES-T Beskydy. |
| Date: from (month/year) to (month/year) | 6/2006 4/2011 |
| Location | Opava, Czech Republic |
| Company | Labour Office Opava |
| Position | Director |
| Description | Responsible for regional public employment services and social benefits, counselling and consultancy, job mediation, requalification, labour market analysis, regional employment strategy, active policy measures, including ESF projects implementation. Namely: - Support of the sheltered work for disabled - Special active labour market measures focused on young unemployed and school leavers - Municipal work for long term unemployed - Creating socially purposed working places - Support of the unemployed starting their own businesses - Get trained! – unique Czech training programme financed by ESF, focused on increasing employability of those threatened by lay-offs due to economic decline |
| Date: from (month/year) to (month/year) | 2/2002 6/2006 |
| Location | Opava, Czech Republic |
| Company | Labour Office Opava |
| Position | Head of labour market department |
| Description | Responsible for regional labour market analysis, regional employment strategy, active policy measures, including implementation of Palmif /Phare programmes |
| Date: from (month/year) to (month/year) | 7/1991 2/2002 |
| Location | Opava, Czech Republic |
| Company | Labour Office Opava |
| Position | analyst |
| Description | Regional labour market statistics, analysis and prognosis |
| Date: from (month/year) to (month/year) | 9/1995 6/2011 |
| Location | Opava, Czech Republic |
| Company | Silesian University |
| Position | Teacher of Public Administration and Regional Development |
| Description | Teaching Statistics, Management, Computer skills |
| Date: from (month/year) to (month/year) | 7/1979 6/1991 |
| Location | Prague, Opava, Czech Republic |
| Company | Computer Center of the Ministry of Commerce |
| Position | Deputy head |
| Description | Responsible for computing data for wholesale and retail |

15. Others:

- Reviewer of labour market research publications, ALMP and social policy evaluation studies of different renowned institutions like Masarykova universita Brno, Výzkumný ústav práce a sociálních věcí Praha etc.

- Approved lecturer of Czech MoLSA on labour market issues

- Experienced teacher, incl. teaching adults

15a. Publications and seminars:    occasional seminar and conference papers, newspaper articles

Active participation in national and international events, like conferencies, seminars and workshops organized by Czech MoLSA, Czech Ministry of Interior, Národní vzdělávací fond NTF Praha, ILO, WAPES, ETF, Cedefop, East West Institute etc.

Active participation in foreign study visits on employment and entrepreneurial issues.

CURRICULUM VITAE

Proposed position in the project:  STE

1.	Family name: 	BILKOVA

2.	First name:	Marie

3. 	Date and place of birth:	21st July, 1961, Praha

4.	Nationality:	Czech

5.	Civil Status:	married

Address (phone/fax/e-mail): 	Mikulase z Husi 1521/2 ,14000 Praha 4

(marie.bilkova@uradprace.cz)

6. 	Education:

| Institutions: | University of Economics, Faculty of National Economy, Praha |
| --- | --- |
| Date: From (months/year)To (months/year) | 09/1980 – 06/1985 |
| Degree: | University degree in economics (academic diploma), Engineer |
| Institutions: | Academy of European Law, European University Institute, Firenze |
| Date: From (months/year)To (months/year) | 06 – 07/2002 |
| Degree: | certificate |
| Institutions: | Charles University, Faculty of social sciences, Law, Prague |
| Date: From (months/year)To (months/year) | 11/1999 – 06/2000 |
| Degree: | certificate |

7. 	Language skills (Mark 1 to 5 for competence, where 5 is the highest):

| Language | Level | Passive | Spoken | Written |
| --- | --- | --- | --- | --- |
| Czech | Mother Tongue |  |  |  |
| Slovak | 5 | 5 | 5 | 5 |
| English | 5 | 5 | 5 | 5 |
| Russian German | 4 | 4 | 4 | 4 |

8.	Membership of Professional Bodies:

9.	Other skills (e.g. computer literacy, etc.): Fully Computer literate: Microsoft Office (Word, Excell, PowerPoint, Outlook), database and relevant

graphics applications, etc.

10.	Present Position: Director General , Labour Office of the Czech Republic

11. Years of professional experience:	over 22 years

12.	Key qualifications:

- 20 years of professional experience in  public administration in context of national finance, employment policy, educational policies, labour market policy

- 10 years of professional experience in applying a legal, secondary and other regulations and acts related the provision of employment policy, e.g. employment mediation, career guidance, employment plans preparations, training , re-training and other supported training programmes; implementation of active labour market policy measures

- Profound experience in pension systems and flexible employment policies

- Extensive experience in design and delivery of active labour market  programmes and measures (ALMPMs) and delivery of public employment services to unemployed and employers, e.g. provision of information, counselling, mediation, preparation of individual action plans, professional orientation, implementation of active labour market policy measures;

- design  and delivery of ALMPM for different target groups,

- strong management, leadership and organisational skills dealing with managing the staff at all positions and levels

13.	Specific experience in the region or else:

| Country | Date: from (month/year) to (month/year) | Name and brief description of the project |
| --- | --- | --- |
| Portugal | 09/2011 | LdV project |
| Sweden and Norway | 09/2009 | Individual project Czech Republic – Sweden (focused on labour market measures) |

14.	Professional experience:

| Date: from (month/year) to (month/year) | 6/2013- ongoing |
| --- | --- |
| Location | Czech Republic |
| Company / Organisation | Labour Office of the Czech Republic |
| Position | Director General of the Labour Office of the Czech Republic |
| Job Description | - In charge of management of the tasks of the headquarter of the labour office dealing with labour market and employment and the provision of employment services ( on the management level) - Comprehensive management of separate organizational units of the state, ensuring the state employment policy and non-insurance social welfare to the extent applicable laws - Negotiation and cooperation with national and local government, tripartite institutions, politics, business community - Negotiations with foreign investors on the highest level - In charge of applying the new model of the Employment Service - Supervision of the design and delivery of ALMPM for different target groups, - implementation of ESF co-financed projects |

| Date: from (month/year) to (month/year) | 10/2009-5/2013 |
| --- | --- |
| Location | Czech Republic, |
| Company / Organisation | Ministry of Finance |
| Position | Director of Financing of the state budget chapters Department |
| Job Description | - financial budgeting, allocations of the budget within the state institutions - EU funding planning and distribution - Financial policy guidelines related Ministries chapters |

| Date: from (month/year) to (month/year) | 1/1990 - 9/2009 |
| --- | --- |
| Location | Czech Republic, Prague |
| Company / Organisation | Ministry of Labour and Social Affairs , Czech Republic |
| Position | Director of Employment Services |
| Job Description | - In charge of management of 145 Labour Offices - Communication with the Government, ministries and other related institutions dealing with employment policy, labour market measures - Negotiation of the bilateral agreements on mutual employment - In charge of development and applying the national employment policy on the national and local levels - Responsible for managing of the different reforms of the public employment services - Responsible for management of the EU Funds (ESF) - Negotiations with the social partners (employment issues, labour law, social contributions, unemployment benefits) - Responsible for the designing and the implementation of active labour market policy measures (within all structure of labour offices) - Responsible for adaptation of pension systems and flexible employment measures implementation |

Article to be deleted if the financing decision does not authorise the use of simplified cost options for a total amount exceeding EUR 60 000.

Article to be deleted if the value of the grant financing the Twinning Project is above EUR 5 million.

GEOSTAT

Ref. Source: Implementation of the European Neighbourhood Policy in Georgia

Progress in 2013 and recommendations for action

IMF: International Monetary Fund

Annex XXX of the AA titled Employment, social policy and equal opportunities, page, Official Journal, L261/p.601 of 30.8.2014

LM – labour market

ALMP – active labour market policy

LMIS – labour market information system

AA – Association Agreement between EU and Georgia

Annex XXX of the AA titled Employment, social policy and equal opportunities, page, Official Journal, L261/p.601 of 30.8.2014

SK-HU-CZ-GE – Slovakia-Hungary-Czech Republic-Georgia

CLs – component leaders

QR – quarterly reports

CSO – civil society organisations

Annex XXX of the AA titled Employment, social policy and equal opportunities, page, Official Journal, L261/p.601 of 30.8.2014

where budget provides sufficient funding for involvement of the two JPLs, these JPLs will also allowed to take part in the PSC meetings

Version 2013.1

Please do not forget to send a copy of this letter to the entities mentioned in Article 5(1) of the Special Conditions of the Contract, if any.

In case of consortium of MSPs.

In case a different account has to be used a new financial identification form has to be timely   submitted.

Directive 2006/43 of the European Parliament and of the Council of 17 May 2006 on statutory audits of annual accounts and consolidated accounts, amending Council Directives 78/660/EEC and 83/349/EEC and repealing Council Directive 84/253 EEC.

Refer also to Annex "E3a2 Checklist for simplified cost options" to the PRAG for additional information.

Not applicable to Twinning Light.

The overall budget for a Twinning project cannot be increased.

These matters are ruled by Article 7.2.3 of the Special Conditions (Annex A) and by Articles 11 and 12 of the General Conditions (Annex A2).

Article 11.10 of the General Conditions (Annex A2).

The overall budget for a Twinning project cannot be increased.

While MS PL may delegate RTA to sign standard side-letters, MS PL cannot delegate RTA to sign addenda or operative side-letters.

http://ec.europa.eu/europeaid/work/procedures/implementation/per_diems/

Under ENPI, these costs may be eligible.

Travel costs of BC officials within a MS are eligible for reimbursement under both IPA and ENPI.

See EU Policy Paper 2006, http://ec.europa.eu/social/main.jsp?catId=502&langId=en