## WP
Transformation of all E systems to C Hepatitis Unified Management Information System |  | Start Date | End Date
Stage 1 | Current System Study for future maintanance & usage | 2017-09-07 | 2018-05-05
Meetings with different parties
STOP C Archtecture, DB and Code review
ELIM C Archtecture, DB and Code review
Team preparation for ELIM C operational support before it's replacement
System maintanance untill it's replacment
System Documentation (including variables in systems, modules, workflows, etc)
Stage 2 | Temporary Reporting/Analytic layer preparation (with focus on analytic layer, using existing data systems/sources) | 2017-10-10 | 2018-01-30
Data cleaning in Stop C, ELIMC
Identificatin approacht to use data from C Screening databas, E Health Financial Module
Data extraction scripts will be updated and optimized where possible.
Stakeholders’ requirements research for analytics and reporting
Identification of access level for different type of reports
Data synchronization in temporary nontransactional data base (Screeing, Stop C, ElimC, Scrreining, Financial Module )
System connection to E Health User Management Module
Creation special analytical roles to access differnt reports
Documentation on analytic and reporting layer development
What kind of classification should be applied to already collected data? (e.g. Valid/Non-Valid, Under Treatment/Accomplished/Interrupted Treatment, Side Effects, Treatment Outcomes, etc)
What are the "findings" of already collected data? (what is it telling us about how effective the program is in various areas)
Stage 3 | Develop requirements and model for new system to replace Elimination C | 2017-10-12 | 2018-05-20
Conduct Stakeholder Meetings to gather requirements
Gather, define and document all requirements for new system
Develop a concept and product design for a replacement system to ElimC
Define hardware needed
Define system architecture document
Define data storage (including how data tables will be structured, how the database is designed, and a data dictionary for the new system)
Data access and user roles defined
Define data that must be collected by system (e.g. Name, age, address , genotype... etc)
Define modules/components needed
Define interdependencies with other MoH systems and non-MoH systems
Define process workflow within the system (By whom should the data be collected (HCPs, Service Centers, MoH, etc))
Define field validation(s) on data entry fields (e.g., drop downs, value ranges, checkboxes, skip logic, and reduce usage of free text fields)
Define how new system will link and feed data to analytic and reporting layers defined above
Define and build in business rules for classifying data (e.g., based on defined criteria in system, assign a current treatment status, etc)
Define and build in business rules for analyzing data ((e.g. Too big (compared to what?) treatment interruption rate, shortage of drug stock (due to pure logistics), uneven access to the project from different risk groups, etc)
Define routine reports and reporting periods (overlaps with Stage 2)
Gather and define examples of ad-hoc queries that stakeholders would like to build on demand (overlaps with Stage 2)
Stage 4 | System development for new treatment part of system | 2018-02-15 | 2018-06-20
System Development
Module development (database & user interface)
Integration in HMIS user management
Managing the users their roles and user rights
Connection with different HMIS modules and agencies
Internal Testing and bug fixing
update scope of work in case of necessity
Renewed internal testing
Product Testing & modifications
User satisfaction test
Module correction based on test results
Renewed Testing
Data Preparation For Migration
Data Migration
Deployment
Publishing module on real servers
Preparation of User Manuals
Preparation of Technical Documentation and System Administration Manual
Creation Usernames and Passwords for real users
Trainings
Presentation of training materials
Training of personnel
Stage 5 | System development for new inventory/logistics part of system | 2018-05-03 | 2018-08-27
System Development
Module development (database & user interface)
Integration in HMIS user management
Managing the users their roles and user rights
Connection with different HMIS modules and agencies
Internal Testing and bug fixing
update scope of work in case of necessity
Renewed internal testing
Product Testing & modifications
User satisfaction test
Module correction based on test results
Renewed Testing
Data Preparation For Migration
Data Migration
Deployment
Publishing module on real servers
Preparation of User Manuals
Preparation of Technical Documentation and System Administration Manual
Creation Usernames and Passwords for real users
Trainings
Presentation of training materials
Training of personnel
Stage 6 | System development for new commission part of system | 2018-07-10 | 2018-11-05
System Development
Module development (database & user interface)
Integration in HMIS user management
Managing the users their roles and user rights
Connection with different HMIS modules and agencies
Internal Testing and bug fixing
update scope of work in case of necessity
Renewed internal testing
Product Testing & modifications
User satisfaction test
Module correction based on test results
Renewed Testing
Data Preparation For Migration
Data Migration
Deployment
Publishing module on real servers
Preparation of User Manuals
Preparation of Technical Documentation and System Administration Manual
Creation Usernames and Passwords for real users
Trainings
Presentation of training materials
Training of personnel
Stage 7 | Reporting/Analytic Ecosystem: | 2018-07-10 | 2018-12-10
Data cleaning needs to take place on STOP-C system. This includes revising SQL queries used to generate reports and making permanent changes to the database.
Stakeholders’ requirements for analytics and reporting, including monitoring and evaluation indicators, will be documented and tied to the functionality of ecosystem.
A data dictionary for each system will be created (data sources such as STOP-C, Elimination C, and Screening database) that contains a database diagram, details of the database structure and complete variable information on all variables.
Any data dependencies and external connections will be documented, where applicable.
Data extraction scripts will be updated and optimized where possible.
ETL and other scripts will be documented with a description of what task they accomplish.
A joint (virtual) database will be created from the two treatment systems, STOP-C and ElimC.
A virtual database will be created linking screening database to treatment database, enabling reporting and analysis on linkage to care.
Creation of one central repository where all stakeholders have access to data. This repository would be used for research purposes and be the single source for all scientific publications for the Scientific Committee.
Customized and Ad-hoc report generation enabled (tables needed based on Stage 2 and ongoing input from Stakeholders)
Dashboards and commonly requested queries developed
Stage 8 | Post Implementation Support | 2018-12-25 | 2019-12-30
Regular Communication with MoHLSA, SSA, NCDC, Health Care providers
Develop workflow for system administration (post-development)
System Modification and updates by a system administrator (new variables, new reports, etc)
Updates to existing doccumentation
Adding new functionality to the system (as agreed upon by stakeholders and dependent on scope)

## Budget
Transformation of all E systems to C Hepatitis Unified Management Information System
| Stage 1 | Current System Study for future maintanance & usage
| Period: | 2017-09-07 | 2018-05-05 | 8 Months
| LABOR | Daily Rate | Days | Total
| Project Manager | 300 | 30 | 9000
| Business Process Analyst | 125 | 15 | 1875
| Master Developer | 200 | 30 | 6000
| Developer | 150 | 30 | 4500
| Developer | 150 |  | 0
| DB Admin | 150 | 10 | 1500
| System Admin | 125 | 2 | 250
| Web Designer | 100 |  | 0
| Sum |  |  | 23125
| Stage 2 | Temporary Reporting/Analytic layer preparation (with focus on analytic layer, using existing data systems/sources)
| Period: | 2017-10-10 | 2018-01-30 | 4 Months
| LABOR | Daily Rate | Days | Total
| Project Manager | 300 | 16 | 4800
| Business Process Analyst | 125 | 10 | 1250
| Master Developer | 200 | 20 | 4000
| Developer | 150 | 25 | 3750
| Developer | 150 | 25 | 3750
| DB Admin | 150 | 20 | 3000
| System Admin | 125 |  | 0
| Web Designer | 100 | 3 | 300
| Sum |  |  | 20850
| Stage 3 | Develop requirements and model for new system to replace Elimination C
| Period: | 2017-10-12 | 2018-05-20 | 8 Months
| LABOR | Daily Rate | Days | Total
| Project Manager | 300 | 16 | 4800
| Business Process Analyst | 125 | 20 | 2500
| Master Developer | 200 | 15 | 3000
| Developer | 150 | 10 | 1500
| Developer | 150 |  | 0
| DB Admin | 150 | 2 | 300
| System Admin | 125 | 2 | 250
| Web Designer | 100 | 4 | 400
| Sum |  |  | 12750
| Stage 4 | System development for new treatment part of system
| Period: | 2018-02-15 | 2018-06-20 | 5 Months
| LABOR | Daily Rate | Days | Total
| Project Manager | 300 | 25 | 7500
| Business Process Analyst | 125 | 10 | 1250
| Master Developer | 200 | 25 | 5000
| Developer | 150 | 35 | 5250
| Developer | 150 | 35 | 5250
| DB Admin | 150 | 5 | 750
| System Admin | 125 | 2 | 250
| Web Designer | 100 | 10 | 1000
| Sum |  |  | 26250
| Stage 5 | System development for new inventory/logistics part of system
| Period: | 2018-05-03 | 2018-08-27 | 4 Months
| LABOR | Daily Rate | Days | Total
| Project Manager | 300 | 18 | 5400
| Business Process Analyst | 125 | 8 | 1000
| Master Developer | 200 | 16 | 3200
| Developer | 150 | 15 | 2250
| Developer | 150 | 15 | 2250
| DB Admin | 150 | 4 | 600
| System Admin | 125 | 2 | 250
| Web Designer | 100 | 5 | 500
| Sum |  |  | 15450
| Stage 6 | System development for new commission part of system
| Period: | 2018-07-10 | 2018-11-05 | 5 months
| LABOR | Daily Rate | Days | Total
| Project Manager | 300 | 18 | 5400
| Business Process Analyst | 125 | 8 | 1000
| Master Developer | 200 | 16 | 3200
| Developer | 150 | 15 | 2250
| Developer | 150 | 15 | 2250
| DB Admin | 150 | 4 | 600
| System Admin | 125 | 2 | 250
| Web Designer | 100 | 5 | 500
| Sum |  |  | 15450
| Stage 7 | Reporting/Analytic Ecosystem:
| Period: | 2018-07-10 | 2018-12-10 | 6 Months
| LABOR | Daily Rate | Days | Total
| Project Manager | 300 | 25 | 7500
| Business Process Analyst | 125 | 18 | 2250
| Master Developer | 200 | 30 | 6000
| Developer | 150 | 30 | 4500
| Developer | 150 | 30 | 4500
| DB Admin | 150 | 20 | 3000
| System Admin | 125 | 13 | 1625
| Web Designer | 100 | 18 | 1800
| Sum |  |  | 31175
| Stage 8 | Post Implementation Support
| Period: | 2018-12-25 | 2019-12-30 | 12 Months
| LABOR | Daily Rate | Days | Total
| Project Manager | 300 | 35 | 10500
| Business Process Analyst | 125 | 15 | 1875
| Master Developer | 200 | 40 | 8000
| Developer | 150 | 40 | 6000
| Developer | 150 | 40 | 6000
| DB Admin | 150 | 15 | 2250
| System Admin | 125 | 4 | 500
| Web Designer | 100 | 5 | 500
| Sum |  |  | 35625
| SUB TOTAL |  |  | 180675
| Company Overhead |  |  | 5%
| TOTAL |  |  | 189708.75 | #REF!
Summary of needed resourses during 16 Months + 1 Year Maintantance
| LABOR | Daily Rate | Days | Total
| Project Manager | 300 | 183 | 54900
| Business Process Analyst | 125 | 104 | 13000
| Master Developer | 200 | 192 | 38400
| Developer | 150 | 200 | 30000
| Developer | 150 | 160 | 24000
| DB Admin | 150 | 80 | 12000
| System Admin | 125 | 27 | 3375
| Web Designer | 100 | 50 | 5000
| Sum |  |  | 180675
Summary of needed resources untill end of May 2018
| LABOR | Daily Rate | Days | Total
| Project Manager | 300 | 62 | 18600
| Business Process Analyst | 125 | 45 | 5625
| Master Developer | 200 | 65 | 13000
| Developer | 150 | 65 | 9750
| Developer | 150 | 25 | 3750
| DB Admin | 150 | 32 | 4800
| System Admin | 125 | 4 | 500
| Web Designer | 100 | 7 | 700
| Sum |  |  | 56725