Agenda

Meeting with Dr. Sergeenko

- August 2017

- Need for Hepatitis Program Manager/Director

  - Direct report to Minister

- Information System/IT: Key findings and recommendations for Workshop

  - Findings

    - Lack of coordination/management of communications

      - Stakeholders: MOLHSA, NCDC, Clinicians, CDC, GS, other

    - STOP-C/Elim-C not optimally designed

      - MOLHSA and CDC key consumers/analytics

      - Analysis is time/resource intense; data not timely

      - Current team at MOLHSA with limited capacity, contract end De 2017

      - Not delivering to stakeholders (Minister, CDC, GS, Clinicians/others)

      - Adequate hardware available; need Project Management is key gap

    - New work in screening data (NCDC), and E-health very promising; skilled production and oversight; progress and timely delivery of screening data/registry associated with new management of system

  - Recommendations

    - Need Project Manager (PM) with skills/experience/authority ASAP to stabilize ELIM/STOP C system and integrate Screening with Treatment Data (needed to optimize linkage to care)

      - TORs developed jointly with MOHLSA/NCDC/CDC

    - PM should report to new Hepatitis Program Manager/Director;

      - Work very closely CDC to understand and solve problems;

      - CDC IT TA will support PM

      - MOHLSA with CDC/DVH will provide analytics guidance (ie indicators, analysis plans, etc)

      - CDC can support staffing/financial with partners

      - Selection of PM:  Given direct involvement/leadership in establishing health management information system for MOLHSA, and of current progress/success of NCDC IT system/Screening Database led by Project Manager/Deputy Director, consider merging IT responsibilities of MOHLSA and NCDC (ie under single IT management) under Hepatitis Program Director;

        - There is need for single PM over treatment and screening for successful linkage to care!

    - After stabilize ELIM/STOP C can consider development of new (model) system that can be shared globally

      - Responsibility of new PM

- State Committee Urgent need to revive!

  - Needed for communication/coordination, already formed: includes members of MOLHSA/Hepatitis Program Director, CDC, NCDC, Clinicians, NGOs, others

- Scientific Committee

  - Need MOLHSA membership

  - Next meeting 24 August 5 PM (NCDC)

- Innovations

  - Treatment integration into harm reduction (TAG recommendation for elimination)

    - Stalled with single OST site

    - Needs revival/discussion? High visibility

    - FIND project

  - Simplified regimens

  - Primary Care Treatment

  - Integration of HIV/HCV/TB screening in Samegrelo

  - Testing expansion: PCR, Gene Expert, HCV CoreAg

- TAG agenda draft developed

- Hepatitis Summit: Strategic Info Session Focus on Georgia

  - Dr. Sergeenko moderator

- ECHO Expansion

  - Blood safety, IPC, TB, beyond treatment

  - Need for a coordinator (with experience in coordination/not SME); CDC/partners can support

- Removing Financial Barriers

  - Removing confirmation

  - Should be discussed with State Committee; assess risk/benefits to stakeholders

  - Move deliberately/carefully including stakeholders

- New/Ongoing Partners

  - LIFER: working with local partners/implementors

  - ECHO role expanding

  - BD

  - EASL-Foundation

  - Primary Care/Family Medicine

  - FIND

  - Other