# Information and Data Systems

# Georgia HCV Elimination Program

# Minister’s Update – March & April 2018

Source of Report:  Information is collected based on regular communication (at least weekly) with CDC IT/Data Expert, Leslyn McNabb, and IT/Data Team in Georgia

Reported by: Leslyn McNabb, CDC

Activities completed in March and April:

- The list of system updates that resulted from the IT Workshop on March 12, 2018 were provided to the ElimC IT team for inclusion in the system.  The list has been analyzed and meetings are taking place with clinicians and CDC to see what can be included in ElimC.

- A master first draft of a data dictionary in Georgian/English that includes all variables from the systems directly involved in the Hepatitis C Elimination program (STOP-C, ElimC, Screening, E-Health Diagnostics, E-Health Monitoring, and the Analytic Dashboard) has been provided.  CDC has requested a few revisions which NCDC are currently working on.  This data dictionary will continue to be updated as decentralization occurs and as IT systems are modified over time.

- Jointly (CDC/NCDC IT) provided a roadmap to Maia Lavlivadze for a proposed path forward for the Elimination C system.

- NCDC IT has prepared a SQL database of Elimination-C, STOP-C, E-health, and the Screening data so they are compatible with each other for exchange of information and merging.

- NCDC IT has begun soliciting requirements from stakeholders for potential analytical reports.

- Prepared methodology for how analytical reports will be created in IT system.

- Developed a beta version of the analytical engine and analytical tables, which will allow users to monitor progress of specific aspects of the Hepatitis C Elimination program and to download specific reports/tables.

- Extensive work has been completed on manuals (see next page) across all systems involved in the Hepatitis C Elimination Program.

Activities in progress and that will continue over the coming 30 days:

- Stakeholders’ requirements for the decentralization of the program will continue to be gathered and analyzed for how and when they can be incorporated into current and future IT systems.

- NCDC IT will continue to be involved in stakeholders’ requirements meetings for a future Drug module

- Establish a long-term planning/proposal for improving and maintaining IT systems of HCV Elimination Program for 2018 – 2020.

- Work will take place on a LIFER proposal to replace the existing one which ends on May 25, 2018.

Items in blue have been delivered and those in black are in progress and will be delivered by May 25, 2018.

STOP-C:

Data Dictionary (Georgian + English)

ElimC:

Data Dictionary (Georgian + English)

User Manual (Georgian)

Admin/Technical Manual (Georgian)

Admin/Technical Manual (English)

Architecture Document (English; provided by Maxo/Giorgi in 2016)

Analytic Dashboard:

Data Dictionary (Georgian + English)

User Manual (Georgian)

User Manual (English)

Admin/Technical Manual (Georgian)

Admin/Technical Manual (English)

Architecture Document (Georgian)

Architecture Document (English)

Screening:

Data Dictionary (Georgian + English)

User Manual (Georgian)

Admin/Technical Manual (Georgian)

Admin/Technical Manual (English)

Architecture Document (Georgian)

Architecture Document (English)