## Slide 1: GHSA-Wide Virtual Town Hall Meetings
March 2018
GHSA 2024 Development

## Slide 2
GHSA 2024 Development
Updates

## Slide 3: GHSA 2024 Development Goals
Develop a GHSA framework for 2019-2024 that:
    Establishes ambitious but realistic goals
    Establishes structures and processes that support achievement of those goals;
    Builds on successes achieved since 2014 and input from the broader GHSA community; and
    Is ready for transition to 2019 by the end of 2018.

## Slide 4: Approach and Milestones
Overall Approach: Consultations, Drafts, Discussions
  Solicit and discuss input from partners on GHSA 2024
  Draft and refine overarching framework and Terms of Reference
Development Timeline
  Nov 2017: GHSA-wide input solicitation (Questionnaire)
  Dec 2017: Discuss key issues at the Steering Group meeting
  Jan 2018: Begin drafting; discuss further at Steering Group meeting
  Feb-Apr 2018: Share initial draft GHSA-wide and conduct virtual consultations; begin drafting Terms of Reference documents (TORs)
  May 2018: Discuss draft Framework & TORs at the Steering Group meeting
  Summer 2018: Continue consultations and update/finalize drafts
  Fall 2018: Present GHSA 2024 Framework at the GHSA Ministerial Meeting
  Nov/Dec 2018: Transition to GHSA 2024

## Slide 5: Draft Framework: Elements
Overarching Framework (v1.0)
Background and Context
Vision, mission, principles, mandate, and objectives
GHSA structure, including:
  Governance (e.g., Steering Group, secretariat function)
  Operational Groups* (e.g., Task Forces)
GHSA-wide activities (e.g., meetings, reporting, tracking)
Annexes (e.g., strategic objectives details)
*Note: Action Packages consultations and discussions are continuing in parallel.
Next: Develop Terms of Reference Documents
Governance (e.g., Steering Group, secretariat function)
Operational Groups (e.g., Task Forces, Action Packages, GHSA members and partners)

## Slide 6: GHSA 2024: Role and Objectives
Align and leverage efforts with relevant partners:
  International organizations (e.g., WHO, OIE, FAO, World Bank)
  Non-governmental stakeholders (e.g., private sector, non-governmental organizations, universities, philanthropies)
  Relevant initiatives (e.g., JEE Alliance, Global Partnership)
Strategic Objectives:
  Promoting and supporting health security at the country level
  Developing tools and sharing lessons learned to strengthen country health security capacities
  Promoting a multi-sectoral and multi-stakeholder approach to health security
  Increasing domestic and international partner financial support for health security
  Strengthening accountability for global health security

## Slide 7: Next Steps
March-April
  GHSA partners join virtual Town Hall meetings (March 20-27)
  GHSA partners provide comments on GHSA 2024 Framework v1.0 by March 28.
  Steering Group begins to draft Terms of Reference documents.
May
  Steering Group discussion on GHSA 2024
Summer
  Steering Group continues consultations (e.g., share updated Framework and Terms of Reference, more virtual Town Hall meetings)
  Steering Group works to finalize GHSA 2024 ahead of fall meetings

## Slide 8: Thank You

## Slide 9: Discussion

## Slide 10: Wrap-Up

## Slide 11: Thank You
For any further questions, please email ghsapost2018@gmail.com