## Sheet1
Stage | Assignment | Total N of days | N of units | N of hours | Total (hours) | Comments
Preparatory stage | Meetings with staff organized and presentation with the overview of a selected model of performance appraisal (two groups) | 1 | 2 goups | max. 3 hours each (plus presentation preparation 2 hours) | 8 hours
| Groups meetings with managers (two meetings) | 1 | 2 groups | max. 3 hours each (plus presentation preparation 2 hours) | 8 hours | Group meetings to convey information on basic processes and documents (in cooperation with HR) to line managers of each LEPL may be also included upon request (5 groups X 3 hours = 4 days)
| Individuals consultations with line managers held | 15 | app. 40 (45) managers | 3 hours each | 120 hours | LEPLs cannot be covered by this activity
| Training of HR staff conducted; necessary tools for monitoring of performance appraisal processes selected | 2 | app. 10 persons | 16 hours | 16 hours
Mid-term evaluation | Capacity building activities for line managers (4 groups + 2 days + 1 day for preparation) | 9 | 4 groups | 16 hours X 8 hours preparation | 72 hours | One group consisting of heads of LEPSs may be added here (timeline: before the midterm asssessment takes place) = in total (plus 2 days for 1 groups 11 days)
| Training of staff on self-evaluation techniques delivered (beginning of the year) | 1 | 2 groups | max. 3 hours each plus preparation | 8 hours
| An analysis of midterm results of staff performance appraisal and lessons learned | 4 |  |  | 32 hours
Final stage | Training of staff on self-evaluation techniques delivered (end of the year) | 1 | 2 groups | max. 3 hours each plus preparation | 8 hours
| Support HR in finalization of results (twice a year) (etc. calculation) | 2 |  |  | 16 hours
| An analysis of results of staff performance appraisal, lessons learned, recommendations developed | 4 |  |  | 32 hours
| Final mission report detailing work conducted during the consultancy including major findings and recommendations. | 1 | 5 pages max. |  | 8 hours
| Group consultations on elaboration of PDP (development plans) | 1 | 2 groups |  | 16 hours
Upon necessity | A workshop on development of job descriptions (upon necessity) for HR and/or line managers | 2 |  |  | 8 hours
| Capacity building activities for line managers (upon necessity based on mid-term results) | 9 | 4 groups | 16 hours X 8 hours preparation | 72 hours
| Consultation meetings with line managers held, upon request of an agency throughout the year | 4 |  |  | 32 hours
| Total (MOH): | 57
| Total (incl. Heads of LEPLs and HRs) - additional 6 days | 63