## Initiatives
Goal | Initiatives | Q3 18 | Q4 18 | Q1 19 | Q2 19 | Q3 19 | Q4 19 | Q1 20 | Q2 20 | Q3 20 | Q4 20 | Date | Owner
Improve payment and contracting mechanisms | Developing and introducing DRG system | DRG grouper integrated to the SSA system; DRG terminology in Georgian; feedback to providers | DRG cost weights and reimbursement principles for the "virtual implementation" | Simualtions and analytics to develop DRG cost weights and reimbursement rules |  | DRG cost weigts and reimbursement policy for 2020; overall preparedness for DRG implementation | [5 empty] | 12.2019 | Director of SSA
| Critical assessment of basic financing PHC (considering the need for integration of rural and UHC, state vertical programs) including RBF principles | [10 empty] | 6.2019 | Head of Health Care Department, MoLHSA
| Developing principles of contracting for purchasing services, including selective contracting and monitoring and evaluation system of contracts performance | Assessment of current contracting arrangements, incl selective contracting practice of MCH care |  | Design of new contracting system, the concept | Design of MDC and case based planning system | Analyses of provider performance, forecast of MDC and case based planning, drafting SOP, SSA internal capacity building |  | Piloting volume based contracting, without financial obligations | Develop monitoring procedures and SOP | Develop legal regulation. Linking with payment mechanisms. | Final preparation for going live. | 12.2020 | Head of UHC, SSA
| Health needs assessment (for health services) for hospital care |  | Assessment of what kind of hospital services are priorities for needs assesement (ex. Cardiosurgery, neurosurgery, critical care, NICU..) | analyze the epidemiological data, existing resourses intenational experinece |  | elaborate the requirements for each directions based on statistical data taking into consideration the geografical accsessibility and utilization) | [5 empty] | 12.2019 | Head of UHC, SSA
HBP in line with population health needs | Designing the system and process of HBP revision and renewal | elaborate of the methodology for assesment of health needs and HBP design | analyze the health service utilization of existing HBP and detect weak an strong sides |  | assesment of health (among them essential) needs, servuce alocation and finansial resoirses |  | Redesighn HBP |  |  |  |  | 3.202 | Head of Health Care Department, MoLHSA
Consolidate highly specialised and hospital care | Analysing the need for hospital care services including highly specialised services and current distribution of service providers. | [10 empty] | 12.2018 | Head of UHC, SSA
| Developing a plan for sustainable purchasing of hospital and highly specialised medical services. | [10 empty] | 5.2019 | Head of UHC, SSA
Ensure equitable access to essential specialist care and strengthen PHC | Analysing and mapping geographical distribution of service providers and population service needs. | [10 empty] | 12.2018 | Head of Health Care Department, MoLHSA
| Developing a concept for geographically equitable provision of essential medical and primary care services, considering better integration and strengthening of service provider capacity (Integrating the concepts of rural medicine and UHC primary care programs to secure equal rights for patients and quality of service). | [10 empty] | 12.2019 | Head of Health Care Department, MoLHSA
| Revision of referral system and developing gate-keeping functions. | [10 empty] | 6.2019 | Head of UHC, SSA
| Upgrading the training and re-qualification system of GP. | [10 empty] | 12.2019 | Head of Health Care Department, MoLHSA
Improvement efficiency and quality of health services | Defining set of indicators to assess the quality of medical services, mechanism to monitor and control quality, and coordinate the quality functions with Regulatory Authority | [10 empty] | 12.2018 | Head of UHC, SSA
| Develop concept of medical audits (in cooperation with Regulatory Authority). | [10 empty] | 12.2019 | Head of Health Care, SSA
| Critical revision of current system and develop a concept to upgrade the system of licencing and accreditation of service providers. | [10 empty] | 6.2019 | Head of Health Care Department, MoLHSA
| Develop principles and functions of health economics within SSA, the structural alignment of functions. | [10 empty] | 12.2018 | Director of SSA
Enhance electronic data exchange and improve quality of data | Mapping of key processes related with health service provision and SP and defining the needs for developing solutions for electronis echange of data with stakeholders. | Defining SP key areas in need of IT development, new tech applications and solutions. Planning initiatives for 2019. |  | System analyses and TOR for ... | [7 empty] | 6.2019 | Deputy Director (IT) of SSA
| Introduce the use of electronic signature. | [10 empty] | 12.2019 | Deputy Director (IT) of SSA
| Mapping of claims management process and design of electronic claims management solution. | Mapping of claims manage ment process AS-IS | Designing SHOULD BE SOP (incl TOR for tech application?) | SSA wide training to introduce new practice | New claims management process introduced | [6 empty] | 12.2018 | Deputy Director (IT) of SSA
Improve population awareness | Development of Citizen Portal and applications to increase transparency for patients. | [10 empty] | 12.2019 | Deputy Director (IT) of SSA
| Develop concept of citizen communication and communication plan for 2019. | [10 empty] | 12.2018 | Head of PR Department, MoLHSA
Increase transparency and accountability | Development of reporting and benchmarking system of health service provision, based on indicators. | [10 empty] | 6.2019 | Head of Health Care Department, MoLHSA
| Development and introducing of quarterly reporting on SP performance | Designing Q(A reporting system, defining data needs | Piloting reporting based on Q 3 & 4 | [8 empty] | 3.2019 | Head of SP/Health Economics? SSA
Initiative under develepoment with milestone definition
Initiiative due date with final approval