Terms of Reference

Development of  National HIV Strategic Plan for 2019 -2022, Georgia

Duty Station: 	   Tbilisi, Georgia

Duration: 	    approximately 4 months, but not later than July 1, 2018

Estimated Starting date:	    February  20th  2018

Background Information

Communicable diseases, including HIV remain high priority public health issues worldwide. During the last two decades the country has been effectively implementing external funding support, predominantly from the Global Fund, reliant on the effective and professional collaboration and coordination with the international agencies, as well as across the national stakeholders.

Georgia was one of the countries in the region of Newly Independent States (NIS) that immediately reacted to the HIV/AIDS epidemic in early 1990s. From the beginning, Georgia has identified a response on AIDS as a priority, and the progress over the last 20 years was commendable.

The first One Agreed National Strategic Plan of Action (NSPA) was developed in 2002 for the period of 2003-2007. In 2010, the UNAIDS has supported the country to develop its second National Strategic Plan for the period of 2011-2016 that was endorsed by the Georgia CCM the same year. In follow up with the NSP endorsement and according to the GF requirements the CCM has developed a linked National HIV M&E Plan for the period of 2011-2013 with financial support of UNAIDS. External support mobilized through the Global Fund to fight HIV/AIDS, Tuberculosis and Malaria (GF) has been critical for scaling up the National Response to HIV/AIDS in Georgia. Though, capacity gaps still exist, in some areas shortage of human and financial resources is notable, some health systems pillars are deficient and all of this limits the national response to the epidemic. Today’s current Global Fund assistance is 18.45 million USD for HIV prevention, treatment and care activities and ends in June 2019. Within the frame of the GF allocation period 2017-2019 Georgia has the opportunity to submit a the grant continuation request for the next three year cilce of funding (till July, 2022). In order to guide the country’s response and avoid funding gaps, it is critical that the country has the updated HIV NSP for the period of 2019 -2022 that will serve as a basis for grant continutation request to GF.

With the support of the Global Fund, which has already invested more than 78 million USD in HIV Programme since 2003, Georgia has achieved important progress in a number of the program areas, specifically: the Georgian ART program was recognized by the international experts as one of the best in the region due to assured universal access to treatment, high coverage of target populations and improved quality of the program interventions. The country was first in the region that moved to WHO Treat All Strategy implementation in December 2015. The coverage of KAPs, especially of PWIDs with harm reducation programs and HIV prevention interventions has been scaled up considerably.

Despite the important positive developments achieved in HIV control, Georgia continues to face a number of serious challenges that need to be addressed through strengthening the health system, the application of patient-centered approaches with appropriate patient support, with adequate funding and strengthened governance.

Georgia has HIV NSP for 2016-2018 endorsed by the CCM in 2017.  The new plan should be revised based on recent epidemiologic data (IBBSSs and PSEs of key affected populations), relevant strategic priorities in a line of UNAIDS fast track targets and SDGs as well as of the GF supported activities transition needs.

The ongoing GF NFM HIV Program is scheduled through June 2019.

The CCM has received Funding Continuation recommendation from GF on 15 december, 2016 indicating the total amount – 17.5 million USD for the next funding cicle (2019-2022) for HIV and TB Programs.  For GF HIV Program new three year funding period starts from July 1, 2019. Although, the CCM will make a final decision regarding the distribution of the total funding between the programs the GF recommended split is 55% to 45% in favour of the HIV Program.

As the amount of available GF funding will be downsizing, the Government of Georgia is committed to increase the level of domestic funding to bridge the gaps and gradually take over the funding of priority HIV interventions. In fact the takeover processes had already been started in accordance to HIV NSP for 2016-2018, i.e. the state budget law endorsed  procurement of the first-line HIV drugs starting in 2015 and the second-line (25%) in 2017. In 2018 portion of the second line ARVs to be procured thorugh the State Budget will increase up to 50%. The State will procure all rapid tests (HIV, HCV, HBV and syphilis) for testing of KAPs, as well as CD4 monitoring tests for ART.

In order to ensure the continuation of the smooth transition processes to the domestic funding during the period of 2019 -2022 and establishing the well-functional and sustainable systems before the donor support is fully withdrawn, it is critical to develop a new NSP for the respective period that will inform the CCM for elaboration of the GF HIV funding continuation request (deadline is August 6, 2018) within the eligible funding, as well as the State HIV Program officials for effective planning of the transitioning of the activities of the National HIV Program left outside of the donor funding.

In 2017 in order to support transition from the Global Fund to the state funding of the TB and HIV programs, the Georgia Country Coordinating Mechanism (CCM) established the Policy and Advocacy Advisor Council (PAAC) with the mandate to assist CCM in identification of challenges of a transition period and advise on potential solutions. The key role for the PAAC is to act as a transition working group and to guide the development of a sustainability plan aimed at ensuring universal access to quality HIV and TB diagnostic and treatment services with domestic resources. The PAAC plaied a key role during preparation of the Sustainability and Transition Plan (STP) for the period of 2017-2021 that provides a framework for transitioning from donor to domestic funding for activities which are currently supported by GF, but not for 2022. The PAAC will provide technical guidance and monitor the progress of new NSP development, as well as inform the CCM regarding the quality of the draft and final documents and provide the recemendations for improvement.

In order to assist the Country Coordinating Mechanism, PAAC, MoLHSA and other governmental and nongovernmental agencies involved in HIV national program in development of the National HIV Strategic Plan for the period of 2019-2022, the National Center for Disease Control and Public Health (PR) is seeking to hire consultant(s)/firm (hereafter ‘consultant’) having the capability of both, the programmatic and financial expertise in HIV national programs.

Objective and Scope of the assignment

The main objective of the assignment is to develop the National HIV Strategic Plan (NSP) for the  Government of Georgia to meet the commitments vis-a- vis GF for the period of 2019-2022.

The Plan should be elaborated through a transparent and participatory process with close incolvement of all major stakholders including CCM, PAAC, MoLHSA, NCDCPH, TB and HIV service providers, CSOs and patients’ groups.

The plan should be informed by the latest HIV National Strategic Plans, GF HIV and TB Programs Sustainability and Transitioning Plan, most recent assessment/survey reports on various aspects of HIV responses. The basic support documents listed in the Annex 1 of the ToR will be provided by the GF PR.

The needed in-country expertice and support will be provided by National Consultants who will be hired by UNFPA Georgian office. The National Consutlants will prepare and provide the relevant background information and the plans for the national HIV program’s relevant segment development for the identified time period.

Scope

Selected Consultant will lead and coordinate the entire process of NSP development including the writing and finalization of the document through:

- planning and coordination of the NSP development in consultation with the CCM’s PAAC Policy and Advocacy Counsil and other stakeholders.

As a leader of the process, consultant should facilitate the work through setting a clear agenda for each step of the process and designing an adequate sequence of the relevant activities in close collaboration with national experts and relevant stakeholders (representatives of the National Aids Center, MoLHSA, National Center for Disease Control and Public Health, active NGOs in the area of HIV/AIDS and the National TB Center).

- conduct a comprehensive gaps analysis/diagnostic review of the previous NSP and setting priorities for a new Plan.

- Compilement of the various components of the HIV national Strategic Plan, including preparing presentations on the draft NSP elements;

- development of the final version of the NSP

- development of the detailed budget of the NSP with clearly identified funding sources based on  the National HIV Program Gap analysis and GF Program sustainability and transitioning needs;

- Development of the National HIV Programme M&E framework

It is envisaged that NSP development implies the following phases:

Phase I

Elaborating time-bound workplan (WP) outlining the NSP development;

Prioritizing and defining the NSP  directions/areas in collaboration with the National Experts and key stakeholders;

Elaborating outline of the NSP, based on the agreed directions/areas and the priority objectives.

Presenting outline to the PAAC and CCM for their approval

Phase II

Elaborating NSP draft which should include (a) gaps analysis for each area (b) specific objectives and targets (c) effective activities for meeting those targets (d) implementation arrangements (responsible enitities, and their role during the transition phase and beyond) (e) cost estimates and distribution of funding between the State and the GF (f) monitoring and evaluation framework.

Presenting the draft to the PAAC and CCM for the review and feedback.

Phase III

Finalizing the draft NSP along with a detailed budget.

Present the final version to the PAAC and CCM for their review and approval.

Special Provisions

NSP development process shall be carried out with maximum participation of all key stakeholders, including government and non-governmental entities, KAPs and PLWD.

The special thematic working groups may be established to work on each functional area of the NSP supported by the National Consultants through the organization of the well-documented meetings based on the pre-approved schedules; The WGs should engage  the entire stakeholders, including GoG, NGOs, CBOs, subject-matter experts, etc. in the process through presentations and roundtable discussions;

During the all stages of the end-product development, the selected consultant shall work in close cooperation with the National Experts, Country Coordination Mechanism (CCM) and Policy, Advocacy Advisory Council (PAAC) under the auspices of CCM;

The cnsultant will assist CCM in facilitating discussions with the Ministry of Labour, Health and Social Affairs and the Ministry of Finance, as well as in communicating the additional TA needs and other challenges of the sustaimability and transition to the State Funding.

the  consultant will be also responsible for:

Recruiting additional expert , if needed (with no additional cost for the PR).

Key Deliverables/timelines

| # | Deliverable | Deadline for Submission |
| --- | --- | --- |
| 1 | Phase I Time-bound work plan for development of NSP agreed with PAAC and agreed with CCM; NSP Outline, including priority objectives according to each direction; | 2 weeks from contract signing Maximum allocation 10% of total budget |
| 2 | Phase II Draft NSP including the gaps analysis per priority areas, specific objectives, targets and activities, responsible entities, detailed draft budget with indication of the unit costs, costs per activities per quarters, funding sourses (GF vs. State, remainings gaps) and monitoring and evaluation framework. | 12 weeks from contract signing Maximum allocation 40% of total budget |
| 3 | Phase III Final NSP with a detailed budget and M&E framework | About 16 weeks from the contract signing (but no later than July 1, 2018) Maximum allocation 50% of total budget |

Qualifications

A consultant is required to have:

Professional Experience:

- At least 8 years professional experience in strategic planning and monitoring-evaluation of large programs in the field of HIV/AIDS or other health sector;

- Expreinace of working with the GF or WHO will be an asset

Education

- PhD or Master degree in public health, development, or social sciences;

- Excellent skills in:

Strategic analysis and planning;

Facilitation skills and effective communication with multiple stake-holders;

Multitasks and multi-stakeholders’ coordination under tight deadline;

Team work and consensus building ;

- Strong strategic information and M&E expertise in particular related to HIV key affected populations; - Good knowledge of HIV epidemiology in Georgia and its response to HIV;

- Excellent command of English, written and spoken, as a significant work of writing is expected as well as coordination with English-speaking sub-recipients, bilateral and multilateral partners and the CCM.

Supervision

The Consultant will be directly supervised by the NCDC in terms of contract administration  and  payment. All deliverables will be revised and approved by the CCM based on the PAAC recomendations.

Indicators for evaluation

Performance indicators for evaluation:

Quality and timeliness of deliverables

Pre-requisite for PR to accept the deliverables, consultant is requested to obtain written consents from the CCM related to:

NSP  outline

Draft HIV NSP with a detailed draft budget file

Final NSP  document.

Contract arrangements

Duration of the assignement is 4 months, subject of extension until the end of the year or any other arrangements to be agreed with the GF;  payment will be made per phase outlined above.

NCDCPH (PR) will provide the necessary background information and documents articulated in the Annex 1 of the ToR

How to apply

A Consultant interested must provide:

Documents certifying the above qualification requirements (implemented programs, published NSPs, researches/evaluations, policy documents, etc.);

CV

Proposal articulating methodologies of the end product development and time-bound proposed implementation plan;

LOF and dayly rates (proposed dayly rates should be proved by the previous contractual agreement documents)

The most recent product produced for the GF or WHO, if any;

Estimated budget (in GEL) split by LOF per phases.

Making the end of AIDS real: consensus building around what we mean by “epidemic control” — a meeting convened by the UNAIDS Science Panel — Glion, Switzerland, 4–6 October 2017

UNAIDS, HIV Prevention 2020 Road Map — Accelerating HIV prevention to reduce new infections by 75%

UNAIDS Strategy 2016-2021

WHO, Global health sector strategy on HIV, 2016-2021