Responsible Party Narrative Progress Report: (reporting period d/m/year - d/m/year)

| Project Title: | Unite to Fight Violence against Women |
| --- | --- |
| Project No: | 00098242 |
| Budget Department: | B5125 |
| Business Unit: | GEO30 |
| Implementing Agency: | UN Women |
| Responsible Party: | THE STATE FUND FOR THE PROTECTION AND ASSISTANCE TO THE (STATUTORY) VICTIMS OF HUMAN TRAFFICKING |
| Date: | 30 – Nov - 2017 |

Outcome 3.1: Enabling environment to eliminate violence against women and girls, especially sexual and domestic violence, created in Georgia

Output 3.1.2 Capacity of key policy and service delivery institutions strengthened to promote and protect women's human rights to life free from VAWG, including DV Indicators:

| Activity 3.1.2.15 to support the State Fund to undertake procurement processes for the establishment of additional DV shelter/s ( Project activities: 1.2.6. To support the State Fund in the development of two violence against women and domestic violence crises centers in Guria and Qvemo Qartli Regions of Georgia; 1.2.7. To support the State Fund in the development and implementation of socio-economic rehabilitation programme for the vitims/survivors of domestic violence) Indicators: - Number of recruited staff – 0 - Number of thematic trainings held - 0 - Number of staff trained - 0 - Number of crisis centers/shelters established - 0 - Number of beneficiaries supported by crisis centers/shelters - 0 - Number of thematic meetings held in target municipalities - 2 - Number of beneficiaries supported with vocational education -3 - Number of consultation meetings held on economic rehabilitation program/guidelines - 4 - Number of inventory purchased - 0 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Milestone | Milestone Target Yes/No or a number of percentage as relevant to the indicators above | Progress Describe progress with a focus on the achievement of specific results contributing to the above activity, output and outcome and their indicators as relevant. Break down beneficiaries by sex, where relevant | Total cost of the activity in GEL | Highlights Challenges faced in implementation; any lessons learned; other considerations and cross-cutting issues pertinent to the results being reported on; key partnerships and inter-agency collaboration impacting results |
| Identification and registration procedures for office space for crisis centers (Guria and Qvemo Kartli regions) |  | The opening of Crisis centers in Guria and Qvemo Kartli were planned in 2018. All the related procedures regarding the identification and registration of the office space will start in November, 2017. |  | N/A |
| Training for 25 employees of Crisis Center (e.g. psychologist, lawyer, social workers, hotline operator, etc.) |  | After the social-economic rehabilitation program will be done by the expert, the related training will be conducted for 25 employees of the Crisis Center (e.g. psychologist, lawyer, social workers, hotline operator, etc.). The aim of training will be to introduce the social-economic rehabilitation program and its guidelines. The training will be conducted for the staff after opening of regional Crisis Centers in 2018. |  | N/A |
| Develop an economic rehabilitation program/guidelines |  | One of the challenges of the victims of violence, especially women is economic strengthening. Achieving economic independence for women is of vital importance for their economic strengthening and stability. In view of that, it is very important to support them in obtaining professional education opportunities and provision of employment support services. Establishing of socio-economic rehabilitation program for the victims of domestic violence, will support to eliminate the domestic violence. It is essential to elaborate the guidelines of the economic rehabilitation program. Based on above mentioned. ToR for the expert has been elaborated. The local expert has been hired on September 7.2017, meetings conducted with Labour Policy Department of Ministry of Labour, Health and Social Affair, Employment Programme Department of Social Service Agency, Atipfund, shelter and crises center staff. Developing of economic rehabilitation guideline will be finalized by the end of November, 2017. The guideline will consists with following components: Analyses of International best practices (example of minimum two countries), assessment of skills and capability of beneficiaries and perspectives of their employment at local market, development of individual professional and personal profiles, elaboration of professional development plans and strategies of beneficiaries, beneficiary development systems and opportunities, communication with employers, communication and adaptation system, linkage with Employment Program Department of Social Service Agency (SSA) (Worknet, Coaching, VET, etc.). The payment will be made after handover. |  |  |
| Needs assessment of beneficiaries |  | During the reporting period 20 beneficiaries of shelters and crisis center were interviewed by local social workers and shelters/crisis center managers. The subject of interview was the interest of the beneficiary regarding desirable working place and additional vocational training for future employment. Based on the outcomes, received from the managers, Atipfund conducted market research in Vocational Education Colleges in relevant regions. |  | N/A |
| Five roundtable discussions and meetings with local businesses and other employers. |  | Roundtable discussion with business representatives will be held after completion of economic rehabilitation program together with Employment Program Department of SSA. |  | N/A |
| Funding individual vocational education courses for 3 beneficiaries |  | The tender was announced for vocational education course of Culinary chef. The contract was signed and 3 beneficiaries applied for course and received certificate. | 7299 | All announced tenders failed. Successful candidate were not identified. About of 6 tenders, which was announced twice only one tender was successful. The remaining tenders failed due to lack of interest from participants. The process showed us that creating parallel employment program for victims on the basis of Atip fund will not be sustainable and successful and showed the necessity of integrating victims employment strategy into existing Employment Program Department of SSA and creating guidelines of cooperation between Atip fund and SSA. |
| Develop social rehabilitation guideline and assessment tools for beneficiaries |  | The contract was signed with Georgian Association of Social Workers (GASW) to develop social rehabilitation guideline. The process entails: Development/improvement of social service provision forms for all rehabilitation stages, provision of effective social rehabilitation service, development of rehabilitation services (rehabilitation modules) based on beneficiary needs, training of social workers(total 36 sessions), training of multidisciplinary group and development of social work supervision concept. The process will be finalized by the end of December, 2017. At this moment 75% of total amount was paid. | 26192 | N/A |

Attachment: A Human Story – describing the work and results/change in the life of a project beneficiary

The story has to demonstrate how UN Women / Responsible Party is working to change a life of a women or a community. The story should be easy to understand for a wide audience and should strive to illustrate our impact and results!

Pitching stories: Writing a good web story takes time, research and involvement in the editing process. Feel free to first pitch a story idea to UN Women Communications Specialist, before writing. Send ideas in one paragraph to Gvantsa Asatiani, Gvantsa.asatiani@unwomen.org with a copy to UN Women Component Manager Irina Japharidze, irina.japharidze@unwomen.org and UN Women Project Analyst Tamar Vashakidze, tamar.vashakidze@unwomen.org

Audience: general public, students, academics, UN and other stakeholders and media. It may also be used for outreach to donors, media talking points of examples of our work, and other purposes.

Length: Aim for 500 words; the maximum is 750.

Story structure: Tell the personal story of an individual or community following the ‘issue, action, impact’ model of storytelling. In other words, explain the problem, what is or has been done about it, and what concrete impact that has had. Show how a specific activity has improved women’s lives. Many readers won’t get past the first paragraph so you need to grab the reader’s attention. Often you can start with a vivid quote or telling vignette from your protagonist – the human face of the story.

Results: Aim to showcase impact and results! Illustrate how we have helped change something for the better. Whenever possible, provide recent statistics or quantitative figures. Remember to cite sources (prefer research by the UN or Governments, and reputable academic or NGO sources) and include links. Also use qualitative evidence, such as quotes from experts or officials or examples of concrete changes in the lives of your protagonists.

Mentioning donors: We have to mention project or programme donors, so please indicate the UN Joint Programme name and funding source.

Voices: Aim for two-to-three great quotes from different people (always include at least one person directly affected by our work, plus other ‘experts’ including partners or NGOs, government.

Write for a global audience: Italicize any non-English words and explain them. Tell us where a community is located (north-east, southern highlands, 190 km west of the capital) and describe the geography and customs in a colourful, non-judgmental way.

Examples of good human interest feature stories:

In Ethiopia, church bells ring for women and girls

Sharp increase of women voters in Pakistan’s recent elections

New law in Kyrgyzstan toughens penalties for bride kidnapping

Survivors’ stories: Survivors of violence often take great risks when telling their story, to their personal safety or to their family. At the same time, they are very powerful and can illustrate impact. When interviewing survivors, make sure they truly understand and consent to their story being told to a wide audience. If they agree, but any potential

safety risk exists, we must ensure they are not identified, so use an alias and avoid mentioning specific place names. If they want to use their real name, they must give consent. See photo guidelines and consent forms for photographing survivors, children and minors.

Examples of stories with identified and non-identified survivors: Healing unseen wounds in Mogadishu

Breaking the silence: Survivors of violence tell how they used their experience to enact change

Photo delivery

All features and news stories should be accompanied by a strong and relevant photograph – ideally of the person/people featured in your story. A compelling photo tells a story, shows an action and/or evokes an emotion, in addition to being well-framed and in good resolution.

Captions and credits: Captions should tell the reader what is going on in a picture, and not just describe the obvious. Every photo must include a caption that is:

- a full sentence,

- includes a location, date, description of what's happening in the photo and names/titles of any key individuals (if relevant).

* They must also include a photo credit with the photographer's name.

Ex: Pakistan’s President Asif Ali Zardari became the one millionth signee in his country’s One Million Signatures campaign to end violence against women during a ceremony at Aiwan-e-Sadr on 27 July 2012. Photo credit: UN Women/Catianne Tijerina.

Format and delivery: Photos should be submitted in .raw, .tiff or .jpeg format, in the highest resolution possible (minimum 300 dpi at 2 MB or more). Don’t crop or compress before sending. Photos should be submitted either as email attachments or via www.wetransfer.com to Communications Specialist Gvantsa Asatiani, Gvantsa.asatiani@unwomen.org).