Dear Graeme,

The “Harvoni” registration process in Georgia has been accomplished. Also please be kindly to give us instruction about empty bottles of Sovaldi. (Because patients bring empty bottles back to clinics and these empty bottles are kept in clinics).

Furthermore we are sharing feedback on ongoing processes: everything is well without problems and delays.

As you may recall With technical assistance of CDC Atlanta the Ministry of Labour, Health and Social Affairs of Georgia has monitoring group which is dedicated to control the process, including assessment of implementation of Phase 1 hepatitis C elimination program: visits to the service providers, double-check of information in the electronic system, request of related information and documentation if necessary.

There are some most commonly reported challenges: 1) Need to case management supports in addition to the review of internal committee; 2) need for more specific guidance in treatment guidelines for regimen selection; and  3) need for additional provider sites to reduce wait times and ling lines at some sites.

To resolve above mentioned problems first of all ministry hopes to receive technical assistance from L.I.F.E.R to develop and implement a platform that can be leveraged to enhance the delivery of hepatitis C specialty care in Georgia.  Project will assist in achieving the goals by creating a community of practice among clinicians Georgia who are working to eliminate Hepatitis C, facilitating joint learning and peer problem solving, and supporting access to expertise and best practices and approaches. Also the purpose of this project is clarification of treatment guidelines and provider education which will also be very helpful.

To resolve third problem additional sites were added in regions in Rustavi (1) and Gori (1) bringing the total to 11 (Tbilisi 4, Batumi 1, Kutaisi 3, Zugdidi 1). Also services which are provided in the framework of program are delivered to prisoners and patients with co-infection HIV/HCV.

With assistance of CDC ongoing monitoring and evaluation is conducted through STOP-C data system. Assessment of additional provider and laboratory sites is ongoing; with technical support of CDC MOLSHA is developing monitoring and evaluation framework for the whole project.

We continue to make improvements based on findings of weekly analysis.

Also we had trainings on Safety Information Reporting and we’ve already provided this training about safety information to Sites to know how to report safety information to you.

Also long term action  plan outline developed and agreed upon by NCDC elimination planning lead of workgroups first draft is ready to receive input on draft elimination plan, including priority activities, indicators, and elimination goal.

MOLSHA is preparing for external TAG meeting. Goal of meeting is to identify key HCV prevention and control strategies and elimination goals, review Georgia’s current hepatitis C epidemiology, surveillance, prevention and control activities.  To establish HCV elimination goals, including impact goals (e.g., mortality, incidence, prevalence), to make recommendations on priority activities to reach elimination goals also advise on ways to address challenges and barriers in program areas and activities, provide guidance and propose mechanisms for partnerships and resource mobilization in support of the HCV elimination program Monitor program activities and progress toward the achievement of elimination goals.

Early Results from Georgia’s HCV Testing and Treatment Effort

As of September 17th, 2015, among 12070 persons with a positive HCV test result presenting to one of the selected eleven sites for treatment evaluation; of those, 4020 have completed evaluation and awaited case review by the HCV Elimination Program Treatment Inclusion Committee. The committee, comprised of clinicians, representatives of patient advocacy groups, and media, reviews each case (de-identified) for determination of treatment eligibility, appropriateness of provider-recommended regimens, and equitable access to treatment, the committee has given approval to 3766 patients in total, to begin a therapeutic regimen;. As you may recall the main reason of difference between number of persons with a positive HCV test and the proportion of people who have started treatment, suggests that they have low level of liver damage (for example F1 or F2) and or they are still undergoing diagnostic tests.

Elimination program Report

Tbilisi, 17 September 2015

- Total number of registered patients: 12070,

  - Amongst the registered patients total 3766 patients are granted access to the program:

    - 3023 Patients have already started treatment. Amongst them Patients, among these patients 383 already completed treatment.

- Decisions of the Commission:

  - On 07.05.2015 first commission reviewed total 35 applications and 32 were granted access to the program (one patient got ill and was not able to go the service provider).

  - On 21.05.2015 second commission reviewed total 369 application and 361 were granted access to the program.

  - On 09.06.2015 third commission reviewed total 503 application and 468 were granted access to the program.

  - On 01.07.2015 fourth commission reviewed total 620 application and 606 were granted access to the program

  - On 17.07.2015 fifth commission reviewed total 570 application and 560 were granted access to the program

  - On 07.08.2015 sixth commission reviewed total 1055 application and 996 were granted access to the program

  - On 17.09.2015 seventh commission reviewed total 754 applications 743 were granted access to the program

- Total number of disbursed medication:

  - To service Providers: 8462

  - Remaining in central stock: 9235

Some of these patients are duplicate revised and reviewed second time (because sometimes they are required additional documentation)

Data is collected on 17th of September.