We would like to share ongoing activities for June 2017

26th Meeting of the International Task Force for Disease Eradication was held at The Carter Center on June 20, 2017 Dr. David Sergeenko presented Progress toward Hepatitis C Elimination in the Country of Georgia.

PR Company has been launched and is very actively spread. Strengthening PR activities for raising awareness is currently in the top priorities. Activities are broadcast by media on TV shows. We have already had screening activities at the Parliament of Georgia, Ministry of Justice, we are Coordinating with other public stakeholders as well as private sector. On July 28th for World Hepatitis Day 2017 we are organizing big event.

Also representatives from neighbor countries are planning to come to Georgia for study tour in terms of HCV elimination project.

As you may recall we’ve already sent Sovaldi to Belarus Government and 3 000 bottles to and to Government of Armenia 1500 bottles. Armenia has already started treatment. (Information about stock is below).

Also “Zepatier” will be introduced shortly maybe in the beginning of July. It took so long because of some technical issues. In the framework of an agreement Zepatier will be donated for all patient on Hemodialysis, but initially it will be introduced for limited number of patients. 150 bottles for 50 patients are ready to be sent to Georgia.

Committee specially dedicated for development and implementation of C Hepatitis elimination strategic plan discussed and agreed that inclusion criteria for those 50 initial patients will be same as in the first phase of project (f3, f4) besides the patient with decompensated cirrhosis (in those Zepatier is contraindication).  And committee members (clinical committee) already revised guidelines in these terms and added regimens with Zepatier.

Almost all the data about screened people from the launch of the program is entered to screening module which will be connected to treatment module and we will have detailed information about care cascade.

There are discussions about HCV core Ag to use it as a serologic marker of HCV infection In Georgia, (as you may recall we’ve received recommendation from TAG and scientific committee). As for evaluation of the agreement between HCV core Ag and HCV RNA for confirmation HCV active infection in anti-HCV screening positive population, was conducted in May-June 2016. Overall agreement between HCV RNA and HCV Ag was 98.5% (Presented at the TAG meeting in October 2016). The first benefit is that it might be cost-effective to use.

## Hepatitis C Care and treatment Cascade, Georgia, April 2015 – June 2017

Up to date from the beginning of program almost 40 000 registered and of those almost 39 000 have already started treatment, of those more than 30 000 completed treatment. SVR was was achieved in 98% of cases in regimens with Harvoni.

As for number of screened it is more than 700 000.

Total number of disbursed Sovaldi bottles: 39 478

To service Providers: 34 559

To Belarus: 1 500

To Armenia: 3 000

Remaining in central stock: 419

Total number of disbursed Harvoni bottles: 128 440

To service Providers: 94 808

Remaining in central stock: 33 632