Elimination program Report JUNE 2016

We will briefly review ongoing processes in current month.

First of all in June 10th we have removed inclusion criteria and expanded treatment and currently we treat all the patients with Hepatitis C. Also we’ve opened of HCV management center in Tbilisi in June 10th. As you may recall center will manage the flow of patients accordingly in parallel each clinic will receive the number (the list) of patients in advance every week, which they are considered to manage, and the program will automatically sort out the patients who have completed their diagnostics and are ready to start treatment. Also managers in center are and will be checking (comparing with scanned documents) and filling out if required all fields in database, including, risk factors, co-morbidity and etc.

Currently the process itself goes very well organized additionally with the help of a new data management system to collect demographic, diagnostic, clinical, and pharmacy data on patients registered for treatment in order to accommodate the increased demand for treatment.

Also Symposium on HCV Elimination Program for Georgia took a place on June 18, 2016 regarding National Guidance and Education Advisory Program. Chairs of meeting were Drs. Nezam Afdhal and Stefan Zeuzem. Objectives of meeting were to incorporate new therapies into the care of patients with chronic HCV, Incorporate improved processes for HCV screening and diagnostic testing into clinical practice. Additionally to outline how the Project ECHO model for expanding specialty care knowledge to community clinicians can aid them in treating HCV patients and describe the progress of the Georgia HCV Elimination Program.

David Sergeenko, Amiran Gamkrelidze, Valeri Kvaratskhelia, Tengiz Tsertsvadze, Drs. Nezam Afdhal and Stefan Zeuzem and other were among presenters. The meeting went extremely well and was very fruitful. Below you can see link with presentations currently we are looking forward to Project ECHO’s and LIFERS recommendations.

https://www.hightail.com/download/cUJYV296VEhtMExtcXNUQw

Also CDC is planning to release MMWR for the World Hepatitis Day. We’ve already received MMWR draft from CDC and sent our comments as well.

As for long term elimination plan, CDC promised that we will receive comments from them soonest though CDC will continue to line edit and format the elimination plan with the help of their writer/editor; this draft will be for English language version of plan to be ultimately endorsed by GOG and CDC and to be shared with international community.

Also Oversight Committee:  GOG, GS, and CDC first meeting is planned 30th of June, we are looking forward to this call.

To facilitate coordination of data and management of this data, we are planning to establish a Scientific Committee within the project.

As for results:

Hepatitis C Care and treatment Cascade, Georgia, April2015 – June 2016

Total number of registered patients: 30 000 are Anti HCV positive, those total 26 000 are HCV RNA more than 14,000 completed HCV diagnostic work up, obtained necessary documentation, and await case review.

More than 13,000 patients are granted access to the program among these patients, more than 6,700 completed treatment. Of those approximately 4,600 are SVR eligible and SVR is achieved in 83-84% of these patients.

- Total number of disbursed Sovaldi bottles: 34596

  - To service Providers: 32109 boxes

  - Remaining in central stock: 2487

- Total number of disbursed Harvoni bottles: 47000

  - To service Providers: 8949 boxes

  - Remaining in central stock: 38051

Data source: Georgia MOLHSA