Elimination program Report March 2016

From March we’ve already started treatment with “Harvoni” and launched second phase though we are still considering those who have severe liver disease and meet criteria for the first phase of Hepatitis C elimination program. We plan to expand criteria gradually though we will consider those who have severe disease, extrahepatic manifestations and etc as priority group.

Also we are opening the service agency in Tbilisi and in near future in Zugdidi, which will be dedicated for screening, management of patient flow and other related activities, we’ve decided to open Agency because of increased demand for treatment and big flow of patients, in parallel we are developing new electronic program in spite the current stop C that has been sufficient to capture the pilot phase, structure of the system presents significant challenges and requires revision our new IT person is already developing program and it’s almost done we are planning to conduct trainings on new stop C and before that to have final presentation of system.

Also in April 6-8 we’ve planned to conduct 3rd national workshop in close collaboration with CDC, WHO, Global fund, and others. The main purpose of workshop is to presents results from seroprevalence survey (with preliminary results  7.5% of Georgia population is Anti HCV +, as for 5.4% of those are HCV RNA + which results approximately 150,000 people living with HCV.

Additionally as you may recall we have side session and presentation at EASL conference on April 14th. EASL organizers offered Georgia to present progress towards HCV elimination in Georgia. This session is high level and is great opportunity for us to highlight the achievements that we’ve already achieved. Also we have Side session which is also very great to share the process in more depth including topics mentioned above.

Country has necessary infrastructure, technical and human capacities to provide quality treatment and care services A total of 93 physicians are involved in the Phase I of the program though we have additional resources including:

| Number of Physicians Licensed to Treat Hepatitis C |  |
| --- | --- |
| Infectious Diseases Physicians | 489 |
| Gastroenterologists | 124 |

These are results for patients treated with Sofosbuvir for the first phase of program:

22,063 patients presented to clinics, Anti HCV positive, of those 17,830 are HCV RNA +, 5.,955 patients started treatment, of those 3416 completed treatment, 2330 are ongoing treatment and 209 didn’t complete treatment due to different reasons including:

209 patients

14

121

Death

Adverse

events

9

Self

discontinuation

5

Lost to

Follow-up

2

Physician

stopped

58

Disease Progression

3,416

patients

1,073

Complete SVR Data

2,343

SVR Pending

SVR:

900 (83.9%)

No SVR:

173 (16.1%)

SVR12 Eligible: 470

SVR12 Not Eligible: 1,873

Some of them evaluated for SVR12 but data not entered into STOP-C

Hepatitis C Care and treatment Cascade, Georgia, April2015 – march 2016

Total number of registered patients: 24667 are Anti HCV positive, among the registered patients total 20,578 are HCV RNA + approximately 8593 meet criteria for inclusion for the first phase, completed HCV diagnostic work up, obtained necessary documentation, and await case review.

7281 patients are granted access to the program among these patients, 6,000 started treatment. SVR is achieved in 87%

Total number of disbursed Sovaldi bottles: 33596

  - To service Providers: 29049 boxes

  - Remaining in central stock: 4547

- Total number of disbursed Harvoni bottles: 2000

  - To service Providers: 798 boxes

  - Remaining in central stock: 1202

Data source: Georgia MOLHSA