## State Fund DIP (2018)
Project Title: | UN Joint Programme for Gender Equality (Sida pass through UNDP)
Project No: | 00098242 -EVAWG Enabling Environment
Budget Department: | B5125
Business Unit: | GEO30
Implementing Agency: | UN Women
Outcome 2: | Enabling environment to eliminate violence against women and girls, especially sexual and domestic violence, created in Georgia
Responsible Party: State Fund for the Protection and Assistance to the Victims (Survivors) of Human Trafficking (State Fund) Detailed Implementation Plan 2018
Outputs | Activity | State Fund Milestone | Jan | Feb | March | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Output 3.1.2. Capacity of key policy and service delivery institutions strengthened to promote and protect women’s human right to life free from violence, especially from sexual and domestic violence | Activity 3.1.2.6 To support the State Fund to establish specialized services for victims/survivors of sexual violence; | Organize 2 trainings: 1.Training on Sexual Orientation and Gender Identity for the employees of crisis center and shelters. 2. Training on Gender Issues for lawyers and hot line staff. | bar: Jun; Oct
Printing brochure and posters on sexual violence issues | bar: March
Broadcasting video clip on the sexual violence issue on media | bar: March to Dec
| Activity 3.1.2.7 To Support provided to the State Fund to establish additional shelter or crisis center in Batumi for DV victims/survivors; | Renovate crisis center in Batumi | bar: Apr to Jul
Purchase furniture and equipment for crisis center | bar: Jun to Jul
Purchase technical equipment for ?????? | bar: Jun to Jul
Name:
Title | Director