State Fund for the Protection and Assistance to the Victims (Survivors) of Human Trafficking (State Fund)

Responsible Party Progress Report to UN Women

| Project Title | UN Joint Programme for Gender Equality |
| --- | --- |
| Project Number | 00098242 –EVAWG Enabling Environment |
| Donor Reference | 11278 |
| Project Duration | 16 November, 2015-31 December, 2020 |
| Reporting Period | January – March, 2018 |
| Geographical coverage | Georgia |
| UN Women Georgia Strategic Note 2016-2020 Impact area | UN Women SN Impact Area 3 |

| Project Outcome #: 2 | Enabling environment to eliminate violence against women and girls, especially sexual and domestic violence, created in Georgia |
| --- | --- |
| Project Output #: 2.2 | Capacity of key policy and service delivery institutions strengthened to promote and protect women’s human right to life free from violence, especially from sexual and domestic violence |
| RP Approved Budget (as per PCA or LoA) | 200,000.00 USD |

I. Purpose

Project Information (word limit: min 250 – max 500 words)

In this section, please describe the rationale of the project, including: - expected results Outcome2: Enabling environment to eliminate VAWG, especially sexual and domestic violence created in Georgia - Output2.1: National laws and policies on VAWG, especially on sexual and domestic violence improved in line with international commitments (DEVAW, CEDAW, BPfA, Istanbul Convention) - Output 2.2 Capacity of key policy and service delivery institutions strengthened to promote and protect women's human rights to life free from sexual violence, VAWG and DV - Output 2.3: Public awareness raised to support prevention and disclosure of the instances of VAWG and DV - reference to how the project aims to support national gender equality and women’s empowerment goals and priorities The joint programme directly supports further realization of the women’s rights and gender equality commitments undertaken by Georgia at international as well as national levels and intends to upscale results achieved by the country with the support of the international community, including UN agencies, in the area of gender equality and women’s empowerment through innovative initiatives. The UNJP is fully aligned with national priorities in the area of gender equality and women’s empowerment and the stated goals and priority areas of UN Partnership for Sustainable Development for 2016-2020 (UNPSD Outcome 2: focus area 1 - democratic governance and Outcome 4: focus area 2 - Jobs, Livelihood and Social Protection), as well as the Results Strategy for Sweden’s Reform Cooperation with Eastern Europe, the Western Balkans and Turkey (2014 – 2020). The Programme is further in line with Georgia’s commitments under nationalized Sustainable Development Goals (SDGs), especially with Goal 1 (target 1.4), Goal 3 (targets 3.1 & 3.7), Goal 4 (targets 4.3.a and 4.7), Goal 5 (targets 5.1, 5.2, 5.3, 5.6 and 5.c) and Goal 16 (targets 16.1, 16.3, 16.7 and 16.b).

| II. Results |  |
| --- | --- |
| Project milestone/activity Indicators |  |
| In this section please provide an assessment of project progress as per the milestones/activity indicators defined in the Detailed Implementation Plan (DIP) and/or agreed with the UN Women project manager. |  |
| Sample indicators: | Progress against indicators: |
| A training on Sexual Orientation and Gender Identity for the employees of crisis center and shelters organized | Will be organized in September |
| The guideline on psychological rehabilitation improved by integrating specificities of rehabilitation of children as well as persons with disabilities | Will be carried out during the next reporting period |
| A crisis center in Batumi renovated | Will be carried out during the next reporting periods |
| Furniture and equipment for the crisis center purchased | Will be carried out during the next reporting periods |

| Milestone/Activity | Progress (word Limit: min 150 words – max 350 words per milestone/activity) |
| --- | --- |
| (Please insert milestones/activities per the DIP) | This section should highlight progress and results during the reporting period against the project milestones/activities. If producing a final report, a statement on the impact of the project should be provided. |
| Organize a training on Sexual Orientation and Gender Identity for the employees of crisis center and shelters | Will be organized in September |
| Improve the guideline on psychological rehabilitation by integrating specificities of rehabilitation of children as well as persons with disabilities | Will be carried out during the next reporting period |
| Renovate a crisis center in Batumi | Negotiations regarding allocation of relevant space for the establishment of a Crisis Centre in Batumi are ongoing. In March a High level meeting between the Minister of Labour Health and Social Affairs and the Chairman of the Government of Adjara took place where importance of Crisis Centre services for Adjara region was underlined and the Government of Adjara pledged to allocate space for the establishment of a Crisis Centre in the nearest future. |
| Purchase furniture and equipment for the crisis center | Will be carried out during the next reporting periods |

| Was the project completed per Budget during the reporting period? |  |  |
| --- | --- | --- |
| Planned Cost | Actual Cost | Variance (difference between planned and actual costs) |
| 6,150.37 | 6,150.37 |  |
| Please explain any variance in planned and actual expenditures |  |  |

What were the three main achievements/main challenges / lessons learned? This section should discuss the key implementation results and constraints / lessons learned in the reporting period (word Limit: min 150 words – max 350 words per achievement/ challenge / lesson learned)

- Identification of space for Crisis Centers in Batumi by local municipality proved to be a challenge

IV. Future Work Plan (word limit: min 250 – max 500 words)

Information in this section should include: - Priority actions planned for the following reporting period to overcome constraints, build on achievements and partnerships, and use the lessons learned; Improve the guideline on psychological rehabilitation by integrating specificities of rehabilitation of children as well as persons with disabilities; Organize a training on Sexual Orientation and Gender Identity for the employees of crisis center and shelters; Renovate a crisis center in Batumi - Indication of any major adjustments in the strategies, targets or key outcomes and outputs planned;

V. Feedback

We would welcome your feedback and comments on UN Women’s management, procedures and systems in relation to the project

VI. Annexes

Please list the annexes accompanying the report underneath the heading. All materials/information that are direct outputs of the project (for example: publications, studies, IEC materials, training reports etc.) should be attached to the report. Please note that there is no need to annex documents that are already attached to the financial report.