## Slide 1
Alignment Update
Strategy Retreat
January 9-10, 2014

## Slide 2: Most alignment activities complete
Systems and relationships to enable collaboration and pursuit of synergy now in place
Progress monitored through Quarterly Review and regular reporting
Work in progress will continue, but can be managed through the standard operating structures. All costs to be incurred by 31 March 2014 for final closure.
Ernst & Young Alignment Audit:
  Framework for alignment in-line with leading practices.
  Every element of leading practice in play.
  Recommendations: revisit strategy, update metrics, review lessons learned.

## Slide 3: Focus on synergy
Shift attention from operational alignment to growth, leverage and diversification
Determine strategic priorities
Pursue and test strategic priorities

## Slide 4: Finance
What was accomplished?
Development of a reporting framework that accommodates the differences between Australian Accounting standards (IFRS) and US GAAP.
Adoption of the Abt financial year.
Adjustment of reporting timelines and requirements to feed Abt reporting.
Alignment of Abt JTA professional services engagements in insurance, legal and accounting.
Successful management of transaction related activities including change management of completion accounts and change of company name and structure.
Work in progress?
Transfer Pricing - PwC, January 2014
Funding / Working Capital – Cash Forecast – Australian Aid, March 2014
Structure of Purchase funding – BDO, December 2013
Maintaining alignment?
Alignment will be maintained through the established regular reporting requirements. No additional meetings need to be scheduled.

## Slide 5: Human Resources
What was accomplished?
Created Director of Strategic Alignment and Alignment Manager position description
Create job description and roles/responsibilities for new positions at Abt Associates and Abt JTA
Relevant Professional Development /training plans are shared
Dual access to recruitment databases
Shared strategies around recruitment methodologies
Able to effectively share talent
Successfully completed intercultural training
Conducted ethics and compliance training
Work in progress?
Aligning Abt JTA online performance management system and competencies with Abt’s
Global cultural webinars to be used by all employees, and for onboarding/orientation
Processes and policies for sharing and seconding staff.
Maintaining alignment?
Weekly calls between Abt JTA GM HR and key HR team members at Abt

## Slide 6: Communications and Creative Services
What was accomplished?
Abt JTA marketing materials have been updated with the new branding
Infosheets, posters, banners and the company website have all been updated with the new branding. A revised brand guide has been developed and shared
The “All Abt JTA” email list is added to the master list for the Abt Associates bimonthly newsletter and all Abt JTA countries are added to Abt’s master list of countries for use in the annual review and other publications
Strategy in place for promoting impact coordinated with Abt Associates
Abt and Abt JTA present a coordinated brand
Abt JTA linked to Town Halls and CEO communications
Work in progress?
Planning and coordination in place around key external conferences and conference calendars
Established processes are in place for sharing good news stories, tweets, etc.
Maintaining alignment?
Ongoing communications between the Creative and Communications teams will be maintained with participation in the Abt monthly communicators meeting.
Marketing materials continue to be developed as required

## Slide 7: Business Development
What was accomplished?
Joint Abt/ Abt JTA Business Development Plan & Opportunity Bid List for Asia-Pacific
Monthly Collaborative Bid List meeting established including senior representatives across Divisions, GBDU and Abt JTA
Abt JTA business development system reviewed, compatible process model developed, and staff training conducted
Confirmed market positioning for Abt/Abt JTA and associated wording to be used in proposals and other formal documentation.
Aligned business development process models
Shared BD Opportunity Tracking and Website Monitoring Program Led by GBDU Team
Capability statements shared and utilised across Abt/Abt JTA
Work in progress?
All tasks have been completed.
Maintaining alignment?
Monthly joint collaborative bid meeting
Monthly sales report to GBDU
Quarterly sales report for inclusion in quarterly review
Coordinated go-no go decisions and resourcing and management of joint bids

## Slide 8: Information Technology
What was accomplished?
Change over of Email system
Videoconferencing successfully tested and used for key meetings/presentations
Establishment of positive ongoing relationships between IT departments
Work in progress?
Define collaboration workspaces
POC video conferencing system live
Share guidance and draft procedures for hosting Webinars, including GoToMeetings for screen sharing and Glowpoint for Town Halls
Maintaining alignment?
Alignment will be maintained through maintenance activities of aligned systems.

## Slide 9: Reputational Capital
What was accomplished?
Abt JTA has joined the global rep cap culture group, meeting times have been adjusted to welcome them to the group.
Abt JTA have been introduced to existing Methods Centers and Technical Working Groups. Interested colleagues are joining the email membership lists of all Centers and TWGs.
The technical awards (Clark Abt Prize for Outstanding Social Impact, Daniel Bell Award for Outstanding Social Science Research, and Best Scholarly Article.) are now open to Abt JTA colleagues.
RepCap professional development resources are being shared with AbtJTA’s Reputational Capital Coordinator, Emma Field on a regular basis. She is disseminating them.
Abt has obtained information about JTA employees (email address, bios, overall stats on work force) to try to tailor RepCap offerings
Abt JTA has joined the Quality Assurance Council.
Work in progress?
Identify Abt JTA’s approach to Quality Assurance.
Investigate Abt JTA project work has human subjects or sensitive data.
Develop a way to share knowledge assets in TLDB.
Maintaining alignment?
Abt JTA staff will provide input, suggestions, and requests into the activities of the Centers and TWGs
Metrics collected and shared (involvement, satisfaction and relevancy)
continue to identify and remove barriers to collaboration

## Slide 10: In conclusion
Alignment laid the foundation for collaboration
Remaining alignment tasks to be completed this fiscal year
Focus shifting to synergy and strategic opportunities
Need to identify and pursue strategic priorities