Monthly Progress Report

USAID Health System Strengthening Project (HSSP)

January 2013

Progress on Project Implementation Activities:

| Objective 1: Strengthen Insurer Capacity to Provide Quality Health Insurance |  |
| --- | --- |
| Activity Area | Progress Report |
| Activity: Development and roll out of professional trainings and knowledge exchange to address capacity building needs of health insurance companies | Progress this month: Georgian Insurance Association (GIA) Grant Proposal pending USAID approval. |
| Activity: Enhance health insurance literacy and support the expansion of the voluntary health insurance market to cover those currently uninsured. | Progress this month: Georgian Insurance Association (GIA) Grant Proposal pending USAID approval. |
| Assist in enhancing private sector delivered and non-state funded health insurance | Progress this Month: None, since the future of the State funded private health insurance sector is only assured till the end year 2013 and the Ministry of Labor, Health and Social Affairs (MoLHSA) is considering overhaul of healthcare system as a result of the recent change in government. As per Government’s plan, the roll-out of the new health insurance program expected from March, 2013. No more details available as of this reporting period. Next Steps: Keep on discussion with the MoLHSA and USAID |

Objective 2: Strengthen provider capacity to manage and deliver quality health care services

| Activity Area | Progress Report |
| --- | --- |
| Activity: Build / strengthen capacity of associations in health care to help their members develop capabilities to deliver higher quality health services and better customer experience | Progress this month: The Code of Doctor’s Professional Conduct: No major progress was demonstrated in this area, due to the shift of resources to respond to MoLHSA’s ad hoc requests. However, activities shall resume from March-April 2013. Next steps: The Code of Doctor’s Professional Conduct : Communicate with Geo-Hospitals and My Family Clinic, the largest health provider networks, to discuss the plans for dissemination and implementation of the Code of Doctor’s Professional Conduct. Begin design of e-certification for Doctors Code of Professional Conduct. |

| Objective 3: Strengthen Government Capacity to Guide and Monitor Health Services |  |
| --- | --- |
| Activity Area | Progress Report |
| Activity: Work with MOLHSA and other stakeholders to develop a Health Management Information System (HMIS) | Progress This Month: Beneficiary Registration Modules (former Ambulatory Module) At the end of the current reporting period, all the modules under the Ambulatory direction, namely: General Outpatient Care, Rural Doctors Program, Dialysis and Psychiatric Care Programs are fully operational. The HSSP team provides implementation support services as required. Case Registration Module During January, the team continued working with the US Embassy Defense Threat Reduction Office Georgia (DTROG) and its implementing partners to set-up the information exchange channels between the HMIS Case Registration module and Electronic Integrated Disease Surveillance System (EIDSS). Partners held number of meetings and conference calls to agree information exchange methods on a technical level. As of the end of the reporting period, connection is established and information exchanged. Consequently, as soon as the case is initiated in the HMIS Case Registration module it is automatically transferred to the EIDSS. In overall, this connection shall add extra value to the EIDSS in terms of filling in the gap of case registration, capturing electronic data from the very first source, eliminating reporting errors and minimizing the reporting time due the automatic transmission of information. Medical Mediation Module Functional improvements and updates were completed. The module is fully operational and in use. However, as per request from the Medical Mediation Service, several new functionalities were added to the system, namely: upgrade of complaint registration and analysis section, enabling higher flexibility in terms of case analysis and settlement. Reporting Module During the current reporting period, the team continued working on expansion of the Reporting Module to other areas, such as: healthcare providers and the National Center for Disease Control and Public Health (NCDCPH). NCDCPH: HSSP finalized the development of new reporting forms with relevant validation functions. The system is under testing by the NCDCPH. New validations shall ensure health providers submitting reports easily, on time and with highest accuracy. Healthcare Providers: Information exchange channels between the Reporting and Financial (and Billing) modules are set-up and will be used as soon as the Financial and Billing Module is launched. This mechanism shall act as the conduit and validation of the information submitted by healthcare providers through the Reporting Module. Consequently, up to 50 different reporting forms were created for this purpose. All forms are equipped with so called validation function and are being tested for the moment. All abovementioned, enables automatic transfer of information regarding the services rendered to patients into the Financial and Billing module, that it turn determines the amount to be reimbursed to healthcare providers rendering the medical service. This scenario ensures simplicity of reporting and accuracy of data submitted by a provider; reduces errors due to manual entering; minimizes information exchange time among different entities and provides capabilities for real-time analysis. Immunization Module Beneficiary and clinical case registration components of the Immunization Module are completed. The module is currently being tested by the NCDCPH. Stock Management Module The stock management module serves various purposes: manages vaccine stocks at central and district levels; also, the stocks of various consumables for EDP (Especially dangerous pathogen) and other labs. Module specifications and functional requirements were agreed among the NCDCPH and DTROG implementing partners, represented by the CH2MHILL. By the end of January, the module went into the software development stage. The stock management module shall be housed at the National Center for Disease Control and Public Health. User Management Module In the month of January the pharmacy and healthcare network information portal (provider profiles) was completely integrated within the User Management Module, including the determination of access/authorization rights. Consequently all medical providers are equipped with usernames and passwords in order to manage and update their information on a regular basis. Reporting component of the Financial and Billing Module was also incorporated into the User Management system. The latter, is currently being tested to prevent user access problems in future. Pharmaceutical Modules E-Prescription System Development of basic functionalities of the module is completed and ready for testing; however, implementation/testing still pending and waiting for a political decision. Pharmacy Database Pharmacy database is completely deployed and operational. Team provides implementation support services, as needed. Electronic Drug Registry HSSP continued working on analytic and data processing interfaces, enabling retrospective analysis and corrections of historical data, which are being cleaned-up simultaneously. Great efforts were made to consolidate the pharmaceutical information from various sources (public web-site, internal excel based registries) into the Electronic Drug Registry, so to eliminate multiple information sources and streamline intradepartmental processes, by eradicating duplication/triplication of information entry. The key accomplishments in this regard are the following: migration of information from the public web-site and creation of a new view-page for departmental staff, largely pharmaceutical experts. Advance testing of the web-services between the Electronic Drug Registry and the Revenue Services/Customs Department moved to February/March. Pharmacy and Healthcare Provider Information Portals (so called “eHealth Cloud”) As per MoLHSA’s recent initiative to collect information and create complete profiles of all health service providers (including the out-patient units and rural physicians registered as physical persons/entrepreneurs), the system was modified and upgraded to include additional information, such as: number of beds, equipment, working medical personnel and etc. The information portal shall serve as a single source for generating and analysis of various country-wide statistics, including mapping of various data. Such real-time information generation shall enable the MoLHSA to regularly assess capacities, monitor various trends, and be informed for better emergency preparedness. Financial Module In the month of January, the team worked on migration of financial units and contracts from the Hesperus (currently employed billing system) to the new financial and billing module. The latter shall significantly reduce an implementation burden on SSA. Moreover, data validation services were created, reducing data entry and transmission errors. Several meetings conducted with the IT department of the Ministry of Finance, to determine and agree on specifications for integrating the Financial and Billing Module into the State Treasury system. The following shall enable the SSA to automatize the reporting process with healthcare providers. By the end of the reporting period, HSSP team works actively to launch the Financial and Billing Module in testing mode. Piloting shall be carried out with active involvement of the SSA and all the relevant Ministerial structures. Other Activities: As per request coming from the DTROG, HSSP presented the case of successful collaboration between the two projects to the delegation visiting Georgia at the end of January, 2013. The delegates represented US Department of Defense, CDC, DTROG and other implementing partners. USAID was represented by the Deputy Mission Director and HSSP project COTR. Major next steps: - Continue working on Pharmacy and Healthcare Provider Information Portal to create complete facility profiles and equip the portal with search and analysis functionalities; - Continue working on deployment of the Financial/Billing Module (including the information exchange with the State Treasury); - Continue working on streamlining the information exchange between the Revenue Service and the HMIS; - Continue support to testing of Immunization and development of the Stock Management modules - Continue operational support to MoLHSA with all modules within the HMIS - Resume activities in terms of implementation of the Code of the Doctor’s Professional conduct |