Monthly Progress Report

USAID Health System Strengthening Project

March 2013

Progress on Project Implementation Activities:

| Objective 1: Strengthen Insurer Capacity to Provide Quality Health Insurance |  |
| --- | --- |
| Activity Area | Progress Report |
| Activity: Development and roll out of professional trainings and knowledge exchange to address capacity building needs of health insurance companies | Progress this month: Georgian Insurance Association (GIA) grant contract is finalized and signed. HSSP held several meetings with the GIA to outline the detailed activity implementation plan. Among the insurance expansion support activities, GIA shall be in charge of promoting HMIS products among the industry, in particular introduce the electronic drug prescribing and case registration modules of the Health Management Information System (HMIS). Several meetings were held with individual insurance companies as well. |
| Activity: Enhance health insurance literacy and support the expansion of the voluntary health insurance market to cover those currently uninsured. | Next Steps: Hold follow-up meetings with the GIA and insurance companies individually. |
| Assist in enhancing private sector delivered and non-state funded health insurance | Next Steps: Meet with the GIA to discuss the impact of the new Universal Healthcare Program and the ways how GIA can assist this process best. |

Objective 2: Strengthen provider capacity to manage and deliver quality health care services

| Activity Area | Progress Report |
| --- | --- |
| Activity: Build / strengthen capacity of associations in health care to help their members develop capabilities to deliver higher quality health services and better customer experience | Progress this month: The Code of Doctor’s Professional Conduct: No major progress was demonstrated in this area, due to the shift of resources to respond to Ministry of Labor, Health and Social Affairs’ (MoLHSA) ad hoc requests. Next steps: The Code of Doctor’s Professional Conduct : Communicate with Geo-Hospitals and My Family Clinic, the largest health provider networks, to discuss the plans for dissemination and implementation of the Code of Doctor’s Professional Conduct. Begin design of e-certification for Doctors Code of Professional Conduct. |

| Objective 3: Strengthen Government Capacity to Guide and Monitor Health Services |  |
| --- | --- |
| Activity Area | Progress Report |
| Activity: Work with MOLHSA and other stakeholders to develop a Health Management Information System (HMIS) | Progress This Month: Beneficiary Registration Module In February, HSSP team actively worked to modify and create a flexible tool for managing beneficiaries of planned and urgent out-patient services provided under the new Universal Healthcare program. During the current reporting period, the new and upgraded module was tested and implemented. All the required validations were put in place to prevent duplicated entries. Starting from March 7, out-patient healthcare facilities are registering their beneficiaries through this system. In addition, the Beneficiary Registration and Financial and Billing Modules were completely integrated, enabling bilateral information exchange and automatic transmission of data into the Financial and Billing Module for generation of payments. The module is of paramount importance in terms of proper administration of the Universal Healthcare program. Since healthcare facilities are reimbursed on capitation basis, the fact that the module provides accurate number of registered beneficiaries ensures that State budgetary funds are administered accurately and properly. Dialysis sub-component: Although the module is fully functional and in use by the health department of the MoLHSA and select healthcare providers, rigorous efforts were made to make it more autonomous as requested by the Social Service Agency (SSA). These changes eliminate the need of connection with the Case Registration Module, so that the dialysis case administration is completely done through the dialysis sub-component. Case Registration Module Similar to the Beneficiary Registration Module, the launch of the new Universal Healthcare program required amendments to the existing Case Registration Module to fully respond the new obligations of urgent in-patient case management. Consequently, the Case Registration module was completely integrated with the Financial and Billing Module and the Information Portal, where healthcare facilities are uploading their service prices. All abovementioned dramatically improves the administration of the urgent in-patient care component of the Universal Healthcare program, through increasing the accuracy and availability of data that in turn decreasing the chance of incorrect payments to healthcare providers. Common Database of Private Health Insurance Beneficiaries: A common database of private health insurance beneficiaries was created in February. Throughout the current reporting period, the database was revised several times; the lists of incorrect entries were shared with respective insurance companies for further corrections. Moreover, specific data exchange mechanisms (so called service connections) were established to correct erroneous entries automatically. For the moment, the database is constantly being updated. Elimination of insurance status errors shall eradicate barrier for service provision and target the program to ones who are eligible (as per Decree # 36, eligibility criteria excludes having a valid corporate or individual health insurance and targets the uninsured population only). Medical Mediation Module The module is fully operational and in use by the Medical Mediation Service. HSSP team provides post-implementation support, as needed. Reporting Module During the current reporting period, significant progress was made to advance and expand the Reporting Module in several directions, namely: Healthcare Provider Component: HSSP team actively worked with the SSA on testing and implementation of new reporting forms. Moreover, supported the SSA with the launch of the module and provided trainings to healthcare facilities across the country. In addition, the reporting module was completely integrated with the Financial and Billing modules, in order to generate payments in real-time mode based on performance data submitted via the Reporting Module. Insurance Reporting Component: The module is fully operational and in use by the Medical Mediation Service. HSSP team provides post-implementation support, as needed. National Center for Disease Control and Public Health (NCDCPH) Component: HSSP team has actively worked with the NCDCPH on new medical statistical forms that resulted in modifications to the structure of the forms and the new validation mechanisms. New medical statistical forms shall enable electronic collection and submission of medical statistics data via the Reporting Module, which in turn shall eliminate reporting delays and data inaccuracies. Immunization Module Beneficiary and clinical case registration components of the Immunization Module are completed. In March, NCDCPH carried out extensive internal testing of the module. Pilot testing on a healthcare provider level is planned for April, 2013. Stock and Warehouse Management Module: The module is still under development. Several new forms were added, namely: stock dispatch and return. Couple interim meetings were held with the NCDCPH and CHM2HILL representatives. Besides the comments and feedbacks received during these meetings, the team shall start working on development of analytical functionalities. User Management Module The SSA part of the Beneficiary Registration Module, Reporting Module for Healthcare Providers, Financial and Billing Module and Information Portal were fully integrated into the User Management Module. Immunization module is to be added soon as well. . Pharmaceutical Modules E-Prescription System Development of basic functionalities of the module is completed and ready for testing. Since the political decision on its piloting/implementation is pending, HSSP plans to start negotiations with insurance industry through the Georgian Insurance Association. Pharmacy Database The module is fully operational and in use by the State Medical Activity Regulation Agency (SMARA). HSSP team solely provides needs based post-implementation support services. Activities in terms of development of the inspection component are pending. Electronic Registry of Drugs In March, significant progress was made in terms of consolidating/migrating all the drug related information at the single source, i.e. Electronic Registry of Drugs. These efforts shall dramatically simplify drug information registration into the system, as it eliminates the need of parallel entering into the old Excel “database” and a public web-site. In parallel, the Registry is continuously being corrected in terms of erroneous entries, due to data migration or missing information. Information Portal (the so called - “eHealth Cloud”) Due to major efforts in terms of data collection taken earlier, currently the Informational Portal includes complete information on all healthcare facilities (including the first ever information on out-patient clinics) along with their capacities of beds, services, staff and etc. Prices of services will be added in the following month. The portal was made public in February, although with limited information. The rest are already used by the MoLHSA for analysis and planning. In March, major step was taken toward integrating the medical service prices into the Information Portal. As a result, all healthcare providers, participating in the Universal Healthcare Program, have uploaded their service prices. The information is not made public yet, but used by the Financial and Billing Module for generating payments. Financial and Billing Module The Financial and Billing Module is the main pillar of successful implementation of the new Universal Healthcare Program, therefore the development of this module was set as the main priority. During the current reporting period: Complete integration of the Case Registration, Beneficiary Registration and E-Reporting Modules was made possible. Financial and Billing modules was linked to the Information Portal, that one hand enables transmission of service price data from the Portal into the Financial component. At the same time, it feeds the Portal with important information, such as contracts and lists of healthcare providers participating in the Universal Healthcare program. Based on rigorous testing efforts, the Financial and Billing Module was significantly optimized in terms operation speed and data exchange among its various components. Team continuous working actively on linking the Financial and Billing Module with the State Treasury, which is to be completed in the following month. By the end of the current reporting period, Financial and Billing module is tested and in limited use. Additional validations and case registration functionalities are being added. Next Steps: - Continue working on Information Portal to create complete facility profiles; - Continue working on streamlining the information exchange between the Revenue Service and the HMIS; - Support the roll-out/testing of various directions of the E-Reporting Module. Work on preparation and optimization of analytic part - Continue working on Financial and Billing Module and support the SSA in its deployment - Advance Immunization Module to testing at healthcare provider level. - Continue the development of the Stock Management Module, including the collaboration with the DRTOG implementing partners; - Continue optimization and streamlining of the Financial and Billing modules, as well as Beneficiary Registration Modules; - Continue operational support to MoLHSA with all modules within the HMIS; - Resume activities in terms of implementation of the Code of the Doctor’s Professional conduct. |