# Project Timeline and Fees

## High Level Project Schedule

Information Intelligence Group Consulting anticipates that the project will be completed in approximately 24 weeks depending upon the resource assignment.  The following is a high-level schedule for each major work package of the project.

|  | Weeks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work packages | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 |
| WP1 – Initiation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP2 - Functional requirements for mobile platform collection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP3 - Functional requirements for 1st part of EHR-HSSP/USAID integration collection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP4- Functional requirements for 2nd part of EHR-HSSP/USAID integration collection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP5 - Project management for analysis phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP6 - Technical specification preparation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP7 - Development and testing of 1st part of EHR-HSSP/USAID integration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP8 - Development and testing of 2nd part of EHR-HSSP/USAID integration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP9 - Mobile Platform development and testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP10 - Project management for development phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP11 - Deployment of the 1st part of EHR-HSSP/USAID integration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP12 - Deployment of the 2nd part of EHR-HSSP/USAID integration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP13 - Mobile platform deployment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP14 - Project management for deployment phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP15 - Acceptance of the 1st part of EHR-HSSP/USAID integration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP16 - Acceptance of the 2nd part of EHR-HSSP/USAID integration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP17 - Mobile platform acceptance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP18 - Project management for acceptance phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Note that this high level project schedule should be reviewed and revised by the customer and EMC project managers at the start of the project.  A more complete project plan will be developed and agreed by the customer and EMC project managers during project initiation and planning.

# Fixed Price Payment

## Fixed Fee Payment Schedule

Customer consider advance payment for 50% of contract price, which is accounted during project phases.

Milestones will be confirmed as "Complete" only when formally accepted in writing by MoLHSA unless otherwise provided for in this SOW. Target dates for completion of the Milestones will be agreed between the parties in the Project Initiation Plan and EMC shall use all reasonable endeavours to meet these agreed dates.

|  | Description | Date | Amount ($) |
| --- | --- | --- | --- |
| Milestone 1 | Completion of Work Package1 | 15.04.15 | 58 000 |
| Milestone 2 | Completion of Work Package 2 | 29.04.15 | 58 000 |
| Milestone 3 | Completion of Work Package 3 | 15.04.15 | 64 000 |
| Milestone 4 | Completion of Work Package 4 | 29.04.15 | 51 000 |
| Milestone 5 | Completion of Work Package 5 | 29.04.15 | 39 000 |
| Milestone 6 | Completion of Work Package 6 | 22.07.15 | 58 000 |
| Milestone 7 | Completion of Work Package 7 | 01.07.15 | 128 000 |
| Milestone 8 | Completion of Work Package 8 | 22.07.15 | 128 000 |
| Milestone 9 | Completion of Work Package 9 | 22.07.15 | 99 000 |
| Milestone 10 | Completion of Work Package 10 | 22.07.15 | 96 000 |
| Milestone 11 | Completion of Work Package 11 | 30.07.15 | 55 000 |
| Milestone 12 | Completion of Work Package 12 | 08.08.15 | 61 000 |
| Milestone 13 | Completion of Work Package 13 | 15.08.15 | 68 000 |
| Milestone 14 | Completion of Work Package 14 | 15.08.15 | 42 000 |
| Milestone 15 | Completion of Work Package 15 | 27.08.15 | 81 000 |
| Milestone 16 | Completion of Work Package 16 | 02.09.15 | 67 000 |
| Milestone 17 | Completion of Work Package 17 | 15.09.15 | 55 000 |
| Milestone 18 | Completion of Work Package 18 | 15.09.15 | 75 000 |
| TOTAL |  |  | 1 283 000 |

Prices quoted are exclusive of Taxes and VAT. Project expenses are however included in the total amount. On the basis of the activities described in this Statement of Work summarized above, this makes a total price of $1 283 000. This sum is final for payment.

This SOW, and the estimate of cost contained in it, is based on EMC’s current understanding of the high level requirements documented by the customer in the Functional requirements document (and set out here in Appendix 10). Following the Analysis phase of the project, EMC will re-estimate the remaining project activities. If the detailed requirements are wider in scope or detail than currently understood, and lead to an increase in overall estimates, EMC will raise a Change Request for the additional funding needed to deliver the project.

Should additional effort be required due to changes in the scope of this Project or material delays by MoLHSA which have been notified as Relief Events pursuant to the terms of the Agreement governing this Statement of Work, the relevant days and expenses will be covered through a Change Request (see Change Control Process) or a simplified "Extension of Contract" form to be provided by the EMC PM.

Note: Payment is due within 50 days of date of invoice.

# Payment plan

|  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WP1 | 641K |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP9 |  |  |  |  |  |  |  |  |  |  | 176K |  |  |  |  |  |
| WP10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP11 |  |  |  |  |  |  |  |  |  |  |  | 55K |  |  |  |  |
| WP12 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP13 |  |  |  |  |  |  |  |  |  |  |  |  | 110K |  |  |  |
| WP14 |  |  |  |  |  |  |  |  |  |  |  |  |  | 148K |  |  |
| WP15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 130K |  |
| WP16 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |