## Experts - PERT
Activity Name | Best case | Worst case | Most likely case | Expected (PERT) | Team Leader |  | Software / System Architect |  | Database Developer |  | Software Developer |  | Tester & Documenter & Support |  | Summ %
1) System design |  |  | Total | 38.8333 | % | days | % | days | % | days | % | days | % | days | %
A1.1 Familiarize with the project documentation and project team. | 5 | 10 | 7 | 7.1667 | 50% | 3.5833 | 30% | 2.15 | 10% | 0.71667 | 10% | 0.71667 |  | 0 | 100%
A1.2 Data analysis and development of datasets specifications | 20 | 50 | 30 | 31.6667 | 55% | 17.4167 | 35% | 11.0833 | 10% | 3.1667 |  | 0 |  | 0 | 100%
2) Software development and testing |  |  | Total | 184 | [5 empty] | 0 |  | 0 |  | 0
A2.1 Set up project development environment | 2 | 5 | 3 | 3.1667 |  | 0 | 50% | 1.5833 | 30% | 0.95 | 20% | 0.63333 |  | 0 | 100%
A2.2 Define, design and implement web theme(s) and User Interface | 10 | 25 | 15 | 15.8333 | 10% | 1.5833 | 20% | 3.1667 |  | 0 | 70% | 11.0833 |  | 0 | 100%
A2.3 LMIS database / data warehouse design and implementation | 15 | 40 | 20 | 22.5 |  | 0 | 30% | 6.75 | 70% | 15.75 |  | 0 |  | 0 | 100%
A2.4 Develop core web framework + sections | 20 | 55 | 30 | 32.5 |  | 0 | 25% | 8.125 |  | 0 | 75% | 24.375 |  | 0 | 100%
A2.5 Design and implement security | 5 | 15 | 7 | 8 |  | 0 | 30% | 2.4 |  | 0 | 70% | 5.6 |  | 0 | 100%
A2.6 Development and testing of data analysis module (charts, tables, data tools, pivot views) | 20 | 50 | 30 | 31.6667 |  | 0 | 15% | 4.75 |  | 0 | 85% | 26.9167 |  | 0 | 100%
A2.7 Development of LMIS administration modules (content management modul, data import module, administration, master data management, event viewer, configuration) | 25 | 55 | 40 | 40 |  | 0 | 25% | 10 | 10% | 4 | 65% | 26 |  | 0 | 100%
A2.8 Developement of ETL (Extract-Transform-Load) packages and procedures | 15 | 35 | 20 | 21.6667 |  | 0 |  | 0 | 50% | 10.8333 | 50% | 10.8333 |  | 0 | 100%
A2.9 System, regresion and performance testing | 5 | 15 | 8 | 8.6667 | 10% | 0.86667 | 10% | 0.86667 |  | 0 | 35% | 3.0333 | 45% | 3.9 | 100%
3) Deployment |  |  | Total | 17.3333 |  | 0
A3.1 Deployment to test environment | 2 | 7 | 4 | 4.1667 |  | 0 | 30% | 1.25 | 30% | 1.25 | 40% | 1.6667 |  | 0 | 100%
A3.3 Acceptance testing | 4 | 12 | 6 | 6.6667 | 10% | 0.66667 | 10% | 0.66667 |  | 0 | 20% | 1.3333 | 60% | 4 | 100%
A3.2 Deployment to production environment | 3 | 12 | 6 | 6.5 |  | 0 | 20% | 1.3 | 30% | 1.95 | 50% | 3.25 |  | 0 | 100%
4) System documentation |  |  | Total | 17.6667 |  | 0 | [5 empty] | 0 |  | 0
A4.1 Prepare user documentation | 5 | 12 | 8 | 8.1667 | 15% | 1.225 |  | 0 |  | 0 |  | 0 | 85% | 6.9417 | 100%
A4.2 Prepare system documentation | 5 | 20 | 8 | 9.5 | 40% | 3.8 | 50% | 4.75 | 10% | 0.95 |  | 0 |  | 0 | 100%
5) System training |  |  | Total | 16.8333 |  | 0
A5.1 Preparation of trainings | 5 | 15 | 10 | 10 | 10% | 1 |  | 0 |  | 0 |  | 0 | 90% | 9 | 100%
A5.2 Delivery of trainings | 5 | 12 | 6 | 6.8333 | 50% | 3.4167 |  | 0 |  | 0 |  | 0 | 50% | 3.4167 | 100%
6) Support after delivery (3 months) |  |  |  | 20.5
A6.1 On-site support | 3 | 10 | 5 | 5.5 | 15% | 0.825 | 5% | 0.275 | 20% | 1.1 | 30% | 1.65 | 30% | 1.65 | 100%
A6.1 Remote support | 5 | 25 | 15 | 15 | 15% | 2.25 | 5% | 0.75 | 20% | 3 | 30% | 4.5 | 30% | 4.5 | 100%
TOTAL WORKING DAYS |  | 0 |  | 295.1667 |  | 36.6333 |  | 59.8667 |  | 43.6667 |  | 121.5917 |  | 33.4083 | 295.1667
Net cost per day | [5 empty] | 600 |  | 650 |  | 450 |  | 450 |  | 350
Total cost |  |  |  | 146952.5 |  | 21980 |  | 38913.3333 |  | 19650 |  | 54716.25 |  | 11692.9167
Travel costs | 4 flights total |  |  | 3400 |  | Flight cost: | 850 | Number of flights: | 4
Hotel costs | 50 nights in Tbilisi |  |  | 2000 |  | Hotel per night | 40 | Number of nights | 50
Periderms | 40 perdiems |  |  | 2000 |  | Perdiems | 50 | Nr. of perdiems | 40
Training cost | Estimated |  |  | 1000
Project management cost | Fee: | 10% |  | 14695.25
TOTAL |  |  |  | 23095.25 |  |  | TOTAL: | 170047.75

## Experts - summary
Job role | Duration (days) | Duration (months) | Persons
Team Leader | 36.6333 | 1.7444 | 1
Software / System Architect | 59.8667 | 2.8508 | 1
Database Developer | 43.6667 | 2.0794 | 1
Software Developer | 121.5917 | 5.7901 | 2
Tester & Documenter & Support | 33.4083 | 1.5909 | 1
Total: | 295.1667 | 14.0556 | 6
Eengineering days per month | 21