## General
Georgia Emergency COVID-19 Response
Thresholds for Procurement of Goods, Works and Non-Consulting services:
Procurement Method | Procurement | Prior Review
1 - Goods
ICB: | >US$1 Mil | As indicated in respective sheets for Goods, Works and Consulting Services
NCB: | ≤ US$1 Mil
SH: | <US$100 K
DC: | None
2- Works
ICB | >US$10 Mil
NCB | ≤ US$10 Mil
SH | <US$200 K
DC
Thresholds for Selection and Employment of Consultants:
Procurement Method | Procurement | Prior Review
3 - Consulting Services Firms |  | As indicated in respective sheets for Goods, Works and Consulting Services
QCBS
QBS
FBS
LCS
CQS | ≤US$300,000
DC
4 - Consulting Services Individuals
IC
DC

## Procurement plan for COVID19
| Date | 2020-04-27
# | Description | Implementation Entity | Type | Procurement Approach | PQ | PR | Packs | Cost (Estimate GEL) | Cost (Estimate USD) | IBRD Financing | Actual Cost (GEL) | Issue of REOI | Issue of BD/ITQ/RFP | Bid/Proposal Opening | Eval done - NO issued | Contract Signed | Contract Start | Contract Finished | Note
Component 1:EMERGENCY COVID19 RESPONSe
Goods/Works/Non-Consultin Services
1 | PPE | MoH | Goods | Open/Shopping/Direct | N | N | Single or Multiple | 48066000 | 15000000 | 6750000
2 | Procurement of Equipment for hospitals | MoH | Goods | Open/Shopping/Direct | N | N | Single or Multiple | 48066000 | 15000000 | 6750000
3 | Procurement of fully Equipped Ambulances | MoH | Goods | Open/Shopping/Direct | N | N | Single or Multiple | 17303760 | 5400000 | 2430000
4 | Procurement of Diagnostic Supplies | MoH | Goods | Open/Shopping/Direct | N | N | Single or Multiple | 3204400 | 1000000 | 450000
5 | Procurement of Equipment for Emergency Control Center | MoH | Goods | Open/Shopping/Direct | N | N | Single or Multiple | 8972320 | 2800000 | 1260000
6 | Minor repairs of public health facilities | MoH | CW | Shopping/Direct | N | N | Single or Multiple | 3204400 | 1000000 | 450000
7 | Remodelling of ICU beds | MoH |  | Shopping/Direct | N | N | Single or Multiple | 3204400 | 1000000 | 450000
[7 empty] | Sub-Total USD of Goods, Works and Non-Consulting Services |  | 41200000 | 18540000
Consulting Services
8 | Training and Assistance | MoH | CS | QBS | N | N | 1 | 961320 | 300000 | 135000
9 | Procurement Consultant | MoH | CS | IC | N | N | 1 | 124971.6 | 39000 | 17550
10 | Project Manager | MoH | CS | IC | N | N | 1 | 142595.8 | 44500 | 20025
11 | Financial Consultant | MoH | CS | IC | N | N | 1 | 123369.4 | 38500 | 17325
12 | Enviromental Specialist | MoH | CS | IC | N | N | 1 | 82032.64 | 25600 | 11520
13 | Social Specialist | MoH | CS | IC | N | N | 1 | 82032.64 | 25600 | 11520
14 | Operating Costs * | MoH | N/A | N/A | N/A | N/A | N/A | 97734200 | 30500000 | 13725000
[6 empty] | Sub-Total (USD) of Consulting services |  |  | 30973200 | 13937940
[6 empty] | Total of Component |  |  | 72173200 | 32477940
*Operating costs refer to Quarantine and mild case management in non-medical settings; Global budget to public and private facilities to ensure preparedness;Costs of case management and treatment
Price Convertion Rate, Date and Source:
| USD/GEL: | 3.2044
| 2020-04-27 | https://www.nbg.gov.ge/index.php?m=2&lng=eng