8ROLLING WORK-PLAN No1

TO TWINNING GRANT CONTRACT ENI/2019/411-554

WORK-PLAN AND BUDGET FOR THE PERIOD: 15/07/2020 -  14/01/2021

Ms. Nino Kochishvili

Programme Officer,

64b Chavchavadze Avenue

0179 Tbilisi, Georgia

Tel: + 995 32 23634364

E-mail: Nino.Kochishvili@eeas.europa.eu

ARTICLE 1: Objective

The Member State and Beneficiary PLs hereby notify the Contracting Authority of the detailed work-plan and budget of the above mentioned Twinning Grant Contract for the 6- month period starting 2020-07-15.

ARTICLE 2: Tasks (Inputs)

Budget Heading - RTA and related expenses

1.1 Remuneration

Compensation wage and non wage 	36590,00 EUR

Compensation Daily Subsistence	94892,00 EUR

1.2 Travel

Taking up duty	1194,00 EUR

Monthly Travel	11343,00 EUR

1.3 RTA Training Brussels

Travel Costs	500,00 EUR

Daily Subsistence Allowance	696,00 EUR

1.4 RTA Assistants contracts

Assistant(s)	31500,00 EUR

Interpreter/translator salary	31500,00 EUR

Budget Heading – Horizontal costs

2.1 Short term staff: MS PL and other Support staff / Component Leaders

Work Plan preparation   8400,00 EUR

Steering Committees   2800,00 EUR

Communication/Visibility programme  11200,00 EUR

Twinning Project Support Cost	30464,00 EUR

Compensation for Daily Subsistence	17820,00  EUR

Travel Costs  (LT)	7761,00 EUR

Travel Costs (NL)	5525,00 EUR

Translation	700,00 EUR

Interpretation 	700,00   EUR

Venue	1400,00 EUR

Small cattering  400,00 EUR

2.2 PC PL and/or RTA Counterpart Training Brussels

Travel Costs	500,00 EUR

Compensation for Daily Subsistence	696,00 EUR

2.3 Communication/Visibility programme

Maximum amount for all components	15000,00 EUR

Expenditure Verification / Audit costs	8000,00 EUR

Budget Heading - Mandatory Results / Components

Component 0: Project management

| Activity 0.1 | Kick-off meeting |
| --- | --- |
| Benchmark agreed | Kick-off meeting organized, visibility plan and part of visibility and Project promotion materials prepared. |
| Method | The Kick-off event will be held in Tbilisi with MS partners involved (provisionally foreseen in the second half of September). This activity will be focused on increasing the visibility of the Project. Furthermore, the Kick-off event shall outline the main results to be achieved during the implementation of the Project. The Project Leaders will present the main issues of the Project and its components targeting invited experts from Georgia and high-level decision makers in order to point out the importance of the Project and the political support given to its implementation in the Kick-off event. The Kick-off event will be held over a day. As the aim of this meeting will be to mark the official start of the Project and to create awareness about the Project and its objective, public awareness of the Project will be raised by inviting the media and by a press release. The Kick-off event will start with a general meeting gathering the relevant authorities and the main experts from all the partners on the first half day. It will focus on the external communication of the Twinning partners with the relevant stakeholders from Georgia. The remaining half-day will be used for internal discussion between MS staff and experts from the BC. Representatives of the MS and BC shall give statements to the media. |
| Project month | September, 2020 |
| MS resources: | 1 mission for 2 days with 6 STEs (12 working days in total) |
| MS experts | PL (LT), JPL (NL), 4 components leaders |
| BC resources | Deputy Minister of Internally displaced persons, Labour, Health and Social affairs, Ambassador of Lithuania to Georgia, Ambassador of Netherlands to Georgia, EUD high officials, MFA representatives, BC PL, RTA counterpart, Component leader counterparts, other key experts |
| Other resources | Simultaneous interpretation, document translation, meeting venue, small catering, visibility material |

| Activity 0.3 | Steering Committee meetings |
| --- | --- |
| Benchmark agreed | Steering Committee meetings organized, Quarterly reports prepared and approved, Work plan updated |
| Method | Steering Committee Meeting (SCM) 2 to be held in July 2020. The main goal of this meeting is to present and approve (to be signed by the Beneficiary and Member State PLs) the Rolling work plan, which shall foresee the activities for six months of Project implementation. Quarterly Steering Committee meetings will be held for the purpose of reviewing the progress made under the Project as well as to discuss results achieved and/or problems occurred. The progress and achievements vis-à-vis the result ensuring good coordination among the actors, finalising the quarterly interim reports and discussing the updated work plan and any new CVs of experts implementing up-coming activities will be verified at the Project Steering Committee meeting. Updated draft work plan is prepared by the RTA, who circulates it to all members of the Project Steering Committee at least two weeks in advance of a meeting. The Quarterly Steering Committee meetings will be organized in July 2020 – by teleconference due to the governmental restrictions for international flights. SCM 3 will be organized in the second half of September or beginning of October 2020 (9-10th month) and 4th Steering Committee Meeting is foreseen in December 2020. |
| Project month | July (2nd quarterly SCM), September-October (3rd quarterly SCM), December (4th quarterly SCM) |
| MS resources | 2 missions for 2 days with 2 STEs (1 mission - 4 working days in total) |
| MS experts | PL (LT), JPL (NL), RTA |
| BC resources | BC PL, RTA counterpart, Component leader counterparts, other key experts |
| Other resources | Interpretation by RTA language assistant |

Component/Mandatory result 1: Approximation of Georgian primary and secondary legislation with the Union acquis on blood safety (Annex XXXI) performed

Indicator agreed

Status of normative acts approximating Georgian primary and secondary legislation with the Union acquis on blood safety

Baseline: 2019 – Amendments not elaborated

Target: 2022 - Normative acts adopted by the GoG or respective ministries

Sub- result 1.1: National regulatory framework in blood safety revised and upgraded in accordance with Union acquis on blood safety

Indicator agreed

Amendments to the Georgian primary and secondary legislation on blood safety prepared in an inclusive and evidence based process using the unified LA methodology;

Target: end of 2021 – Amendments/new normative acts adopted by the GoG or respective ministries:

- Law of Georgia on Donation of Blood and Blood Components

- Law of Georgia on Licenses and Permits

- Resolution of the Government of Georgia №385, 17.12.2010

- Decree of MoIDPLHSA №14/N, 14.01.2002

- State Safe Blood Program

- Resolution of the Government of Georgia №74, 15.01.2014

- Decree of MoIDPLHSA №241/N, 05.12.2005

- Resolution of the Government of Georgia №539, 05.09.2014

- Decree of MoIDPLHSA №110/N, 14.03.2001

- Decree of MoIDPLHSA №01-26/N, 25.03.2019

- Availability of the Tables of Concordance

A set of legal acts of Lithuania proposed by Lithuanian STEs and translated for the Georgian working group:

- Order of the Minister of Health On the approval of licensed healthcare services

- Order of the Minister of Health On the approval of good practise provisions for Blood establishments (BE) and hospital blood banks (BB) (Directive 2002/98/EB, 2016/1214)

- General requirements  for BE activities;

- Basic requirements for BE Quality system standards and specifications:

  - Requirements for personal

  - Requirements for premises

  - Requirements for equipment and reagents

  - Requirements for documentation;

  - Requirements for blood collection

  - Requirements for testing

  - Requirements for processing

  - Requirements for labelling;

  - Requirements for release, storage and distribution

  - Requirements for non-conformances and contract management

  - Requirements for recall

  - Requirements for internal audit or self-assessment

- list of data provided by BE to the State Accreditation for Health Activities body to assess compliance with the requirements of the Good Practice Provisions

- General requirements  for BB activities

- Basic requirements for BB Quality system standards and specifications

- Order of the Minister of Health On the approval requirements for donors health assessment, blood and blood components collection;

  - Information provided for donors and obtained from donors

  - Donors medical assessment

  - Donor data verification in Blood donor national register

  - Blood and components collection frequency, doses and requirements.

  - Donor questionnaire

- Order of the Minister of Health on donors immunohematological testing;

  - Tests methods and requirements for first time and repeat donors.

- Order of the Minister of Health On donors testing for infectious markers:

  - Requirements for serological screening and confirmatory testing for HIV, HB, HC and syfilis and evaluation of results.

  - Requirements for screening and confirmatory molecular testing for HIV, HB, HC and evaluation of results

- Order of the Minister of Health On the approval of blood components preparation and quality control requirements:

  - Blood and components specifications

  - Blood and components quality parameters and control, sampling frequency

- Order of the Minister of Health On on traceability and reporting to the Ministry of Health about SAR/SAE

  - Reporting forms, investigations requirements.

- Order of the Minister of Health On information about blood components used for transfusions and available stocks in hospitals.

- Order of the Minister of Health On the approval of transfusion indications

- Order of the Minister of Health On Approval of a program to promote unpaid donation

Baseline: 2019 – Draft documents elaborated by Ministry’s working group:

- Standards for blood testing

- Standards for blood processing

- Standards for donor selection

- Standards for collection, storage and distribution of blood and blood components

Target: end of 2021 - amendments for approximation with following EU legal acts elaborated:

- Directive 2002/98/EC of the European Parliament and of the Council of 27 January 2003

- Commission Directive 2004/33/EC of 22 March 2004

- Commission Directive 2005/62/EC of 30 September 2005

- Directive 2005/61/EC of 30 September 2005

| Activity 1.1.1 | Review draft Law on Quality and Safety of Blood and Blood Components and concomitant law package |
| --- | --- |
| Benchmark agreed | Report of evaluation of draft law on Quality and Safety of Blood and Blood Components |
| Method | STE’s will perform upcoming draft legislation analysis where revise draft Law on Quality and safety of blood and blood components. They will meet with the BC working group and other stakeholders. STE’s will present Lithuanian and Dutch practice: EU legislation and main blood law. They evaluate and identify how draft law corresponds to EU policies and EU MSs best practices. STEs will compose their mission reports where provide their findings and thoughts regarding the submission draft Law on Quality and Safety of Blood and Blood Components to Georgian Parliament for their endorsement. They will present report for draft legislation working group. GAP’s in draft law as compared with EU directive. The activity was conducted in teleconference mode due to epidemiological situation and following the EUD permission. |
| Project month | 12, 15-18 June, 2020 |
| MS resources | 1 mission for 5 days with 5 STE: 2 STE (LT) + 3 STE (NL) (25 working days in total) |
| MS experts | (LT): Laimute Stoniene (NBC), Agne Kaminskiene (NBC), (NL): W.Martin Smid (Sanquin), Wim de Kort (UA), Olenka van Ardenne (Sanquin) |
| BC resources | PL, RT counterpart, CL(4), Healthcare Policy Department of MoIDPLHSA (3), NCDC (4), State regulation agency (2), Aids center (1), Blood banks (2), stakeholders |
| Other resources | Translations draft legal acts, interpretation by RTA language assistant |

| Activity 1.1.2 | Translation of recommendations and guidelines applied to the blood collection and supply centers and public health institutions for the use in emergency situations due to Coronavirus pandemic |
| --- | --- |
| Benchmark agreed | Translation of urgent documents which will be disseminated among the blood centers and public health institution for the use |
| Method | RTA-C will perform analysis of needed legislation and present the list of documents for urgent translation |
| Project month | April, May 2020 |
| MS resources | RTA assistants, without budget modification of the project |
| MS experts | STE’s are not involved in the activity |
| BC resources | RTA-C, CL, stakeholders |
| Other resources | Translations of legal acts and recommendations |

| Activity 1.1.3 | Translation of the General and Basic requirements for Blood establishments quality system of Lithuania and assistance of STEs in the process of development of draft Georgian standards |
| --- | --- |
| Benchmark agreed | Draft Georgian standards developed with the assistance of STEs; Mission reports of STEs with recommendations regarding introduction of standards in Georgian legislation; Draft Georgian standards developed. |
| Method | Standards of Lithuanian bloods establishments are presented and Lithuanian legislation in the field is shared by STEs. RTA-C together with the Georgian working group members and with the expertise and assistance of Lithuanian STEs perform analysis of translated standards and regulations of Lithuania on the Blood establishments’ quality system (1st mission). Georgian working group together with Lithuanian STEs evaluate and identify how the Lithuanian practice in the field can be adopted and introduced to the Georgian legislation. STEs provide their assistance in drafting Georgian standards (2nd mission). Draft Georgian standards are finalized (3rd mission) The activity may be conducted by teleconference if the epidemiological situation of coronavirus prevents missions on the place. |
| Project month | August-October 2020 |
| MS resources | 3 missions: First mission for 2 days with 2 STE Second mission for 2 days with 2 STE Third mission for 2 days with 2 STE (12 working days in total) |
| MS experts | (LT): Laimute Stoniene (NBC), Agne Kaminskiene (NBC) |
| BC resources | RTA counterpart, Component 1 working group, other stakeholders |
| Other resources | Translations draft legal acts, interpretation by RTA language assistant |

Component/Mandatory result 2: A well-organized, nationally coordinated blood transfusion system established and functioning in accordance with the provisions of the Association Agreement

Indicator agreed

Share of blood banks with non-profit legal status

Baseline:  2018 -14% (3 BB out of 22) of blood establishments have non-profit organizational status

Target: 2022 - 100% of blood establishments have non-profit legal status

Share of blood processing and blood collection centers

Baseline: 2019 - 22 (100%) of blood establishments collect blood and process blood components

Target: 2025 - No more than 3 blood banks produce blood and blood components across  the country  and the rest of the licensed blood establishments operate as blood collection centers

Share of blood donations that underwent NAT at centralized TTI testing laboratories

Baseline: None

Target: 2019 – 3% (3000) of total donations; 2020 – 50% (50 000) of total donations; 2021 – 70% (70 000) of total donations; starting from 2022 – 100% (100 000) of total donations

Sub-result 2.1: National Competent Authority established and fully functional to take the role, tasks and resposibilities required by EU Blood Directives.

Indicator agreed

- Status of normative acts related to the establishment of the NCA;

Baseline: 2019 - Not established

Target:

End of 2020 – legal bases for the establishment developed, including structure, functions, budget, organizational chart, planning, inspection program, JAS, standard operating procedures (SOP), check-lists for inspectors, training plan, registries

2021 - NCA established and fully functional to provide overall surveillance of blood transfusion service from blood selection to clinical use of blood and blood products (including accreditation, designation, authorization or licensing of blood establishments as well as Inspections and control measures)

| Activity 2.1.1 | The activity related to the establishment of the NCA as required by EU Blood Directives. |
| --- | --- |
| Benchmark agreed | Report of roundtable discussions (1st mission) draft regulations on the role and responsibilities of NCA (2nd mission) |
| Method | STEs will discuss with the working group responsible for preparing the related normative act and stakeholders the role, tasks and responsibilities of NCA in Georgia required by EU Blood Directives (1st mission). Georgian working group with the support of STEs develop draft regulations on the role and responsibilities of NCA (2nd mission) The activity may be conducted in teleconference mode if the epidemiological situation prevents mission on the place. |
| Project month | July-October, 2020 |
| MS resources | 2 missions: First mission for 2 days with 5 STE (2 STE (LT) + 3 STE (NL) Second mission for 3 days with 5 STE 2 STE (LT) + 3 STE (NL) (25 working days in total) |
| MS experts | (LT): Laimute Stoniene (NBC), Agne Kaminskiene (NBC) (NL): W.Martin Smid (Sanquin), Wim de Kort (UA), Olenka van Ardenne (Sanquin) |
| BC resources | PL, RTA counterpart, CL(1), Healthcare Policy Department of MoIDPLHSA (2), NCDC (5), State regulation agency (2), AIDS center (1), Blood banks (2), stakeholders |
| Other resources | Interpretation by RTA language assistant Document translations (Georgian/ English/ Lithuanian/ Dutch) |

Sub-result 2.2: Assesment of blood banks performed

Indicator agreed

- Number of blood banks participating in the assessment;

Baseline: 2018 - 4 blood establishments

Target: 2020 - 22 blood establishments

- Status of the functional review/assessment report of the blood establishments;

Baseline: 2018 - TAIEX expert report available

Target: 2020 - comprehensive assessment of all (22) licensed blood establishments conducted, gaps identified, recommendations for improvement prepared and submitted to Georgian health authorities

| Activity 2.2.1 | Study visit to MS to get acquainted with European model of Blood Transfusion Systems |
| --- | --- |
| Benchmark agreed | Acquaintance of Georgian experts with Lithuanian and Dutch currently operating models of blood transfusion systems |
| Method | Visit of Georgian experts to Lithuanian and Dutch blood establishments and National Competent Authorities to get acquainted with the current situation in the countries. They will meet with persons responsible for the organization and control of the blood transfusion service and other related stakeholders. Experts will visit the central and reference laboratories of the countries and get acquainted with the testing algorithms and quality system management. |
| Project month | September – mission to Lithuania /confirmed/, September-October - mission to the Netherlands |
| MS resources | 3 days study visit: 1 preparation and 3 days; 5 STE working days (Lithuania) 3 days study visit: 1 preparation and 3 days; 4 STE working days (Netherlands). |
| MS experts | (LT): Daumantas Gutauskas (NBC), Laimute Stoniene (NBC), Agne Kaminskiene (NBC), Ieva Linkeviciute (NBC) (NL):W. Martin Smid (Sanquin), Hans Vrielink (Sanquin), Peter van den Burg (Sanquin) |
| BC resources | PL, stakeholders; 5 Georgian experts to each Study visit (5 to Lithuania, 5 to the Netherlands) 2 study visits x 5 BC participants x 3 working day + RTA language assistant (LT, NL) |
| Other resources | Interpretation by RTA language assistant |

| Activity 2.2.2 | Assessment of blood banks in Georgia |
| --- | --- |
| Benchmark agreed | Preparation of questionnaire for blood establishments in Georgia (1st mission) Presentation results of analysis in the workshop (2nd mission). |
| Method | STE’s will perform the first mission to the BC and will discuss a scope and specificity of questionnaire. STE’s will prepare the questionnaire for the assessment of blood banks in Georgia to identify gaps in blood safety and blood products supply system, as well as evaluate the degree of their incompliance with EC directives and EU standards. The 1st mission of this activity may be organized by teleconference if the epidemiological situation and the governmental restrictions on international travel are pending. Data processing of the questionnaire submitted by the blood banks will be conducted by local company. STE’s will perform a second mission to the BC and conduct a workshop for policymakers and stakeholders presenting data of questionnaire evaluation. The proceeding of further on-site assessment of blood banks will depend on the results of questionnaire. The activity may be conducted by teleconference if the epidemiological situation of coronavirus prevents missions on the place. |
| Project month | August 2020 (1st mission), September-November 2020 (2nd mission) |
| MS resources | 2 missions: First mission for 4 days with 4 STE Second mission for 4 days with 5 STE (36 working days in total) |
| MS experts | (LT): Daumantas Gutauskas (NBC), Laimute Stoniene (NBC), Renata Poviliuniene (NBC) (NL): W. Martin Smid (Sanquin), Wim de Kort (UA) |
| BC resources | PL, RTA counterpart, CL(4), Healthcare Policy Department of MoIDPLHSA (3), NCDC (2), State regulation agency (2), AIDS center (1), Blood banks (22), stakeholders |
| Other resources | Interpretation by RTA language assistant Data processing of the questionnaire submitted by the blood banks (private Sector Input) |

Sub-result 2.3: Reorganisation of blood transfusion service (BTS) provided

Indicator agreed

- Status of written normative documents required to implement all legal, structural and functional changes for BTS reorganization;

Baseline: 2019 – N/A

Target: end of 2020 - Legal bases for BTS reorganization developed including BTS optimization plan, recommendations for effective statutory models, contingency plan etc.

- Status of the BTS reorganization strategy and its action plan;

Baseline: 2019 – N/A

Target: end of 2020 -  BTS development (reorganization) strategy and its action plan endorsed by the GoG

- Number of preliminary memoranda with EU member states to ensure sufficiency of blood supplies during and after reorganization process;

Baseline: 2019 - none

Target: end of 2020 – memoranda with at least two EU Member States

| Activity 2.3.1 | Drafting an Institutional Reform Plan for Blood Safety System in Georgia |
| --- | --- |
| Benchmark agreed | Report on of Strategic aspects of Institutional Reform Plan for Blood Safety System in Georgia |
| Method | STE’s will perform missions to BC where conduct assessment reports of evaluation of all Georgia blood banks assessment (Activity 2.2.2). STE’s will prepare the questionnaire for the assessment of hospitals in Georgia to identify gaps blood products supply and utilization system, relationships with blood banks, evaluate the degree of their incompliance with EC directives and EU standards (1st mission) The mission reports will be prepared and set proposals for an Institutional Reform Plan for Blood Safety System in Georgia to elaborate as follows: possible variants of reorganisation considering to regional specifics, location of hospitals, logistics and etc. (2nd mission) The activity may be conducted by teleconference if the epidemiological situation of coronavirus prevents missions on the place. |
| Project month | October-December 2020 |
| MS resources | 2 missions: First mission for 2 days with 3 STE Second mission for 3 days with 3 STE (15 working days in total) |
| MS experts | (LT): Laimute Stoniene (NBC) (NL): W. Martin Smid (Sanquin), Wim de Kort (UA) |
| BC resources | PL, RTA counterpart, CL(4), Healthcare Policy Department of MoIDPLHSA (3), NCDC (2), State regulation agency (2), Social service agency (1), Agency for emergency situation coordination and urgent care (2), AIDS center (1), Blood banks (22), stakeholders |
| Other resources | Interpretation by RTA language assistant |

| Activity 2.3.2 | Upgrade licensing requirements for blood establishments |
| --- | --- |
| Benchmark agreed | Gap analysis of current licensing blood establishments; Report on Improvement licensing mechanisms for blood establishments |
| Method | STEs will carry out a mission to the BC. Based on the new blood and blood components quality and safety law, evaluation reports of all Georgia blood banks assessment (Activity 2.2.2), approved by the Georgian Blood Transfusion Service Institutional Reform Plan (Activity 2.3.1), they identify gaps in current licensing blood establishments. Proposals to update licensing requirements and develop blood-based accreditation mechanisms will be prepared. The activity may be conducted by teleconference if the epidemiological situation of coronavirus prevents missions on the place. |
| Project month | November-December 2020 |
| MS resources | 1 mission for 4 days with 2 STE (8 working days in total) |
| MS experts | (LT): Agne Kaminskiene (NBC) (NL): W. Martin Smid (Sanquin) |
| BC resources | RTA counterpart, CL(1), Healthcare Policy Department of MoIDPLHSA (3), NCDC (2), State regulation agency (4), AIDS center (1), stakeholders |
| Other resources | Interpretation by RTA language assistant Document translations (Georgian/ English/ Lithuanian/ Dutch) |

Sub-result 2.4:  Transition to the mandatory non-profit organisational form for blood establishments initiated.

Indicator agreed

- Status of legal and political documents required to implement legal, structural and functional transition from for-profit to non-profit organizational arrangements;

Baseline: 2019 – N/A

Target: end of 2020 - Legal bases for BTS transition from profit based to non-profit organizational form developed including BTS transition plan

- Share of blood establishments with non-profit organizational status;

Baseline: 2019 - 14% (3 BB out of 22) of blood establishments are based on non-profit organizational status

Target: 2022 - 100% of blood establishments have non-profit legal status

| Activity 2.4.1 | Develop proposals including recommendations for transition to the mandatory non-profit organizational form for blood establishments regarding EU regulations |
| --- | --- |
| Benchmark agreed | Recommendation on development of the Georgian blood safety legislation with regards to EU regulations; Report of roundtable discussion. |
| Method | Roundtable meeting will be held with the Legal Group / Stakeholders and guidance on what regulations are needed for implementation will be provided. The activity will be conducted by teleconference as the epidemiological situation of coronavirus prevents missions on the place. |
| Project month | July-August 2020 |
| MS resources | 1 mission for 2 days with 4 STE (8 working days in total) |
| MS experts | (LT): Laimute Stoniene (NBC), Agne Kaminskiene (NBC), (NL): Wim de Kort (UA), W. Martin Smid (Sanquin) |
| BC resources | PL, RTA counterpart, CL(2), Healthcare Policy Department of MoIDPLHSA (4), NCDC (2), State regulation agency (2), AIDS center (1), stakeholders |
| Other resources | Interpretation by RTA language assistan Document translations (Georgian/ English/ Lithuanian/ Dutch) |

Sub-result 2.5: Centralised TTI testing laboratory(s) established

Indicator agreed

- Availability of legal and political documents required to establish centralized TTI testing laboratory;

Baseline: 2019 – N/A

Target: end of 2020 - centralized TTI testing laboratory established

- Number of blood donations that underwent TTI testing at centralized laboratory(s).

Baseline: N/A

Target: 2022 – 100% of donations

| Activity 2.5.1 | Develop standards for centralized testing laboratory (including serological and molecular (NAT) testing |
| --- | --- |
| Benchmark agreed | Report on justification of the need for centralized laboratories Draft standards for operation of centralized laboratories |
| Method | STE will perform mission to the BC. He will meet with specialists from Lugar center and other laboratories relevant with donor screening for TTI and blood products testing on the round table. The centralized testing laboratory in the Netherlands will be presented as an example. STE will identify gaps in this field and justify the need for centralized laboratories. The list of necessary upcoming legal documents for establishment and operation of centralized and laboratories will be elaborated. Draft standards foe operation of centralized laboratories will be developed with STE assistance. The activity may be conducted by teleconference if the epidemiological situation of coronavirus prevents missions on the place. |
| Project month | November-December 2020 |
| MS resources | 1 mission for 4 days with 1 STE (4 working days in total) |
| MS experts | (NL) Marco Koppelman (Sanquin) or Anton van Weert (Sanquin) |
| BC resources | RTA counterpart, CL(1), Healthcare Policy Department of MoIDPLHSA (3), NCDC (2), State regulation agency (3), Blood banks (22), stakeholders |
| Other resources | Interpretation by RTA language assistant Document translations (Georgian/ English/ Lithuanian/ Dutch) |

Sub-result 2.6: National reference laboratory established

Indicator agreed

- Availability of approved documents required to establish centralized National Reference Laboratory;

Baseline: 2019 – N/A

Target: end of 2021 – Appropriate legal act approving establishment of the National Reference laboratory (including organizational structure, functions and related issues) endorsed by the GoG.

| Activity 2.6.1 | Roundtable on the need for National Reference Laboratory and its functions |
| --- | --- |
| Benchmark agreed | Conclusions of the roundtable discussion |
| Method | STE will perform a mission to the BC. He will meet with specialists from laboratories relevant to donors screening and blood products testing and reference laboratories on the round table. The centralized testing laboratory in the Netherlands will be presented as an example. STE and the roundtable participants will make conclusions about demand and functions of National reference Laboratory and the place where it could be established. The activity may be conducted by teleconference if the epidemiological situation of coronavirus prevents missions on the place. |
| Project month | September-October 2020 |
| MS resources | 1 mission for 4 days with 2 STEs (8 working days in total) |
| MS experts | (LT) Vilnele Lipnickiene (National Public Health Surveillance Laboratory), (NL) Marco Koppelman (Sanquin) or (NL) Anton van Weert (Sanquin) |
| BC resources | RTA counterpart, CL(1), Healthcare Policy Department of MoIDPLHSA (2), NCDC (3), Blood banks (22), experts from other laboratories (3), stakeholders |
| Other resources | Interpretation by RTA language assistant Document translations (Georgian/ English/ Lithuanian/ Dutch) |

Sub-result 2.7: Nucleic Acid testing for blood screening for human immunodeficiency virus (HIV), hepatitis B virus (HBV) and  hepatitis C virus (HCV) introduced at centralized testing laboratory(ies)

Indicator agreed

Availability of approved documents required for introduction of NAT methodology and other high sensitive technologies;

Baseline: 2019 – N/A

Target: 2020 – Appropriate normative acts/amendments to the current regulations introducing NAT methodology for TTI testing (State Safe Blood Program, technical requirements) endorsed by the GoG

- Share of blood units among total donations screened by NAT;

Baseline: 2019 - 0

Target: 2019 – 3% (3000) of total donations; 2020 – 50% (50 000) of total donations; 2021 – 70% (70 000) of total donations; starting from 2022 – 100% (100 000) of total donations

| Activity 2.7.1 | The evaluation of pilot NAT blood screening testing in Lugar center |
| --- | --- |
| Benchmark agreed | Recommendations for improvement of workflow organization |
| Method | STE will perform a mission to the BC. He will visit Lugar center and will get acquainted with the results of the pilot study, SOP’s and other quality systems management documents. Tips and advices will be discussed with the staff performing NAT donor screening tests. The experience of the Central Laboratory in the Netherlands on this issue will also be presented. The activity may be conducted by teleconference if the epidemiological situation of coronavirus prevents missions on the place. |
| Project month | November-December 2020 |
| MS resources | 1 mission for 4 days with 1 STE (4 working days in total) |
| MS experts | (NL) Marco Koppelman (Sanquin) |
| BC resources | RTA counterpart, CL(1), Healthcare Policy Department of MoIDPLHSA (2), State regulation agency (2), NCDC (3), Blood banks (22), stakeholders |
| Other resources | Interpretation by RTA language assistant Document translations (Georgian/ English/ Lithuanian/ Dutch) |

Sub-result 2.9: Unified Electronic Donor Database upgraded

Indicator agreed

- Availability of manuals, guidelines, ToRs;

Baseline: 2019 – N/A

Target:

ToRs for upgrading of Donor Database developed within 9 months from the beginning of the project

2020 – operational guidelines / manuals in place

- Number of health professionals trained in the operation of the upgraded donor database;

Baseline: 2017 – 425 trainees (blood bank and hospital staff)

Target: 2021 – at least 50 blood bank professional and 400 hospital data operators

- Share of blood establishment that manage data according to the updated guidelines;

Baseline: 2019 – N/A

Target:

2021 – 100% of blood establishments operate in the upgraded database

Upgraded database ensures vein-to vein traceability, accountability, and hemovigilance related to blood donations

- Share of hospitals enrolled in the upgraded database;

Baseline: 2019 – 60% of hospitals performing blood transfusion

Target: 2021 – 100% of hospitals performing blood transfusion

| Activity 2.9.1 | Evaluation of databases related to donors in Georgia and legal framework |
| --- | --- |
| Benchmark agreed | Report on evaluation databases related to donors |
| Method | STE’s will perform a mission to the BC. STE’s will prepare the detailed questionnaire for the assessment of present Georgian National Blood Registry/Electronic Donor Database: legislation, functions, responsibilities, volume of data provided and etc. They will meet with specialists from NCDC&PH responsible for donor database, evaluate the results of questionnaire and discuss how it works in the country. The workshop will be organized to present the legal framework for the blood donors’ database in Lithuania and to share the experience: legislation, functions, responsibilities, the order of on-line reporting, Lithuanian experience of possibilities for Donor register data usage, examples of statistic data/reports and etc. The activity may be conducted by teleconference if the epidemiological situation of coronavirus prevents missions on the place. |
| Project month | August-September 2020 |
| MS resources | 1 mission for 3 days with 2 STE (6 working days in total) |
| MS experts | (LT): Svetlana Bogdanova (CPVA), Ugnė Butkute (CPVA) |
| BC resources | RTA counterpart, CL(1), Healthcare Policy Department of MoIDPLHSA (1), State regulation agency (1), NCDC (4), Blood banks (22), hospitals (5), stakeholders |
| Other resources | Interpretation by RTA language assistant Document translations (Georgian/ English/ Lithuanian/ Dutch) |

Component/Mandatory result 3: Blood transfussion services based on voluntary blood donation are able to ensure safe, adequate and sustainable blood supplies.

Indicator agreed

Share of blood centers that collect 100% of blood donations from voluntary non-remunerated donors

Baseline: 2018 – 0

Target: 2025 – at least 90% of blood establishments

Share of unpaid voluntary donations among total number of donations

Baseline: 2018 – 28% of total donations

Target: 2025 – at least 90% of the total donations

Share of repeat donors among total donor pool recruited within the year

Baseline: 2018 – 12% of total donations

Target: 2025 – at least 50% of total donations

Share of educational institutions with specific awareness raising program on blood transfusion and unpaid voluntary donations

Baseline: 2018 - 0

Target: 2022 – at least 50% of educational institutions

Sub-result 3.1: Awareness of the general population and specific target groups on blood transfusion increased

Indicator agreed

- Availability of a communication strategy for enhancing voluntary, non-remunerated donations from at low risk population including education, motivation, attraction, mobilization, recruitment and retention;

Baseline: Findings from 2016 focus group survey (94 interviewees)

Target: end of 2020 – communication strategy for popularization unpaid voluntary donations developed

- Availability of thematic courses on societal benefits of blood donations for secondary schools and higher educational institutions and status of their integration into the educational curricula of secondary schools and higher educational institutions;

Baseline: 2019 – N/A

Target: 2020 – educational curricula for secondary schools and higher educational institutions developed / endorsed and their  piloting started in at least 10 public schools and 2 higher educational institutions across the country

- Availability of collaboration platforms between governmental entities, public and private institutions to promote a positive social image of blood donors and to create a culture of voluntary unpaid donations;

Baseline: 2019 – N/A

Target: 2020 – Memorandum of Understanding with the Ministry of Education, Science, Culture  and Sport of Georgia signed;

Intersectoral working group established

- Availability of an implementation plan for the introduction of obligatory non-remunerated blood

donations;

Baseline: 2019 – N/A

Target: 2020 – legal bases and implementation plan for introduction of obligatory non-remunerated donations developed including contingency plans to response possible blood shortage and ensure country’s self-sufficiency

| Activity 3.1.1 | Sharing experience of Lithuania and the Netherlands on enhancing voluntary, non-remunerated donations |
| --- | --- |
| Benchmark agreed | Organized workshop to share experience of Lithuania and the Netherlands on enhancing voluntary, non-remunerated donors. Recommendations for implementation of voluntary, non-remunerated donations strategies. |
| Method | STE’s will perform a mission to the BC where the workshop will be organized and the experience of Lithuania and the Netherlands presented to implement the programs promoting the unpaid blood donation, as well as changing donation strategies. The communication strategy and other complementary programs to promote donors motivation, attraction, mobilisation, recruitment and retention will also be presented. The activity may be conducted by teleconference if the epidemiological situation of coronavirus prevents missions on the place. |
| Project month | September-October 2020 |
| MS resources | 1 mission for 4 days with 5 STE (20 working days in total) |
| MS experts | (LT): Diana Remeikiene (HLUHS), Vaida Jaramine (VUHSK), Ieva Linkeviciute (NBC) (NL): Wim de Kort (UA), Hans Vrielink (Sanquin) |
| BC resources | RTA counterpart, CL(1), Healthcare Policy Department of MoIDPLHSA (2), Ministry Education and Science (2), Tbilisi State Medical University (2), Agency for emergency situation coordination and urgent care (2), NCDC (4), Blood banks (22), stakeholders |
| Other resources | Interpretation by RTA language assistant Document translations (Georgian/ English/ Lithuanian/ Dutch) |

Component/Mandatory result 4: Capacity of relevant state authorities and other key stakeholders strengthened to ensure safety and quality of blood transfusion service

Indicator agreed;

Number of NCA personnel capable to perform blood bank inspections in accordance with EU standards

Baseline: 2019 – N/A

Target: end of 2021 – at least 4 inspectors and 2 administrative personnel

Number of TTI testing laboratory specialists capable to perform NAT testing

Baseline: 2019 – N/A

Target: end of 2021 – at least 6 laboratory specialists and 2 administrative personnel

Number of Reference Laboratory specialists capable to conduct QC, QA and QM in accordance with EU standards

Baseline: 2019 – N/A

Target: end of 2021 – at least 6 laboratory specialists and 2 administrative personnel

Number of public health professionals at BA and relevant governmental organizations with special knowledge and well  understanding of new requirements and updated regulations in blood safety

Baseline: 2019 – N/A

Target: end of 2021 – at least 10 public health professionals (BA, MoIDPLHSA and other relevant governmental entities)

## Sub-result 4.2. Capacities of the centralized laboratory and healthcare institutions (blood establishments, hospitals) strengthened

Indicator agreed;

-Availability of training needs analyses;

Baseline: 2019 – N/A

Target: Training needs analysis developed, needs identified and training plans developed with 6 month of project inception.

- Number of laboratory specialists trained and skilled in NAT methodologies and other high technologies for TTI testing;

Baseline: 2019 – N/A

Target: end of 2021 – at least 6 laboratory specialists and 2 administrative personnel

- Availability of Reference Laboratory specialists capable to conduct QC, QA and QM in accordance with EU standards;

Baseline: 2019 – N/A

Target: end of 2021 – at least 6 laboratory specialists and 2 administrative personnel

- Number of healthcare professionals (blood bank, clinical personnel) trained in application of new legislation, guidelines, standards and information management technologies for blood production, clinical use and haemovigilance.

Baseline: 2019 – N/A

Target: 2021 - at least 50 blood bank professional and 400 hospital personnel

| Activity 4.1.1 | Analysis of European regulation on organizing National Competent Authorities functions. |
| --- | --- |
| Benchmark agreed | Organized workshop to share experience of European countries on organizing National Competent Authorities functions. Report of workshop. Recommendations for implementation. |
| Method | A workshop and discussion with specialists from NCDC, Regulation Agency for Medical and Pharmaceutical Activities and other stakeholders on the experience of European countries on organizing National Competent Authorities functions were held: the role, tasks, and responsibilities of NCA as required by EU Blood Directives were reviewed: ensure that an appropriate mechanism for designating, authorising, licensing exists to provide that the activities of blood establishments are performed in accordance with the requirements of EU Blood Directives; organise inspection and control measures, to be carried out by officials representing the competent authority, to ensure the compliance of the blood establishments. STE’s will present the basic principles/methodologies of inspection organisations, qualification requirements for inspectors. The activity was conducted in teleconference mode due to epidemiological situation and following the EUD permission. |
| Project month | 25-26, 29-30 June, 2020 |
| MS resources | 1 mission for 4 days with 2 STE (8 working days in total) |
| MS experts | (LT): Agne Kaminskiene (NBC) (NL): W.Martin Smid (Sanquin), Jitske Heijn (Sanquin) |
| BC resources | RTA counterpart, CL(1), Healthcare Policy Department of MoIDPLHSA (5), State regulation agency (4), Social service agency (1), NCDC (5), stakeholders |
| Other resources | Interpretation by RTA language assistant Document translations (Georgian/ English/ Lithuanian/ Dutch) |

| Activity 4.2.1 | Analysis of European practical experience in centralized laboratory and healthcare institutions (blood establishments, hospitals) |
| --- | --- |
| Benchmark agreed | Organized workshop to share the European practical experience in the field of centralized laboratory and healthcare institutions (blood establishments, hospitals). Report of the workshop. |
| Method | STE’s will perform a mission to the BC. They will meet with specialists from NCDC and other stakeholders. STE’s will prepare questionnaire to collect relevant data on the current situation due to blood screening in Georgian blood centers/hospitals, including number of donations, testing methods and etc. Discussion and summarizing of questionnaire results will be organized. A workshop and discussion presenting the practical experience of European countries on organizing centralized laboratory. Training needs identification for laboratory specialists: based on the results of questionnaire and current European requirements for blood testing. The activity may be conducted by teleconference if the epidemiological situation of coronavirus prevents missions on the place. |
| Project month | November-December 2020 |
| MS resources | 1 mission for 4 days with 1 STE (4 working days in total) |
| MS experts | (NL) Anton van Weert (Sanquin) or Marco Koppelman (Sanquin) |
| BC resources | RTA counterpart, CL(1), NCDC (3), blood centers (22), hospitals (5), stakeholders |
| Other resources | Interpretation by RTA language assistant Document translations (Georgian/ English/ Lithuanian/ Dutch) |

ARTICLE 3: Risks

Successful implementation of the Project depends on a number of factors related to both internal conditions and those falling beyond of control of the Project partners. The following internal conditions related to the project must be fulfilled in order to guarantee its success:

- Sufficient communication, strong support and proactive cooperation of Twinning partners;

- Dedication and motivation, as well as resources of NCDC to implement the project;

- The blood Safety Working Group established at the MoIDPLHSA will cooperate with the project staff on the upgrading of the national legislation;

- Strong advocacy at high political level ensured.

| Risk | Corrective measures | Assumptions |
| --- | --- | --- |
| Corona pandemic and related situations had a direct impact on the performance of project with regard to timely implementation of planned activities | Use of telework modalities was allowed by the EUD during a country-wide lockdown and State of Emergency declared by the Government that lasted about two months. The project team decided to maintain some of the project activities through teleworking which was supported by the Beneficiary Administration and implemented in close cooperation with respective representatives. | It is assumed that despite delays in activities the current situation with regard to pandemics is mitigated and with a strong support and proactive cooperation of MS experts and BC administration the proper results will be achieved through activities conducted by teleconference. |
| Need for additional financial, technical, human resources | Translation of an additional legal framework from Lithuania into English was required within the 1st component that needs allocation of additional financial resources | It is assumed that additional financial resources will be mobilized to ensure fulfillment of functional and logistical issues |
| Need for additional financial, technical, human resources | Data processing of the questionnaire submitted by the blood banks (within activity 2.2.2) is to be conducted by a private sector to be hired under this project. | It is assumed that financial resources will be allocated to ensure implementation of technical, functional and logistical issues |
| Delays in project implementation process | Development of questionnaire for blood establishments in Georgia was delayed because of unavailability of international flights. The activity was postponed for several times as MS experts need to perform a mission to the BC and discuss a scope and specificity of questionnaire with Georgian working group in place. | It is assumed that international flight opportunities are opened from August and MS experts will be able to perform a mission to Georgia |

| Project imp. month |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| year |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |
| Act. | Title month | january | february | march | april | may | june | july | august | september | october | november | december | january | february | march | april | may | june | july | august | september |  |
| a. | RTA related activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # a.1. | # Start of implementation | # X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # a.2. | # Selection of RTA assistants | # X | # X | # X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # a.3. | # Drafting Initial Work Plan | # X | # X | # X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # a.4. | # Drafting Rolling Work Plan |  |  |  |  |  | # X |  |  | # X |  |  |  | # X |  |  | # X |  |  | # X |  | # X |  |
| # a.5. | # Drafting Quarterly report |  |  |  | # X |  | # X | # X |  |  | # X |  |  | # X |  |  | # X |  |  | # X |  | # X |  |
| 0. | Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # 0.1. | # Kick of meeting |  |  |  |  |  |  |  |  | # X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # 0.2. | # Final meeting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | # X |  |
| # 0.3. | # Steering Committee |  |  | # X |  |  |  | # X |  |  | # X |  |  | # X |  |  | # X |  |  | # X |  | # X |  |
| 1. | COMP 1: Approximation of Georgian primary and secondary legislation with the Union acquis on blood safety (Annex XXXI) performed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # 1.1 | Act. 1.1. - National regulatory framework in blood safety revised and upgraded in accordance with Union acquis on blood safety |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## 1.1.1. | ## Review draft Law on Quality and Safety of Blood and Blood Components and concomitant law package |  |  |  |  |  | ## X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## 1.1.2 | ## Translation of the recommendations and ## guidelines applied to blood collection and ## supply centers and public health facilities ## developed for the use in coronavirus emergency ## situations |  |  |  | ## X | ## X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## 1.1.3 | ## Translation of the General and Basic requirements for Blood establishments quality system of Lithuania and assistance of STEs in the process of development of draft Georgian standards |  |  |  |  |  |  |  | ## X | ## X | ## X |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. | COMP 2: A well-organized, nationally coordinated blood transfusion system established and functioning in accordance with the provisions of the Association Agreement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # 2.1. | National Competent Authority established and fully functional to take the role, tasks and resposibilities required by EU Blood Directives |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## 2.1.1. | ## The activity related to the establishment of the NCA as required by EU Blood Directives. |  |  |  |  |  |  | ## X | ## X | ## X | ## X |  |  |  |  |  |  |  |  |  |  |  |  |
| # 2.2. | Assesment of blood banks performed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## 2.2.1. | Study visit to MS to get acquainted with the European model of Blood Transfusion Systems |  |  |  |  |  |  | ## X | ## X | ## X | ## X |  |  |  |  |  |  |  |  |  |  |  |  |
| ## 2.2.2. | ## Assessment of blood banks in Georgia |  |  |  |  |  |  |  | ## X | ## X | ## X | ## X |  |  |  |  |  |  |  |  |  |  |  |
| # 2.3. | Reorganisation of blood transfusion service (BTS) provided |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## 2.3.1 | ## Drafting an Institutional Reform Plan for Blood Safety System in Georgia |  |  |  |  |  |  |  |  |  | ## X | ## X | ## X |  |  |  |  |  |  |  |  |  |  |
| ## 2.3.2 | ## Upgrade licensing requirements for blood establishments |  |  |  |  |  |  |  |  |  |  | ## X | ## X |  |  |  |  |  |  |  |  |  |  |
| # 2.4. | Transition to the mandatory non-profit organisational form for blood establishments initiated |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## 2.4.1. | ## Develop proposals including recommendations for transition to the mandatory non-profit organizational form for blood establishments regarding EU regulations |  |  |  |  |  |  | ## X | ## X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # 2.5. | Centralised TTI testing laboratory(s) established |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## 2.5.1. | Develop standards for centralized testing laboratory (including serological and molecular (NAT) testing |  |  |  |  |  |  |  |  |  |  | ## X | ## X |  |  |  |  |  |  |  |  |  |  |
| # 2.6. | National reference laboratory established |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## 2.6.1 | ## Roundtable on the need of National Reference Laboratory and its functions |  |  |  |  |  |  |  |  | ## X | ## X |  |  |  |  |  |  |  |  |  |  |  |  |
| # 2.7. | Nucleic Acid testing for blood screening for human immunodeficiency virus (HIV), hepatitis B virus (HBV) and hepatitis C virus (HCV) introduced at centralized testing laboratory(ies) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## 2.7.1. | The evaluation of pilot NAT blood screening testing in Lugar center |  |  |  |  |  |  |  |  |  |  | ## X | ## X |  |  |  |  |  |  |  |  |  |  |
| # 2.9. | Unified Electronic Donor Database upgraded |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## 2.9.1 | Evaluation of databases related to donors in Georgia and legal framework |  |  |  |  |  |  |  | ## X | ## X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. | COMP 3: Blood transfussion services based on voluntary blood donation are able to ensure safe, adequate and sustainable blood supplies. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # 3.1. | Awareness of general population and specific target groups on blood transfusion increased |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1. | Sharing experience of Lithuania and the Netherlands on enhancing voluntary, non-remunerated donations |  |  |  |  |  |  |  |  | ## X | ## X |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. | COMP 4: Capacity of relevant state authorities and other key stakeholders strengthened to ensure safety and quality of blood transfusion service |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # 4.1. | ## Capacities of the National Competent Authority and Beneficiary Administration strengthened |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.1. | Analysis of European regulation on organizing functions of the National Competent Authorities. |  |  |  |  |  | ## X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # 4.2. | ## Capacities of the centralized laboratory and healthcare institutions (blood establishments, hospitals) strengthened |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.2.1. | Analysis of European practical experience in centralized laboratory and healthcare institutions (blood establishments, hospitals) |  |  |  |  |  |  |  |  |  |  | ## X | ## X |  |  |  |  |  |  |  |  |  |  |

ARTICLE 5: Human Resources

| Member State or Beneficiary | Name | Present position | Employer | Years of experience | Education | Specialist knowledge | BC experience | Languages |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Lithuania | Daumantas Gutauska | Director of PI National Blood Center | PI National Blood Center | 7 years | Mykolas Romeris University – Master of law; Vytautas Magnus University – Master of International Relations | Professional experience in strategic planning and work process management |  | Fluency in written and spoken English |
| Lithuania | Agnė Kaminskienė | Lawyer | PI National Blood Center | 11 years | Mykolas Romeris University, master’s and bachelor’s degrees in law | Professional experience in drafting and assessment of health minister orders, participation in working groups; representation of the institution in international conferences, other institutions, courts, preparation of procedural documents; ensuring that all activities carried out by the institution comply with the applicable legislation. |  | Fluency in written and spoken English |
| Lithuania | Laimute Stoniene | Head of Quality assurance department | PI National Blood Center | 28 years | Master degree of Public Health | 28 years practical experience in relevant related to blood collection, preparation and quality assurance areas in blood establishment. Experience in implementing EU directives related to quality system in blood establishments (2002/98/EC, 2004/33/EC, 2005/61/EC, 2005/62/EC, Good Practice Guidelines following adoption of the GPG by the EC, through Commission Directive (EU) 2016/1214.) in Lithuania and drafting legislation in Lithuania. |  | Fluent in English |
| Lithuania | Renata Poviliuniene | Deputy director of Klaipeda branch | PI National Blood Center | 8 years | MD medicine, bachelor of Management and Business administration | Sound comparative knowledge of BTS organization and controlling/supervisory institutional structures (including accreditation, designation, authorization or licensing of blood establishments as well as Inspections and control measures) |  | Fluent in English |
| Lithuania | Diana Remeikine | Head of Blood Center | Hospital of Lithuanian University of Health Sciences Kauno klinikos | 28 years | MD medicine | Involvement in the drafting of national legislation in the field of voluntary blood donation. Daily activities include creation and implementation of the methods for motivation, attraction, and retention of regular blood donors. Popularization and encouragement of voluntary unpaid donations are between the main duties of daily work. |  | Fluent in English |
| Lithuania | Ieva Linkeviciute | Medical doctor, Acting Head of Donation Departament | PI National Blood Center | Medical doctor – 2,7 years; lawyer – 1 year; temporary Head of Donation Departament position – 10 month. | Master of medicine (medical doctor qualification); Master of biomedicine law | Sound knowledge and particular skills in blood donor recruitment and popularization of regular voluntary non – renumerated donations; experience in awareness raising, information campaigns and knowledge of different communication Tools. Specific knowledge of organizational structure, statutory models and institutional capacities of blood transfusion service in Member State |  | Upper-intermediate in written and spoken English; elementary written and spoken Russian |
| Lithuania | Vaida Jaramine | Quality manager | Vilnius University Hospital Santaros Klinikos (VUHSK) | 7 years | Statistician, statistics | Quality management, donor recruitment Further continous in house IT system upgrading |  | Fluent in English |
| Lithuania | Svetlana Bogdanova | Head of the Donor Register | Insitute of Hygiene | 18 years | Engineer programmer, Master gegree engineer-economis | Development of Blood Donor Register (preparation of Blood Donor Register legislation, preparation of technical description, analysis of needed human resources and technical equipment) |  | Fluent in English |
| Lithuania | Ugne Butkute | Head of children health monitoring information system | Insitute of Hygiene | 12 years | Master of Administration of Health Care Institution, Bachelor of Public Health | Creating the model of Children's Health Monitoring Information System (IS). Revising legislation of children's health and proposals to change. Consulting developers about creating IS. Testing of creating IS: error identification, suggestions after testing. Analysing documents prepared by the developers and conformity of IS being developed with them. |  | Fluent in English |
| Lithuania | Juozas Galginaitis | Advisor o the Dean (Legal affairs), Associate professor | Vilnius University, Faculty of Medicine Faculty of Law | 28 years | Master of Law, PhD Social Sciense | Experience with legal information systems, higher education management information systems |  | Fluent in English |
| Lithuania | Vilnele Lipnickiene | Laboratory medicine physician | National Public Health Surveillance Laboratory; Medical Diagnostic and Treatment Center | 38 years | BA in Epidemiology, Hygiene and Sanitary Physician | Forensic medicine expert, laboratory medicine physician in Lithuanian AIDS Center, currently involved in clinical biochemistry and immunology laboratory activities |  | Upper-Intermediate level in spoken English, Advanced in Russian |
| Netherlands | Hans Vrielink | Transfusion and Apheresis Specialist/ Consultant | Sanquin Blood Supply Foundation | 27 years | PhD, MD Medicine | Transfusion medicine Apheresis specialist Training and education on apheresis and donor recruitment |  | Fluent in English |
| Netherlands | Martin Smid | Managing Director Sanquin Consulting Services Director Academic Institute for International Development of Transfusion Medicine | Sanquin Blood Supply Foundation | 27 years | MBA, PhD, MD Medicine | Transfusion medicine Management Blood Bank Education |  | Fluent in English |
| Netherlands | Peter van den Burg | Transfusion specialist Medical Director EBA | Sanquin Blood Supply Foundation | 25 years | PhD, MD Medicine | Transfusion specialist Education EDQM |  | Fluent in English |
| Netherlands | Marco Koppelman | Head of NAT laboratory | Sanquin Blood Supply Foundation | 30 years | PhD, Molecular biology | NAT Blood screening Development of PCR |  | Fluent in English |
| Netherlands | Anton van Weert | Manager National Screening Centre | Sanquin Blood Supply Foundation | 28 years | PhD Medicine, Master in Chemistry | Management of National Screening Centre for TTI testing and blood grouping |  | Fluent in English |
| Netherlands | Wim de Kort | Professor of Donor Health Care | University of Amsterdam | 22 years | PhD, MD Medicine | Excellent experience in high quality research >100 international peer reviewed papers Editor-in-Chief Donor Management Manual (DOMAINE project) |  | Fluent in English |
| Netherlands | Olenka van Ardenne | Senior Legal Counsel | Sanquin Blood Supply Foundation | 36 years | Master of Civil Law/Attorney at Law.. | Legal expert Experienced in advices on professional registration of medical disciplines, guidelines, development of regional cooperation, several projects, developing standards in the field of technical medicine. |  | Fluent in English |
| Netherlands | Jitske Heijn | Director Quality and Regulatory Affairs | Sanquin Blood Supply Foundation | 15 years | Bachelor Health Science/Physical Therapy | Qualtiy expert, Lead Auditor/Health Care auditing |  | Fluent in English |

ARTICLE 6: Budget

See, Annex 1: Budget of the Rolling Work Plan

Annexes to the Rolling Work Plan:

Annex 1: Budget of the Rolling Work Plan

Annex 2: CV’s of short term experts

The Member State PL

[signature]

[date]

The Beneficiary Country PL

[signature]

[date]