Results Framework

COUNTRY: Georgia Georgia Emergency COVID-19 Project

Project Development Objective(s)

The Project Development Objective is to prepare for and respond to the COVID-19 pandemic in Georgia

Project Development Objective Indicators

| Indicator Name | DLI | Baseline | End Target |
| --- | --- | --- | --- |
| The Project Development Objective is to prepare for and respond to the COVID-19 pandemic in Georgia |  |  |  |
| Number of suspected cases of COVID-19 reported and investigated per approved protocol (Number) |  | 336.00 | 10,000.00 |
| Number of designated public hospitals with fully equipped and functional intensive care units (ICUs) for COVID-19 patients (Number) |  | 0.00 | 4.00 |
| Share of households in the poorest quintile who are receiving the COVID-19 pandemic related social assistance programs. (Percentage) |  | 40% | 45% |

Intermediate Results Indicators by Components

| Indicator Name | DLI | Baseline | Intermediate Targets | End Target |
| --- | --- | --- | --- | --- |
|  |  |  | 1 |  |
| Emergency COVID-19 Response |  |  |  |  |
| Number of designated laboratories with COVID-19 diagnostic equipment, test kits, and reagents per MOHLSA guidelines. (Number) |  | 0.00 |  | 4.00 |
| Number of personal protection equipment (PPE) purchased.(Number) |  | 0.00 |  | 800,000 |
| “Percentage of designated public hospitals with isolation capacity (Percentage)” |  | 0.00 |  | 75%.0 |
| Temporary income support for poor households and vulnerable individuals affected by COVID-19 |  |  |  |  |
| Number of vulnerable households receiving temporary emergency cash benefit, disagregated by disaggregated by (i) households with/wo at least one work able member without labor income, (ii) households with children (up to 18 years-old), (iii) households with at least a member with disabilities. (Number) |  | 0.00 |  | 120,000 |
| Number of formal private sector workers laid off because of COVID-related lockdown restrictions who receive a temporary unemployment benefit, by gender. (Number) |  | 0.00 |  | 90,000 |
| Number of TSA beneficiary households. (Number) |  | 118,100 |  | 150,000 |
| Complaints received related to COVID-related social assistance programs (percentage). |  | 0.00 |  | 5% |
| Project Management |  |  |  |  |
| Percentage of beneficiaries reporting that community engagement and outreach meet their needs (percentage) |  | 0.00 |  |  |

IO Table SPACE

UL Table SPACE

| Monitoring & Evaluation Plan: PDO Indicators |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Indicator Name | Definition/Description | Frequency | Datasource | Methodology for Data Collection | Responsibility for Data Collection |

| Indicator Name | Definition/Description | Frequency | Datasource | Methodology for Data Collection | Responsibility for Data Collection |
| --- | --- | --- | --- | --- | --- |
| Number of suspected cases of COVID-19 reported and investigated per approved protocol | Cumulative number of suspected cases reported that are investigated according to MoLHSA -approved protocol | Every 6 monhts | MoLHSA and NCDC | Administrative data, audits | MoLHSA and NCDC |
| Number of designated public hospitals with fully equipped and functional intensive care units (ICUs) for COVID-19 patients (Number) | An ICU unit will be considered fully equipped and operational if two conditions are satisfied: (i) all individual beds in the ICU unit have the necessary equipment as per MoHLSA guidelines; and (ii) ICU unit (comprising of multiple beds) has all necessary shared equipment as per MoHLHSA guidelines.. | Every 6 months | MoLHSA. | Administrative data records, field verification of availability of equipment. | MoLHSA. |
| Share of households in the poorest quintile who are receiving the COVID-19 pandemic related social assistance programs. | COVID-19 pandemic related social assistance programs refer to the emergency cash benefit, the temporary unemployment benefit and the TSA. Quintile of the adult equivalent consumption distribution net of social assistance transfers. | Annually | HIES survey | Survey data nationally representative. | GEOSTAT |

ME PDO Table SPACE

| Monitoring & Evaluation Plan: Intermediate Results Indicators |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Indicator Name | Definition/Description | Frequency | Datasource | Methodology for Data Collection | Responsibility for Data Collection |  |
| Emergency COVID-19 Response |  |  |  |  |  |  |
| Number of designated laboratories with COVID-19 diagnostic equipment, test kits, and reagents per MOH guidelines. (Number) | Number of designated laboratories supported under the project with COVID-19 diagnostic equipment, test kits, and reagents per MoHLSA guidelines. The technical specifications of the tests will be defined in the Project Implementation Manual based on the national norms and standards for COVID-19 response. | Every 6 months | MoHLSA | Laboratory Audit | MoHLSA |  |
| Number of personal protection equipment (PPE) purchased. (Number) | Cumulative number of personal protective equipment purchased, including gloves, protective goggles, chirurgical masks/ear loop, face mask FF2, face mask N95, gown AAMI level 3, shoe covers, protection caps, scafanders. | Every 6 months | MoHLSA | Administrative data | MoHLSA |  |
| Percentage of designated public hospitals with isolation capacity (Percentage)” | Percentage of designated public hospitals that have operational isolation capacity (isolation rooms in admission departments and isolation wards in designated departments). Designated public facilities are those identified by the MOHLSA for observation of suspected cases and treatment of confirmed COVID-19 cases. | Every 6 months | MoHLSA | Administrative data and audit reports | MoHLSA |  |
| Temporary income support for poor households and vulnerable individuals affected by COVID-19 |  |  |  |  |  |  |
| Number of vulnerable households receiving temporary emergency cash benefit, disagregated by disaggregated by (i) households with/wo at least one work able member without labor income, (ii) households with children (up to 18 years-old), (iii) households with at least a member with disabilities. | “Vulnerable” households are defined as those households with at least one work able member without labor income, households with children; households with at least one member with disability. Data will be disaggregated by : - households with/wo at least one work able member without labor income, - households with children (up to 18 years-old); - households with at least a member with disabilities. | Every 6 months | Social Registry (SSA) | SSA Administrative data | SSA in MoHLSA |  |
| Number of formal private sector workers laid off because of COVID-related lockdown restrictions who receive a temporary unemployment benefit, by gender. (Number) | Formal private sector workers are defined as workers appearing in Revenue Service Registry data (workers for which employers pay payroll taxes). Laidoffs will be reported by employers and confirmed by Revenue Service based on their registry. Sex-disaggregated data will be monitored. | Every 6 months | Social Registry (SSA) | SSA Administrative data | SSA in MoHLSA |
| Number of TSA beneficiary households. (Number) | TSA beneficiary households are defined as households with a PMT score below 65,001 based on the existing scoring formula (determined by Res. 758 of December 31, 2014). | Every 6 months | Social Registry (SSA) | SSA Administrative data | SSA in MoHLSA |
| Complaints received related to COVID-related social assistance programs (percentage). | This indicator tracks the number of complaints received relating to COVID-19 related social assistance programs to help identify problems and address them as necessary. COVID-19 pandemic related social assistance programs refer to the emergency cash benefit, the temporary unemployment benefit and the TSA. | Every 6 months | SSA management system | SSA monitoring reports | SSA in MoHLSA |
| Project Management |  |  |  |  |  |  |

ME IO Table SPACE