## Slide 1: Strategic Purchase Strategy Indicators and Initiatives

## Slide 2: Objective: Improvement of quality and efficiency of health care services
2019 | 2020 | 2021
Situational analysis and advocacy between interest groups (state agencies, providers, doctors); Develop quality improvement strategies and instruments | Quality improvement strategy and tools are ready for implementation | 
Development of Control Concept for Quality of Service; Mobilization of structural units and human resources; Development of Control Concept for Quality of Service; | Piloting of indicators and instruments | Start the introduction of indicators system
 | Identification of standards and audit criteria; Elaboration / development of assessment levels and methodologies; | Final review of the medical audit concept; Analysis of feedback from professionals and international partners
Develop a quality system resume concept.
Development of quality, monitoring and control mechanisms of medical care.
Implementation of medical audit.
Initiatives

## Slide 3
2019 | 2020 | 2021
Preparing for pilot clinics DRG Pilot Clinics; Developing DRG fees and remuneration policies; | DRG's "virtual introduction" in all clinics; General readiness for DRG implementation | Introduction of DRG as a mechanism for remuneration
Review of financial healthcare systems, involvement of RBF indicators; Piloting RBF; | Last review; Preparing for a new model of primary healthcare funding | 
Develop a new system of contraception; Designing the design of hospital services according to major diagnostic categories (MDC) | Evaluate the work of the provider and develop MDC-based planning principles / preparation of a "virtual contract" pilot; Approval of regulation | Final preparation, introduction
 | Analysis of services, existing resources, epidemiological and international data | Introduction of each direction needs
Develop and implement DRG system.
Critical assessment of primary health care financing principles based on the results of funding (RBF).
Elaboration of the principles of contracts, including selective contracts and monitoring / evaluation of the performance of the contract.
Assessment of healthcare needs needs
Objective: Improvement of Payment and Controlling Mechanisms
Initiatives

## Slide 4: Objective: The package of health care services meets the needs of the population
Review and update package of health care services
2019 | 2020 | 2021
 | Analysis of existing packets consumption, identification of weak and strong sides; Health needs, alarms and financial resources analysis | Renewal of health care services package
Initiatives

## Slide 5: Objective: Providing equitable access to specialist services and strengthening primary care
Review of referral system and development of family doctor's functions
Strengthening Capacity of Family Doctors (Certification and Continuous Medical Education)
Initiatives
2019 | 2020 | 2021
Piloting of data collection and new contracts in selected PAC centers in Tbilisi | Piloting of data collection and new contracts in the area of 14 pcs in the regions. Analysis of the frequency and out-patient conditions of hospitalization according to the PAC centers. Revision / change of primary health care system. | 
Develop a continuous medical education system and curriculum for family doctors | Development of a family doctor's qualification monitoring system Certification and continuous medical education plan. Review, final readiness to introduce family doctors training and reckling system | 

## Slide 6: Goal: Consolidation of highly specialized and hospital services
Initiatives
Establish a sustainable procurement plan for hospital, including highly specialized services.
2019 | 2020 | 2021
 | Hospital services Analysis of need; Provide current distribution of providers; Approval of the law (regulation). | Introduction of the plan

## Slide 7: Objective: More transparency and raising awareness of the population
Initiatives
Introduction of quarterly statements of strategic procurement strategy;
Development of citizens' mobile and applications to increase transparency for patients;
Establishment of communication plan with citizens
2019 | 2020 | 2021
Piloting - reporting |  | 
Survey of citizens; Feedback analysis; Final job of citizen's portal and applications, open information about beneficiaries To access |  | 
Develop and develop communication concept with citizens |  | 

## Slide 8: Objective: Improve electronic data exchange and data quality
Initiatives
Determining the needs of electronic data exchange with the participation of interest groups;
Introduction of electronic signature
Identification of the application management process, electronic solution
2019 | 2020 | 2021
System analysis and IT development plan to support strategic procurement |  | 
Defining the software features (activity depends on the introduction of electronic medical records); Final preparation, introduction. |  | 
Defining the future SOP for the universal health care program Introduction and training to get familiar with new practices in the Agency. Introduction of new applications for application management |  | 

## Slide 9: Objective: Adjusting the structure of the Social Service Agency on Strategy
Initiatives
2019 | 2020 | 2021
Approval of the new structure design and preparation of the plan of implementation; Analysis of human resources needs; Appointment of the main position of the central structure of the Agency; Go to new structure, central office 01.07.2019; Elaboration of the plan for bringing in regional and central structures; The new design of the health care direction agency is fully implemented |  | 
Social New design of the health care direction structure of the Agency Agency;
Development of the principles and functions of the healthcare economy in the Agency;
Compliance with functions structure

## Slide 10: Objective: To increase the motivation and competence of the Social Service Agency personnel
Initiatives
Determination of core competences for the implementation of strategic procurement, elaboration of the competence development system and the plan for the health care personnel of the Agency.
2019 | 2020 | 2021
The functions and competences of the new structural personnel of the agency are defined; Competence Raising Plan is fundamental to the main staff of the structure and is ready for implementation |  | 

## Slide 11: Objective: Improve monitoring, reporting and analysis
Development of the organization's health direction organizational planning and reporting system;
Reporting and performance reports (regional offices, strategy);
Annual Work Report
Initiatives
2019 | 2020 | 2021
The report on the implementation of the Strategy is prepared and the quarterly working group meeting is held; Annual annual sample (yearbook) 2019 has been developed in the first years of experience; The strategic procurement strategy 2020-2022 revision process has been completed | Annual report (yearbook) of the Strategic Purchase Strategy of 2019 is prepared |