Logical Framework

Primary Health Care (PHC)

|  | Results chain: Main expected results | Indicators | Source of data | Assumptions |
| --- | --- | --- | --- | --- |
| Impact (Overall Objective) | All people in Georgia have equitable access to essential quality health care and are protected from catastrophic health expenditures | Mortality rate attributed to cardiovascular disease, cancer, diabetes or chronic respiratory disease (SDG 3.4.1) Baseline (2021): TBD Target (2025): Reduced against BL | GeoStat National Center for Disease Control and Public Health | - The Government of Georgia remains committed to the implementation of Universal Health Care Programme; - The macro-economic situation in the country stabilizes and the forecasts for the health sector are realistic; - The Development Partners continue to support the implementation of the Universal Health Care Programme |
|  |  | Coverage of population by essential health services (SDG 3.8.1) Baseline (2021): TBD Target (2025): Increased to at least 90% | UHC-P / WHO monitoring database National Center for Disease Control and Public Health |  |
|  |  | Proportion of children immunized and fully vaccinated Baseline (2021): TBD Target (2025): Increased against BL | ფ. IV-077 (იმუნიზაციის მართვის ელექტრონული მოდული) |  |
| Outcomes (Specific Objectives) | Outcome 1: Strengthened health sector governance and financing mechanisms with an emphasis on PHC in place | Health system score of governance and financing performance Baseline (2021): TBD Target (2025): Increased/improved against BL | Performance monitoring and reporting on governance and financing, measured in scores |  |
|  | Outcome 2: Integrated PHC of improved access and service quality in place | Patients’ satisfaction with accessibility and quality of PHC services Baseline (2021): TBD Target (2025): Increased/improved against BL | Study to survey patient satisfaction |  |
|  |  | Proportion of visits to a physician / nurse per reporting period Baseline (2021): TBD Target (2025): Increased against BL | ფ. IV-01 (სამედიცინო დაწესებულების ანგარიში), EHR (UHC) |  |
|  |  | Proportion of population covered by integrated screening (HEP C, HIV, TB) Baseline (2021): TBD Target (2025): Increased against BL | ფ. IV-16 C ჰეპატიტის სკრინინგის ელექტრონული აღრიცხვიანობის მოდული |  |
| Outputs | Output 1.1: Governance mechanisms upgraded at the national, sub-national and local levels linked to effective use of information/HMIS data, HR development and bottom up initiatives enabling performance improvements | Evidence of development and monitored implementation of updated regulation, methods and procedures of health governance function at the national, sub-national and local levels Baseline (2021): Designed and planned Target (2025): Implemented nationwide | National regulation – GoG decrees Ministry of Health regulation – decrees, orders, instructions, MOH annual reports for GoG Performance monitoring and reporting on governance and financing, measured in scores |  |
|  | Output 1.2: Robust public budgeting in health is introduced and meets requirements of PFM and nationwide implementation of UHC Programme with health financing mechanisms enabling equity, efficiency and quality of service delivery | Evidence of health sector budget developed and allocated equally across the country and strategic purchasing of health services with enhanced facility autonomy, within enhanced PFM context Baseline (2021): Designed and planned Target (2025): Implemented | Ministry of Finance (MOF) data on budgets planned/approved MoF quarterly and annual reports on budget execution inclusive sub-national and local budgetary levels Performance monitoring and reporting on governance and financing, measured in scores |  |
|  | Output 2.1: Concept and mechanism of integrating PHC delivery developed, agreed and implemented with an emphasis on strengthening family medicine | Number and percentage of health facilities, which functions/services integrated into the PHC delivery Baseline (2021): TBD Target (2025): Increase against BL | National regulation – GoG decrees MOH regulation – decrees, orders, instructions |  |
|  | Output 2.2: Population access to integrated PHC services improved | Proportion of population served by PHC facilities rendering integrated health services Baseline (2021): TBD Target (2025): Increase against BL | GeoStat - Demographic statistics by jurisdictions National Center for Disease Control and Public Health |  |
|  |  | Number of women and girls served by PHC facilities rendering integrated health services Baseline (2021): TBD Target (2025): Increase against BL | GeoStat - Demographic statistics by jurisdictions National Center for Disease Control and Public Health |  |
|  |  | Proportion of persons enrolled in a chronic medication program Baseline (2021): TBD Target (2025): Increased against BL | ქრ. მედიკამენტების მოდული |  |
|  |  | Number of visits to patients receiving DOT treatment per month Baseline (2021): TBD Target (2025): Increased against BL | ფ. IV-07/1 ტუბერკულოზის შემთხვევათა რეგისტრაციის ანგარიში; ფ. IV-07/2 12 თვის წინ რეგისტრირებული სენსიტიური ტუბერკულოზის შემთხვევების მკურნალობის შედეგების ანგარიში EHR (UHC) |  |
|  |  | Proportion of diabetes patients who underwent at least one HbA1c (glycohemoglobin) test in the past 12 months Baseline (2021): TBD Target (2025): Increased against BL | ფ. IV-01 სამედიცინო დაწესებულების ანგარიში EHR (UHC) |  |
|  |  | Proportion of patients diagnosed with coronary heart disease who underwent lipid spectrum screening in the past 12 months Baseline (2021): TBD Target (2025): Increased against BL | ფ. IV-01 სამედიცინო დაწესებულების ანგარიში; EHR (UHC); ქრ. მედიკამენტების მოდული |  |
|  |  | Proportion of patients diagnosed with hypertension who receive chronic medication Baseline (2021): TBD Target (2025): Increased against BL | ფ. IV-01 სამედიცინო დაწესებულების ანგარიში; EHR (UHC); ქრ. მედიკამენტების მოდული |  |
|  | Output 2.3: Quality management and improvement mechanism developed and introduced in health facilities with the emphasis on PHC settings | Evidence of development and implementation of updated Continuous Professional Development and Continuous Medical Education in PHC Baseline (2021): Developed Target (2025): Introduced nationwide | National regulation – GoG decrees MOH regulation – decrees, orders, instructions |  |
|  |  | Number and percentage of PHC health facilities with introduced quality management and improvement measures inclusive of updated clinical protocols and Standard Operational Procedures; rational drug management practices; quality improvement planning and routine business planning Baseline (2021): TBD Target (2025): Increase against BL | Health facility survey |  |
|  |  | Proportion of referrals to specialists / for clinical-diagnostic research / for instrumental research Baseline (2021): TBD Target (2025): Increased against BL | EHR (UHC) |  |
|  |  | Proportion of hospitalization Baseline (2021): TBD Target (2025): Decreased against BL | ფ. IV-066; UHC - შეტყობინებათა მოდული, |  |

Defined as the average coverage of essential services based on tracer interventions that include reproductive, maternal, new-born and child health, infectious diseases, non-communicable diseases and service capacity and access, among the general and the most disadvantaged population (please also refer to Decree No 36 of the Government of Georgia of 21 February 2013 on Universal Health Care Program)

To develop/adapt and apply health governance and financing performance assessment to Georgia (please also refer to WHO PHC-IMPACT and Primary Care Evaluation Tool)

Survey to be designed by MoH

This indicator included to reflect the HDP will contribute to the Gender Action Plan of the EU (2016-2020) - and concretely to its objective 10 (access to quality health care services for women and girls.

Content of required Quality Management and Quality Improvement package to be defined by MOH for indicator measurement