TERMS OF REFERENCE
Improving Nursing and Midwifery Skills in Georgia: 
Establishing a Professional Regulator, Licencing and Registration

[DRAFT FOR COMMENTS] 6 August 2020

# Introduction

Economic inclusion is at the heart of the European Bank for Reconstruction and Development’s (EBRD) mandate to foster transition towards sustainable market economies among its countries of operations. Economic inclusion is the opening up of economic opportunities to disadvantaged social groups. Economic opportunities, in turn, encompass such groups’ access to jobs and skills; to finance and entrepreneurship; and to the services and tools that enable economic activity (such as education, transport, infrastructure, ICT, utilities and others).

EBRD’s approach to economic inclusion delivers a broad range of targeted programmes improving economic opportunities and outcomes for young people, women, those living in under-developed regions and others (including people with disabilities, older workers and refugees). Since 2012, EBRD has generated more than 200 projects explicitly promoting economic inclusion and gender equality underpinned by more than EUR 7.5 billion in investments.

Aligned with this agenda, EBRD and the Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs of Georgia (“the Ministry”) signed a formal Memorandum of Understanding in March 2020 “In Respect of Improving Nursing and Midwifery Occupations in Georgia through Professional Licencing, Related Skills Standards and Implementation Support” (“the MoU”). The MoU’s aim is to strengthen Georgia’s nursing and midwifery occupations, boosting workforce skills, professional development and, ultimately, healthcare quality. The MoU, in substance, commits to the fulfilment of three core objectives:

- Establishing core governance principles and standards for Georgia’s forthcoming professional licencing / certification scheme for nurses (including midwives);

- Defining related knowledge criteria, exam standards and a test-bank aligned to the new professional licencing / certification curriculum; and

- Creating and piloting a short-term continuous learning programme aligned to the new professional licencing / certification requirements.

The Terms of Reference outlined below (“the Assignment”) underpin fulfilment of the first of these objectives (Objective A). (Follow-up assignments forthcoming in 2021 will contribute towards the MoU’s Objectives B and C.)

EBRD and the Ministry seek the deliverables outlined below from an expert implementation partner (“the Consultant”) to define a detailed blueprint for establishing a new professional regulator for nursing and midwifery in Georgia, fulfilling professional licencing, registration and associated functions. The work will cover core governance principles and standards for such a regulatory body; the key responsibilities of affiliated stakeholders and those affected by the new body; funding needs and sustainability implications; and other important considerations, applying the international best practices in this area to Georgia’s context. The Assignment will ultimately guide the Ministry in establishing a robust regulatory body by 2023 and implementing the full rollout of its licencing and registration functions by 2025 in line with the Ministry’s strategic priorities.

# Background

Insufficient education for nurses and midwives inhibits Georgia’s healthcare sector. Bachelor’s level programmes are not subject to clear teaching standards, giving rise to skills mismatches. Neither occupation is robustly regulated nor subject to professional licensing requirements, which reduces accountability for skills and conduct. Moreover, an absence of local-language textbooks results in ad hoc learning outcomes. Nursing and midwifery occupations consequently underperform in Georgia, despite their high demand. The ongoing Covid-19 pandemic crisis has only emphasised the cause for enhancing Georgia’s healthcare workforce skills and improving regulation.

Georgia’s medical workforce is distinguished by a significant shortage of nurses and midwives, achieving one of the lowest per-capita levels in EBRD’s geography and totalling only 0.7 nurses for every medical doctor (significantly below the World Bank’s recommended ratio of 4:1 for ensuring cost-effective and quality care). Georgia encounters equally critical shortages among midwives.

The Parliament of Georgia issued a Vision for Developing the Healthcare System in Georgia by 2030 in 2017, highlighting a number of objectives and actions related to nurses and midwives’ education, training and performance (pp.11-13):

2.1.3.	Increase the number of nurses to achieve an adequate balance of medical staff.

2.2.	Support education for nurses, including the following:

2.2.1.	Subsidize/stimulate education for nurses from the side of the state.

2.2.2.	Due to the lack of nurses, support the system of re-training nurses at the transitional stage.

2.2.3.	Support the development of bachelor and master programmes in nursing.

2.3.	Develop and implement tools for regulating nursing activities with active engagement of professional organizations in the field:

2.3.1.	Define competencies for nurses and develop the tools for assessing their professional knowledge and skills.

2.3.2.	Gradually introduce/implement the process of registration/certification for nurses.

2.3.3.	Ensure the functioning of a formalised system of continuing professional development for nurses and support the sustainability of the system.

The Vision includes a monitoring target to increase the ratio of nurses to medical doctors from its then 0.7:1 to at least 2:1 by 2030.

The Ministry issued a more targeted Strategy for the Development of Nursing in July 2019 (GoG Decree 334, 16.07.2019) with a primary objective (Goal 1) on “Promoting the improvement of the quality and availability of healthcare services” with full take-up of professional licencing and registration among nurses by 2025 (Outcome Indicator 1.2.2) alongside related sub-objectives:

| Indicators |  | Baseline (and year) | Mid-term target by 2022 | Eventual target by 2025 |
| --- | --- | --- | --- | --- |
| Goal 1. Promoting the improvement of the quality and availability of healthcare services through generation of qualified human resources in nursing and creation of a sustainable professional regulation system |  |  |  |  |
| Impact Indicator 1.1. | In-patient mortality rate | 2.6% (2017) | 2.4% | 2.2% |
| Impact Indicator 1.2. | Ratio of nurses to medical doctors | 0.7:1 (2017) | 1:1 | 1.3:1 |
| Impact Indicator 1.3. | Patients’ satisfaction with nursing services | n/a | 40% of respondents | 65% of respondents |
| Objective 1.1. Developing a healthcare system focused on generating qualified human resources in nursing |  |  |  |  |
| 1.1.1. New nursing graduates per year |  | 916 (2018) | +15% | +30% |
| 1.1.2. Number of nurses per 100,000 people |  | 509 (2017) | 550 | 610 |
| Objective 1.2. Developing a sustainable system of continuous professional development and regulation |  |  |  |  |
| 1.2.1. Share of employed nurses participating in formal system of continuous professional development |  | 0% (2019) | 10%* | 50% |
| 1.2.2. Share of employed nurses who have gone through licencing /registration / certification processes |  | 0% (2019) | 10%* | 100% |
| Objective 1.3. Promotion and awareness-raising of nursing |  |  |  |  |
| 1.3.1. Students enrolled for nursing and midwifery |  | 958 (2018) | +15%* | +30% |
| 1.3.2. Awareness of the significance of nursing |  | n/a | 50% positive response* | 70% positive response |

Note: * Mid-term target to meet by 2023.
Source: Ministry of Health, Labour and Social Affairs (2019) Strategy for the Development of Nursing.

Adequately tackling Georgia’s labour shortages and skills-related deficits in nursing and midwifery will improve employment outcomes for young women and men, helping to secure a more sustainable future for Georgia’s healthcare workforce and improving healthcare standards country-wide.

# Scope of work and deliverables

The main purpose of the Assignment is to support the Ministry, on behalf of EBRD, in establishing a new professional regulatory body to delivering a robust programme of professional licencing and registration for nurses and midwives in Georgia, in line with international best practices, together with the necessary laws defining the powers and responsibilities of such a body. The Consultant will deliver the Assignment in a number of distinct Activities (A-F), as follows (deliverables are underlined):

- The Consultant will conduct a detailed assessment of needs in close discussion with the Ministry and other relevant stakeholders to understand their vision and practical and legal requirements in relation to establishing the new regulatory body and launching the planned professional licencing and registration programme for nurses and midwives. The Consultant will outline the findings concisely in a Baseline Assessment document to present as part of the Interim Report and presentation of interim findings (under Activity C).

- The Consultant will conduct desk research and a review of the leading academic and grey literature (supplemented, if needed, with expert interviews) to outline the leading international practices around regulation, professional licencing and registration of nurses and midwives, as implemented by leading healthcare systems around the world, and how these are established in law. The findings will be summarised into a concise Review of International Nursing Regulatory Bodies’ Functions, Practices and Legal Foundations document presenting best practices and key insights in relation to Georgia’s existing healthcare institutions and regulatory context. This should draw on the established models and best practices adopted by leading national regulators and competent authorities such as the United Kingdom’s Nursing and Midwifery Council (https://www.nmc.org.uk/), France’s Ordre National des Infirmiers (https://www.ordre-infirmiers.fr/), Poland’s Naczelnej Izby Pielęgniarek i Położnych (https://nipip.pl/) and a range of others to be identified. NCSBN’s Global Regulatory Atlas may provide a useful reference in this respect (see: https://www.regulatoryatlas.com/). As above, the Consultant will encompass its analysis under the Interim Report and presentation of interim findings (in Activity C).

- The Consultant will prepare an Interim Report encompassing the ‘baseline assessment’ and ‘review of international nursing regulatory bodies’ functions, practices and legal foundations’ into a single document alongside an outline of the different regulatory models that could be adopted in Georgia. The presentation of models will encompass the main strengths and weaknesses of different options including (broadly speaking) the fiscal cost of running them. The Consultant will formally present the headline findings and options / models identified to senior Ministry stakeholders through a presentation of interim findings aiming to reach consensus over the core option / model to be taken forward by the Ministry.

- Based on the Ministry’s clear steer on the chosen type of programme, the Consultant will prepare a range of Detailed Provisions defining the key principles, procedures, responsibilities, scope and legislative requirements for establishing the desired regulatory body and launching its licencing and registration functions. This should encompass, inter alia:

  - Mandate and necessary legal underpinning for the new regulatory body.

  - Procedures for licencing and registering nurses and midwives including:

    - Scope of coverage (nurses, midwives, nursing associates, public health nurses…?);

    - Eligibility and qualification requirements;

    - Other registration requirements (health requirements; references…);

    - Language requirements and assessment process;

    - Special requirements for internationally qualified professionals;

    - Special requirements for refugees; and

    - Template application forms.

  - Definition of a ‘professional code’ encompassing standards of professional conduct, performance and ethics.

  - Administration of competency tests, curriculum and underlying principles (including formal identity check at exam).

  - Procedures and responsibilities for maintaining the professional register and renewing / revalidating professional licences.

  - Connection and compatibility with continuing professional development requirements (including with the most up-to-date Ministry plans in this respect).

  - Procedures and responsibilities for recognising and registering qualified nurses and midwives from other countries (including refugees).

  - Procedures and legal powers for investigating and addressing professional misconduct and conditions for disqualification from the register.

  - Relevant budgetary and staffing requirements, including a detailed costing.

  - Relevant physical space / office requirements, including a detailed costing.

  - Relevant ICT systems requirements, including a detailed costing.

  - Key considerations around applicable data protection and privacy requirements.

  - Monitoring and evaluation principles, procedures and key performance indicators.

The Consultant will present the above details under the Final Report and final project presentation (under Activity F).

- Looking ahead to the establishment of the new regulatory body and implementation of the new professional licencing and registration programme, the Consultant will prepare a clear Implementation and Communication Plan for the formal launch and the piloting of the new regulatory, licencing and registration functions. This should include key communication materials in different media (both physical and online) alongside a timeline and core principles for the launch and pilot implementation of core functions. The Consultant will encompass this deliverable under the Final Report and final project presentation (in Activity F).

- The Consultant will prepare a Final Report encompassing the ‘detailed provisions’ and ‘implementation and communication strategy’ into a single document alongside concluding considerations for securing the success of the new regulatory body and the sustainability of its professional licencing and registration functions. This will include careful consideration of how the new programme will impact upon Georgia’s incumbent healthcare institutions and stakeholders including, inter alia:

  - The Ministry itself in terms of its core mandate and budgetary requirements;

  - Incumbent nurses and midwives currently practicing in Georgia alongside their employers, representative organisations and professional bodies;

  - Georgia’s nursing and midwifery education providers – both vocational (level 5) and higher (level 6) – and relevant regulators including the National Center for Education Quality Enhancement (EQE); and

  - Georgia’s incumbent professional licencing and registration programme for medical doctors plus (if applicable) any other groups of healthcare professionals.

The Consultant should conduct detailed discussions with stakeholders of each of the above groups (alongside others, as advised by the Ministry) in collecting its findings.

As a final, concluding step, the Consultant will make a final project presentation of its complete findings to senior Ministry stakeholders (and others, as advised) in order to agree next steps; pinpoint any additional technical support needs in fulfilling Objective A of the MoU between EBRD and the Ministry; and prepare the ground for fulfilling MoU Objectives B and C.

# Summary of deliverables

| Project stage / deliverable | Deadline (indicative) |
| --- | --- |
| Kick-off meeting | Within 2 weeks of signing |
| Development of Baseline Assessment (Activity A) | 1 month from Assignment start |
| Development of International Programmes Review (Activity B) | 3 months from Assignment start |
| Delivery of Interim Report and presentation of interim findings (Activity C) | 3 months from Assignment start |
| Development of Detailed Provisions (Activity D) | 6 months from Assignment start |
| Development of Implementation and Communication Plan (Activity E) | 6-8 months from Assignment start |
| Delivery of Final Report and final project presentation (Activity F) | 6-8 months from Assignment start |

The Consultant will produce the main body of each deliverable in the Georgian language alongside a concise Executive Summary section produced in both Georgian and English. The two presentations envisaged in Activities C and F should be carried out in Georgian with the option of simultaneous translation into English.

Payment will be made upon successful completion of deliverables in four tranches as follows: 10 percent advance payment; 40 percent payment upon completion of Activities A-C; 30 percent payment upon completion of Activity D; and 20 percent payment upon completion of Activities E-F.

# Implementation arrangements, budget and timeframe

The total budget for this Assignment is up to EUR 70,000.

The Assignment will commence in Q4 2020 and conclude within a scope of 6-8 months.

The Consultant will report to Mr Marko Stermšek, Associate – Inclusion Specialist, EBRD (StermseM@ebrd.com), throughout the delivery of this Assignment.

For more information, see: https://www.ebrd.com/what-we-do/projects-and-sectors/economic-inclusion.html.