## დიაგნოსტიკა
| სულ გვაქვს გამოყოფილი | 25750000
| დახარჯულია | 11577398.4
| დაგეგმილი | 16135195.6352
| დეფიციტშია | -1962594.0352
| 5. COVID19/G/DC-07 / Procurement of Diagnostic Supplies | დაგეგმილი შესყიდვები |  |  |  | გაფორმებული ხელშეკრულებები
| Activity Reference No. / Description: | Estimate supplier | Estimated Quantity /planned | Estimated Amount (US$)/planned/ |  | Singed contract/Suppliers Name | Contract N/ signed dated | Manufacturer’s Authorization /country of Origin | Applicable Incoterms / Consignee | Amendments | Delivery Date as defined by Incoterms | Quantity required Quantity and physical unit | Delivered Quantity | Unit price | Actual Total Price per Line item (Col. 7+8)
| Rapid COVID-19 Test Cassette |  |  |  |  | JV Biogene LTD and Green Lab LTD | COVID19/G/DC-01 17/05/2020 | CHINA | CIP | Amendment N1 | Delivered | 97000 | Delivered | 5, 20 USD | 504400
| Procurement of Standard COVID-19 Antigen Tests |  |  |  |  | SD BIOSENSOR | COVID19/G/DC-04 | Republic of Korea | CIP |  | Delivered | 50000 | Delivered |  | 612200
| COVID19/G/DC-09 / Procurement of Qiagen RNA Mini Kit |  |  |  |  | Prima Medi LTD | COVID19/G/DC-09 01/07/2020 | QIAGEN/Germany | DDP/ (NCDC) |  | Delivered | 250 Packs | Delivered | 4 200, 00 GEL | 338708
| Thermos Scientifics COVID-19 tests |  |  |  |  | ABM LTD | COVID19/G/DC-10 01/07/2020 | USA | DDP/ (NCDC) |  | 1st delivery 21.07 2020 2nd delivery 21.08.2020 3rd delivery 21.09.2020 4th delivery 21.10.2020 | 1800 | 1st delivery is delaying |  | 5685100
| Orient Gene Covid 19 IgG/IgM ( Whole Blood/Serum/Plasma) |  |  |  |  | JV Biogene LTD and Green Lab LTD | COVID19/G/DC-01 | CHINA | CIP | Amendment N2 | Until August 5, 2020 | 100 000 |  | 5, 20 USD | 520000
| Standard COVID-19 AG Test |  |  |  |  | SD BIOSENSOR | COVID19/G/DC-13 | Republic of Korea | CIP / (NCDC) |  | Within 1 week after payment of 40% on shipment , but not exceeding four (4) weeks of order placement. | 100000 |  | 9.1875 | 918750
| Xpert Xpress SARS-CoV-2 kit/10 tests |  |  |  |  | UNICEF | COVID19/G/UN-01 03/07/2020 | USA | CIP |  | October | 2000 packs | 2020-10-30 |  | 478240.4
| Nucleic Acid Diagnostic Kit |  |  |  |  | Biotech | COVID19/G/DC-11 | CHINA | CIP / (NCDC) |  | within 30 business days after receiving the advance payment | 240000 |  |  | 2520000
| COVID19/G/DC-08 / Procurement of In Vitro Diagnostic Medical Device (cobas) |  | 1 | 493980 | WB No-objection has been received | [9 empty] | 0
| Laboratory Supplies COVID19/G/RFQ-05 |  | 200000 | 350000 | WB No-objection has been received | [9 empty] | 0
| EMEA Procleix SARS-CoV-2 Assay CE IVD Reagent Procleix Panther System | LUX MED LTD | 10000 | 253000 | WB No-objection has been received |  |  | GRIFOLS | DDP / (NCDC) |  | within 45 days |  |  |  | 0
| GeneMATRIX Viral RNA/DNA Purification Kit (100 detection | Bio-Medi Ltd | 125,000 (1250 Kits) | 372500 | WB No-objection has been received |  |  | EURX, Poland | CIP / (NCDC) |  | 100 kits can supply immediately . 400 kits in August. 500 kits in September. |  |  |  | 0
| MATRIX Viral RNA/DNA Purification Kit | Prima medi | 125000 | 530000 | WB No-objection has been received | [9 empty] | 0
| Tests for Cobas | Roche | 150000 | 4026000 | [10 empty] | 0
| Omni Gene oral from microbial DNA and RNA | DNA Genetic | 50000 | 337500 |  |  |  | DNA genotek | CIP / (NCDC) | [5 empty] | 0
| Biosensor |  | 200000 | 2400000 | [10 empty] | 0
| ტესტ-ნაკრები Logix Smart Coronavirus disease 2019 (COVID19) kit | შპს ირისე | 100000 | 781758.9577
| ტესტ-ნაკრები Fast Track Diagnostics | შპს ირისე | 100032 | 1140429.9674
| ტესტ-ნაკრები BGI | შპს ემდიესი | 100000 | 1477687.2964
| TaqPath™ COVID-19 CE-IVD RT-PCR Kit | შპს ეიბიემ | 100000 | 1892339.4137 | [10 empty] | 0
| biotech |  | 160000 | 1680000 | [10 empty] | 0
| მანუალური ექსტრაქცია |  | 150000 | 400000 | [10 empty] | 0
TOTAL |  |  | planned | 16135195.6352 | [10 empty] | 11577398.4

## PCR
Georgia Emergency COVID-19 Response Project (P173911) WB, AIIB Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs of Georgia
N | Company Name | Description of Goods | Country of Origin | Physical unit | Total quantity | Total Price | Place of Final Destination (Project Site) | Delivery
[8 empty] | Information on deli livery |  | Quantity Delivered
N | [9 empty] | July |  | august |  | September |  | October
2 | LTD ABM | TaqPath™ COVID-19 CE-IVD RT-PCR Kit, 1000 tests | USA | 250 | 250 000 | USD 5 685 100 | NCDC | 1st batch 40-60 tests; 2nd batch 20-60 batch; 3rd batch - 70-100 batch; 4th batch - 70-100 tests | 1st delivery 21.07 2020 2nd delivery 21.08.2020 3rd delivery 21.09.2020 4th delivery 21.10.2020 | 21.07 2020 | 60000 | 21.08.2020 | 60000 | 21.09.2020 | 60000 | 21.10.2020 | 70000
|  | Magma™ Viral/Pathogen II (MVP II) Nucleic Acid Isolation Kit, 2,000 preps | USA | 150 | 300 000 |  | NCDC | 1st batch 40-60 tests; 2nd batch 20-60 batch; 3rd batch - 70-100 batch; 4th batch - 70-100 tests | 1st delivery 31.07 2020 2nd delivery 31.08.2020 3rd delivery 30.09.2020 4th delivery 31.10.2020 | 31.07 2020 | 60000 | 31.08.2020 | 60000 | 30.09.2020 | 80000 | 31.10.2020 | 100000
|  | Kingfisher Deepwell 96 Plate, V-bottom, polypropylene, case of 60 plates | USA | 400 | 300 000 ექსტრაქციის შესაბამისი სახარჯები |  | NCDC | 1st batch 40-60 tests; 2nd batch 20-60 batch; 3rd tests - 70-100 batch; 4th batch - 70-100 tests | 1st delivery 31.07 2020 2nd delivery 31.08.2020 3rd delivery 30.09.2020 4th delivery 31.10.2020 | 31.07 2020 |  | 31.08.2020 |  | 30.09.2020 |  | 31.10.2020
|  | KingFisher 96 KF microplate (200μL) case of 48 plates | USA | 200 |  |  | NCDC | 1st batch 40-60 tests; 2nd batch 20-60 batch; 3rd batch - 70-100 batch; 4th batch - 70-100 tests | 1st delivery 31.07 2020 2nd delivery 31.08.2020 3rd delivery 30.09.2020 4th delivery 31.10.2020 | 31.07 2020 |  | 31.08.2020 |  | 30.09.2020 |  | 31.10.2020
|  | KingFisher 96 tip comb for DW magnets, 10 x 10 pcs/box | USA | 300 |  |  | NCDC | 1st batch 40-60 tests; 2nd batch 20-60 batch; 3rd batch - 70-100 batch; 4th batch - 70-100 tests | 1st delivery 31.07 2020 2nd delivery 31.08.2020 3rd delivery 30.09.2020 4th delivery 31.10.2020 | 31.07 2020 |  | 31.08.2020 |  | 30.09.2020 |  | 31.10.2020
|  | Thermo Scientific™ Matrix™ 850-1250ul Pipette Filter Tips (960 per case) | USA | 500 |  |  | NCDC | 1st batch 40-60 tests; 2nd batch 20-60 batch; 3rd batch - 70-100 batch; 4th batch - 70-100 tests | 1st delivery 31.07 2020 2nd delivery 31.08.2020 3rd delivery 30.09.2020 4th delivery 31.10.2020 | 31.07 2020 |  | 31.08.2020 |  | 30.09.2020 |  | 31.10.2020
| Prima Medi LTD | QIAamp Viral RNA Mini Kit Ref: 52906 | Germany | 250 | 250 packs | 1050000 | NCDC | Delivered (Delivery-Acceptance Act 20.07.2020 )
| UNICEF | Xpert Xpress SARS-CoV-2 kit/10 tests | USA |  | 2000 packs | 478240.4 | NCDC | 30.10.20
| SANSURE BIOTECH INC. | Nucleic Acid Diagnostic Kit 1*48 test | CHINA | 240000 | 5000 kits | 2520000 | NCDC | within 30 business days after advance paiment made. (Contract signed on 22.07.2020) |  | advance payment is not paid yet.
| LUX MED LTD | EMEA Procleix SARS-CoV-2 Assay CE IVD Reagent Procleix Panther System | GRIFOLS (Spain) | 240000 | 10000 Kits | 253000 | NCDC | within 45 days after contract signature | the contract negotiatiion is ogoing
| Bio-Medi Ltd | GeneMATRIX Viral RNA/DNA Purification Kit (100 detection | EURX, Poland | 100000 | 1000 Kits | 298000 | NCDC | 100 kits can supply immediately . 400 kits in August. 500 kits in September | the contract negotiatiion is ogoing
| Roche | Tests for Cobas | Switzerland | 203520 |  | 4606920 |  |  | the contract negotiatiion is ogoing