# STRATEGIC PLANNING

PURPOSE: This documents describes the standard procedure at  Institute for the development of the Strategic Plan.

Scope: The procedures covers the phases and activities that need to take place whendeveloping the Strategic Plan.

# Responsibilities:

Minister/Minister advisory board: Minister/Minister advisory board is responsible for setting strategic directions, providing feedback to the draft strategy and approving the Institutution strategy.

CEO/Deputy Minister: CEO/Deputy minister is responsible for approving the guidelines for the development of the strategic plan, approval of the draft strategic plan and final strategic plan

SP WG: is responsible for the Preparation of the Guidelines and timelines for the strategic planning Process, organizing a strategic planning workshop which include staff and Minister advisory board/Deputy minister/MInisterSP WG members,  Consolidation of the first draft of the Strategic Plan, Coordination of further drafting of the final draft Strategic Plan in collaboration with departments, finalize final draft of the strategic plan after receiving comments from the Deputy Minister/Minister/Minister advisory Minister advisory board/Deputy minister/MInister, and staff before sending to the Deputy Minister/Minister/Minister advisory Minister advisory board/Deputy minister/MInister for the final approval and organizing internal workshop with staff for the operationalization.

Structural Units of MoLHSA/SSA: Departments are responsible in gathering Information, analysis and planning of the initiatives and participating in the preparation of the departmental drafts and start implementation after the approval of the Strategic Plan.

Finance deaprtment: Responsible for the preparation of the budget for the next five years plan.

# Terms and Definitions

# CEO: Chief Execative Officer (Deputy Minister)

# SP WG: Strategic Planning Working Group

# Description of Action

- Development of the Strategic Plan is initiated by the Minister/Minister advisory Minister advisory board/MInister by setting the strategic directions and priorities for the Institutution for the next five years.

- Then SP WG Officer is responsible for the preparation of the TOR to secure external consultant who will be supporting the development of the Strategic Plan. Then he/she will prepare the guidelines for the development of the Strategic plan and share with the CEO for approval.

- SP WG officer will organise a workshop and share with staff/departments the guidelines and brain storm how to go about drafting the Strategy, timelines and their responsibility of gathering the information and analysis and planning of the initiatives.

- All departments will submit their information to SP WG Officer for consolodation of the draft Strategic Plan and share it with Finance department for the preparation of the five years budget.

- The draft Strategy is sent to the Deputy Minister for approval, if there any changes or inputs it will come back to SP WG Officer, if there is nothing, then the draft Strategy is sent to the Minister advisory board/Minister for comments and feedback.

- SP WG Officer continues to coordinate the inputs from the departments and and finalised the Strategy and send to the Deputy Minister for the approval of the Strategic plan draft. If there any comments or inputs from the Deputy Minister, the draft of document is sent back to SP WG officer to incooperate them and send back to the Deputy Minister , then the final Strategy is sent to the Minister advisory board/ Minister for approval.

- After approval of the Strategic Plan, SP WG Officer is responsible to organise a workshop with all staff to agree on the operationalisation.

# Annual Planning

PURPOSE: This documents describes the standard procedure at Institute for the preparation of the Annual Planning processes.

Scope: The procedures covers the phases and activities that need to take place when preparing the Annual Plan.

# Responsibilities:

Minister/Minister advisory board : The Minister/Minister advisory board is responsible for approving the Institution Annual Plan.

CEO/Deputy Minister: CEO is responsible for initiating and coordinating the Annual Planning processes and approving of the draft Annual Plan and final Annual Plan.

SP WG: is responsible for the Preparation of the Guidelines and timelines for the Annual Planning Process, organizing a Annual planning workshop to review and agree on the Annual Plan and Consolidation of the Annual Plan document.

Structural Units of MoLHSA/SSA: Departments are responsible to prepare their departmental plans.

Finance deaprtment: Responsible for the preparation of the Annual budget .

# Terms and Definitions

# CEO: Chief Execative Officer (Deputy Minister)

# SP WG: Strategic Planning Working Group

# Description of Action

- Development of the Annual Plan process is initiated by the Minister advisory board/Minister/Deputy MInister by instructing the SP WG Officer to prepare the guidelines which will include the processes and time lines and secure external consultant if need be.

- The Annual Plans guidelines are shared with staff/ Heads of Department to prepare their departmental plans.

- Then SP WG Officer will organise a workshop to discuss and agree on the plans and consolidate the plan and send to the finance Department to prepare the Annual Budget. Then the Plan together with its budget is sent to the Deputy Minister for comments and approval.

- After approval from the Deputy Minister the Annual plan is sent to the Minister advisory board/MInister for approval of the Annual Plan and its Budget.

- After the approval by the Minister advisory board/MInister , SP WG Officer will provide feedback to staff for the implementation of the Annual Plan.

# Preparations of the Quartely and Annual Reports

PURPOSE: This documents describes the standard procedure at  Institute for the preparation of the Quartely and Annual Reports.

Scope: The procedures covers the phases and activities that need to take place when preparing the Quartely and Annual Reports.

# Responsibilities:

Minister/ Minister advisory board: The Minister advisory board/Minister is responsible for noting and approving the Institutution Quartely and Annual Reports

CEO/Deputy Minister: CEO is responsible for managing the quartely management meetings which discusses the progress of activities implementation and approving the Quartely and Annual Reports before sent to the Minister advisory board/Minister.

SP WG officer: is responsible for the Preparation of the monitoring templates to be used by Heads of Deaprtment to report the progress of implementaton of the activities. He/she is also responisble in the preparations of the management monitoring meetings, coordination and preparation of the Quartely and Annual Reports, consolidation of the both reports to be sent to the Minister advisory board/Deputy minister/MInister.

MoLSHA/SSA Unit Departments: Departments are responsible to provide information to the matrix prepared by the SP WG Officer and review the reports before sent to the CEO for Approval.

Finance deaprtment: Responsible for the preparation of the financial Quartely and Annual Reports  to be reviewed by the management.

# Terms and Definitions

# CEO: Chief Execative Officer (Deputy Minister)

# SP WG Strategic Planning Working Group

# Description of Action

- Preparations of the quarterly and Annual reports starts with the preparation of the monitoring template by the SP WG Officer, which is shared to staff/Heads of the Departments to upadate and provide information on the progressof the activities per quarter.

- There are quartely management meetings preparaed by the SP WG Officer and chaired by the CEO to discuss the progress of implementation of the activities per quarter. During the meeting, every department get an opportunity to presents their progress. There are discussion around issues raised for management decision and other issues for management nofication.

- SP WG Officer coordinates and consolidate both reports. Draft reports are shared by the heads of departments for reviews and inputs and then sent  to CEO for comments and approval.

- The final Quartelry and Annual report is sent to the Minister advisory board/MInister for notification and approval.

- After Minister advisory board/MInister approval, SP WG Officer share the feedback of the Minister advisory board/MInister on the management meeting.