## TOTAL
| Cost estimate (USD) | Outstanding amount (USD) |  | 6000000 | retroactive
Component 1. Emergency COVID-19 Response and Component 3. Project Management and Monitoring | 41500000 | 36122818
Component 1. Emergency COVID-19 Response
GOODS | Cost estimate (USD) | ACTUALS (contracted) | Remaining funds after contracting | UNCOMITTED | Planned
1. Procurement of Personal Protective Equipment | 5000000 | 179820 | 4820180 | -252120 | 5072300
2. COVID19/G/DC-06 / Procurement of Hospital Equipment for dedicated COVID-19 clinics: Rukhi, Batumi, Tbilisi Infectious, Tbilisi University, Kutaisi Regional, LG, and Sachkhere Regional. | 6500000 | 403437.6 | 6096562.4 | 5992581.632 | 103980.768 | 0
3. COVID19/G/RFQ-03 / Procurement of Motorcycle for ambulance first responders with helmets | 1000000 | 0 | 1000000 | 0 | 1000000
4. COVID19/G/RFQ-01 / Procurement of fully equipped Ambulance car C type - Intensive Care Mobile Unit (30 Units) | 2250000 | 0 | 2250000 | 300000 | 1950000
5. COVID19/G/DC-07 / Procurement of Diagnostic Supplies | 25750000 | 13613398.4 | 12136601.6 | -1546094.0352 | 13682695.6352
6. COVID19/G/RFQ-02 / Procurement of Equipment for Emergency Control Center | 5300000 | 313476 | 4986524 | 1986524 | 3000000
7. COVID19/G/RFQ-07 / Procurement of ICT goods for public health facilities | 50000 | 0 | 50000 | 50000 | 0
8. COVID19/G/RFQ-04 / Procurement of motor vehicles for Infectious Control Monitoring Center | 350000 | 0 | 350000 | -43000 | 393000
9. Equipment for Primary Care Facilities | 3000000 | 0 | 3000000 | 3000000 | 0
SUM | 49200000 | 14510132 | 34689868 | 9487891.5968 | 25201976.4032
WORKS | Cost estimate (USD) | ACTUALS (contracted) | Remaining funds after contracting | UNCOMITTED | Planned
COVID19/CW/RFB-01 / Repair works of public health facilities | 1000000 | 0 | 1000000 | 704628 | 295372
SUM | 1000000 | 0 | 1000000 | 704628 | 295372
CONSULTANCY SERVICE | Cost estimate (USD) | ACTUALS (contracted) | Remaining funds | UNCOMITTED | Planned
| 300000 | 6250 | 293750 | 293750 | 0
| 300000 | 6250 | 293750 | 293750 | 0
Quarantine, Preparedness, Cost of case | 20500000
Component 3. Project Management and Monitoring
CONSULTANCY SERVICE Component III | Cost estimate (USD) | ACTUALS (contracted) | Remaining funds | UNCOMITTED | Planned
| 300000 | 160800 | 139200 | 138200 | 1000
| 300000 | 160800 | 139200 | 138200 | 1000
SUM | 71300000 | 14677182 | 36122818

## WORKS I
| Activity Reference No. / Description: | Estimate supplier | Type of procurement | Estimated Quantity /pland | Estimated Amount (US$)/pland/ | Contractors name | Contract N/ signed dated | Manufacturer’s Authorization /country of Origin | Applicable Incoterms / Consignee | Ammendments | Delivery Date as defined by Incoterms | Quantity required Quantity and physical unit | Unit price | Actual Total Price per Line item (Col. 7+8)
| COVID19/CW/RFB-01 / Repair works of public health facilities |  |  |  | 1000000
1 | Kutaisi Emergency Coordination and Emergency Assistance Center |  | RFB |  | 230000 | [8 empty] | 0
2 | O.Chkhobadze Disabled and Elderly Medical Rehabilitation Clinical Center |  | RFB |  | 65372 | [8 empty] | 0
3 | Tbilisi |  | RFB | [10 empty] | 0
[5 empty] | 295372 | [8 empty] | 0

## GOODS I
Component 1. Emergency COVID-19 Response | Activity Reference No. / Description: | Estimate supplier | Type of procurement | Estimated Quantity /planned | Estimated Amount (US$)/planned/ | Singed contract/Suppliers Name | Contract N/ signed dated | Manufacturer’s Authorization /country of Origin | Applicable Incoterms / Consignee | Amendments | Delivery Date as defined by Incoterms | Quantity required Quantity and physical unit | Delivered Quantity | Unit price | Actual Total Price per Line item (Col. 7+8)
2.1 | 1.COVID19/G/DC-05 Procurement of Personal Protective Equipment |  |  |  | 5000000
1 | Goggles, protective | Commander Health Supply | Direct |  |  | Commander Health Supply | Commander -001/ 10.07.2020 | China | CIP |  | within 30 days from date of issues of Preproduction Inspection Report | 54000 |  | 3.33 | 179820
2 | GOWN Disposable |  | Direct | 2000000 | 4420000
3 | RESPIRATOR, mask, FFP2/N95, type IIR, s.u., unvalued, nose clip |  | Direct | 30000 | 75000
4 | FACE SHIELD, clear plastic, disp. |  | Direct | 40000 | 36400
5 | Boot covers with bio protection |  | Direct | 50000 | 500
6 | Headband |  | Direct | 20000 | 400
7 | gloves | M&M | Direct | 6000000 | 540000 | [9 empty] | 0
8 | Mask |  | Direct | 3000000
TOTAL |  |  |  |  | 5072300 | [9 empty] | 179820
2.1 | 2. COVID19/G/DC-06 / Procurement of Hospital Equipment for four dedicated COVID-19 clinics: Rukhi Hospital, Batumi Hospital, Lisi Hospital and Infectious Disease Hospital |  |  |  | 6500000
| Second hand good (CT scanner) | LTD Ivermedi. | Direct | 1 | 103980.768 | [10 empty] | 3.6372
1 | Rukhi Republic Hospital |  |  |  | 0 | [9 empty] | 0 | 3.0782
1 | Batumi |  |  |  | 0 | [9 empty] | 0
1 | Tbilisi Infectious Disease Hospital |  |  |  | 0 | [9 empty] | 0
1 | Chkhobadze medical center in Kutaisi |  |  |  | 0 | [9 empty] | 0
1 | ICU of the Infectious LG Hospital in Kutaisi |  |  |  | 0 | [9 empty] | 0
1 | Sachkhere Hospital |  |  |  | 0 | [9 empty] | 0
| COVID19/G/DC-02 / Procurement of Critical Care Ventilators and Related Services |  | Direct |  | 0 | MTECH LLC | 2020-05-21 | CHINA/Mindray |  | Ammendment N1 | 30th of August, 2020 | 30 |  | 13447.92 | 403437.6
1 | ICU of the university hospital |  |  |  | 0 | [9 empty] | 0
TOTAL |  |  |  |  | 103980.768 | [9 empty] | 403437.6
2.1 | 3. COVID19/G/RFQ-03 / Procurement of Motorcycle for ambulance first responders with helmets |  | Limited |  | 1000000
| Motorcycle for ambulance first responders with helmets |  |  | 50 | 1000000 | [9 empty] | 0
TOTAL |  |  |  |  | 1000000 | [9 empty] | 0
2.1 | 4. COVID19/G/RFQ-01 / Procurement of fully equipped Ambulance car C type - Intensive Care Mobile Unit (30 Units) |  | Limited |  | 2250000
| Intensive Care Mobile Unit (30 Units) |  | RFQ | 30 | 1950000
TOTAL |  |  |  |  | 1950000 | [9 empty] | 0
1.1 | 5. COVID19/G/DC-07 / Procurement of Diagnostic Supplies |  | Direct |  | 25750000
| Rapid COVID-19 Test Cassette |  | Direct |  |  | JV Biogene LTD and Green Lab LTD | COVID19/G/DC-01 17/05/2020 | CHINA | CIP | Amendment N1 | Delivered | 97000 | Delivered | 5, 20 USD | 504400
|  |  | Direct |  |  |  |  | CHINA | CIP | Amendment N2 | Until August 5, 2020 | 100 000 | Delivered | 5, 20 USD | 520000
| Procurement of Standard COVID-19 Antigen Tests |  | Direct |  |  | SD BIOSENSOR | COVID19/G/DC-04 | Republic of Korea | CIP |  | Delivered | 50000 | Delivered |  | 612200
| COVID19/G/DC-09 / Procurement of Qiagen RNA Mini Kit |  | Direct |  |  | Prima Medi LTD | COVID19/G/DC-09 01/07/2020 | QIAGEN/Germany | DDP/ (NCDC) |  | Delivered | 250 Packs | Delivered | 4 200, 00 GEL | 338708
| Thermos Scientifics COVID-19 tests |  | Direct |  |  | ABM LTD | COVID19/G/DC-10 01/07/2020 | USA | DDP/ (NCDC) |  | 1st delivery 21.07 2020 2nd delivery 21.08.2020 3rd delivery 21.09.2020 4th delivery 21.10.2020 | 1800 | 1st delivery is delaying |  | 5685100
| Standard COVID-19 AG Test |  | Direct |  |  | SD BIOSENSOR | COVID19/G/DC-13 | Republic of Korea | CIP / (NCDC) |  | Within 1 week after payment of 40% on shipment , but not exceeding four (4) weeks of order placement. | 100000 |  | 9.1875 | 918750
| Xpert Xpress SARS-CoV-2 kit/10 tests |  | Direct |  |  | UNICEF | COVID19/G/UN-01 03/07/2020 | USA | CIP |  | October | 2000 packs | 2020-10-30 |  | 478240.4
| Nucleic Acid Diagnostic Kit 124 test |  | Direct |  |  | SANSURE BIOTECH INC | COVID19GDC-14 | CHINA | CIP / (NCDC) |  | within 30 business days after receiving the advance payment | 400000 |  |  | 4200000
| GeneMATRIX Viral RNA/DNA Purification Kit (100 detection |  | Direct | 125,000 (1250 Kits) |  | Bio Medi LLC | COVID19GDC-16 | EURX, Poland | CIP / (NCDC) |  | 100 kits can supply immediately . 400 kits in August. 500 kits in September. | 1000 paks |  | 298 | 356000
| COVID19/G/DC-08 / Procurement of In Vitro Diagnostic Medical Device (cobas) |  | Direct | 1 | 493980 | [9 empty] | 0
| Laboratory Supplies COVID19/G/RFQ-05 |  | RFQ | 200000 | 350000 | [9 empty] | 0
| EMEA Procleix SARS-CoV-2 Assay CE IVD Reagent Procleix Panther System | LUX MED LTD | Direct | 10000 | 253000 |  |  | GRIFOLS | DDP / (NCDC) |  | within 45 days |  |  |  | 0
| MATRIX Viral RNA/DNA Purification Kit | Prima medi | Direct | 125000 | 530000 | [9 empty] | 0
| Tests for Cobas | Roche | Direct | 150000 | 4026000 | [9 empty] | 0
| Omni Gene oral from microbial DNA and RNA | DNA Genetic | Direct | 50000 | 337500 |  |  | DNA genotek | CIP / (NCDC) | [5 empty] | 0
| AG/AB rapid tests | Biosensor | Direct | 200000 | 2000000 | [9 empty] | 0
| ტესტ-ნაკრები Logix Smart Coronavirus disease 2019 (COVID19) kit | შპს ირისე | Direct | 100000 | 781758.9577
| ტესტ-ნაკრები Fast Track Diagnostics | შპს ირისე | Direct | 100032 | 1140429.9674
| ტესტ-ნაკრები BGI | შპს ემდიესი | Direct | 100000 | 1477687.2964 | [9 empty] | 0
| TaqPath™ COVID-19 CE-IVD RT-PCR Kit | შპს ეიბიემ | Direct | 100000 | 1892339.4137
| extraction |  | Direct | 150000 | 400000 | [9 empty] | 0
TOTAL |  |  |  |  | 13682695.6352 | [9 empty] | 13613398.4
| 6. COVID19/G/RFQ-02 / Procurement of Equipment for Emergency Control Center |  | Open - National |  | 5300000
2 | COVID19/G/DC-03 / Procurement of Mobile Emergency Ventilators and Related Services |  | Direct |  | 0 | MDS LTD | 2020-05-20 | Hamilton Medical AG Switzerlan | Emergency situations coordination and urgent assistance center”. | Ammendment N1 July 16, 2020 | Period-1: From 16.06.2020 to 03.07.2020; Period-2: From 30.06.2020 to 17.07.2020; Period-3: From 12.08.2020 - to 30.08.2020.” | 20 |  |  | 313476
| Radio systems |  |  |  | 3000000 | [9 empty] | 0
TOTAL |  |  |  |  | 3000000 | [9 empty] | 313476
| 7. COVID19/G/RFQ-07 / Procurement of ICT goods for public health facilities |  | Open - National |  | 50000
Computers
Camera
Camera of the patient's salon
Tablets for ambulances
TOTAL |  |  |  |  | 0 | [9 empty] | 0
| 8. COVID19/G/RFQ-04 / Procurement of motor vehicles for Infectious Control Monitoring Center |  | Open - National |  | 350000
| 15 motor Motor Vehicles for Infectious Control Monitoring Center |  | RFQ | 15 | 393000
TOTAL |  |  |  |  | 393000 | [9 empty] | 0
| 9. Equipment for Primary Care Facilities |  |  |  | 3000000
1 | furniture |  | Direct |  | 60000
2 | Equipment |  | Direct |  | 350000
[5 empty] | 410000 | [9 empty] | 0

## CS I
|  | Activity Reference No. / Description: | Estimate supplier | Type of procurement | Estimated Quantity /pland | Estimated Amount (US$)/pland/ | Conultant name | Contract N/ signed dated | Manufacturer’s Authorization /country of Origin | Applicable Incoterms / Consignee | Ammendments | Delivery Date as defined by Incoterms | Quantity required Quantity and physical unit | Unit price | Actual Total Price per Line item (Col. 7+8)
| COVID19/CS/QBS-01 / Training and technical assistance to MoLSHA |  |  |  |  | 300000
1 | COVID19/CS/CDS-02 / Technical Assistance for post crises COVID-19 strategy for Health Sector - Assistant Consultant | Consultant Services |  | Direct |  | 0 | [8 empty] | 3125
2 | COVID19/CS/CDS-01 / Technical Assistance for post-crises COVID-19 strategy for Health Sector - Lead Consultant | Consultant Services |  | Direct |  | 0 | [8 empty] | 3125
| TOTAL |  |  |  |  | 0 | [8 empty] | 6250

## CS COMP.III
| Activity Reference No. / Description: | Estimate supplier | Type of procurement | Estimated Amount (US$)/pland/ | Conultant name | Contract N/ signed dated | Duration monthe/day | Ammendments | Delivery Date | Actual Total Price per Line item (Col. 7+8)
PIU |  |  |  | 300000
COVID19/CS/INDV-01 / Procurement Manager | Project Management |  | Direct | [6 empty] | 36000
COVID19/CS/INDV-05 / Social Standards Specialist | social specialist |  | Direct | [6 empty] | 19200
COVID19/CS/INDV-02 / Financial Manager | Financial manager |  | Direct | [6 empty] | 30000
COVID19/CS/INDV-06 / Environmental Standards Specialist | enviromental Specialist |  | Direct | [6 empty] | 19200
COVID19/CS/INDV-04 / Health Specialist | Health specialist |  | Direct | [6 empty] | 30000
COVID19/CS/INDV-03 / Procurement Specialist | Procurement specialist |  | Direct | [6 empty] | 26400
Translator | Interpreter |  | Direct | 1000
|  |  |  | 1000 | [5 empty] | 160800