## iniciatives+actions
| Goals | Initiatives | Q3 18 | Q4 18 | Q1 19 | Q2 19 | Q3 19 | Q4 19 | Q1 20 | Q2 20 | Q3 20 | Q4 20 | Date | Owner
1 | Improve payment and contracting mechanisms | Developing and introducing DRG system | Contact the organization delivering the grouper software and license | DRG grouper integrated to the SSA system; DRG terminology in Georgian; feedback to providers; Adaption of regulation needed for implementation of DRG system; Preparation for DRG cost weights and reimbursement principles |  | DRG cost weights and reimbursement principles for the "virtual implementation" | Simualtions and analytics to develop DRG cost weights and reimbursement rules | DRG cost weigts and reimbursement policy for 2020; overall preparedness for DRG implementation |  |  |  |  | 3.2020 | SSA/MoLHSA
|  | Critical assessment of basic financing PHC (considering the need for integration of rural and UHC, state vertical programs) including RBF principles | Assessment of current financing mechanisms of PHC considering possibility of integration of rural and UHC |  | Revision/redisign of financial mechanisms of PHC including RBF indicators; Piloting RBF using redesigned financing of PHC |  |  |  | Final revision/preparation for redesigned PHC financing |  |  |  | 3.2020 | MoLHSA/SSA
|  | Developing principles of contracting for purchasing services, including consolidation of highly specialised and hospital care, selective contracting and monitoring and evaluation system of contracts performance |  | Assessment of current contracting arrangements, including selective contracting practice of MCH care. analysing the current distribution of Highly specialised hospital services; Analyzing proper epidemiological data for selective contracting services, existing services allocation comparing to international experience | Design of the concept for new contracting service system; Elaborate highly specialised hospital services allocation according to data analysis | Design of Major Diagnostic Categories and case based planning system | Analyses of provider performance, forecast of MDC and case based planning, drafting SOP, SSA internal capacity building | Piloting volume based contracting, without financial obligations | Develop monitoring procedures and SOP |  | Develop legal regulation. Linking with payment mechanisms. | Final preparation for going live. | 12.2020 | MoLHSA/SSA
|  | Needs assessment in health care services | Assessment of what kind of services are priorities for needs assesement (ex. onco surgery, critical care, NICU..) | Analyze epidemiological data, service utilization, existing resources, international experience |  |  | elaborate the requirements for each directions based on statistical data taking into consideration the geografical accsessibility and utilization | [5 empty] | 6.2020 | MoLHSA/SSA
2 | HBP in line with population health needs | Designing the system and process of HBP revision and renewal | elaborate of the methodology for assesment of health needs and HBP design | analyze the health service utilization of existing HBP and detect weak an strong sides |  | assesment of health (among them essential) needs, service alocation and finansial resoirses |  | Redesighn HBP |  |  |  |  | 3.2020 | MoLHSA
3 | Ensure equitable access to essential specialist care and strengthen PHC | Revision of referral system and developing GP functions. | Elaboration of PHC strategy; Elaborate requirements (technical , specialisation …) for service providers taking into consideration mapping results; elaborate the data-collecting system to receive the data from PHC centers about pacients with ambulatory care-sensitive conditions, their outpatient visits and referrals |  |  | Analyze received data, hospitalization rate with ambulatory care sensitive conditions according to PHC centers |  |  | revise/redign the referral system |  |  |  | 3.2020 | MoLHSA/SSA
|  | Strengthening the capacity of GP |  | Elaborate the training and qualifications system of GP taking into consideration the data received by analysis of work of PHC centers with patients ambulatory care-sensitive conditions |  | Consider draft of training sistem with primary health care professionals and international partners and analyze their remarks and comments; Elaboration of GP qualification monitoring syste |  |  | revise/finalise the wonk on training and re-qualification system of GP. |  |  |  | 3.2020 | MoLHSA/SSA
4 | Improvement efficiency and quality of health services | Developing the concept to upgrade quality assurance and improvement system | Analysis of current situation |  | Elaboration of quality improvement strategy and instruments |  |  | start of implementation of quality strategy |  |  |  |  | 3.2020 | MoLHSA
|  | Defining set of indicators to assess the quality of medical services, mechanism to monitor and control quality, and coordinate the quality functions with Regulatory Authority |  |  | Define the set of quality indicators |  | Elaborate the mechanism to monitor and control quality | start of implementation of set of indicator ssystem |  |  |  |  | 3.2020 | MoLHSA/SSA
|  | Develop concept of medical audits (in cooperation with Regulatory Authority). |  |  | Identify the standards and audit criteria |  | selecting and developing appropriate performance levels; identify inclusion/exclusion criteria abd exceptions |  | Elaborate measuring performance methodology: data collection, data analysis, drawing conclusions, presentation of results; Identify principal steps of quality improvement plans and sustaining improvements according the elaborated mechanism to monitor and control quality |  | Final revision of concept of medical audits, analysing feedback from professionals and international partners |  | 12.2020 | MoLHSA/SSA
|  | Develop principles and functions of health economics within SSA, the structural alignment of functions. | Analysis of current structural alignment of functions of SSA |  | Revision/redign of structural alignment of functions according to principles and functions of health economics within SSA | [7 empty] | 6.2019 | SSA
5 | Enhance electronic data exchange and improve quality of data | Mapping of key processes related with health service provision and SP and defining the needs for developing solutions for electronis exchange of data with stakeholders. | Defining SP key areas in need of IT development, new tech applications and solutions. |  | System analyses and TOR for SP and IT development |  | Final preparation for going live. | [5 empty] | 12.2019 | SSA
|  | Introduce the use of electronic signature. | Implement the relevant software with legislative changes on electronic signature |  | estimate the software characteristics | Final preparation for going live. | [6 empty] | 6.2019 | SSA
|  | Mapping of claims management process and design of electronic claims management solution. | Mapping of claims manage ment process AS-IS | Designing SHOULD BE SOP (incl TOR for tech application...) |  | SSA wide training to introduce new practice |  | New claims management process introduced |  |  |  |  | 12.2019 | SSA
6 | Improve population awareness | Development of Citizen Portal and applications to increase transparency for patients. | Ensure to provide precise information for beneficiaries about covered services by State and other (municipal and etc.) programs |  | Elaborate the questionary for visitors of web site |  | Analyze the feedback for improvement of site data/information/characteristics/appearance | Final work on Citizen Portal and applications to present a transparent clear information/data for beneficiaries |  |  |  |  | 12.2019 | SSA
|  | Develop concept of citizen communication and communication plan for 2019. | elaboration of communication plan; elaboration of key messages | Finaising communication plan | [8 empty] | 12.2018 | MoLHSA
7 | Increase transparency and accountability | Development and introducing of quarterly reporting on SP performance | Designing Q(A reporting system, defining data needs |  | Piloting reporting based on Q 3 & 4 | [7 empty] | 3.2019 | SSA
Initiative under develepoment with milestone definition
Initiiative due date with final approval

## iniciatives+indicators
Goal | Initiatives | Indicator | Definition | Why this indicator is important? | Unit | Formula |  |  |  | Frequency | Owner | Baseline (year 2017 or latest available) | Targets
[6 empty] | Nominator |  | Denominator |  |  |  |  | 2018 | 2019 | 2020
Improve financial protection and secure effective coverage |  | 1) OOP on drugsas % total health expenditures | OOP on drugs as a share of total health expenditures (THE) Data source: NHA; | OOP on drugs as a share of total health expenditures (THE) is broadly indicative indicator of financial protection for Georgian reality | % | Total out-of-pocket payments for drugs and services | 1031 | Total health care expenditure | 2861 | Annually | MoLHSA | 36.04% | 36% | 35% | 34%
|  | 2) Share of OOP payments from SSA reimbursed services under UHC inpatient services | OOP payments from SSA reimbursed services under UHC program, including only inpatient services Source: SSA reporting module | the aim is to track OOP Under UHC program | % | Total OOP payments for SSA reimbursed services under UHC program inpatient services | 64741 | Total cost for SSA reimbursed services under UHC program inpatient services | 423855699.97 | Annually | SSA | 25% | 25% | 24% | 23%
|  | 3) Share of households who have financial barriers to get health services | to measure financial protection Data source: UNICEF WMS | to measure financial protection | % |  |  |  |  | every 2 years | MoLHSA | 22.3% |  | 16%
Utilization/purchasing of services in the right level |  | 4) Share of avoidable hospitalizations | Share of hospitalizations due to ACSC (ACSC defined for Georgia: Perforated/bleeding ulcer: K250-K252,K254-K256,K260-K262,K264-K266, K270-K272,K274-K276,K280-K282,K284-K286; Urinary tract infections/Pyelonephritis: N10,N11,N12,N136,N390; Angina: I20,I240,I248,I249; Asthma: J45,J46; Chronic Obstructive Pulmonary; Disease: J20,J41-J44,J47; Congestive heart failure: I110,I50,J81; Convulsions and epilepsy: G40,G41,O15,R56; Diabetes complications: E100-E108,E110-E118,E120-E128,E130-E138, E140-E148; Hypertension: I10,I119; Pneumonia: J13,J14,J153,J154,J157,J159,J168,J181,J188; Tuberculosis A15,A16,A19; Data source: SSA reporting module/NCDC | ACSCs are conditions that can be treated in ambulatory settings and high level of hospitalization with ACSC indicates the suboptimal capacity of health services delivery to effectively prevent, diagnose, treat and/or manage these conditions in ambulatory settings in a timely manner. (WHO handbook http://www.euro.who.int/__data/assets/pdf_file/0010/305875/Assessing-HSD-performance-with-ACSH.pdf) | % | # of acute care hospitalizations for ambulatory care sensitive conditions | 41975 | # of total acute care hospitalizations | 279647 | Annually | SSA | 15.01% | 15% | 14% | 13%
|  | 5) Share of PHC (include prevention) out of expenditure of health state programs | Share of PHC and prevention expenditures from total health state programs Data Source: NHA | The share of pHC and prevention spending from total heath state programs' budget enables to monitor priority given to the PHC in the health budget over the time. | % | Total PHC spending state health care program, mill | 266 | Total state bhealth care program spending, mill | 921 | Annually | MoLHSA | 29% (2016) | 32% | 34% | 35%
Improve payment and contracting mechanisms | Developing and introducing DRG system | 6) Share of DRGs in hospital care | Share of the hospital care purchased by using DRGs Data source: SSA reporting module | Implementation of the DRG is one of the SSA's priorities and part of the DRG implementation process is to define the phase out strategy how to move to the DRG based payment with the objective to cover all providers and acute inpatient care (details of the phase out will be agreed in 2019). This indicator enables to monitor the progress made over the time. | % | Total SSA spending through DRG payments |  | Total SSA spending on inpatient care |  | Annually | SSA | Will be available after DRG implementation in 2020
| Critical assessment of basic financing PHC (considering the need for integration of rural and UHC, state vertical programs) including RBF principles | 7) share of PHC with RBF principles from total number of PHC facilities | PHC with RBF principles from total number of PHC facilities | Measure implementation of new methids of payment in PHC level | % | PHC with RBF |  | total number of PHC facilities |  | Annually |  | Will be available in 2019
| Developing principles of contracting for purchasing services, including consolidation of highly specialised and hospital care, selective contracting and monitoring and evaluation system of contracts performance | 8) Share of inpatient specialised care expenditure purchased through selective contracting from total expediture | Share of inpatient specialised care expenditure purchased through selective contracting Date source: SSA reporting module | SSA's aim is to expend principles of selective contraction from delivery to other clinical areas. This indicator enables to measure the progress over the years. | % | SSA spending by using principles of selective contracting, under UHC inpatient care | 18747259 | Ssa spending on inpatient care under UHC | 423855699.97 | Annually | SSA | 4.423% | ???? | ????
|  | 9) Share of SSA's purchased highly specialised from multiprofile hospitals (only inpatient services- levelAC,AD,) | Share of SSA's purchased care from multiprofile hospitals (only inpatient services) | estimate the consolidation of highly specialised hospital care | % | SSA's spendings purchased highly specialised care from multiprofile hospitals (only inpatient services) |  | Total cost for SSA reimbursed services under UHC program inpatient services | 423855699.97 | Annually | SSA | 0%
| Needs assessment for health services | 10) share of needed phc facilities from out of total PHC facilities; share of needed hospital beds from out of total hospital beds; | share of needed phc facilities from out of total PHC facilities | diference beetween needs and reality | % | eeded phc facilities needed hospital beds |  | total number of PHC facilities total hospital beds |  | Annually | MoLHSA/SSA | Will be available in 2019
HBP in line with population health needs | Designing the system and process of HBP revision and renewal | 11) Unmet need | Percentage of consultations where medicine was prescribed but not purchased because it was too expensive Sourse of data HUES | to measure unmet need | % |  |  |  |  | Annually | MoLHSA | 9.6%
Ensure equitable access to essential specialist care and strengthen PHC | Revision of referral system and developing GP functions. | 10) Share of referals to outpatient specialists from all GP vizits |  | to mesure referals from GP to specialists | No | number of referals to outpatient specialists |  | All GP vizits |  | Annually | SSA/MoLHSA | Will be available in 2019
| Strengthening the capacity of GP | 12) Share of GPs include CME and BMJ system from total numbero of GP | GP who will participate continous medical education system | to measure GP's professionalism | % | Number of GPs include CME and BMJ |  | total number of GP |  | Annually | MoLHSA | Will be available in 2019
|  | 12) PHC vizits per person | avarage out-patients visits per person | estimate the utilization of outpatient care and confidence in primary healthcare | No | Number of vizits in PHC | 14609228 | Number of population | 3700000 | Annually | MoLHSA | 4.0 | 4.2 | 4.4 | 4.6
|  | 13) Share of PHC vizits from total vizits (include inpatient and outpatient vizits) |  | estimate the utilization of outpatient care and confidence in primary healthcare | % | Number of vizits in PHC | 14609228 | total number of vizits in PHC and Hospitals | 15104972 | Annually | MoLHSA | 95% | 96% | 97% | 97.5%
Improvement efficiency and quality of health services | Developing the concept to upgrade quality assurance and improvement system | 14) Share of hospitals with acreditation from total number of hospitals |  | To improved quality of health services | % | hospitals with acreditation |  | total number of hospitals |  | Annually | MoLHSA | Will be available in 2019
|  | 15) Develop concept of medical audits (in cooperation with Regulatory Authority). |  | To improved quality of health services | No | Number of hospitals medical audits is conducted |  | total number of hospitals |  | Annually | MoLHSA/SSA | Will be available in 2019
| Defining set of indicators to assess the quality of medical services, mechanism to monitor and control quality, and coordinate the quality functions with Regulatory Authority | 16) Share of implemented indicators from set of indicators |  | to measure quality of health services | % | Number of implemented indicators |  | total number of indicators |  | Annually | MoLHSA | Will be available in 2019
| Develop principles and functions of health economics within SSA, the structural alignment of functions. | 17) Surgical procedures as % of cases performed in day surgery (cataract surgery, tonsil- or adenoidectomy). | Surgical procedures as % of cases performed in day surgery (cataract surgery, tonsil- or adenoidectomy). Data Source: SSA | improve efficiency | % | # of cases of day surgery (ophtalmology and oto-rhino-laringology) | 52968 | Total # of surgical cases | 1209144 | Annually | SSA | 4.381% | 5% | 6% | 10%
|  | 18) Re-hospitalization rate | An admission to an acute care hospital within 30 days of discharge from an acute care hospital with the same diagnoses Data source: SSA reporting module | Readmission following hospitalization is a costly and often preventable event. Too high readmission rate may indicate quality problems or signal that current financial incentives may not work as expected. | % | # of re-hospitalizations during 07.2017-12.2017 | 111854 | # of discharges during 07.2017-12.2017 | 674299 | every 6 month | SSA | 16.59% | 16% | 15% | 13%
Enhance electronic data exchange and improve quality of data | Mapping of key processes related with health service provision and SP and defining the needs for developing solutions for electronis exchange of data with stakeholders. | 19) Quality of SSA claims data | Deviation of reported data in different channels, based on selected indications (no of delivery, C-section, ...) source: SSA/NCDC | Quality of data | to be added | # of c-section according to NCDC data | 47071 | # of c-section according to SSA data | 47069 | quarterly | SSA | Will be available in 2019
| Introduce the use of electronic signature. | 20) electronic signature is introduced and used |  | For simplifying the reporting process
| Mapping of claims management process and design of electronic claims management solution. | 21) electronic claims management solution is designed |  | For simplifying the reporting process and improve qualiry of data
Improve population awareness | Development of Citizen Portal and applications to increase transparency for patients. | 22) People satisfaction with SSA service | customer survey by standard questionary (in ssa branches) | estimate the awareness of the population / satisfaction with the services covered. This will help clarify the health needs | % | # of people filled questionary |  | # of total population |  | to be added | SSA | will be available after patient survey
| Develop concept of citizen communication and communication plan for 2019. | 23) Share of people registered on the citizen portal | customer awareness about online service/information access | estimate customer awareness about online service to plan online survey for different purposes (satisfaction and etc.) | % | # of registered population on the citizen portal | 25 | # of total population | 3700000 | to be added | SSA | 0.0006757% | 20% | 30% | 45%
Increase transparency and accountability | Development and introducing of quarterly reporting on SP performance | 24) Share of claims not reimbursed by SSA | Share of claims not reimbursed by the SSA (Reasons: diagnoses was incorrect; data was not correct, does not follow the regulations) | The SSA's ability to detect fraud claims is essential to ensure the efficient and transparent use of public funds. Also, it is important that SSA is taking preventive measures (e.g. transparent and clear rules of procedure, electronic controls, data mining/analytics) that would optimize the adminitrative burden realated to the fraud detection activities | % | # of claims not reimbursed by SSA | 198254 | total # of claims | 1209144 | Annually/quarterly | SSA | 16.4%
Align SSA management and structure around the strategy |  | 25) SOP coverage of key processes | Defined core and support processes covered with standard operational procedures | Clarify standad procedures |  | # of SOP |  | # of key processes |  | annually | MoLSHA/SSA | will be available in 2019
Improve motivation and competencies of SSA staff |  | 26) Staff turnover in key departments related to SP | Staff turnover in the SSA's UHC, IT, Health Department | Gives indication about overall level of staff satisfaction as high turnover is usually the result of dissatisfaction with staff policy | % | # of people left SSA's key departments | 8 | Average # of staff in key departments | 225 | annually | SSA | 3.556% | 3% | 2% | 2%
|  | 27) Competency level | According the Law on Civil Services | to assess competency of stafs | level |  |  |  |  | annually |  | will be available in 2019
Develop IT systems |  | 28) Average length of processing a claim | Average length of processing a claim | indicate about claim processing complexity and IT system adjustment | minutes | Total time spent on making decision to reimburse the claim | 5771254 | total # of claims in 10.2017-12.2017 period | 288521 | quarterly | SSA | 20.0029
|  | 29) Reliability of key IT applications | Total time when IT system is not operable | Enables to measure IT system's reliability and to compare the actual performance against set target | minutes | time when system is not operable | 108000 | 7/24 | 7862400 | quarterly | SSA | (1.3% of total time) | 1% | 0.7% | 0.5%
Improve monitoring, reporting and anaysis |  | 30) Quarterly reporting on SP strategy implementation |  | Traking of SP strategy implementation process | [7 empty] | will be available in 2019

## iniciatives
| Goals | Initiatives
1 | Improve payment and contracting mechanisms | Developing and introducing DRG system
Critical assessment of basic financing PHC (considering the need for integration of rural and UHC, state vertical programs) including RBF principles
Developing principles of contracting for purchasing services, including consolidation of highly specialised and hospital care, selective contracting and monitoring and evaluation system of contracts performance
Needs assessment in health care services
2 | HBP in line with population health needs | Designing the system and process of HBP revision and renewal
3 | Ensure equitable access to essential specialist care and strengthen PHC | Revision of referral system and developing GP functions.
Strengthening the capacity of GP ( certification, recertification and continious medical education)
4 | Improvement efficiency and quality of health services | Developing the concept to upgrade quality assurance and improvement system
Defining set of indicators to assess the quality of medical services, mechanism to monitor and control quality, and coordinate the quality functions with Regulatory Authority
Develop concept of medical audits (in cooperation with Regulatory Authority).
Develop principles and functions of health economics within SSA, the structural alignment of functions.
5 | Enhance electronic data exchange and improve quality of data | Mapping of key processes related with health service provision and SP and defining the needs for developing solutions for electronis exchange of data with stakeholders.
Introduce the use of electronic signature.
Mapping of claims management process and design of electronic claims management solution.
6 | Improve population awareness | Development of Citizen Portal and applications to increase transparency for patients.
Develop concept of citizen communication and communication plan for 2019.
7 | Increase transparency and accountability | Development and introducing of quarterly reporting on SP performance