## Slide 1: 0
PROGRAMME REVIEW FOR REPRODUCTIVE, MATERNAL, NEWBORN, CHILD AND ADOLESCENT HEALTH
Facilitator’s Guide
December 2017

## Slide 2
  Introduction
  Outline of the RMNCAH Programme Review process
  3
  4
  I. Preparation of the RMNCAH Programme Review
    1.1 Planning for the Programme Review
    1.2 Data collection
    1.3 Preparation for the Workshop
  5
  5
  6
  6
  II. RMNCAH Programme Review Workshop
    2.1 Logistics for the Workshop
    2.2 Steps of Programme Review Workshop
    2.3 Sample agenda
    2.4 Workshop facilitation tips
  7
  7
  8
  9
  13
  III. Findings of the RMNCAH Programme Review
    3.1 Presentation of the findings
    3.2 Suggested outline for documenting findings and
    recommendations of the RMNCAH Programme Review
    3.3 Suggestions for developing action plan
  21
  21
  22
  23
Contents
  Annexes
    A.1 Data resources
    A.2 Introductory presentation (separate file)
  24
  --

## Slide 3
  The purpose of this guide is to assist countries in planning, organizing and facilitating an integrated review of Reproductive, Maternal, Newborn, Child, and Adolescent Health (RMNCAH) programmes. This guide provides a recommended approach for conducting RMNCAH programme reviews but is not intended to be prescriptive in that the processes should be adapted to suit the needs of the country or programmes where it is being used.
  The guide outlines the main steps for coordinating a programme review for RMNCAH, including:
  Preparation for the programme review process
  Data collection
  Planning and facilitating the programme review workshop
  Reporting findings of the programme review
  The target audience for this guide are those who are organizing and facilitating a Programme Review for RMNCAH.
  This Facilitators’ Guide complements a Guidance Document and Data Tool.
Introduction

## Slide 4
Outline of RMNCAH Programme Review process
Suggested overview outline of steps for the RMNCAH Programme Review
1.1 Planning for the Programme Review
Officially engage the Programme Review Coordinator and Committee to make plans for the review, including scope, facilitators, participants, indicators and data that will be reviewed and resources required
Schedule the Presentation Meeting of the findings and recommendations of the Programme Review to senior MOH representatives, partners and other stakeholders (to occur at the end of or as soon as possible after the Programme Review Workshop)
Invite participants for the Programme Review Workshop
1.2 Data Collection
Review indicators in Data Tool and adapt (i.e. add, delete, modify indicators) to country needs
Compile existing data (from surveys, HMIS, LMIS, etc.) and enter in the Data Tool
Validation/confirmation of information
  Key informant interviews/focus group discussions, field visits, and client perspectives
  Data quality assessment
1.3 Preparation of the Workshop
Programme Review Committee prepares presentations for the Workshop
Committee prepares copies of Workshop materials, including: agenda, participants lists, programme review documents with completed Data Tool, and other relevant materials
Committee checks that all logistical arrangements have been completed as planned
Committee makes preliminary assignments of participants to subgroups
Facilitators for the Workshop are selected and briefed on their tasks during the Workshop
2. Programme Review Workshop
Review and analyze information in Data Tool and prioritize intervention packages for analysis
Facilitators guide participants in assessing progress RMNCAH programmes and formulating recommendations
Programme Review Committee and facilitators should hold a daily evaluation of activities and document the subgroup work and begin the report of the review
Programme Review Presentation Meeting is held to inform senior MOH representatives, partners and other stakeholders about the findings and recommendations of the review*
3. Reporting findings of the Programme Review
Programme Review Committee and facilitators document the findings and recommendations of the review into a Programme Review report
MOH prepares a plan of action to ensure that recommendations of the Programme Review are used
Final Programme Review Report is completed and disseminated by MOH
  *This presentation can be held after the Workshop concludes, time permitting.

## Slide 5
I. Preparation of the RMNCAH Programme Review
When the Ministry of Health (MOH) identifies a need for an RMNCAH Programme Review and decides to conduct one, plan for about 2-4 weeks to complete preparations for the Programme Review Workshop.
It is important to take into consideration the fact that the actual time towards preparation of the actual Programme Review may take longer than 4 weeks in order to align with other planning events that are ongoing in a country. In case special surveys such as SARA, EmONC needs assessment or quality of care assessment are to be conducted, they should be conducted before the review.
1.1 Planning for the Programme Review
Below is a suggested checklist of actions that should be completed in preparation for the Programme Review. Each step may be modified by the country based on existing systems, processes, and available resources. Securing of time commitment and budgetary resources should be more straightforward in cases where the programme review had already been incorporated in the sector annual plan and financing framework. The scope and order of tasks may be modified to best align with the country’s ongoing processes.
Engagement of Programme Review Committee
Decide on scope of the RMNCAH Programme Review
Identify Programme Review Coordinator if desired
Plan for Data Collection process
Plan for Programme Review Workshop (dates, venue, inviting participants)
Select a lead facilitator and co-facilitators for the Programme Review Workshop
Schedule meeting to present findings and recommendations of Programme Review to senior MoH officials and other partners and stakeholders
Mobilization of resources
Map out timeline and budget for Programme Review (Workshop, Committee, consultant fees (if necessary), etc.) and mobilize funds
  Secure additional funding depending on budgetary constraints
Select and invite RMNCAH Programme Review Committee

## Slide 6
1.2 Data collection
The time length and scope of the collection of information required for the RMNCAH Programme Review depends on the availability and quality of existing data. Validation exercises may be necessary. Information should be organized for the Programme Review Committee to review.
1.3 Preparation for the Workshop
Approximately 1-2 weeks prior to the Workshop, the Programme Review Committee should assess the status of final planning details and assign those that have not bee completed. Finalizing these preparatory will help to ensure that the RMNCAH Programme Review Workshop will run smoothly.
Data collection
Review indicators in Data Tool and adapt to country needs (add, delete, modify indicators)
Compile existing data (routine monitoring systems, latest surveys)*
Assess status of data (availability, quality, completeness, and existing validation mechanisms)
  Document data quality and availability issues identified
  Additional information collection, analysis and validation if necessary (Key informant interviews/focus groups, client perspectives, field visits)
Enter data into Data Tool and compile other findings for Workshop
Preparation for the Programme Review Workshop
Review and finalize Data Tool and other compiled information
Prepare presentations for the Workshop and draft agenda
Check that all logistical arrangements (communication to participants, venue, equipment, catering, materials, etc.) have been arranged /reserved
Make preliminary assignments of participants to subgroups
Brief facilitators on their tasks during the Workshop
Prepare Workshop materials, including: agenda, list of participants, programme review documents with completed Data Tool, etc.
*See Annex 1 for a suggested list of data sources.

## Slide 7
II. RMNCAH Programme Review Workshop
A few days prior to the Workshop, the lead facilitator and co-facilitators should meet to confirm that all preparations are complete, to review materials, and to agree upon roles for each step of the agenda (i.e. taking turns as note-taker for each plenary section). This meeting can serve as a practice session for facilitating each step of the Workshop and should cover:
2.1 Logistics for the Workshop
Below is a suggested checklist of details that the facilitators should review during their meeting prior to the Workshop. Items on this list are non-exhaustive and will depend on the setting of the Workshop and available resources.
Logistics for the Programme Review Workshop
Visit venue to arrange where and how plenary and group sessions will be held
Confirm equipment and materials needed for the Workshop are reserved
  Projector for plenary sessions
  Laptop computer(s) USB flash drives for plenary presentations and group work
  Printer access
  Flipcharts with markers
  Etc.
Review number of participants attending Workshop
  Confirm sufficient catering (lunches, tea-breaks) is ordered
Confirm materials for participants are prepared
  Printed materials and/or USB flash drives with materials (for group work sessions and/or all participants)
  Note-paper and pens
  Remind participants to bring data, strategic plans, and laptops to Workshop
  Review Data Tool and all materials that participants use when doing each step
  Instructions to give the participants
  Suggestions for how to facilitate each step and guide group discussions
  Expected output of the subgroup work for each step
  Finalize agenda
Each facilitator should take a turn practicing giving instructions on how to do a step or two.

## Slide 8: Figure 1. RMNCAH Programme Review Workshop: Key steps
2.2 Steps of Programme Review Workshop
A sample four-day agenda for the RMNCAH Programme Review Workshop is provided in this guide. The agenda may be condensed or lengthened to suit a country’s needs, but the suggested steps/sessions should be followed in order as the sequence matches the logic flow of the Programme Review process in Figure 1.
  1. To what extent have the RMNCAH programmes improved the health status of women, children, and adolescents?
  Review goals, objectives, targets and baselines to identify the most critical needs of women, children, and adolescents
  Outcome: Assess whether RMNCAH programme(s) is/are making positive, negative, or no progress in improving health status
  Review intervention coverage in terms of progress towards achieving target impact
  Outcome: Identify underperforming intervention packages for in-depth analysis.
  2. Which RMNCAH intervention packages were implemented and where? How well were they implemented?
  Review indicators of availability, access, quality and demand – available information plus personal knowledge and experience
  Outcome: Identify achievements and gaps in implementation of each package
  Review availability of packages – geographic areas and levels of health system
  Outcome: Identify areas and levels where packages are implemented and where improvement is needed
  3. What are the RMNCAH programmes’ most important problems that are causing gaps in implementation?
  Outcome: List problems causing implementation gaps and identify most important ones
  4. What are solutions and recommendations for the most important problems?
  Outcome: Propose solutions that address causes of main problems and formulate recommendation on how these solutions should be carried out

## Slide 9
2.3 Sample agenda
Time | Activity | Format
8:30 – 9:00 | Registration | 
9:00 – 9:30 | Welcome and opening | Plenary
9:30 – 11:00 | Introduction to RMNCAH Programme Review process and steps: Discussion and questions | Plenary
11:00 – 11:30 | Break | 
11:30 – 12:00 | Introduction of Step 1a: What are the goals, objectives, targets and baselines? | Plenary
12:00 – 13:00 | Step 1a: Review goals, objectives, targets and baselines to identify the most critical needs of women, children, and adolescents | Group work
13:00– 14:00 | Lunch | 
14:00 – 14:30 | Step 1a group work continued | Group work
14:30 – 15:30 | Presentations on group work findings | Plenary
15:30 – 16:00 | Break | 
16:00 – 17:00 | Discussion and questions on presentations and plan for the rest of the Programme Review | Plenary
17:00 – 18:00 | Facilitators’ meeting | 
Day 1

## Slide 10
Time | Activity | Format
8:30 – 9:00 | Recap Day 1 activities | Plenary
9:00 – 9:30 | Introduction of Step 1b: To what extent have the RMNCAH interventions contributed to achieving the target impact? | Plenary
9:30 – 10:30 | Step 1b: Review coverage of RMNCAH interventions to identify underperforming interventions or intervention packages and assess disparities in coverage | Group work
10:30 – 11:00 | Break | 
11:00 – 11:30 | Step 1b group work continued | Group work
11:30 – 12:30 | Presentations on group work findings | Plenary
12:30– 13:30 | Lunch | 
13:30 – 14:00 | Introduction of Step 2a: Which RMNCAH intervention packages were implemented and where? | Plenary
14:00 – 15:00 | Step 2a: Review availability of packages – geographic areas and levels of health system – where interventions or packages were implemented and where improvement is needed | Group work
15:00 – 15:30 | Break | 
15:30 – 16:00 | Step 2a group work continued | Group work
16:00 – 17:00 | Presentation on group work findings | Plenary
17:00 – 18:00 | Facilitators’ meeting | 
Day 2
2.3 Sample agenda con’t.

## Slide 11
2.3 Sample agenda con’t.
Time | Activity | Format
8:30 – 9:00 | Recap Day 2 activities | Plenary
9:00 – 9:30 | Introduction of Step 2b: How well were RMNCAH intervention packages implemented? | Plenary
9:30 – 10:30 | Step 2b: Review indicators of availability, access, quality, and demand | Group work
10:30 – 11:00 | Break | 
11:00 – 11:30 | Step 2b group work continued | Group work
11:30 – 12:30 | Presentations on group work findings | Plenary
12:30– 13:30 | Lunch | 
13:30 – 14:00 | Introduction of Step 3: What are the RMNCAH programmes’ most important problems that are causing gaps in implementation? | Plenary
14:00 – 15:00 | Step 3: Identify the most important problems that are causing the gaps in implementation | Group work
15:00 – 15:30 | Break | 
15:30 – 16:00 | Step 3 group work continued | Group work
16:00 – 17:00 | Presentation on group work findings | Plenary
17:00 – 18:00 | Facilitators’ meeting | 
Day 3

## Slide 12
2.3 Sample agenda con’t.
Time | Activity | Format
8:30 – 9:00 | Recap Day 3 activities | Plenary
9:00 – 9:30 | Introduction of Step 4: What are the solutions and recommendations for problems identified? | Plenary
9:30 – 10:30 | Step 4: Specify solutions to the most important problems and formulate recommendations on what the programme and partners should do | Group work
10:30 – 11:00 | Break | 
11:00 – 11:30 | Step 4 group work continued | Group work
11:30 – 12:30 | Presentations on group work findings | Plenary
12:30– 13:30 | Lunch | 
13:30 – 14:00 | Discussion and questions on solutions and recommendations | Plenary
14:00 – 15:00 | Summary and discussion of next steps | Plenary
15:00 – 15:30 | Closing | Plenary
15:30 – 16:30 | Facilitators’ meeting | 
Day 4
  Note on presentation of findings to senior MoH officials and other stakeholders: If the de-brief on findings of the RMNCAH Programme Review is scheduled for the end of the Workshop, the agenda should be modified to accommodate this.

## Slide 13
2.4 Facilitation tips for the Workshop
INTRODUCTION SESSION
Lead facilitator should make a presentation to the participants about the workshop and the work they will do and the expected outcomes of the workshop. Use the Introduction to the Programme Review Workshop as the basis for the presentation*.
What is the Programme Review for reproductive, maternal, newborn, child and adolescent health (RMNCAH)?
How does the Programme Review fit into a programme’s planning cycle?
Framework for the Programme Review
Logical basis for the steps of the Programme Review workshop
Steps to be done in the Programme Review workshop
It is important that the workshop participants understand the logic behind the steps that they are doing. The introductory presentation at the beginning of the Workshop, which explains the framework, logical basis and the steps of the workshop describes this. However, facilitators should revisit and review some of these concepts as the workshop progresses, as the participants develop understanding or confusion At each step of the workshop, the facilitator can point out the current step on Figure 1 (of this document), in relation to those already completed and those still to be done.
FLOW OF PLENARY TO GROUP WORK
Generally, the facilitator should introduce each step in plenary by reviewing the objectives of the step below. Point out the step on a wall chart or slide of the steps of the Programme Review Workshop. Read aloud in plenary the objectives and outcomes of each step.
Facilitating the RMNCAH Programme Review Workshop can be done in various ways to match the setting, number and type of participants, and other particulars to each programme structure. Below are some general suggestions based on past experiences with facilitating programme reviews.
Plenary sessions
*See Annex 2 for sample introductory presentation slides (separate file).

## Slide 14: Figure 2. Suggested group assignments for Programme Review Workshop
2.4 Facilitation tips for the Workshop
GROUP ASSIGNMENTS
When registration is complete, the co-facilitators may quickly compare the preliminary group assignments to the list of individuals who have registered (who are present at the Workshop). They may need to add or move some participants to balance the groups. After the discussion of the goals and objectives, and while the participants are still together in plenary, explain that the participants will divide into groups.
Divide the participants into groups with a facilitator assigned to each. Then ask the participants to move into those groups by moving to different corners of the room or into breakout rooms. During the course of the Workshop, the groups can be reorganized to facilitate discussions on cross-cutting issues.
An example of possible group arrangements for the Workshop is depicted in Figure 2. In this example, the participants are initially split by RMNCAH programme area (for Steps 1a to 3) and then re-organized by cross-cutting issues (at Step 4) to better analyze and address overlapping thematic problems and formulate recommendations and solutions. Group assignments are flexible and should be adapted by the Workshop facilitators to match the makeup and number of participants and flow of the agenda topics.
Group-work sessions
Group 1a: Sexual & Reproductive Health
Group 2a: Maternal & Newborn Health
Group 3a: Child Health
Group 4a: Adolescent Health
HEALTH PROGRAMME AREAS
Group 1b: Human resources
Group 2b: Finances
Group 3b: Supply chain & infrastructure
Group 4b: Strategy
CROSS-CUTTING ISSUES*
Steps 1a to 3
Step 4
*Note: If problems that are unique to a programme area (e.g. Adolescent or Reproductive health) are identified throughout the Workshop, a programme-specific group can be formed at Step 4 to discuss solutions and recommendations for these issues in addition to the groups for cross-cutting issues.

## Slide 15
2.4 Facilitation tips for the Workshop con’t.
Group-work sessions con’t.
GENERAL TIPS
The principle job of the facilitator in the group is to guide the discussion of the information in the Data Tool and from other materials with respect to each step and to guide the group to make decisions which are then documented.
When the participants have met in the group, ask them to review the objectives and outcomes of the step. The group facilitator may allow time for participants to review relevant materials silently or may lead them through the materials.
For each step, when the group convenes, the facilitator should select:
Note-taker to document the group’s decisions
Reporter who will present the group’s decisions to the plenary
For each step these two roles may be assigned to the same person, but it is helpful to choose different individuals for these roles as the workshop continues. Facilitators then plan how the group reports will be collected at the end of each step and given to the lead facilitator.
One way is for each group to have a USB drive where they save their work. During the session, the note-taker types notes on the group’s discussion and conclusions into group work templates and saves them on the group’s flash drive. These notes can be projected for the plenary presentation, and the lead facilitator can keep a copy of all files. Then the flash drive will be returned to the group to use during the next step.
Once the Workshop participants have been split into groups (either by RMNCAH areas or cross-cutting issues), the facilitator will lead discussions and ensure that group’s decisions are documented and ready for presentation in plenary. For each step the facilitators can use the suggested sets of questions throughout the Facilitator's Guide to guide the participants in meeting the objective of the step. The participants will use the populated Data Tool and other prepared materials to review and answer each question.
Sometimes it may be useful for the group facilitator to have an individual discussion with a particular participant aside from the group to help facilitate the subgroup’s progress, or to ask the lead facilitator to do this. This may be needed, for example, to:
Address communication barriers that prevent certain participants from voicing their views in the group (such as a dominant participant, or a participant who is reticent to speak out in front of individuals who outrank them).
Discuss sensitive issues such as staff performance or relationships that participants may be unwilling to discuss in the group.

## Slide 16
2.4 Facilitation tips for the Workshop con’t.
Group-work sessions
STEP 1A: What are the goals, objectives, targets and baselines?
The group facilitator should explain that the purpose of this step is to review goals, objectives, targets and baselines to identify the most critical needs of women, children, and adolescents. The outcome of this step will be an assessment of whether the RMNCAH programme(s) is/are making progress towards meeting their set goals, objectives, and targets and to improving health status of women, children and adolescents.
STEP 1A discussion questions*
What are the goals and objectives of the programme(s)? What are the target dates for achieving each objective?
What are the targets set? What is the baseline for the key indicators and what is the most recent data value for each health status indicator of the programme(s)?
What are the trends in each indicator over time? Are the programme(s) on track to achieving the targets?
Are there data available on all relevant indicators?
Are there significant variations in health status indicators by equity differentials/ characteristics such as socioeconomic status, wealth quintile, geographic areas, urban/rural, sex, and/or education? Are there any data available for these elements?
*NB: Each question pertains to the programme area/topic assigned to that group (e.g. Sexual and Reproductive Health or Child Health).
What is a goal?
A goal is what a programme is going to achieve in the long term. Goals are long term improvements in RMNCAH that are expected by a programme.
What is an objective
An objective is what the programme is going to achieve in the shorter term to reach goals. Objectives are based on the interventions that will be implemented by the programme and the progress expected in the short or medium term.
EXAMPLE
Goal
To reduce stunting and wasting rates among children under 5 years of age
Objectives
Increase rate of exclusive breastfeeding from X% to Y% by 2022
Increase proportion of children under 2 years receiving appropriate complementary feeding from X% to Y% by 2022

## Slide 17
2.4 Facilitation tips for the Workshop con’t.
Group-work sessions
STEP 1B: To what extent have RMNCAH interventions contributed to achieving the target impact?
During this step, the facilitator will guide the group in reviewing coverage of RMNCAH interventions to identify underperforming interventions or packages and assess disparities in coverage. The outcomes of this step are to assess where we are in intervention coverage in terms of progress towards achieving impact and to prioritize which intervention packages should be discussed and examined in-depth in subsequent steps of the workshop.
STEP 1B discussion questions
Review the coverage of interventions or intervention packages to identify which interventions or intervention packages have the poorest coverage and/or have made the least progress.
For each intervention package, are there data available on quality of care (i.e. effective coverage)?
Which intervention packages are top priorities for the programme(s) and for achieving the target impact?
Based on the above, which intervention packages should be analyzed further during the workshop?
STEP 2A: Which RMNCAH intervention packages were implemented and where?
During this step, the facilitator will guide the group in reviewing the availability of (i.e. geographic areas and levels of health system) interventions or packages. The outcome of this step is to identify areas and levels where packages are implemented and where improvement is needed.
The facilitator can point out that the analysis in this and subsequent steps will focus on where and how interventions are being implemented. Because interventions are generally implemented in packages, the participants will analyze them this way. For example, it would not make sense to assess only availability of case management of diarrhoea, because it is implemented as a part of the package IMCI. If there is a problem with supply of ORS, this would not be addressed on its own, but as one of the essential medicines for IMCI.
STEP 2A discussion questions*
For each prioritized intervention package (from Step 1b):
At what levels of the health system are the services provided? Is service being provided at the lowest appropriate level of care?
In which areas of the country are the services being provided? Are there specific areas in which coverage of the intervention is particularly poor?
What are potential reasons for disparities in coverage of the intervention package?
Example: Intervention vs. intervention package
Intervention package: Antenatal care (ANC)
Interventions of ANC (sample list)
Tetanus toxoid immunization
Birth and emergency planning
Detection and management of complications
Detection and treatment of syphilis
Information and counselling on self-care, nutrition, safer sex, breastfeeding, family planning for birth spacing

## Slide 18
2.4 Facilitation tips for the Workshop con’t.
Group-work sessions
STEP 2B: How well were the RMNCAH intervention packages implemented?
During this step, the group will review indicators of availability, access, quality and demand, including both available information plus personal knowledge and experience. The outcome of this step is to identify achievements and gaps in implementation of each intervention or package selected for further analysis.
STEP 2B discussion questions
For each intervention package, review data available on availability, access, quality and demand. If a target has been set, what is its status?
Which intervention packages do not have data available for these indicators?
What are the major achievements and gaps in availability, access, quality, and demand for each intervention package?
Availability is the extent that the health services (preventive and treatment interventions) are available to those who need them. Availability is not only the presence of a health facility in a geographic area. Availability of an intervention package requires implementation of that package.
Access means that members of the target population are able to reach and use the health services, when they are available. Possible barriers to access include geographic distance, financial barriers (e.g. unable to afford costs of transport, goods or services), cultural barriers (e.g. husband or other family members may not agree for women or adolescents go to a health facility on their own), or time limitations.
Quality means that the health services are provided according to technical standards, and in a way that is appropriate for the target population. Increasing the quality of a service often increases demand for it.
Demand means that clients are motivated to seek and make use of the health services. Improved demand indicates that clients have knowledge of the availability and benefits of the services and are motivated to use them.
  The facilitator should explain that this discussion is different than previous steps since participants may add information based on their own knowledge and experience. This is because data on availability, access, quality and demand for different packages is usually very limited. However, people who work in the programme often have some knowledge of these aspects. For example, there may not be data to show it, but a participant may know that certain groups do not access childbirth care for particular social or religious reasons. This is important when identifying gaps in implementation.

## Slide 19
2.4 Facilitation tips for the Workshop con’t
  STEP 3: What are the RMNCAH programmes’ most important problems that are causing gaps in implementation?
The outcome of this step is to identify the most important problems causing implementation gaps. The facilitator can begin by explaining that the group will examine the gaps identified during the previous group work sessions. They will suggest problems that are causing those gaps. Here, the facilitator, will need to guide the group not to just list the gaps as the problems, but to list the probable causes of those gaps. After the group has created a good list of problems, they will work together to choose the 3-5 most important problems causing gaps in implementation.
Group-work sessions
STEP 3 discussion questions
What are the possible causes of the gaps in implementation of the intervention packages?
Of the possible problems causing these gaps, which are the most important?
To identify the most important problems, consider elements such as:
  Does the problem occur across multiple interventions/packages, or is it limited to just one?
  Does the problem occur throughout the country, or is it limited to some geographic areas?
  Does the problem occur at multiple levels of the health care system, or is it limited to one level?
  Does the problem significantly reduce the effectiveness of the package?
  Does the problem significantly reduce the demand for or use of the service by the target population?
  Is a feasible solution available?
The facilitator will lead the group through a process to select the most important problems, which the note-taker for the session should record. Various methods for deciding on the most important problems can be used. Below are two suggestions:
Each group participant is given 3 cards on which he/she writes the 3 problems that he/she thinks are most important --one problem on each card. Then the cards are sorted and counted. The 3-5 problems that appear most frequently are the most important.
Problems are listed on a flip chart. One by one, members place a tick beside the 3 problems that they consider most important. The ticks are counted; the 3-5 problems with the most ticks are selected as the most important.

## Slide 20
2.4 Facilitation tips for the Workshop con’t
Group-work sessions
STEP 4: What are solutions and recommendations for the most important problems?
Each group will be given a copy of the prioritized issues identified in Step 3 . If it makes sense, It is at this step that groups may be reorganized by cross-cutting issues. It is important for the facilitator to focus the group discussion to ensure a productive session with solutions for each issue clearly mapped out. The outcome for this step is to propose solutions that address causes of the most important problems and formulate recommendation on how these solutions should be carried out by the programme(s) and partners.
The facilitator will lead the group in discussions on each problem. As they suggest probable causes of the problem, the note-taker should record them. Sometimes solutions are specific to a particular problem and intervention package. Other solutions may apply to multiple problems and intervention packages.
After further discussion, the group should reduce the list to the main causes and then propose possible solutions that will overcome or reduce the main causes. The facilitator should guide participants to identify solutions that:
Address causes of the problem
Are feasible with available human, material and financial resources
Build on existing activities when possible
STEP 4 discussion questions
When proposing solutions and formulating recommendations, please consider elements such as:
  Will the solution have an impact on coverage of effective interventions, and thereby reduce mortality and morbidity for the women, newborns, children or adolescents in the short and long term?
  Is additional background information or data needed to analyze the problem fully?
  Can the solution be implemented with available resources, or are additional resources required?
  If policy changes are necessary, are they possible in the short or medium term?
Recognize that it may not always be possible to identify feasible solutions to a problem. If additional data are required, note these data needs and include them as a recommendation for further action. If problems cannot be immediately solved, then a recommendation may be to allocate responsibility for working on the problem in the longer term. The note-taker will record the main points of the discussion (problem, causes, possible solutions).
Solutions vs. recommendations
Solutions help to address and overcome the causes of the most important problems. Recommendations are the specific actions that need to be taken to achieve these solutions to problems.

## Slide 21
2.4 Facilitation tips for the Workshop con’t.
STEP 4 con’t: What are solutions and recommendations for problems?
The group will also work to develop detailed recommendations about what the programme needs to do in the future to continue its achievements and solve the problems. The recommendations should provide detail on how the solutions identified may be carried out. The recommendations should be specific, action-oriented, feasible and realistic to incorporate into the next workplans. The note-taker should record the recommendations as well.
Facilitators should guide participants to form recommendations that are concise, clear and action-oriented; start each with a verb. Also specify to whom the recommendation is made (e.g. MOH, immunization programme, donor) and at what level the recommendation will be implemented (national, regional or district).
Group-work sessions
Increase staff
Improve communications with caregivers of children under 5
Not
Develop capacity by training 100 more midwives by March 2019. (University X)
Develop posters and take-home cards for caregivers on care for development and care of sick children in the community by June 2018. (MOH)
Provide funding for printing of posters and take-home cards. (Partner Y)
Instead
III. Findings of the RMNCAH Programme Review
The Programme Review Committee will present on and draft a report documenting the findings and recommendations to the MoH.
3.1 Presentation of the findings
The Programme Review Committee will present the findings and recommendations of the Programme Review Workshop to senior MoH representatives, other Ministries, partners, and other stakeholders. This presentation may occur at the end of the Workshop or at a time scheduled soon after its conclusion. The presentation should be scheduled in advance to secure attendance from key stakeholders.
Examples of recommendations

## Slide 22
  3.2 Suggested outline for documenting findings and recommendations of the RMNCAH Programme Review
  Executive summary
  This summary should highlight the key issues that emerged from the Programme Review and are covered in detail in the body of the report.
  Introduction
  In this section, the background on why the programme review was carried out and the context (i.e. stage in programme cycle) of the RMNCAH programmes.
  Purpose and objectives: The goals that were agreed upon when beginning the review should be re-stated to make sure that they were met.
  Methodology: The main methods used to collect, summarize and analyze the information used for the review should be reported. This can include a brief description of the Programme Review Workshop, sources of data, etc.
  Findings from analysis
  This section should include important problems and patterns that are causing the gaps in availability, access, quality, and demand for a package, and as a result, low coverage. The impact of the programme(s) on addressing these issues should be highlighted.
  Recommendations and solutions
  In reporting the suggested solutions and recommendations, one must include details on implementation and a way forward. This should reflect any additional recommendations and discussion during the presentation of the findings. In addition, some partners may have agreed to roles in implementation, which should be added to the action plans.
  ANNEXES
  Resources used to conduct the review should be included. Some examples include:
  Populated Data Tool
  Listing with brief descriptions of RMNCAH Programmes’ packages of interventions
  Information on Programme Review process (Programme Review Coordinator, Programme Review Committee TOR and members, Workshop participants and facilitators; Workshop agenda, etc.)

## Slide 23
3.3 Suggestions for developing plan of action
Where will the actions be implemented?
How will selected actions will be monitored?
  What are the baselines and targets?
New recommendations can be incorporated into the work plans of technical staff, donors, NGOs or other stakeholders when
  National health sector or related programs specific plans are being developed
  Ministries are allocating annual budgets or staff to particular areas
  Global funding initiatives or Partners are seeking proposals for funding
  Partners are seeking proposals for funding
  Partners have on-going activities in related or similar area
  Local or international NGOs are beginning work in a particular district or group or districts – or have on-going work in a similar technical area
  Decisions are being made about medical manpower training – the type of skills and the numbers of staff required
  Non-health groups or organizations (community-based organizations, religious groups, teachers, etc.) are looking for ways of being involved with local health projects.
MONITORING AND PLANNING
Where will the actions be implemented?
Who is responsible and who will be involved in implementation?
  Programme managers from different divisions need to agree to take action in their own areas.
Timeframe for implementation. Timing of actions on the recommendations will be influenced by availability of staff and financial resources, and other factors.
How to finance the implementation?
  Available resources and how additional resources will be mobilized.
LOGISTICAL INFORMATION
The Ministry of Health will meet to develop a plan of action, based on the recommendations from the Workshop. The plan should include actions to be taken, which are concrete, specific, realistic, time bound and achievable, grouped and sequenced in a logical and feasible plan.
For each action specify:

## Slide 24
    A.1 Data Resources
Data source |  | Access | 
Routine monitoring data |  |  | 
Health Management Information System (HMIS) Logistics Management Information System (LMIS) Human Resources Information System (HRIS) |  |  | Country-specific system(s) Country-specific system(s) Country-specific system(s)
Population surveys |  |  | 
Demographic and Health Survey Multiple Indicator Cluster Survey |  | http://dhsprogram.com/Data/ http://mics.unicef.org/surveys | 
Health Facility Assessments |  |  | 
Service Availability and Readiness Assessment Service Provision Assessment Service Delivery Indicators Service Provision Assessment | http://www.who.int/healthinfo/systems/sara_reports/en/ http://dhsprogram.com/What-We-Do/Survey-Types/SPA.cfm http://datatopics.worldbank.org/sdi/ UNFPA |  | 
Analysis resources |  |  | 
Equity analysis - EQUIST Equity analysis – Health Inequality Monitoring Modeling and projections - Spectrum (including LiST, FamPlan, DemProj, etc.) |  | http://www.equist.info/ http://www.who.int/gho/health_equity/assessment_toolkit/en/ http://www.avenirhealth.org/software-spectrum.php | 
Compiled country reports |  |  | 
Countdown to 2030 |  | http://countdown2030.org/ | 
The suggested list of resources below is non-exhaustive and should be adapted to fit the country’s data needs for the RMNCAH Programme Review.