## Sheet1
Draft roadmap for the pilot and the meeting(s) with pilot hospitals
| Activities | April 2019 | May 2019 | June 2019 | July 2019 | Aug 2019 | Sep 2019 | Oct 2019 | Nov 2019 | Dec 2019
1 | Asses adaptation of the DRG grouper to the SSA’s IT system
2 | Analyze the DRG grouping results
3 | Detect frequent “errors” from provider’s side based on retrospective data analysis
4 | Analyze Data quality
5 | Analyze the “Error DRG” reasons (whys and wherefores)
6 | Prepare contract draft with providers on the pilot to enroll all of them according to their willingness
7 | Organize a meeting(s) with hospitals intending to participate/invovlved in the pilot
8 | Contracting pilot hospitals |  |  |  | ?
9 | Asses gaps in capacity and develop a training plan for capacity building among different stakeholders
10 | Improve competence in DRG systems for all stakeholder organizations by offering training and educational opportunities according to need, share with them DRG grouping characteristics, provide feedback about grouping results
11 | Redesign IT system to support DRG implementation for pilot
12 | Redesign IT system to optimize the claims management process