## 1Q2019
Goals | Initiatives | Q1 19 | Q2 19 | Q3 19 | Q4 19 | Q1 20 | Q2 20 | Q3 20 | Q4 20 | Q1 21 | Q2 21 | Q3 21 | Q4 21 | Owner | Cooperation | Implementation status (end of March '19)
3.3. Improvement efficiency and quality of health services | 3.3.1. Developing the concept to upgrade quality assurance and improvement system | ToR for the consultant to support development of quality improvement startegy and instruments prepared | Situation analysis and advocacy among stakeholders (state agencies, providers, clinicians) regarding quality improvement needs done | Elaboration of quality improvement strategy and instruments |  | Quality improvement strategy and instruments ready for implementation | [7 empty] | Head of Health Care Department MOH | Head of Department of UHC SSA, Head of Department of Health Programs SSA, State Regulatory Agency of Medical Activities
| 3.3.2. Defining set of indicators to assess the quality of medical services, mechanism to monitor and control quality, and coordinate the quality functions with Regulatory Authority |  | Elaboration concept of quality control for medical services | Establishment of structural unit and human resources | Elaborate indicators and mechanism to monitor and control quality | Pilot elaborated indicators and monitoring tools |  | Pilot elaborated indicators and monitoring tools |  | Start implementation set of indicator system |  |  |  | Head of Health Care Department MOH | Head of Department of UHC SSA, Head of Department of Health Programs SSA, State Regulatory Agency of Medical Activities
| 3.3.3. Develop concept of medical audits (in cooperation with Regulatory Authority) |  |  |  |  | Identify the standards and audit criteria |  | Selecting and developing appropriate performance levels; identify inclusion/exclusion criteria and exceptions |  | Elaborate measuring performance methodology: data collection, data analysis, drawing conclusions, presentation of results; Identify principal steps of quality improvement plans and sustaining improvements according the elaborated mechanism to monitor and control quality |  |  | Final revision of concept of medical audits, analysing feedback from professionals and international partners | Head of Health Care Department MOH | Head of Department of UHC SSA, Head of Department of Health Programs SSA, State Regulatory Agency of Medical Activities
3.4. Improve payment and contracting mechanisms | 3.4.1. Developing and introducing DRG system | DRG grouper integrated to the SSA system | Preparations for the pilot in piloting hospitals. Analytical work to prepare for the development of DRG pricing and reimbursement policy | DRG pilot in piloting hospitals. DRG cost weights and reimbursement principles for the "virtual implementation" | Simulations and analytics to develop DRG cost weights and reimbursement rules for 2020 "virtual implementation" period | DRG "virtual implementation" in all hospitals |  | DRG cost weights and reimbursement policy for 2020; overall preparedness for DRG implementation, |  | DRG implementation as reimbursement system |  |  |  | Head of Department of UHC SSA | Head of Department of IT SSA; Head of Health Care Department MOH; Head of Department of Health Programs SSA
| 3.4.2. Critical assessment of basic financing PHC (considering the need for integration of rural and UHC, state vertical programs) including RBF principles |  | Revision/redesign of financial mechanisms of PHC including RBF indicators | Piloting RBF using redesigned financing of PHC |  | Final revision/preparation for redesigned PHC financing | [7 empty] | Head of Department of UHC SSA | Head of Health Care Department MOH; Head of Department of Health Programs SSA; Head of Department of IT SSA;
| 3.4.3. Developing principles of contracting for purchasing services, including selective contracting and monitoring and evaluation system of contracts performance |  |  | Design of the concept for new contracting system | Design of planning system for hospital care based on Main Diagnostic Categories (MDC) | Analyse provider performance and develop principles for MDC based planning; SSA internal capacity building | Prepare piloting MDC based "virtual" contracting | Develop standards of procedure for contracting (planning, execution, monitoring) | Develop legal regulation. | Final preparation for going live |  |  |  | Head of Health Care Department MOH | Head of Department of UHC SSA; Head of Department of Health Programs SSA; Head of Department of IT SSA;
| 3.4.4. Needs assessment of health care services |  |  |  |  | Analyze epidemiological data, service utilization, existing resources, international experience |  | Elaborate the requirements for each directions based on statistical data taking into consideration the geographical accessibility and utilization |  | Implementation of requirements for each directions |  |  |  | Head of Health Care Department MOH | Head of Department of UHC SSA; Head of Department of Health Programs SSA; Head of Department of IT SSA;
3.5. HBP in line with population health needs | 3.5.1. Designing the system and process of HBP revision and renewal |  |  |  |  | Analyze the health service utilization of existing HBP and detect weak an strong sides |  | Assessment of health (among them essential) needs, service allocation and financial resources |  | Redesign HBP |  |  |  | Head of Health Care Department MOH | Head of Department of UHC SSA; Head of Department of Health Programs SSA; Head of Department of IT SSA;
3.6. Ensure equitable access to essential specialist care and strengthen PHC | 3.6.1. Revision of referral system and developing GP functions | Elaborate requirements (technical , specialisation …) for PHC service providers Develop new contracts and payment system for the PHC centers Elaborate the data-collecting system to receive the data from PHC centers about patients, their clinical condition, outpatient visits and referrals | Piloting data collection and new contracts among piloting PHC centres in Tbilisi |  | Piloting data collection and new contracts among 14 piloting PHC centres in each region |  | Analyze received data, hospitalization rate with ambulatory care sensitive conditions according to PHC centers | Revise/redesign the PHC system | [5 empty] | Head of Health Care Department MOH | Head of Department of UHC SSA, Head of Department of Health Programs SSA, Head of Department of IT SSA
| 3.6.2. Strengthening the capacity of GPs (certification and continuous medical education) |  |  | Elaborate the continuous medical education system and curricula of GPs |  | Elaboration of GP qualification monitoring system. Implementation plan for certification and continuous medical education for GPs | Revise/finalise the work on training and re-qualification system of GP | [6 empty] | Head of Health Care Department MOH | State Regulatory Agency of Medical Activities
3.7. Consolidate highly specialised and hospital care | 3.7.1. Analysing the need for hospital care services including highly specialised services and current distribution of service providers and Developing a plan for sustainable purchasing of hospital and highly specialised medical services |  |  |  |  | Analysing the need for hospital care services including highly specialised services and current distribution of service providers |  | Developing a plan for sustainable purchasing of hospital and highly specialised medical services. | Develop legal regulation. | Implementation of the plan |  |  |  | Head of Health Care Department MOH | Head of Department of UHC SSA, Head of Department of Health Programs SSA, Head of Department of IT SSA
3.8. Increase transparency and accountability | 3.8.1. Development and introducing of quarterly reporting on SP performance | Piloting reporting based on 2018 Q3 & Q4 | [11 empty] | Head of Health Care Department MOH | Head of Department of UHC SSA, Head of Department of Health Programs SSA
3.9. Improve population awareness | 3.9.1. Development of Citizen Portal and applications to increase transparency for patients | Elaborate the questioner for visitors of web site | Conduct of survey | Analyze the feedback for improvement of site data/information/characteristics/appearance | Final work on Citizen Portal and applications to present a transparent clear information/data for beneficiaries | [8 empty] | Head of Department of UHC SSA | Head of Department of Health Programs SSA, Head of Department of IT SSA, Head of Health Care Department MOH
| 3.9.2. Develop concept for citizen communication and communication plan | Prepare ToR for outsourcing the concept of citizen communication | Development of the concept of citizen communication | [10 empty] | Head of the Department of PR, MOH | Head of Health Care Department MOH
3.10. Enhance electronic data exchange and improve quality of data | 3.10.1. Mapping of key processes related with health service provision and SP and defining the needs for developing solutions for electronic exchange of data with stakeholders | System analyses and IT development plan to support SP Strategy implementation | [11 empty] | Head of Department of IT SSA | Head of Department of UHC SSA, Head of Department of Health Programs SSA
| 3.10.2. Introduce the use of electronic signature | Estimate the software characteristics (activity depends on the implementation of Electronic Medical Records) | Final preparation for going live | [10 empty] | Head of Department of IT SSA | Head of Department of IT MOH
| 3.10.3. Mapping of claims management process and design of electronic claims management solution | Designing SHOULD BE SOP for UHC program and implementation plan (incl TOR for tech application...) | Implementation and SSA wide training to introduce new practice |  | New claims management process introduced | [8 empty] | Head of Department of UHC SSA | Head of Department of IT SSA, Head of Department of Health Programs SSA
3.11. Align SSA management and structure around the strategy | 3.11.1. Design the new SSA health care related structure to reflect strategic needs and implement the new structure (regulation, appointment of key staff and managers, etc.). Develop principles and functions of health economics within SSA, the structural alignment of functions | Design of the new SSA health related structure approved Human recourses needs assessed Plan to implement the new structure prepared | Job descriptions and necessary legislative amendments approved Key positions of the new SSA structure (headquarter level) are filled New structure launched headquarter level 01.07.2019 | Regional structure of the SSA assessed and plan to align the regional structure to the headquarter new structure is papered | New SSA health care related structure fully implemented | [8 empty] | Head of Human Resouce Department | Head of Department of UHC SSA; Head of Department of IT SSA, Head of Department of Health Programs SSA
3.12. Improve motivation and competencies of SSA staff | 3.12.1. Define key competencies to support implementation of strategic purchasing strategy and develop a system for prospective competency development and compile a competency development plan for SSA health care related key staff, (linked to the strategic initiatives 3.11. |  |  | Functions and competences of the new SSA health care related structure defined | Competency development plan for SSA health care related key staff developed | Competency development plan for SSA health care related key staff finalised and ready for implementation | [7 empty] | Depity Director of SSA | Head of Department of UHC SSA; Head of Department of IT SSA, Head of Department of Health Programs SSA
3.13. Develop IT systems | 3.13.1. Define and prioritize SSA health care related IT system development needs (related to the strategic initiative 3.10.1) | System analyses and IT development plan to support SP Strategy implementation | [11 empty] | Head of Department of IT SSA | Head of Department of UHC SSA; Head of Department of IT SSA, Head of Department of Health Programs SSA
3.14. Improve monitoring, reporting and analysis | 3.14.1. Develop comprehensive SSA health care organizational planning and reporting system, covering the cascade of management tools – translation of strategic planning into operational execution and reporting of performance and outcomes (SSA regional offices performance, strategic purchasing strategy), annual performance report (related to the strategic initiative 3.8.1) | 4Q2018 strategy execution report prepared and quarterly SPS WG reporting meeting conducted SOP for the planning and reporting system for the SP Strategy prepared | 1Q2019 strategy execution report prepared and quarterly SPS WG reporting meeting conducted | 2Q2019 strategy execution report prepared and quarterly SPS WG reporting meeting conducted SP Strategy 2020-2022 review process plan prepared | 2Q2019 strategy execution report prepared and quarterly SPS WG reporting meeting conducted Template for the annual report (yearbook) 2019 developed based on first year experiences SP Strategy revision for the period 2020-2022 completed | SP Strategy yearbook 2019 prepared | [7 empty] | Head of Department of UHC SSA | Head of Department of IT SSA; Head of Health Care Department MOH; Head of Department of Health Programs SSA
Initiative under development with milestone definition
Initiative due date with final approval