## 2019-2021
| Goals | Initiatives | Q1 19 | Q2 19 | Q3 19 | Q4 19 | Q1 20 | Q2 20 | Q3 20 | Q4 20 | Q1 21 | Q2 21 | Q3 21 | Q4 21 | Date | Owner | Cooperation
1 | Improve payment and contracting mechanisms | Developing and introducing DRG system | DRG grouper integrated to the SSA system | Preparations for the pilot in piloting hospitals. Analytical work to prepare for the development of DRG pricing and reimbursement policy | DRG pilot in piloting hospitals. DRG cost weights and reimbursement principles for the "virtual implementation" | Simualtions and analytics to develop DRG cost weights and reimbursement rules for 2020 "virtual implementation" period | DRG "virutal implementation" in all hospitals |  | DRG cost weights and reimbursement policy for 2020; overall preparedness for DRG implementation, |  | DRG implementation as reimbursement system |  |  |  | 3.2021 | Head of Department of UHC SSA | Head of Department of IT SSA; Head of Health Care Department MoLHSA; Head of Department of Health Programs SSA
|  | Critical assessment of basic financing PHC (considering the need for integration of rural and UHC, state vertical programs) including RBF principles |  | Revision/redesign of financial mechanisms of PHC including RBF indicators; | Piloting RBF using redesigned financing of PHC |  | Final revision/preparation for redesigned PHC financing | [7 empty] | 3.2020 | Head of Department of UHC SSA | Head of Health Care Department MoLHSA; Head of Department of Health Programs SSA; Head of Department of IT SSA;
|  | Developing principles of contracting for purchasing services, including selective contracting and monitoring and evaluation system of contracts performance |  |  | Design of the concept for new contracting system | Design of planning system for hospital care based on Main Diagnostic Categories (MDC) | Analyse provider performance and develop principles for MDC based planning; SSA internal capacity building | Prepare piloting MDC based "virtual" contracting | Develop standards of procedure for contracting (planning, execution, monitoring) | Develop legal regulation. | Final preparation for going live. |  |  |  | 3.2021 | Head of Health Care Department MoLHSA | Head of Department of UHC SSA; Head of Department of Health Programs SSA; Head of Department of IT SSA;
|  | Needs assessment in health care services |  |  |  |  | Analyze epidemiological data, service utilization, existing resources, international experience |  | Elaborate the requirements for each directions based on statistical data taking into consideration the geografical accsessibility and utilization |  | Implementation of requirements for each directions |  |  |  | 9.2020 | Head of Health Care Department MoLHSA | Head of Department of UHC SSA; Head of Department of Health Programs SSA; Head of Department of IT SSA;
2 | HBP in line with population health needs | Designing the system and process of HBP revision and renewal |  |  |  |  | Analyze the health service utilization of existing HBP and detect weak an strong sides |  | Assesment of health (among them essential) needs, service alocation and financial resources |  | Redesighn HBP |  |  |  | 9.2020 | Head of Health Care Department MoLHSA | Head of Department of UHC SSA; Head of Department of Health Programs SSA; Head of Department of IT SSA;
3 | Consolidate highly specialised and hospital care | Analysing the need for hospital care services including highly specialised services and current distribution of service providers and Developing a plan for sustainable purchasing of hospital and highly specialised medical services |  |  |  |  | Analysing the need for hospital care services including highly specialised services and current distribution of service providers |  | Developing a plan for sustainable purchasing of hospital and highly specialised medical services. | Develop legal regulation. | Implementation of the plan |  |  |  | 3.2020 | Head of Health Care Department MoLHSA | Head of Department of UHC SSA, Head of Department of Health Programs SSA, Head of Department of IT SSA
4 | Ensure equitable access to essential specialist care and strengthen PHC | Revision of referral system and developing GP functions | Elaborate requirements (technical , specialisation …) for PHC service providers; develop new contracts and payment system for the PHC centers, elaborate the data-collecting system to receive the data from PHC centers about pacients, their clinical condition, outpatient visits and referrals | Piloting data collection and new contracts among piloting PHC centres in Tbilisi |  | Piloting data collection and new contracts among 14 piloting PHC centres in each region |  | Analyze received data, hospitalization rate with ambulatory care sensitive conditions according to PHC centers | Revise/redesign the PHC system | [5 empty] | 3.2020 | Head of Health Care Department MoLHSA | Head of Department of UHC SSA, Head of Department of Health Programs SSA, Head of Department of IT SSA
|  | Strengthening the capacity of GPs (certification and continious medical education) |  |  | Elaborate the continuous medical education system and curricula of GPs |  | Elaboration of GP qualification monitoring system. Implementation plan for certification and continuous medical education for GPs | Revise/finalise the work on training and re-qualification system of GP | [6 empty] | 6.2020 | Head of Health Care Department MoLHSA | State Regulatory Agency of Medical Activities
5 | Improvement efficiency and quality of health services | Developing the concept to upgrade quality assurance and improvement system | ToR for the consultant to support development of quality improvement startegy and instruments | Situation analysis and advocacy among stakeholders (state agencies, providers, clinicians) regarding quality improvement needs | Elaboration of quality improvement strategy and instruments |  | Quality improvement strategy and instruments ready for implementation | [7 empty] | 12.2019 | Head of Health Care Department MoLHSA | Head of Department of UHC SSA, Head of Department of Health Programs SSA, State Regulatory Agency of Medical Activities
|  | Defining set of indicators to assess the quality of medical services, mechanism to monitor and control quality, and coordinate the quality functions with Regulatory Authority |  | Elaboration concept of Quality control for medical services | Establishment of structural unit and human resources | Elaborate indicators and mechanism to monitor and control quality | Pilot elaborated indicators and monitoring tools |  | Pilot elaborated indicators and monitoring tools |  | Start implementation set of indicator ssystem |  |  |  | 3.2020 | Head of Health Care Department MoLHSA | Head of Department of UHC SSA, Head of Department of Health Programs SSA, State Regulatory Agency of Medical Activities
|  | Develop concept of medical audits (in cooperation with Regulatory Authority) |  |  |  |  | Identify the standards and audit criteria |  | selecting and developing appropriate performance levels; identify inclusion/exclusion criteria abd exceptions |  | Elaborate measuring performance methodology: data collection, data analysis, drawing conclusions, presentation of results; Identify principal steps of quality improvement plans and sustaining improvements according the elaborated mechanism to monitor and control quality |  |  | Final revision of concept of medical audits, analysing feedback from professionals and international partners | 12.2020 | Head of Health Care Department MoLHSA | Head of Department of UHC SSA, Head of Department of Health Programs SSA, State Regulatory Agency of Medical Activities
|  | Develop principles and functions of health economics within SSA, the structural alignment of functions |  |  | Develop ToRs, hire a person(s), establish structural changes | Revision/redesign of structural alignment of functions according to principles and functions of health economics within SSA | [8 empty] | 12.2019 | Head of Department of UHC SSA | Head of Health Care Department MoLHSA; Head of Department of Health Programs SSA
6 | Enhance electronic data exchange and improve quality of data | Mapping of key processes related with health service provision and SP and defining the needs for developing solutions for electronis exchange of data with stakeholders | System analyses and IT development paln to support SP Strategy implementation | [11 empty] | 3.2019 | Head of Department of IT SSA | Head of Department of UHC SSA, Head of Department of Health Programs SSA
|  | Introduce the use of electronic signature | Estimate the software characteristics (activity depends on the implementation of Electronic Medical Records) | Final preparation for going live | [10 empty] | 6.2019 | Head of Department of IT SSA | Head of Deaprtment of IT MoLHSA
|  | Mapping of claims management process and design of electronic claims management solution | Designing SHOULD BE SOP for UHC program and implementation plan (incl TOR for tech application...) | Implementation and SSA wide training to introduce new practice |  | New claims management process introduced | [8 empty] | 12.2019 | Head of Department of UHC SSA | Head of Department of IT SSA, Head of Department of Health Programs SSA
7 | Improve population awareness | Development of Citizen Portal and applications to increase transparency for patients | Elaborate the questionary for visitors of web site | Conduct of survey | Analyze the feedback for improvement of site data/information/characteristics/appearance | Final work on Citizen Portal and applications to present a transparent clear information/data for beneficiaries | [8 empty] | 12.2019 | Head of Department of UHC SSA | Head of Department of Health Programs SSA, Head of Department of IT SSA, Head of Health Care Department MoLHSA
|  | Develop concept of citizen communication and communication plan for 2019 | Preapre ToR for outsourcing the concept of citizen communication | Development of the concept of citizen communication | [10 empty] | 6.2019 | Head of the Department of PR, MoLHSA | Head of Health Care Department MoLHSA
8 | Increase transparency and accountability | Development and introducing of quarterly reporting on SP performance | Piloting reporting based on 2018 Q3 & Q4 | [11 empty] | 3.2019 | Head of Health Care Department MoLHSA | Head of Department of UHC SSA, Head of Department of Health Programs SSA
Initiative under develepoment with milestone definition
Initiative due date with final approval
Note on P1: Please revise this after reviewing milestones and reviewing priorities
Note on Q1: Please add owner as concreate structural unit of the SSA or MoLHSA
Note on B7: add quarterly milestones for 2019

## indicators
Goal | Indicator | Definition | Why this indicator is important? | Unit | Formula |  |  |  | Frequency | Owner | Baseline (year 2017 or latest available) | Targets
[5 empty] | Nominator |  | Denominator |  |  |  |  | 2018 | 2019 | 2020
Improve financial protection and secure effective coverage | 1) OOP on drugsas % total health expenditures | OOP on drugs as a share of total health expenditures (THE) Data source: NHA; | OOP on drugs as a share of total health expenditures (THE) is broadly indicative indicator of financial protection for Georgian reality | % | Total out-of-pocket payments for drugs and services | 1031 | Total health care expenditure | 2861 | Annually | MoLHSA | 36.04% | 36% | 35% | 34%
| 2) Share of OOP payments from SSA reimbursed services under UHC inpatient services | OOP payments from SSA reimbursed services under UHC program, including only inpatient services Source: SSA reporting module | the aim is to track OOP Under UHC program | % | Total OOP payments for SSA reimbursed services under UHC program inpatient services | 64741 | Total cost for SSA reimbursed services under UHC program inpatient services | 423855699.97 | Annually | SSA | 25% | 25% | 24% | 23%
| 3) Share of households who have financial barriers to get health services | to measure financial protection Data source: UNICEF WMS | to measure financial protection | % |  |  |  |  | every 2 years | MoLHSA | 22.3% | Survey result
Utilization/purchasing of services in the right level | 4) Share of avoidable hospitalizations | Share of hospitalizations due to ACSC (ACSC defined for Georgia: Perforated/bleeding ulcer: K250-K252,K254-K256,K260-K262,K264-K266, K270-K272,K274-K276,K280-K282,K284-K286; Urinary tract infections/Pyelonephritis: N10,N11,N12,N136,N390; Angina: I20,I240,I248,I249; Asthma: J45,J46; Chronic Obstructive Pulmonary; Disease: J20,J41-J44,J47; Congestive heart failure: I110,I50,J81; Convulsions and epilepsy: G40,G41,O15,R56; Diabetes complications: E100-E108,E110-E118,E120-E128,E130-E138, E140-E148; Hypertension: I10,I119; Pneumonia: J13,J14,J153,J154,J157,J159,J168,J181,J188; Tuberculosis A15,A16,A19; Data source: SSA reporting module/NCDC | ACSCs are conditions that can be treated in ambulatory settings and high level of hospitalization with ACSC indicates the suboptimal capacity of health services delivery to effectively prevent, diagnose, treat and/or manage these conditions in ambulatory settings in a timely manner. (WHO handbook http://www.euro.who.int/__data/assets/pdf_file/0010/305875/Assessing-HSD-performance-with-ACSH.pdf) | % | # of acute care hospitalizations for ambulatory care sensitive conditions | 41975 | # of total acute care hospitalizations | 279647 | Annually | SSA | 15.01% | 15% | 14% | 13%
| 5) Share of PHC (include prevention) out of expenditure of health state programs | Share of PHC and prevention expenditures from total health state programs Data Source: NHA | The share of pHC and prevention spending from total heath state programs' budget enables to monitor priority given to the PHC in the health budget over the time. | % | Total PHC spending state health care program, mill | 266 | Total state bhealth care program spending, mill | 921 | Annually | MoLHSA | 29% (2016) | 32% | 34% | 35%
Improve payment and contracting mechanisms | 6) Share of DRGs in hospital care | Share of the hospital care purchased by using DRGs Data source: SSA reporting module | Implementation of the DRG is one of the SSA's priorities and part of the DRG implementation process is to define the phase out strategy how to move to the DRG based payment with the objective to cover all providers and acute inpatient care (details of the phase out will be agreed in 2019). This indicator enables to monitor the progress made over the time. | % | Total SSA spending through DRG payments |  | Total SSA spending on inpatient care |  | Annually | SSA | Will be available after DRG implementation in 2020
| 7) Share of inpatient specialised care expenditure purchased through selective contracting from total expediture | Share of inpatient specialised care expenditure purchased through selective contracting Date source: SSA reporting module | SSA's aim is to expend principles of selective contraction from delivery to other clinical areas. This indicator enables to measure the progress over the years. | % | SSA spending by using principles of selective contracting, under UHC inpatient care | 18747259 | Ssa spending on inpatient care under UHC | 423855699.97 | Annually | SSA | 4.423% | 4% | 7% | 7%
HBP in line with population health needs | 8) Unmet need | Percentage of consultations where medicine was prescribed but not purchased because it was too expensive Sourse of data HUES | to measure unmet need | % |  |  |  |  | every 3 years | MoLHSA | 9.6% | Survey result
Consolidate highly specialised and hospital care | 9) Share of SSA's purchased care from multiprofile hospitals (only inpatient services, AC,AD) | Share of SSA's purchased care from multiprofile hospitals (only inpatient services) | For measuring Consolidate highly specialised and hospital care | % |  |  |  |  | Annually | SSA | will be available in 2019
| 10) Occupancy rate of hospital beds | The number of hospital bed days divided by the number of available hospital beds multiplied by the number of days in a year. Data source: NCDC/SSA | For measuring Consolidate highly specialised and hospital care | % | # of hospital bed days in a year |  | # of available hospital beds in a year |  | Annually | NCDC | 52% | 55% | 56% | 57%
| 11) Number of hospitals by categories: under 50 beds, 50-99 beds, 100-249 beds, more than 250 beds | Average number of hospital beds per hospital Data source: NCDC/SSA | It is important to monitor the integration of hospitals | No | Number of hospitals with <50 beds Number of hospitals with 50-99 beds Number of hospitals with >100 beds |  |  |  | Annually | NCDC | 0-49 - 177' 50-99 - 49; 100 > - 42 | Depending on country policy
Ensure equitable access to essential specialist care and strengthen PHC | 12) PHC vizits per person | avarage out-patients visits per person | estimate the utilization of outpatient care and confidence in primary healthcare | No | Number of vizits in PHC | 14609228 | Number of population | 3700000 | Annually | MoLHSA | 3.6 | 3.7 | 3.8 | 3.8
| 13) Share of public expenditure on drugs as % of total drug expenditure | Public expenditure on drugs (GEL) divided on Total drug expenditure | For measuring of quritable access on drugs | % |  |  |  |  | Annually | MoLHSA | 25% | 26% | 28% | 30%
Improvement efficiency and quality of health services | 14) Surgical procedures as % of cases performed in day surgery (eg. cataract surgery, tonsil- or adenoidectomy). | Surgical procedures as % of cases performed in day surgery (cataract surgery, tonsil- or adenoidectomy). Data Source: SSA | improve efficiency | % | # of cases of day surgery (ophtalmology and oto-rhino-laringology) | 52968 | Total # of surgical cases | 1209144 | Annually | SSA | 4.381% | 4.381% | Depend on medical market development
| 15) Re-hospitalization rate | An admission to an acute care hospital within 30 days of discharge from an acute care hospital with the same diagnoses Data source: SSA reporting module | Readmission following hospitalization is a costly and often preventable event. Too high readmission rate may indicate quality problems or signal that current financial incentives may not work as expected. | % | # of re-hospitalizations during 07.2017-12.2017 | 111854 | # of discharges during 07.2017-12.2017 | 674299 | every 6 month | SSA | 16.59% | 16% | 15% | 13%
Enhance electronic data exchange and improve quality of data | 16) Quality of SSA claims data | Deviation of reported data in different channels, based on selected indications (no of delivery, C-section, ...) source: SSA/NCDC | Quality of data | to be added | # of c-section according to NCDC data | 47071 | # of c-section according to SSA data | 47069 | quarterly | SSA | Will be available in 2019
Improve population awareness | 17) Share of people registered on the citizen portal | customer awareness about online service/information access | estimate customer awareness about online service to plan online survey for different purposes (satisfaction and etc.) | % | # of registered population on the citizen portal | 25 | # of total population | 3700000 | to be added | SSA | 0.0006757% | 0.01% | 0.5% | 1%
Increase transparency and accountability | 18) Share of claims not reimbursed by SSA | Share of claims not reimbursed by the SSA (Reasons: diagnoses was incorrect; data was not correct, does not follow the regulations) | The SSA's ability to detect fraud claims is essential to ensure the efficient and transparent use of public funds. Also, it is important that SSA is taking preventive measures (e.g. transparent and clear rules of procedure, electronic controls, data mining/analytics) that would optimize the adminitrative burden realated to the fraud detection activities | % | # of claims not reimbursed by SSA | 198254 | total # of claims | 1209144 | Annually/quarterly | SSA | 16.4% | will be discussed after DRG implementation
Align SSA management and structure around the strategy | 19) SOP coverage of key processes | Defined core and support processes covered with standard operational procedures | Clarify standad procedures |  | # of SOP |  | # of key processes |  | annually | MoLSHA/SSA | will be available in 2019
Improve motivation and competencies of SSA staff | 20) Staff turnover in key departments related to SP | Staff turnover in the SSA's UHC, IT, Health Department | Gives indication about overall level of staff satisfaction as high turnover is usually the result of dissatisfaction with staff policy | % | # of people left SSA's key departments | 8 | Average # of staff in key departments | 225 | annually | SSA | 3.556% | 3% | 2% | 2%
Develop IT systems | 21) Average length of processing a claim | Average length of processing a claim | indicate about claim processing complexity and IT system adjustment | minutes | Total time spent on making decision to reimburse the claim | 5771254 | total # of claims in 10.2017-12.2017 period | 288521 | quarterly | SSA | 20.0029 | will be discussed after DRG implementation
Improve monitoring, reporting and anaysis | 22) Quarterly reporting on SP strategy implementation | reporting for monitoring SP strategy implementaion | Traking of SP strategy implementation process | [7 empty] | will be available in 2019