[Session] of (year)

(date), (Location)

Item (number) of the provisional agenda

Country programmes and related matters

Draft country programme document for Georgia (2021-2025)

Content

|  | - UNDP’s Contribution to the Cooperation Framework |  |  |
| --- | --- | --- | --- |
|  | - Programme Priorities and Partnerships |  |  |
|  | - Programme and Risk Management - Monitoring and Evaluation |  |  |
| Annexes |  |  |  |
|  | A. Results and Resources Framework B. Fully-costed Evaluation Plan |  |  |
| Attachments | I. Resource Mobilization Target (RMT) Table II. CO Profile & PCAT III. One-page diagram of the programme’s theory of change |  |  |

## I. UNDP’s Contribution to the Cooperation Framework

- Georgia is a country built on the self-confident resilience of an ancient civilization that has sought, since restoring independence in 1991, to achieve the prosperity, stability and security that membership of the European Union connotes to the Georgian public. Georgia has made significant progress on this path, including the signing of an Association Agreement with the European Union (EU), which took force in 2016.

- While the country has enthusiastically embraced the Sustainable Development Goals, Agenda 2030 gains the greatest traction where it also promotes European integration. The two agendas are mutually reinforcing: the EU Association Agreement incorporates 63% of Georgia’s nationalized SDG targets. And together they provide the framework for the UNDP programme for 2021-25.

- As Georgia marks 30 years of independence, it can take pride in its achievements in building democratic institutions. No stranger to political turmoil, the country nonetheless sets high standards for governance, and its successes have been widely recognized, including in the latest round of the World Bank Worldwide Governance Indicators. That said, the political system is still a work in progress. Reacting to perceived imbalances in the division of power, Georgia shifted to a fully parliamentary system of governance in 2019 and revised the rules for the 2020 elections to promote greater party pluralism.

- Shedding a legacy of defunct Soviet industries, sweeping market-based reforms have delivered steady growth and significantly reduced poverty. GDP grew by an average of 4.9% per year between 2010 and 2019, and GDP per head increased to USD 4,769 in 2019 from USD 1,351 in 1991, boosting Georgia to high-middle-income status. Poverty measured by national standards fell to 19.5% in 2019 from 38.8% in 2007.

- These achievements have not been linear, however, and the country has weathered many setbacks. Most prominent among these, armed conflict in the early 1990s and 2008 displaced some 300,000 people and left Abkhazia and the Tskhinvali region/South Ossetia beyond the control of the authorities in Tbilisi. Any resolution for the conflict has proven elusive. Georgia’s prospects have also been constrained by the complicated geopolitics of the South Caucasus, including the protracted Nagorno-Karabakh conflict.

- Georgia’s economic strategy has applied liberal free-market reforms to encourage foreign investment and business growth. Creating a positive business environment has been a long-standing priority, and Georgia ranked 7th of 190 countries in the 2020 edition of the World Bank’s “Doing Business.” More recent policies have put increased emphasis on social welfare, through provision of universal healthcare and expansion of social assistance, which even before COVID benefited 11.2% of the population.

- Even before the pandemic hit, the structure of the economy was a source of concern. Although exports grew from 23% to 45% of GDP between 2000 and 2015, they are still not competitive enough to lift the country to prosperity. The potential of the free trade area with the EU is not yet being grasped. Georgia remains a net importer of food, and two-thirds of agricultural exports come from wine, water, spirits and nuts. Tourism has been a notable bright spot, soaring to 9.3 million visitors and USD 3.3 billion in revenues in 2019. Already the sector accounts for 8% of employment and 36% of exports. But pandemic-driven border closures brutally reversed these trends. Even if tourists return, COVID-19 has reopened a debate about which sectors to prime as engines of prosperity.

- The pandemic has also shone new light on the groups that are missing out on the fruits of Georgia’s successes. Despite the remarkable decline in poverty, one in every five Georgians is still poor by national standards, and 8.9% fit the World Bank’s definition of extreme poverty. Regional poverty rates run as high as 33% in poorer areas.

- Poverty also has a rural face. Rural poverty, at 23.7%, is higher than the urban rate, 16.4%. And although one-third of the population lives in Tbilisi, Georgia remains one of the most agrarian countries in the region. More than 40% of the population lives in rural areas and does some kind of farming. Yet agriculture delivers just 7.2% of GDP. Low productivity is a constraint to growth: an average worker’s value added in agriculture is less than one-tenth that in industry or services. Most rural dwellers are self-employed or unpaid workers, while more secure wage work is overwhelmingly urban. The rural population thus depends heavily on pensions and social assistance for income.

- At 26% in 2019, Georgia has a very high share of young people who are not in education, employment or training. This challenge is particularly acute for young women: 29.1% fall into this category versus 23.3% of men. The cause: an education system that fails to provide both functional literacy and soft and hard skills required for employability.

- Although equal rights are fully guaranteed by law and gender attitudes are shifting rapidly, women still face discrimination and inequality in all spheres of life. They are underrepresented in political leadership, holding only 14% of parliamentary seats and just one of 64 mayoral positions. In economic terms, they face an 18.1-percentage-point gap in labor activity rates, owing mainly to the disproportionate share of unpaid work they shoulder at home. They earn an average wage that is just 64% of that for men, yet they have higher educational attainments across the board. Occupations are segregated by gender, with women holding only 12% of science, technology, engineering and mathematics jobs. One in five women experiences sexual harassment in the workplace, and one in seven has faced violence at the hands of an intimate partner.

- The LGBTQI community is arguably the most marginalized group in Georgia. Discrimination on the basis of sexual orientation and gender identity is illegal, but LGBTQI persons routinely encounter bias, hate speech and violence.

- Georgia ratified the UN Convention on the Rights of Persons with Disabilities in 2013, but persons with disabilities (PwDs) experience a disturbing lack of visibility. Only 3% of the population is registered as having a disability, whereas international norms suggest that the actual share must be around 12%. Stigma leads families to keep disability hidden, so few children with disabilities attend school or enter the labour force (only 55 PwDs are employed in the public sector). Disability is still assessed using a medical rather than social model. Physical barriers are widespread, as are disempowering stereotypes.

- The inclusion of national minorities remains a challenge. Ethnic Azerbaijanis make up 6.2% of the population, and ethnic Armenians, 4.5%. Although guaranteed equal rights, opinion polls suggest national minorities feel alienated from mainstream Georgian society. This was evident during the COVID-19 crisis, when Kvemo Kartli, where a high proportion of ethnic minorities live, accounted for 35% of the first 800 cases.

- The conflict legacy undermines prospects for IDPs. At end-2019, 286,216 persons, or 7.7% of the population, were registered as IDPs, one of the world’s highest displacement rates. Georgian authorities have promoted integration into host communities, but many IDPs remain isolated and dependent on state benefits. Only 45% have received purpose-built housing, leaving tens of thousands living in squalid and dilapidated “collective centers.” Job opportunities remain scarce. People living along conflict dividing lines also face hardship, with only 18% having access to a bank or cash machine. Finally, people living in Abkhazia and the Tskhinvali region suffer the consequences of isolation, restricted freedom of movement and poor-quality social services.

- The pandemic has heightened awareness of local and global environmental challenges. With climate change disrupting weather patterns, Georgia is seeing more frequent and more destructive floods, landslides, mudslides and droughts. Damages to infrastructure and economic losses are extensive: USD 190 million is spent annually on flood recovery, and USD 68 million to compensate for flood damage to farming. Improved use of climate risk information is needed to make communities and economic assets more resilient to environmental shocks. Precipitation and temperature extremes also risk disrupting the hydropower supply, and other renewable sources (wind, solar and geothermal) amount to just 0.6% of the energy balance. Urban air pollution in Georgia is among the most toxic in Europe, causing a measurable increase in mortality. Nearly 11% of Georgia’s territory is designated as protected area, but illegal logging and other incursions underline the need for better management and more sustainable use of natural resources.

- UNDP’s previous country programme sought to address these challenges by applying the core SDG principle: “to leave no one behind.” An Independent Country Programme Evaluation (ICPE) conducted in 2019 called UNDP’s contribution “highly relevant and strategically positioned.” Achievements cited included: strengthening Parliament and civil society; improving government transparency and accountability; defining decentralization policies; protecting human rights; furthering gender equality; advancing rural development; modernizing vocational education and training; improving social services in conflict-affected areas; keeping lines of communication open across conflict divides; reducing greenhouse gas and other harmful emissions; enhancing flood resistance; building urban resilience; and enlarging protected areas.

- The ICPE also endorsed the findings of the Mainstreaming, Acceleration and Policy Support (MAPS) exercise that UNDP conducted in 2019 together with the Government Administration. This yielded a consensus around four “high impact solutions” with the potential to unlock progress towards high-priority goals: decentralized development; human rights and gender equality; investing in youth and rural areas; and green energy and sustainable cities. These areas have also emerged as cornerstones for the UN’s joint COVID-19 response and recovery offer aimed at “building forward better.”

## II. Programme Priorities and Partnerships

- The ICPE recommendations and MAPS priorities have shaped the UNDP country programme for 2021-25. It combines two aims: first, UNDP will support national development priorities by focusing on the intertwined goals of European integration and sustainable development, relying on the complementarity of the two agendas to multiply their impact; second UNDP will adapt all activities to help Georgia weather the COVID-19 pandemic, protecting lives and livelihoods in the short term while seeking ways to “build forward better” in the longer term.

- UNDP will add value by combining top-down policy advice drawn from global networks of expertise with bottom-up practical solutions pioneered through hands-on implementation. These two approaches are mutually reinforcing. UNDP will also draw on trusted partnerships established through years of practical collaboration in which the organization’s core principle is to take careful stock of what partners have to say.

- UNDP solutions will be more integrated than in the past, working across different sectors and applying multiple areas of expertise to address the root causes of development challenges. This multisectoral approach will underpin UNDP’s role as “integrator” within the UN system and it will also provide an anchor for policy advice and normative recommendations from specialized agencies. At the same time, UNDP will fulfill its role as the UN technical lead agency for the COVID-19 socio-economic recovery by helping to interweave the many different strands of agency work into a single cohesive effort. It will also contribute to the debate about possible new pathways to prosperity for Georgia.

- Building on e-initiatives launched in response to the pandemic, UNDP will seek to apply “digital disruption” to improve governance, bridge distances, increase competitiveness and improve social inclusion. The UNDP Accelerator Lab established in Tbilisi in 2020 will contribute to this effort, in particular to ensure that programming reflects human-centered design and behavioral science.

- Drawing on its track record and in-house capacities, and in alignment with the priorities identified in the new UN Sustainable Development Cooperation Framework (UNSDCF), the UNDP programme will focus on four main goals:

- Improving governance for equality and justice. Building on years of work supporting Georgia’s aspirations to establish model institutions of democratic governance, UNDP will focus in 2021-25 on breathing life into legislative frameworks and ensuring that standards and principles adopted in past years are realized in everyday practice.

  - UNDP will assist the Parliament in undertaking its expanded role as the country’s core decision-making institution.

  - Support to public administration reform will continue, with a focus on building a merit-based and non-partisan civil service and helping to standardize and improve the quality of public service delivery.

  - UNDP will assist institutions and civil society in monitoring Georgia’s compliance with human rights standards, while directly supporting PwDs, the LGBTQI community and other at-risk groups. Diversity and tolerance will be promoted as positive social values.

  - UNDP will work with UN partner agencies to advance gender equality. Promoting political participation by women will be in focus, particularly at the local level, where a 50:50 quota will shape the 2021 municipal elections. UNDP will also seek to expand women’s opportunities for skills development and employment and work to reduce the gender wage gap. Building the foundations of a “care economy” will also be a priority, showing that public spending on care services is an investment with a triple payoff: new jobs for women; improved care for vulnerable persons; and relief from the unpaid care work that so often hinders women’s employment.

  - Access to justice will be expanded by making mediation and other forms of alternative dispute resolution more readily available.

- Unlocking the potential of rural areas. UNDP will take a two-pronged approach to bridging the urban-rural divide in Georgia: helping rural and remote communities use the legal framework for decentralization to improve their social and economic prospects, while professionalizing farming and improving agricultural productivity. Reform of the vocational training system will aim to provide rural youth with the skills needed to thrive in the private sector. Efforts to diversify the rural economic landscape will continue, both by promoting non-farm livelihoods and building municipal capacity to plan and manage local economic development from the bottom up. Private-sector competitiveness will be improved by applying approaches such as value chains and clustering. Digitalization will be promoted as a way of saving rural jobs and breaking the isolation of village life. Taken together, these efforts aim to reduce poverty by creating jobs and slow emigration by enhancing the attractiveness of life outside Tbilisi.

- Climate-proofing Georgia’s communities. UNDP will continue to assist in providing policy advice, legislative support and field work to fulfil the country’s commitments on climate change and map out a development pathway with reduced carbon emissions. It will help improve the management and financial sustainability of Georgia’s national parks and other protected areas. And it will expand the use of renewable energy and energy-efficient solutions, as a counterbalance to often controversial hydropower dams. The core focus will be to complete a USD 74 million programme to prevent all forms of climate-driven disasters and build community resilience, risk-and-hazard mapping of 11 river basins, establishing a nationwide early-warning system and constructing nature-based protective solutions for at least 100 high-risk communities.

- Improving living conditions for conflict-affected people. In an effort to create an enabling environment for reconciliation and lasting peace, UNDP will continue to strengthen civil society in conflict-affected areas, facilitate collaboration between professional groups and improve people-to-people contacts across conflict divides. Provided that access to Abkhazia remains open, UNDP will work to enhance the quality of social services and help local communities improve living conditions in line with priority needs, for example by refurbishing school buildings, building sports fields or ensuring access to drinking water. UNDP will also work to reduce flood risks and expand environmental protection efforts in Abkhazia (for example in waste management and nature protection). Finally, UNDP will support IDP communities as well as vulnerable people living along the administrative boundary lines, with a focus on improved social services and economic self-sufficiency, particularly for women. Activities will expand to the Tskhinvali region if conditions allow.

# III. Programme and Risk Management

- The COVID-19 crisis has required an agile response. Thanks to the flexibility of partners and donors, UNDP was able swiftly to repurpose funding and reorient programming to face pandemic challenges. Given the unknowns in the pandemic’s trajectory and the increasingly volatile impact of climate change, adaptability will need to continue to be a UNDP hallmark throughout 2021-25.

- The Georgian economy has held up well in the face of pandemic stresses, with GDP predicted to decline 6% in 2020 before rebounding in 2021. This resilience owes much to support from multilateral financial institutions, which have so far dedicated USD 3 billion to Georgia’s efforts to protect businesses and families from COVID’s impact. But if pandemic-driven restrictions have to be prolonged, UNDP is prepared to reorient its programme to provide suitable support.

- Geopolitics remains a risk for Georgian operations and particularly affects the ability of the UN agencies to operate in conflict-affected areas. Transparency and strict adherence to humanitarian principles will help to mitigate this risk.

- The political scene in Georgia will remain animated and elections hotly contested. The transition to a proportional election system will be a test for Georgia’s political parties. However, any change of power is expected to proceed in an orderly fashion in accordance with established democratic principles. UNDP stands ready to adapt its programming in line with shifts in priorities as determined by Government partners. Securing sufficient funding to implement the UNDP programme remains a focus. Diversification of sources and long-term planning are the key to risk mitigation. UNDP’s Social and Environmental Standards and Accountability Mechanism will be applied.

- This country programme document outlines UNDP’s contributions to national results and serves as the primary unit of accountability to the Executive Board for results alignment and resources assigned to the programme at country level. Accountabilities of managers at the country, regional and headquarter levels with respect to country programmes are prescribed in the organization’s Programme and Operations Policies and Procedures and Internal Control Framework.

- The programme will be nationally executed. If necessary, national execution may be replaced by direct execution for part or all of the programme to enable response to force majeure. Harmonised Approach to Cash Transfers (HACT) will be used in a coordinated fashion with other UN agencies to manage financial risks. Cost definitions and classifications for programme and development effectiveness will be charged to the concerned projects.

# IV. Monitoring and Evaluation

- Development progress will be monitored against the indicators in the results and resources framework, which incorporates nationalized SDG indicators and is aligned with the UNSCDF. To measure its contribution to national results, UNDP will employ Georgia’s SDG Tracker and other national monitoring systems, official statistical data and reports from line ministries, development partners and research institutions. Perception surveys and innovative tools such as sensemaking, micro-narratives and big data will also be used to assess results and behavioural change. The national statistical office and other partners will receive support to produce reliable data.

- UNDP will strengthen its internal capacity while helping external partners develop skills in monitoring and evaluation. UNDP will collaborate with other UN entities to monitor targets and validate progress towards UNSDCF results. Independent project and impact evaluations will be commissioned to assess UNDP contributions to transformative change. Spending towards gender equality will be tracked. Findings will be shared with Government and civil society counterparts, development partners and the public.

#### ANNEX A:  RESULTS AND RESOURCES FRAMEWORK

| NATIONAL PRIORITY OR GOAL: Government programme “Georgia 2020” recognizes principles of democratic development, rule of law, efficient administration, respect for human rights and basic freedoms as a basis for its policy and strives its attainment |  |  |  |  |
| --- | --- | --- | --- | --- |
| COOPERATION FRAMEWORK (OR EQUIVALENT) OUTCOME INVOLVING UNDP #1: By 2025, all people in Georgia enjoy improved good governance, more open, resilient and accountable institutions, rule of law, equal access to justice, human rights, and increased representation and participation of women in decision making |  |  |  |  |
| RELATED STRATEGIC PLAN OUTCOME: Outcome 2 – Accelerate structural transformations for sustainable development |  |  |  |  |
| COOPERATION FRAMEWORK OUTCOME INDICATOR(S), BASELINES, TARGET(S) | DATA SOURCE AND FREQUENCY OF DATA COLLECTION, AND RESPONSIBILITIES | INDICATIVE COUNTRY PROGRAMME OUTPUTS (including indicators, baselines targets) | MAJOR PARTNERS / PARTNERSHIPS FRAMEWORKS | ESTIMATED COST BY OUTCOME (US$) |
| 1.1. (CF Indicator 1.1) [NSDG 16.6.2.5] Rule of Law index Baseline (2015): 65% Target: higher than baseline 1.2. (CF Indicator 1.2) [NSDG 16.6.2.2] Voice and Accountability Baseline (2015): 55% Target: higher than baseline 1.3. (CF Indicator 1.6.1) [NSDG 5.5.1] Proportion of seats held by women in national parliaments and local governments Baseline (2019). a) Women’s representation in Parliament 14.8% (22 women, 127 men). b) Women’s representation in local governments 13.5% (277 women, 1,781 men). Target: a) < 20%; b) < 20% | - 1.1. Central Election Commission - 1.2-1.3. Worldwide Governance Indicators: http://datacatalog.worldbank.org | Output 1.1. Inclusive national and local governance systems have greater resilience and capacities to mainstream gender, ensure evidence-based and participatory policymaking, map and address inequalities and deliver quality services to all - Indicator 1.1.1 Implementation rate of gender sensitive Public Administration Reform (PAR) strategy 2021-2024 Baseline (2020): Strategy being prepared Target (2025): At least 70% of Strategy annual action plans pertaining to policy, civil service and public service delivery implemented. Source: PAR Monitoring Reports (AOG), EU Sector Assessment Reports, annually - Indicator 1.1.2 Share of National-level Policies complying with new whole-of-government policy standards emphasizing inclusiveness and participation Baseline (2020): New policy standard implementation began January 2020 Target (2025): At least 70% of National-level policies fully comply with the new whole-of-government policy standards and are approved by the Government. Source: PAR Monitoring Reports (AOG), EU Sector Assessment Reports, annually - Indicator 1.1.3 Level of capacity and professionalism of civil servants at local and national levels to better serve constituencies Baseline (2020): a) Baseline on implementation of civil servants’ professional development plans to be established in 2021; b) 15% of civil servants improved capacities by attending professional development courses Target (2025): a) 50% of public agencies fulfil organizational professional development plans; b) 50% of civil servants (gender disaggregated) have improved knowledge and skills by participating in capacity development activities Source: Civil Service Bureau’s (CSB’s) Human Resource Management System and Annual Reports, annually - Indicator 1.1.4 Percentage of population satisfied with local self-governments Baseline (2019): General: 67.3%; Urban: 64%; Rural 72%; High mountainous 80% Target (2025): General: 69%, Urban: 65%; Rural 75%; High mountainous 82% Source: UNDP Citizens’ Satisfaction with Public Services Survey, biannually (2021, 2023, 2025) - Indicator 1.1.5 Municipal budget total receipts as a percentage of GDP Baseline (2019): 4.7% Target (2025): 7% Data source: MRDI 2020-2025 Decentralization Strategy implementation report, annually - Indicator 1.1.6 Quality/level of evidence based and participatory law-making processes and executive oversight Baseline (2020): Score 59/100 Target (2025): Score 65/100 Source: Georgia National Integrity System Assessments, 2023, 2025. Output 1.2: National legislation and policies to eliminate discrimination, deliver gender-equal results, enhance human rights and equal access to justice, and equitable access to/coverage of quality social services, especially for the most vulnerable and marginalized. - Indicator 1.2.1 Percent of courts operating court mediation centers, which have completed at least one referred mediation case Baseline (2020): 17% in Tbilisi, Gori, Rustavi, Mtskheta operate mediation centers. Target (2023): At least 75% of regional and appellate courts have court mediation center that has at least one referred case Source: Mediators Association of Georgia’s Annual Report, High Council of Justice relevant decisions, annually - Indicator 1.2.2 National Human Rights Strategy 2021- 2030 implementation rate Baseline (2020): Strategy being prepared Target (2025): 50% of objectives implemented Source: Strategy Action Plan reports produced by the Human Rights Secretariat, annually - Indicator 1.2.3: State Inspector Service Institutional Strategy 2021-2023 implementation rate Baseline (2020): 2021-2023 Strategy not yet adopted Target (2023): The strategy adopted and 70% of objectives implemented Source: Strategy Implementation reports, annually - Indicator 1.2.4: Public perception on human rights situation in the country. Baseline (2018): 47% reported the state is not oriented to enhance human rights protection, 53% that human rights are totally unprotected Target (2023): At least 60% considers state is oriented on enhancement of human rights and their rights are totally protected Source: UNDP public opinion survey, 2023 - Indicator 1.2.5: Proportion of Gender Equality chapter(s) of the National Human Rights Strategy 2021-2030 implemented Baseline (2020): 0 Target (2025): at least 30% Data source: AOG/Public Defender’s Office reports, annually - Indicator 1.2.6: Improved inclusive and gender sensitive legislation and policy ensuring rights of all people with disabilities Baseline (2020): The Rights of Persons with Disabilities Law was adopted in 2020, but legislation on accessible environment and information and communication technology accessibility is not in line with international standards Target (2025): National Accessibility Plan is approved; Guidelines with recommendations on development of national standards on accessible ICT are approved. Source: Official Gazette of Legal Acts www.matsne.gov.ge, annually | Government Administration Government (AOG); line ministries; Parliament, Adjara Supreme Council, GEOSTAT; Ministry of Regional Development and Infrastructure (MRDI), High Council of Justice, Human Rights Secretariat, Personal Data Protection Inspector, Digital Development Agency, CSB, PSDA, Public Service Hall, Mediators Association, National Association of Local Authorities; Local self-governments; CSOs | Regular 437,500 USD |
|  |  |  |  | Other 21,566,482 USD |
| NATIONAL PRIORITY OR GOAL: National Environmental Action Program-3 (2018-2021) Strategic Objective 1: Improving the status of the environment and ensuring the protection/sustainable use of natural resources and preventing/minimizing risks that threaten human health and the welfare of the population. |  |  |  |  |
| COOPERATION FRAMEWORK 2021-2025 OUTCOME INVOLVING UNDP #5: By 2025, all people, without discrimination, enjoy enhanced resilience through improved environmental governance, climate action and sustainable management and use of natural resource(s) in Georgia |  |  |  |  |
| RELATED STRATEGIC PLAN OUTCOME: Outcome 3 – Strengthen resilience to shocks and crises |  |  |  |  |
| COOPERATION FRAMEWORK OUTCOME INDICATOR(S), BASELINES, TARGET(S) | DATA SOURCE AND FREQUENCY OF DATA COLLECTION, AND RESPONSIBILITIES | INDICATIVE COUNTRY PROGRAMME OUTPUTS (including indicators, baselines targets) | MAJOR PARTNERS / PARTNERSHIPS FRAMEWORKS | ESTIMATED COST BY OUTCOME (US$) |
| 2.1. (CF Indicator 5.1) [NSDG 13.2.1] Number of countries that have communicated establishment or operationalization of an integrated policy/strategy/plan which increases their ability to adapt to the adverse impacts of climate change, and foster climate resilience and low greenhouse gas emissions development in a manner that does not threaten food production. Baseline (2015): In 2015 Georgia adopted Intended Nationally Determined Contributions (INDC). The following are prepared: 1) Climate Action Plan (CAP), 2021-2030; 2) Nationally Determined Contributions (NDC), 2021-2030; Target (2025): 1) Updated NDC approved by the Government and submitted to UNFCCC; 2) NAP for Energy Sector produced (2023); 3) LT LEDS elaborated/adopted (2021); 4) 3rd Biennial Update Report (BUR) (2022) 5) 4th National Communication to UNFCCC (2021) | - 2.1. MEPA/UNFCCC websites | Output 2.1 Environmental governance and institutional capacity enhanced to enable rational, equitable and sustainable use of natural/land resources, to ensure conservation of ecosystems, use of innovative and climate-friendly technologies for inclusive green economy, energy efficiency and clean energy production, and make communities more resilient to environmental shocks. - Indicator 2.1.1: Targeted protected areas under improved management and increased annual long-term funding Baseline (2017): 0 ha, US$650,000 Target (2023): 431,872has, US$950,000 Source: MEPA Protected Areas Database, 2023 - Indicator 2.1.2 [NSDG 1.5.4]: Proportion of local governments that adopt and implement local Disaster Risk Reduction (DRR) strategies in line with national disaster risk reduction strategy Baseline (2020): 0 Target (2025): At least 10 local governments have local DRR strategies, including gender-sensitive disaster preparedness and response plans for multiple climate-induced hazards Source: UNDP, annually - Indicator 2.1.3: Number of initiatives aimed at capacity-building efforts for government and other stakeholders in mainstreaming gender in formulating, monitoring and implementing national climate change policies and plans Baseline (2020): 0 2.1.3a. Gender-sensitive socio-economic vulnerability assessment methodology developed/applied 2.1.3b. Standardized methodologies and SoPs for multi-hazard risk-informed, preparedness and response plans developed considering gender and vulnerable groups 2.1.3c. Gender Sensitive institutional and legal frameworks are in place to roll-out standardized multi-hazard mapping and risk assessment methodology 2.1.3d. Gender sensitive capacity development plans put in place to enhance knowledge on nation-wide multi-hazard mapping and risk assessment Source: UNDP, annually Output 2.2 Climate-sensitive, resilient and risk-informed development promoted across all economic sectors in rural and urban areas to increase adaptive capacities and mitigate climate change impact - Indicator 2.2.1 Adaptation and mitigation capacities are increased through enhanced use of climate information, products and services and well-established multi-hazard early warning systems (MHEWS), including on community level. Baseline: 2.2.1a. Hydrometric monitoring network outdated/inadequate; 2.2.1b. 0 multi-hazard and risk maps; 2.2.1c. MHEWS and Forecasting for climate -induced hazards does not exist; 2.2.1d. 0 risk reduction measures, based on multi-hazard risk maps, in high-risk areas; 2.2.1e. 0 Community-based climate risk management/EWS Target: 2.2.1a/ Improved hydro and agrometeorological network; 2.2.1b. maps for 11 river basins; 2.2.1c. established and functional; 2.2.1d. 12 measures implemented; 2.2.1e. applied in 100 communities Source: UNDP, annually - Indicator 2.2.2 Gender-responsive technological solutions, initiatives and projects, per LTLEDS are in place or applied Baseline: LTLEDS under elaboration, 0 projects Target (2025): At least 3 LTLEDS initiatives and/or projects Source: LTLEDS implementation report, 2023, 2025 | MEPA, MRDI, MIA, National Security Council, National Environmental Agency, National Food Agency, Agriculture-Scientific Research Centre, Environmental Information and Education Center, Emergency Management Service, Caucasus Nature Fund, NGOs | Regular 437,500 USD |
|  |  |  |  | Other 34,160,197 USD |
| NATIONAL PRIORITY OR GOAL: “Georgia 2020” priorities under strategic direction 1, improved competitiveness of private sector: 1.1. Improved investment and business environment; 1.2. Support development of innovations and technologies; 1.3 Support export growth; strategic direction 2 prioritizes development of labour force according to labour market requirements and particularly 2.1 Developing vocational education and training. |  |  |  |  |
| COOPERATION FRAMEWORK 2021-2025 OUTCOME INVOLVING UNDP #3: By 2025, all people without discrimination benefit from a sustainable, inclusive and resilient economy in Georgia |  |  |  |  |
| RELATED STRATEGIC PLAN 2018-2021 OUTCOME: Outcome 1 – Advance poverty eradication in all its forms and dimensions |  |  |  |  |
| COOPERATION FRAMEWORK OUTCOME INDICATOR(S), BASELINES, TARGET(S) | DATA SOURCE AND FREQUENCY OF DATA COLLECTION, AND RESPONSIBILITIES | INDICATIVE COUNTRY PROGRAMME OUTPUTS (including indicators, baselines targets) | MAJOR PARTNERS / PARTNERSHIPS FRAMEWORKS | ESTIMATED COST BY OUTCOME (US$) |
| 3.1. (CF Indicator 3.1) [NSDG 1.2.1] Proportion of population, including children, living below the national poverty line, by location and by sex Baseline (2015): Georgia- 21.6% Urban- 18% Rural- 26.4%; Age Groups: 0-17 - 24.2%, 18-64 - 22%, 65 and above - 16.4% Female - 21.3% Male - 22% Target (2030): Reduce by 20% 3.2. (CF Indicator 3.2) [NSDG 8.5.2] Unemployment rate, by sex, age and persons with disabilities Baseline (2015): All - 14.1%; Female - 12.4%; Male - 15.6%; Age Groups: 15-24 - 33.8%, 25-34 - 20.3%, 35-44 - 15.2%, 45-54 - 12.0%, 55-64 - 8.2%, 65 and above - 1.1% Target (2030): All - 9.5% 3.3. (CF Indicator 3.3.1) [NSDG 8.6.1] Proportion of youth (15-24, 15-29 years) not in education, employment or training (NEET), by sex Baseline (2014): 27.9% Target: Reduce by 8% | - 3.1-3.3: GEOSTAT | Output 3.1 Improved competitiveness of private sector and labour force, especially youth and vulnerable groups through labour policy, private sector development, social responsibility and skills development. - Indicator 3.1.1: Number of new services (advisory, finance instruments) introduced by public and private business development providers within business development and innovations ecosystem including in regions Baseline (2020): Limited number of services Target (2025): At least 4 new services Data source: UNDP, annually - Indicator 3.1.2: Percent of supported companies in selected sectors demonstrating at least 20% increased turnover or exports Baseline (2020): 0%; Target (2025) At least 50%; Data source: UNDP, annually - Indicator 3.1.3 Number of public-private partnerships providing Life Long Learning (LLL) VET established Baseline (2020): 0 Target (2025): At least 5 Source: UNDP, annually - Indicator 3.1.4: Percent of targeted farmers receiving extension services that increase income by at least 15% Baseline (2020): 70% of 7,000 targeted farmers (30% women) Target (2025) (incl. baseline): At least 70% of targeted 14,000 farmers (at least 30% women). Source: UNDP, annually - Indicator 3.1.5: Percent of public VET college graduates employed/self-employed Baseline (2018): 62% Target (2025): At least 67% Source: MESCS Tracer Study, annually Output 3.2 Sustainable and inclusive rural and agriculture development and improved livelihoods. - Indicator 3.2.1 Annual Action Plans of Agriculture and Rural Development Strategy (ARDS 2021-2027) percent implemented Baseline: 0 Target (2025): At least 70% annually Source: Annual Implementation Reports, annually - Indicator 3.2.2 Number of newly created jobs in supported rural non-farm enterprises in selected regions Baseline (2020): 0 Target (2025): At least 300 Data source: UNDP, Agriculture and Rural Development Agency records, annually - Indicator 3.2.3: Number of forest and protected area hectares under sustainable and climate-resilient management benefitting targeted rural population Baseline (2017): 0 Target (2022): At least 420,000 ha (2022) Data source: MEPA, annually - Indicator 3.2.4: Number of businesses and households benefitting from energy efficiency, renewable energy, digital and other technologies Baseline (2020): 0 Target (2025): At least 300 businesses and households Data source: UNDP, annually | MEPA, MESD; Ministry of Education, Science, Culture and Sport (MESCS); business organizations; trade unions; professional organizations; VET colleges; universities; private training providers | Regular 437,500 USD |
|  |  |  |  | Other 21,565,389 USD |
| NATIONAL PRIORITY OR GOAL: Government programme “for a strong, democratic, united Georgia” prioritizes conflict resolution and community resilience through public diplomacy, economic rehabilitation and business projects with active engagement of local and international partners. |  |  |  |  |
| COOPERATION FRAMEWORK (OR EQUIVALENT) OUTCOME INVOLVING UNDP #4: By 2025, conflict affected communities enjoy enhanced human security and resilience |  |  |  |  |
| RELATED STRATEGIC PLAN OUTCOME: Outcome 3 – Strengthen resilience to shocks and crises |  |  |  |  |
| COOPERATION FRAMEWORK OUTCOME INDICATOR(S), BASELINES, TARGET(S) | DATA SOURCE AND FREQUENCY OF DATA COLLECTION, AND RESPONSIBILITIES | INDICATIVE COUNTRY PROGRAMME OUTPUTS (including indicators, baselines targets) | MAJOR PARTNERS / PARTNERSHIPS FRAMEWORKS | ESTIMATED COST BY OUTCOME (US$) |
| 4.1. (CF Indicator 4.1) Political Stability and Absence of Violence Index Baseline (2018): percentile rank - 30; Target (2025): Improvement of Georgia’s percentile ranking 4.2. (CF Indicator 4.2) Global Peace Index Baseline (2020): rank 95; Overall score: 2.116; Target (2025): Improvement of Georgia’s global ranking and/or overall score; 4.3. (CF Indicator 4.3) Positive Peace Index Baseline (2019): Georgia’s global rank – 54; overall score: 2.7; Target (2025): Improvement of Georgia’s global ranking and/or overall score; 4.4. (CF Indicator 4.4) Women, Peace and Security Index Baseline (2019): WPSI index value: 0.777, rank 46/166 Target (2025): Improvement of Georgia’s index value and ranking | - World Governance Indicators; https://info.worldbank.org/governance/wgi/Home/Reports - 4.2 Global Peace Index, Institute for Economics and Peace; - http://visionofhumanity.org/indexes/global-peace-index/ - 4.3 Positive Peace Index, Institute for Economics and Peace; http://visionofhumanity.org/reports/ - 4.4. Georgetown Institute for Women, Peace and Security; https://giwps.georgetown.edu/the-index/chapters/ | Output 4.1: Conflict-affected populations have improved access to essential services, including education, healthcare, Gender Based Violence (GBV) response/legal assistance and improved socio-economic conditions, community resilience and self-reliance - Indicator 4.1.1: Number of cases of legal services received by conflict-affected persons (including GBV survivors) by sex Baseline (2019): 640 (82% women) Target (2025): 920 (including baseline), at least 80% women Source: UNDP, annually - Indicator 4.1.2: Number of cases of psychological assistance services received by conflict-affected persons (including GBV survivors) by sex Baseline (2019): 757, 94% women Target (2025): 1,177, at least 90% women Source: UNDP, annually - Indicator 4.1.3: Number of conflict-affected youngsters with improved access to schools, VET colleges and university Baseline (2019): 20,174 (40% female youth) Target (2025): 31,578 (including baseline), at least 50% female youth Source: UNDP, annually - Indicator 4.1.4 Number of conflict-affected population with improved access to essential healthcare services Baseline (2019): 10,886 (about 60% female youth) Target (2025): 16,054 (including baseline), at least 50% female youth Source: UNDP, annually - Indicator 4.1.5: Number of people benefiting directly from improved socio-economic conditions and improved human security Baseline (2019): 5,362 (51% women) Target (2025): 14,742 (including baseline), at least 50% women Source: UNDP, annually Indicator 4.1.6: Number of people with improved community resilience against climate-induced multi-hazard natural disasters Baseline (2020): Not available Target (2025): 780 direct beneficiaries (at least 50% female) Source: UNDP, annually Output 4.2: Space widened for dialogue and participation that strengthens civil society, community resilience, social cohesion and implementation of Women, Peace and Security Agenda - Indicator 4.2.1: Number of initiatives to support direct people-to-people contacts, liaison activities (deliveries of medication and/or other essential goods) and to enhance enabling environment for dialogue and trust within and across the divided communities Baseline (2020): 121 Target (2025): 221 (including baseline) Source: UNDP, annually - Indicator 4.2.2: Number of people who benefit from peacebuilding initiatives that ensure enhanced confidence within and between the conflict divided communities Baseline (2020): 26,430, 49% women Target (2025): 42,000 (including baseline), at least 50% women Source: UNDP, annually | State Minister for Reconciliation, CSOs, international organizations, UN agencies | Regular 437,500 USD |
|  |  |  |  | Other 21,564,911 USD |

UNDP, “Accelerating Progress towards the SDGs: Identifying Priority Areas for Action in Georgia,” 2019.

“Status of internally displaced persons and refugees from Abkhazia, Georgia, and the Tskhinvali region/South Ossetia, Georgia,” (A/74/878), 3 June 2020.

UNDP Independent Evaluation Office, “Independent Country Programme Evaluation: Georgia,” March 2020.

UNDP, “Accelerating Progress towards the SDGs: Identifying Priority Areas for Action in Georgia,” 2019.

UNCT Georgia, “Building Back Better in Georgia: UN COVID-19 Response and Recovery Offer,” August 2020.