## Sheet1
Steps | Deployment Steps | For all Providers | COVAX Astra Zeneca | COVAZ Pfizer | Serum Institute Astra Zeneca | Moderna | Synoharm
National Vaccine Deployment Plan (NVDP) | The completed NDVP has been uploaded to the COVID-19 Partners Platform and validated by the country administrator | Completed
Confidentiality | Confidentiality and non disclosure agreement under review |  | Completed | In Progress | Not Applicable | In Progress | In progress
Confidentiality | Sign a Confidentiality and non disclosure agreement |  | Completed |  | Not Applicable
Indemnification | Indemnity and Liability Agreement under review |  | Completed |  | Not Applicable
Indemnification | Sign Indemnity and Liability Agreement |  | In Progress |  | Not Applicable
NRA authorization | Obtain authorization of the National Regulatory Authority |  | In Progress |  | In Progress
Procurement | Obtain an import license |  | In Progress |  | In Progress
Procurement | Procurement authorization letter provided |  | Not Applicable | Not applicable | Completed
Procurement | The vaccine purchase agreement under review (Indicate doses) |  | 184000-315000 | 29250 | 150000 |  | 100000
Procurement | The vaccine purchase agreement fully executed (Indicate doses)
Delivery | Delivery mode |  | Via UNICEF | Via UNICEF | CIP By Air
Delivery | Vaccine delivery data expected |  | To be confirmed | To be confirmed | To be confirmed
Delivery | Vaccine delivery date confirmed
Delivery | Vaccine delivery status
Last updated on February 17th 2021