Georgia Emergency COVID-19 Response Project (WB IBRD 9113-GE and AIIB L0388A)                                                                                                                                                                                                                                          Effectiveness date May 28, 2020

The Closing Date is April 30, 2022

Signature date, May 1, 2020

With the aim to prevent, detect and respond to the threat posed by the COVID-19 pandemic, and strengthen national systems for public health preparedness in Georgia, “the Emergency COVID-19 Response Project” having total of US$180 mln support from the World Bank Group and the Asian International Investment Bank (AIIB) was launched in June 2020.

To the date, over 16 contracts have been concluded to deliver on ambitious goals that the Georgian Government and the Ministry (MoIDPLHSA) has committed to implementing under the Project:

- Over 1,800,000 PCR and rapid test systems, and lab equipment, costing over US$18 mln, have been supplied, to support the strengthening of disease surveillance systems and the capacity of the selected public health laboratories to confirm cases of COVID-19.

- Purchase of PPE (Personal Protective Equipment) supplies via the BFP (Bank Facilitated Procurement) international offers is ongoing, totaling to US$5mln spending.

- US$6mln package of vitally important equipment for key hospital level institutions playing crucial role in the response has been prepared to procure through UNOPS LTAs (Long-term Agreements), and over US$5mln more will be spent in coming months to guarantee adequate preparedness for COVID-19 patients care and treatment further.

- Significant efforts have been made and procurement initiated to bring the technical capacities of the “Emergency Situations Coordination and Urgent Assistance Center” to more advanced level via strategically important supplies for better equipment, transport base, communications and radio systems, and other relevant supplies. The Tenders and Direct Contracting is ongoing. Over US$8mln planned to spend with this strategic purpose.

- Importantly, innovative IT solutions applied in priority areas of epidemic control considered. - Namely, the upgrade and continuous support for functioning the Government’s Stop COVID-19 application to trace the new diagnosed cases and control spread of the disease; and the development of a specific electronic application enabling technology for effective management of COVID-19 related data to facilitate quarantined persons’ transition to self-isolation, if appropriate. Supporting these IT solutions do not entail high costs, but clearly, these are the highlights of the Project.

- Emergency procurement of the vital package of essential equipment and furniture for the 100 strategic PHC facilities to strengthen the frontline of the response made possible under the Project via the Bank’s direct procurement modality, that costed almost 400,000 US$;

Also

- Development of the national COVID-19 crisis management strategic plan has been supported under the TA element of the Project

All above, under the Project Component 1. Emergency COVID-19 Response, with the two Subcomponents 1.1: Case Detection and Confirmation, and Subcomponent 1.2: Health System Strengthening for Case Management , that aims to contribute to the strengthening of health system preparedness, improve the quality of medical care provided to COVID-19 patients, and minimize the risks for health personnel and patients.

Prominently, Georgia’s commitment to participating in the Global COVAX facility for the COVID-19 vaccine in the hopefully near future stands as an open issue under the Project, and the Ministry hopes for fastest solution of the issue of possible financial support from the Bank, as the deadline for guarantee and advance payment under the new commitment approaching soon.

Under the Component 2. Enabling Health Measures to Contain the COVID-19 Outbreak through Temporary Income Support for Poor Households and Vulnerable Individuals, support provided by financially mitigating the eventual hardship on poor and vulnerable households caused by introducing measures for social distancing and a lock-down in April-May 2020 to contain COVID-19.

Subcomponent 2.1: Cash Transfers to Poor and Vulnerable Households covers all reimbursements to assist households negatively affected by the health measures adopted to contain the outbreak and the resulting economic downturn through:

(a) The scale-up of the existing TSA (Targeted Social Assistance) program for extremely poor households;

(b) a new temporary cash benefit for vulnerable households; and

(c) a top-up benefit for households with more than three children.

Similarly, Subcomponent 2.2: Temporary Unemployment Assistance for Individuals who Lose their Job because of the COVID-19 Outbreak, covers all expenses to reimburse temporary unemployment assistance benefit for private sector formal wage workers; - a flat benefit of 200 GEL per month for lay-off workers.

This subcomponent will also cover a one-off benefit targeted to self-employed and informal workers who lost their job because of the economic downturn resulting from the measures adopted to contain the outbreak. The one-off benefit provided on demand through an online portal and SESA (State Agency for Social Assistance), applying following eligibility criteria: (a) not having any source of declared income, verified through the tax income payroll database of the Revenue Service; and (b) not being a beneficiary of public social assistance (including the TSA, the social pensions, and/or other temporary cash transfers under the subcomponent 1). The one-off benefit amounted to GEL 300 (around US$96).

To the date, projections show that the funds allocated to Component 2 of the project are sufficient to address all the needs of vulnerable individuals listed in the categories above. – according to the estimate, almost 40 mln GEL will be saved and can be made available to be utilized in other strategic directions under the health domain of the Project.