| EU-GEORGIA ASSOCIATION AGREEMENT IMPLEMENTATION FRAMEWORK Trade and Sustainable Development Work Plan 2021-23 ENVIRONMENT AND CLIMATE ACTION |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Article/Paragraph of the Association Agreement or the Association Agenda | Priority Area | Planned Activity | Type of Activity | Result / Output | Indicators | Responsible Institution/ Supporting Institution | Implementation Timeframe | Donor funding /technical assistance on-going/planned |
| Association Agreement; Article 230; paragraph 2" | 1. Illegal wildlife Trade | Adoption, implementation and effective enforcement of the Georgian legislation for fighting wildlife trafficking; Implementation of the CITES convention. | Legal Framework | Activities to support implementation of the legislation on CITES are carried out. Trade between Georgia and the EU in CITES-listed species meets the obligations under CITES; | Effective system of implementation of CITES is in place for species traded with the EU in high numbers, such as Galanthus spp.; Submission of the law “On Biodiversity” to the Parliament of Georgia and the and development of the secondary legislation. | Ministry of Environmental Protection and Agriculture of Georgia | 2021-2023 | German Corporation for International Cooperation (GIZ) |
|  |  | Strengthening capacity of Revenue Service and Environmental Supervision Department in order to fulfill the obligations under the CITES Convention | Capacity building/Human Resources | Relevant training are conducted for employees of the Department of Environmental Supervision and Customs Department of the LEPL Revenue Service | Customs department and Department of Environmental Supervision are better enforcing provisions of the convention | Ministry of Environmental Protection and Agriculture | 2021-23 | German Corporation for International Cooperation (GIZ); Fauna & Flora International Further donor support to be explored |
| Association Agreement; Article 233; paragraph 2, a" | 2. Sustainable Forest Management | Start the implementation of the New Forest Code of Georgia |  | Ensuring sustainable management of forest through legal mechanisms and effective separation of responsibilities | Finalisation of the National Forest Inventory and maintenance of the database | Ministry of Environmental Protection and Agriculture of Georgia | 2021-2023 | German Corporation for International Cooperation (GIZ) |
|  |  | Development of the final drafts of by-laws of Forest Code of Georgia | Legal Framework | Detailed regulations on forest developed in accordance with the new Forest Code | By-laws are adopted by the Government | Ministry of Environmental Protection and Agriculture of Georgia | 2021-22 | German Corporation for International Cooperation (GIZ) |
|  |  |  |  | Establishment of an economically viable state forest management body |  | Ministry of Environmental Protection and Agriculture of Georgia | (to be discussed) |  |
| Association Agreement; Article 233; paragraph 2, c" |  |  | Institutional Framework | Strengthening the capacity of the Department of Environmental Supervision by conducting trainings for forester-inspectors and employees of other relevant services of the Department | Number of trainings and workshops; Number of trained employees | Ministry of Environmental Protection and Agriculture of Georgia | 2021-2023 | EU (EU4Environment initiative) |
| Association Agreement; Article 230, Paragraph 4" | 3. Effective implementation of UNFCCC | Implementation of the UNFCCC Paris Agreement | Policy Framework | Adopt an updated NDC Start the implementation of the Nationally Determined Contribution (NDC) Start implementation of Georgia’s 2030 Climate Strategy and 2021-2030 Action Plan Awareness raising Action Plan for NDC and Climate Action Plan conducted | Revised Nationally Determined Contribution (NDC) adopted by the Government and submitted to the UNFCCC Submit the Interim Implementation report on the NDCs – to clarify | Ministry of Environmental Protection and Agriculture of Georgia | Asap an in any case well before COP26 to be held in Nov 2021 2021-2023 2021 2021 (if not done yet in 2020) 2021 | Different donors including EU through EU4Climate |
|  |  |  |  | Finalisation and adoption of the Long-Term Low-Emission Development Strategy 2050 Finalisation of the national GHG inventory and development of legal framework as a basis for a binding Measurement, Reporting and Verification (MRV) system is lacking in Georgia. Adoption of an Adaptation Strategy Ratification of the Kigali amendment to Montreal Protocol | Adoption of the Strategy by the Government and submission to the UNFCCC |  |  | EU4Climate |

| LABOUR |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Article/Paragraph of the Association Agreement or the Association Agenda | Priority Area | Planned Activity | Type of Activity | Result / Output | Indicators | Responsible Institution/ Supporting Institution | Implementation Timeframe | Donor funding /technical assistance on-going/planned |
| Article 229 -Multilateral labour standards and agreements | 1. Effective implementation of core labour standards - strengthening labour Inspection | Strengthening the enforcement mechanism for inspection on OSH in line with international standards Strengthening the enforcement mechanism for all core labour standards and rights | Legal framework | Program of Accreditation of OSH managers in force Legal acts necessary to implement the OSH law (including those of the scope of the application of the law and the functions of the labour inspectorate: Legal acts to give effect to new Labour Code | Legal acts are adopted Legal acts adopted | Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs of Georgia | 2021-2023 | EU twinning project International Labour Organisation (ILO) EU TAIEX support (workshop with AA countries, individual requests) EU Socieux + facility |
|  |  | Transformation of the Labour Inspection Department into a Legal Entity under Public Law and its Institutional Strengthening Functioning of the Labour Inspectorate in accordance with the extended mandate defined by the legislation | Institutional development/Capacity-building | Set up the Labour Inspectorate on the basis of the new Labour Inspection Law with broad mandate and ensure sufficient capacity including adequate staff, organization, training, equipment, etc. adequate financial resources etc., for the inspection of all working conditions and labour relations | Labour Inspection staffed with relevant human resources; Number of measure to increase capacity labour inspectors Number of companies inspected and recommendations issued; Number of recommendations implemented | LEPL – Labour Inspection Service set up. | 2021-2023 | EU twinning project EU, ILO,Other donors / international organizations (e.g. the Danish government) EU Socieux + facility |
|  |  |  | Awareness raising | Promoting awareness among employers of the benefits of labour inspection | Number of meetings with employers in order to rise awareness on labour inspections |  | 2021-2022 | EU, Other donors / international organizations |
|  |  |  |  | Discussion of feasibility of ratification of ILO convention N81 | Minutes of the TSPC meetings; relevant decisions of the Commission |  | 2022-2023 |  |
|  | 2. Effective implementation of core labour standards | Strengthen the operational framework regarding Child Labour Enhance non-discrimination in the workplace; promote equal pay for work of equal value | Policy/Capacity building | # Ensuring enforcement of new rules on hazardous work and light work (by Labour Inspectorate) Awareness raising of employers, municipalities, educational providers (schools) on Child Labour issues Work undertaken in the framework of EU-Georgia Sub-Committee On Employment, Social Policy, Equal Rights and Public Health on legislative amendments to fully incorporate the equal pay for equal work " principle and on developing tools to prevent discrimination, notably gender-based in the whole recruitment process. Develop guidelines for employers to ensure equal pay for equal work | Number of companies inspected Number of meetings with stakeholders Discussed under TSD sub-committee Guidelines are discussed with stakeholders and elaborated | Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs of Georgia | 2021-2023 | ILO, EU, Other donors / international organizations UN Women ILO |
|  | 3. Effective implementation of core labour standards - strengthening social dialogue | Strengthen the Tripartite Social Partnership Commission (TSPC)at national and regional level |  | Ensure involvement of trade unions and employers organizations in regular TSPC meetings; Adequate tripartite consultation on improvement of labour standards. Continuing tripartite social partnership commission at regional level, at least in one region. | Number of meetings at working group and TSPC level Number of issues discussed by TSPC according to Strategic plan | Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs of Georgia | 2021-2023 | ILO, EU |