## WP
Georgia Emergency COVID-19 Response Project Work Plan (WB IBRD 9113-GE and AIIB L0388A) Effectiveness date May 28, 2020 The Closing Date is April 30, 2022 Signature date, May 1, 2020
|  | Effectivness date | 2020 | [9 empty] | 2021 | [11 empty] | 2022
Activities |  | 2020-05-01 | Q1 | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2
|  |  | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May
A. Project Management Activities
A.1 | Finilizing the POM | [7 empty] | X | X
A.2 | Update ESCP |  |  |  |  | X | X | X | X
A.3 | Update of draft ESMF&LMP | [5 empty] | X | X
A.3.1 | WB clerarance of updated draft of ESMF&LMP | [6 empty] | X
A.3.2 | Disclosure date of updated draft of ESMF&LMP | [6 empty] | X
A.3.3 | Public consultations (ESMF, LMP) | [6 empty] | X
A.3.4 | Update of draft ESMF&LMP due to public consultations | [6 empty] | X | X
A.3.5 | Submitting final draft of ESMF&LMP to WB for review and celarance | [7 empty] | X
A.3.6 | WB clerarance of final draft of ESMF&LMP
A.3.7 | Final disclosure of ESMF&LMP
A.4 | Update of draft SEP&GRM |  |  |  |  | X | X | X
A.4.1 | WB clerarance of updated draft of SEP&GRM | [5 empty] | X | X
A.4.2 | Disclosure of updated draft of SEP&GRM | [6 empty] | X
A.4.3 | Public consultations (SEP&GRM) | [6 empty] | X | X
A.4.4 | Update of draft SEP&GRM due to public consultations | [7 empty] | X | X
A.4.5 | Submitting final draft ofSEP&GRM to WB for review and celarance | [7 empty] | X | [7 empty] | X | [10 empty] | X
A.4.6 | WB clerarance of final draft of SEP&GRM |  |  |  | X |  |  |  |  | X
A.4.7 | Final disclosure of SEP&GRM | [8 empty] | X | X
A.4.8 | SEP iplementation, monitoring & reporting
A.4.9 | GRM iplementation, monitoring & reporting
A.5 | Purchasing Equipments and Supplies |  |  |  | X | X | X | X | X | X | X | X | X
A.5.1 | monitoring and reporting of delivery of goods |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X
A.6 | Reimbursement of the Expenditures
A.6.1 | reimbursement of Unemployment benefits, SESA | [8 empty] | X | X | X
A.6.2 | reimbursement of one-off benefits, SESA | [8 empty] | X | X
A.6.3 | reimburstment of TSA, SSA | [8 empty] | X | X | X
A.7 | Finilizing all dated covenants | [7 empty] | X | X
B. Rehabilitation works
B.1 | Consultancy services for redesign and Supervision
B.1.1 | Elaboration of ToR for consultancy services for redesign and Supervision | [7 empty] | X | X
B.1.2 | Procurment of consultancy services for redesign and Supervision | [9 empty] | X
B.2. | Rehabilitation of the Regional Healthcare Center, Kutaisi | [12 empty] | X | X | X | X
B.2.1 | Redesign (cost estimate) | [9 empty] | X
B.2.2 | Preparation of tender documentation | [10 empty] | X
B.2.3 | Enviromental and Social screening of SP | [7 empty] | X
B.2.4 | Develpmnet of project-specific ESMP&ICWMP
B.2.5 | Submitting draft of ESMP&ICWMP to WB for review and celarance
B.2.6 | WB clerarance of draft ESMP&ICWMP
B.2.7 | Disclosure of draft of ESMP&ICWMP
B.2.8 | Public consultations (ESMP&ICWMP)
B.2.9 | Update of draft ESMP&ICWMP due to public consultations
B.2.10 | Submitting final draft ESMP&ICWMP to WB for review and celarance
B.2.11 | WB clerarance of final draft of ESMP&ICWMP
B.2.12 | Final disclosure of ESMP&ICWMP
B.2.13 | monitoring of ESMP&ICWMP implementation | [10 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
B.2.14 | supervision of civil activities
B.3 | Rehabilitation of Kutaisi regional emergency centre
B.3.1 | redesign (cost estimate)
B.3.2 | preparation of tender documentation
B.3.3 | Enviromental and Social screening of SP | [7 empty] | X
B.3.4 | develpmnet of project-specific ESMP&ICWMP
B.3.5 | Submitting draft of ESMP&ICWMP to WB for review and celarance
B.3.6 | WB clerarance of draft ESMP&ICWMP
B.3.7 | Disclosure of draft of ESMP&ICWMP
B.3.8 | Public consultations (ESMP&ICWMP)
B.3.9 | Update of draft ESMP&ICWMP due to public consultations
B.3.10 | Submitting final draft ESMP&ICWMP to WB for review and celarance
B.3.11 | WB clerarance of final draft of ESMP&ICWMP
B.3.12 | Final disclosure of ESMP&ICWMP
B.3.13 | monitoring of ESMP&ICWMP implementation | [10 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
B.3.14 | supervision of civil activities
| C. Reporting Requirement and Arrangements |  |  |  | X |  |  | X |  |  | X |  |  | X |  |  | X |  |  | X |  |  | X |  |  | X
C.1 | Monthly reports | [7 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
C.2 | Project Inception report |  |  |  |  | X | X
C.3 | Project Quarterly report | [8 empty] | X |  |  | X |  |  | X |  |  | X |  |  | X |  |  | X |  |  | X
C.4 | BI-annual PMRs, annual PMRS
C.5 | Mid-Term Review Report
C.6 | Interim Financial Reports (IFR) (after 45 days from submission of quarterly report) | [9 empty] | X |  |  | X |  |  | X |  |  | X |  |  | X |  |  | X
C.7 | Implementation Completion and Results Report | [26 empty] | X

## Sheet1
Georgia Emergency COVID-19 Response Project Work Plan (WB IBRD 9113-GE and AIIB L0388A) Effectiveness date May 28, 2020 The Closing Date is April 30, 2022 Signature date, May 1, 2020
Monitoring & Evaluation Plan: PDO Indicators |  |  | 2020 |  |  | 2021 |  | 2022
# | Indicator Name | Responsibility for Data Collection | April | July | October | April | October | April
1 | Number of people tested for COVID-19 identification per MoILHSA protocol | MoILHSA and NCDC | X | X
2 | Number of COVID-19 patients treated per SSA reimbursement guidelines. | MoILHSA and SSA | X | X
3 | Share of the population in the poorest quintile who are receiving the COVID-19 pandemic related social assistance programs. | GEOSTAT | X | X
4 | Number of designated laboratories with COVID-19 diagnostic equipment, test kits, and reagents per MOILHSA guidelines. | MOILHSA | X | X
5 | Number of personal protection equipment (PPE) purchased. | MoILHSA | X | X
6 | Number of designated public hospitals with fully equipped and functional intensive care units (ICUs) for COVID-19 patients | MoILHSA | X | X
7 | Number of designated public hospitals with isolation capacity. | MoILHSA | X | X
8 | Number of vulnerable households receiving temporary cash benefit. | SSA in MoILHSA | X | X
9 | Number of formal private sector workers laid off because of COVID-related lock down who receive temporary unemployment benefits, by gender. | SESA in MoILHSA | X | X
10 | Number of TSA beneficiary households. | SSA | X | X
11 | Complaints received related to COVID-related social assistance programs. | SSA in MoILHSA | X | X
12 | Number of informal workers who receive the one-off benefit , by gender | MoIHLSA | X | X
13 | Percentage of beneficiaries reporting that community engagement and outreach meet their needs. | SSA and MoILHSA | X | X