## TOTAL
Last updated on Oct 15-2020
|  | Cost estimate (USD) | Outstanding amount (USD)
Component 1. Emergency COVID-19 Response
| საქონელი | სავარაუდო ხარჯი (USD) | გაფორმებული კონტრაქტები | რესურსი | მომავალი / სავარაუდო კონტრაქტები | უკვე დაგეგმილი კონტრაქტები
საქონელი | GOODS | Cost estimate (USD) | ACTUALS (contracted) | Remaining funds after contracting | UNCOMITTED | Planned
1. პერსონალური დაცვის საშუალებები COVID19/G/DC-05 | 1. Procurement of Personal Protective Equipment | 5000000 | 846220 | 4153780 | 134780 | 4019000
2. კოვიდ-19 საპასუხო ღონისძიებებში ჩართული ჰოსპიტლებისთვის აღჭურვილობის შეძენა (რუხი, ბათუმი, თბ. ინფექციური, თბ. საუნივერსიტეტო, ქუთ. რეგიონული, LG, და საჩხერის რეგ. დაწესებულებები) COVID19/G/DC-06 / | 2. COVID19/G/DC-06 / Procurement of Hospital Equipment for dedicated COVID-19 clinics: Rukhi, Batumi, Tbilisi Infectious, Tbilisi University, Kutaisi Regional, and Sachkhere Regional | 8600000 | 507417.6 | 8092582.4 | 156584.4 | 7935998
3. პირველადი გადაუდებელი საპასუხო ღონისძიებებისთვის მოტოციკლები (სრული კომპლექტაცია) COVID19/G/RFQ-03 / | 3. COVID19/G/RFQ-03 / Procurement of Motorcycle for ambulance first responders with helmets | 1000000 | 0 | 1000000 | 0 | 1000000
4. ცე-ტიპის (ინტენსიური დახმარების) მობილური ჯგუფებისთვის მნქანები და აღჭურვილობა (სრული კომპლექტაცია) 30 ცალი COVID19/G/RFQ-01 / | 4. COVID19/G/RFQ-01 / Procurement of fully equipped Ambulance car C type - Intensive Care Mobile Unit (30 Units) | 2250000 | 0 | 2250000 | 300000 | 1950000
5. სადიაგნოსტიკო მასალები COVID19/G/DC-07 / | 5. COVID19/G/DC-07 / Procurement of Diagnostic Supplies | 25250000 | 17072211.7333 | 8177788.2667 | 3248788.2667 | 4929000
6. სასწრაფო-გადაუდებელი დახმარების ცენტრის აღჭურვილობა COVID19/G/RFQ-02 / | 6. COVID19/G/RFQ-02 / Procurement of Equipment for Emergency Control Center | 5300000 | 313476 | 4986524 | 1986524 | 3000000
7. ინტერნეტ-საკომუნიკაციო აღჭურვილობა / კომპიუტერული ტექნიკა საზ. ჯანდაცვის დაწესებულებებისთვის COVID19/G/RFQ-07 / | 7. COVID19/G/RFQ-07 / Procurement of ICT goods for public health facilities | 170000 | 0 | 170000 | 170000 | 0
8. ავტოსატრანსპორტო საშუალებები სამინისტროს შესაბამისი სააგენტოებისთვის COVID19/G/RFQ-04 / | 8. COVID19/G/RFQ-04 / Procurement of motor vehicles for Ministry | 780000 | 379240 | 400760 | 400760 | 0
9. პირველადი ჯანდაცვის აღჭურვილობა | 9. Equipment for Primary Care Facilities | 850000 | 388020 | 461980 | 461980 | 0
ჯამი | SUM | 49200000 | 19506585.3333 | 29693414.6667 | 6859416.6667 | 22833998
| WORKS | Cost estimate (USD) | ACTUALS (contracted) | Remaining funds after contracting | UNCOMITTED | Planned
| COVID19/CW/RFB-01 / Repair works of public health facilities | 1000000 | 0 | 1000000 | 704628 | 295372
| SUM | 1000000 | 0 | 1000000 | 704628 | 295372
| CONSULTANCY SERVICE | Cost estimate (USD) | ACTUALS (contracted) | Remaining funds | UNCOMITTED | Planned
|  | 300000 | 9375 | 290625 | 290625 | 0
|  | 300000 | 9375 | 290625 | 290625 | 0
| Quarantine, Preparedness, Cost of case | 20500000
Component 3. Project Management and Monitoring
| CONSULTANCY SERVICE Component III | Cost estimate (USD) | ACTUALS (contracted) | Remaining funds | UNCOMITTED | Planned
|  | 300000 | 160800 | 139200 | 139200 | 0
|  | 300000 | 160800 | 139200 | 139200 | 0
| SUM | 71300000 | 19676760.3333 | 31123239.6667

## GOODS I
Component 1. Emergency COVID-19 Response | Activity Reference No. / Description: | Estimate supplier | Type of procurement | Estimated Quantity /planned | Estimated Amount (US$)/planned/ | Singed contract/Suppliers Name | Contract N/ signed dated | Manufacturer’s Authorization /country of Origin | Applicable Incoterms / Consignee | Amendments | Delivery Date as defined by Incoterms | Quantity required Quantity and physical unit | Delivered Quantity | Unit price | Actual Total Price per Line item (Col. 7+8)
2.1 | 1.COVID19/G/DC-05 Procurement of Personal Protective Equipment |  |  |  | 5000000
1 | Goggles, protective |  | Direct |  |  | Commander Health Supply | Commander -001/ 10.07.2020 | China | CIP |  | within 30 days from date of issues of Preproduction Inspection Report | 54000 |  | 3.33 | 179820
| Disposable Surgical Masks |  | Direct |  |  | Sinoventure International Business and Managemnet company | COVID-G-DC-24, 02/10/2020 | China | CIP |  | within 60 days from date of issues of Preproduction Inspection Report | 3000000 |  | 0.203 | 618000
2 | GOWN Disposable |  | RFQ | 1300000 | 1950000
3 | RESPIRATOR, mask, FFP2/N95, type IIR, s.u., unvalued, nose clip/GLOVES | commander | Direct |  | 500000
4 | FACE SHIELD, clear plastic, disp. |  | Direct |  |  | ERTUNC OZCAN SAGLIK TESİSLERİ VE TIBBI CIHAZLAR INSAAT AS. | Ertunc Ozcan-001 02/10/2020 | turckey | CIP |  | Within 60 days from the date of issue of a pre-production test report | 40000 |  | 1.18 | 48400
5 | Boot covers with bio protection |  | RFQ | 300000 | 300000
6 | Disposable Shoe Covers |  | RFQ | 1000000 | 30000
7 | Headband |  | RFQ | 1000000 | 30000
8 | gloves |  | Direct | 4300000 | 600000 | [9 empty] | 0
9 | Mask | Sino Venture | Direct | 3000000 | 609000
TOTAL |  |  |  |  | 4019000 | [9 empty] | 846220
2.1 | 2. COVID19/G/DC-06 / Procurement of Hospital Equipment for four dedicated COVID-19 clinics: Rukhi Hospital, Batumi Hospital, Lisi Hospital and Infectious Disease Hospital |  |  |  | 8600000
| Second hand good (CT scanner) |  | Direct |  | 0 | LTD Ivermedi. | COVID19/G/DC-20 October 08, 2020 | Simens | DDP |  | Within one month after contract signature | 1 |  | 103980 | 103980 |  | 3.6372
| Rukhi Republic Hospital |  |  |  | 0 | [9 empty] | 0 |  | 3.0782
| Batumi |  |  |  | 0 | [9 empty] | 0
| Tbilisi Infectious Disease Hospital |  |  |  | 0 | [9 empty] | 0
| Chkhobadze medical center in Kutaisi |  |  |  | 0 | [9 empty] | 0
| ICU of the Infectious LG Hospital in Kutaisi |  |  |  | 0 | [9 empty] | 0
| Sachkhere Hospital |  |  |  | 0 | [9 empty] | 0
| COVID19/G/DC-02 / Procurement of Critical Care Ventilators and Related Services |  | Direct |  | 0 | MTECH LLC | 2020-05-21 | CHINA/Mindray | DDP | Ammendment N1 | 30th of August, 2020 | 30 |  | 13447.92 | 403437.6
| laboratories |  |  |  | 1000000 | [9 empty] | 0
| Dializis |  |  | 36 | 750000
| AGREEMENT FOR DELIVERY OF OUTPUTS (medical equipment and supplies) | UNOPS | Direct |  | 6185998 | UNOPS | August, 2020 |  |  |  | delivery schedules of the items/supplies will be determined in consultation with the parties
TOTAL |  |  |  |  | 7935998 | [9 empty] | 507417.6
2.1 | 3. COVID19/G/RFQ-03 / Procurement of Motorcycle for ambulance first responders with helmets |  | Limited |  | 1000000
| Motorcycle for ambulance first responders with helmets |  |  | 40 | 1000000 | [9 empty] | 0
TOTAL |  |  |  |  | 1000000 | [9 empty] | 0
2.1 | 4. COVID19/G/RFQ-01 / Procurement of fully equipped Ambulance car C type - Intensive Care Mobile Unit (30 Units) |  | Limited |  | 2250000
| Intensive Care Mobile Unit (30 Units) |  | RFQ | 30 | 1950000
TOTAL |  |  |  |  | 1950000 | [9 empty] | 0
1.1 | 5. COVID19/G/DC-07 / Procurement of Diagnostic Supplies |  | Direct |  | 25250000
| Rapid COVID-19 Test Cassette |  | Direct |  |  | JV Biogene LTD and Green Lab LTD | COVID19/G/DC-01 17/05/2020 | CHINA | CIP | Amendment N1 | Delivered | 97000 | Delivered | 5, 20 USD | 504400
|  |  | Direct |  |  |  |  | CHINA | CIP | Amendment N2 | Until August 5, 2020 | 100 000 | Delivered | 5, 20 USD | 520000
| Procurement of Standard COVID-19 Antigen Tests |  | Direct |  |  | SD BIOSENSOR | COVID19/G/DC-04 | Republic of Korea | CIP |  | Delivered | 50000 | Delivered |  | 612200
| COVID19/G/DC-09 / Procurement of Qiagen RNA Mini Kit |  | Direct |  |  | Prima Medi LTD | COVID19/G/DC-09 01/07/2020 | QIAGEN/Germany | DDP/ (NCDC) |  | Delivered | 250 Packs | Delivered | 4 200, 00 GEL | 338708
| Thermos Scientifics COVID-19 tests |  | Direct |  |  | ABM LTD | COVID19/G/DC-10 01/07/2020 | USA | DDP/ (NCDC) |  | 1st delivery 21.07 2020 2nd delivery 21.08.2020 3rd delivery 21.09.2020 4th delivery 21.10.2020 | 1800 | 1st delivery is delaying |  | 5685100
| Standard COVID-19 AG Test |  | Direct |  |  | SD BIOSENSOR | COVID19/G/DC-13 | Republic of Korea | CIP / (NCDC) |  | Within 1 week after payment of 40% on shipment , but not exceeding four (4) weeks of order placement. | 100000 |  | 9.1875 | 918750
| Xpert Xpress SARS-CoV-2 kit/10 tests |  | Direct |  |  | UNICEF | COVID19/G/UN-01 03/07/2020 | USA | CIP |  | October | 2000 packs | 2020-10-30 |  | 478240.4
| Nucleic Acid Diagnostic Kit 124 test |  | Direct |  |  | SANSURE BIOTECH INC | COVID19GDC-14 | CHINA | CIP / (NCDC) |  | within 30 business days after receiving the advance payment | 400000 |  |  | 4200000
| GeneMATRIX Viral RNA/DNA Purification Kit (100 detection |  | Direct |  |  | Bio Medi LLC | COVID19GDC-16 | EURX, Poland | CIP / (NCDC) |  | 100 kits can supply immediately . 400 kits in August. 500 kits in September. | 1000 paks |  | 298 | 356000
| COVID19/G/DC-08 / Procurement of In Vitro Diagnostic Medical Device (cobas) |  | Direct |  |  | Roche Diagnostics Turkey A.Ş. | COVID19/G/DC - 08 | Switzerland / CH | CIP |  |  | 1 |  |  | 493980
| Laboratory Supplies COVID19/G/RFQ-05 |  | RFQ | 400000 | 650000 | [9 empty] | 0
| EMEA Procleix SARS-CoV-2 Assay CE IVD Reagent Procleix Panther System | LUX MED LTD | Direct | 10000 | 253000 |  |  | GRIFOLS | DDP / (NCDC) |  | within 45 days |  |  |  | 0
| MATRIX Viral RNA/DNA Purification Kit |  | Direct |  |  | Prima Medi LTD | COVID19/G/DC-15/ 07/09/2020 | Germany |  |  | DDP Within one month after contract signature | 500 Packs, 125 000 extraction |  | 3 200 GEL | 533333.3333 | 1600000
| Tests for Cobas | Roche | Direct | 150000 | 4026000 | [9 empty] | 0
| Omni Gene oral from microbial DNA and RNA |  | Direct |  |  | DNA Genetic | COVID19/G/DC-18 September 29, 2020 |  | CIP |  | One month after contract signature | 50000 |  |  | 363000
| AG/AB rapid tests |  | Direct |  |  | Biosensor | COVID19/G/DC-20 September 16, 2020 | korea | CIP |  | Within two weeks after contract signature | 200000 |  |  | 2068500
| ტესტ-ნაკრები Logix Smart Coronavirus disease 2019 (COVID19) kit | შპს ირისე | Direct | 100000
| ტესტ-ნაკრები Fast Track Diagnostics | შპს ირისე | Direct | 100032
| ტესტ-ნაკრები BGI | შპს ემდიესი | Direct | 100000 | [10 empty] | 0
| TaqPath™ COVID-19 CE-IVD RT-PCR Kit | შპს ეიბიემ | Direct | 100000
| extraction |  | Direct | 150000 | [10 empty] | 0
TOTAL |  |  |  |  | 4929000 | [9 empty] | 17072211.7333
| 6. COVID19/G/RFQ-02 / Procurement of Equipment for Emergency Control Center |  | Open - National |  | 5300000
2 | COVID19/G/DC-03 / Procurement of Mobile Emergency Ventilators and Related Services |  | Direct |  | 0 | MDS LTD | 2020-05-20 | Hamilton Medical AG Switzerlan | Emergency situations coordination and urgent assistance center”. | Ammendment N1 July 16, 2020 | Period-1: From 16.06.2020 to 03.07.2020; Period-2: From 30.06.2020 to 17.07.2020; Period-3: From 12.08.2020 - to 30.08.2020.” | 20 |  |  | 313476
| Raciebi |  |  |  | 3000000 | [9 empty] | 0
TOTAL |  |  |  |  | 3000000 | [9 empty] | 313476
| 7. COVID19/G/RFQ-07 / Procurement of ICT goods for public health facilities |  | Open - National |  | 170000
Computers
Camera
Camera of the patient's salon
network
server
Tablets for ambulances
TOTAL |  |  |  |  | 0 | [9 empty] | 0
| 8. COVID19/G/RFQ-04 / Procurement of motor vehicles for Infectious Control Monitoring Center |  | Open - National |  | 780000
| 15 motor Motor Vehicles for Infectious Control Monitoring Center |  | RFQ |  |  | JV LLC KIA motors Georgia and LLC GI TI Motors | 30.09.2020 COVID19/G/RFQ-04 | South Korea/South aftica Kia /Ford | DDP |  | within 100 days | 15 Unit |  |  | 379240
TOTAL |  |  |  |  | 0 | [9 empty] | 379240
| 9. Equipment for Primary Care Facilities |  |  |  | 850000
1 | Furniture for Primary Healthcare Facilities |  | Direct |  |  | LLC Geo + | COVID19/G/DC-22 | LLC Geo + | DDP |  | 25 days from contact signature |  |  |  | 60000
2 | Equipment for Primary Healthcare Facilities |  | Direct |  |  | Tbilisi medic | COVID19/G/DC-23/ 28.09.2020 |  |  |  | 90 days from contact signature |  |  |  | 328020
[5 empty] | 0 | [9 empty] | 388020

## WORKS I
| Activity Reference No. / Description: | Estimate supplier | Type of procurement | Estimated Quantity /pland | Estimated Amount (US$)/pland/ | Contractors name | Contract N/ signed dated | Manufacturer’s Authorization /country of Origin | Applicable Incoterms / Consignee | Ammendments | Delivery Date as defined by Incoterms | Quantity required Quantity and physical unit | Unit price | Actual Total Price per Line item (Col. 7+8)
| COVID19/CW/RFB-01 / Repair works of public health facilities |  |  |  | 1000000
1 | Kutaisi Emergency Coordination and Emergency Assistance Center |  | RFB |  | 230000 | [8 empty] | 0
2 | O.Chkhobadze Disabled and Elderly Medical Rehabilitation Clinical Center |  | RFB |  | 65372 | [8 empty] | 0
3 | Tbilisi |  | RFB | [10 empty] | 0
[5 empty] | 295372 | [8 empty] | 0

## CS I
| Component 1. Emergency COVID-19 Response | Activity Reference No. / Description: | Estimate supplier | Type of procurement | Estimated Quantity /pland | Estimated Amount (US$)/pland/ | Consultant name | Contract N | signed dated | Manufacturer’s Authorization /country of Origin | Applicable Incoterms / Consignee | Ammendments | Delivery Date as defined by Incoterms | Quantity required Quantity and physical unit | Unit price | Actual Total Price per Line item (Col. 7+8)
300000
1 | COVID19/CS/CDS-02 / Technical Assistance for post crises COVID-19 strategy for Health Sector - Assistant Consultant | Consultant Services |  | Direct |  | 0 | Tinatin Manjavidze | COVID19/CS/CDS-02 / | 02.07.2020 |  |  |  | 25 working days |  |  | 6250 | 19100
2 | COVID19/CS/CDS-01 / Technical Assistance for post-crises COVID-19 strategy for Health Sector - Lead Consultant | Consultant Services |  | Direct |  | 0 | Natia Skhvitaridze | COVID19/CS/CDS-01 / | 02.07.2020 |  |  |  | 25 working days |  |  | 3125 | 9550
| TOTAL |  |  |  |  | 0 | [9 empty] | 9375

## CS COMP.III
| Activity Reference No. / Description: | Estimate supplier | Type of procurement | Estimated Amount (US$)/pland/ | Conultant name | Contract N | signed dated | Duration monthe/day | Ammendments | Delivery Date | Actual Total Price per Line item (Col. 7+8)
PIU |  |  |  | 300000
COVID19/CS/INDV-01 / Procurement Manager | Project Management |  | Direct |  | Nino Kvernadze | Covid19/CS/INDV-01 | 16.06.2020 | 16.06.2021 |  |  | 36000
COVID19/CS/INDV-05 / Social Standards Specialist | Enviromental Standards Consultant |  | Direct |  | Giorgi Kobaladze | Covid19/CS/INDV-06 | 16.06.2020 | 110 working days |  |  | 19200
COVID19/CS/INDV-02 / Financial Manager | Financial manager |  | Direct |  | Natalie Godziashvili | Covid19/CS/INDV-02 | 24.06.2020 | 24.06.2021 |  |  | 30000
COVID19/CS/INDV-06 / Environmental Standards Specialist | Social Standarts Specialist/Consultamt |  | Direct |  | Nino patarashvili | Covid19/CS/INDV-05 | 25.06.2020 | 150 working days |  |  | 19200
COVID19/CS/INDV-04 / Health Specialist | Health specialist |  | Direct |  | Lia tavadze | Covid19/CS/INDV-04 | 16.06.2020 | 16.06.2021 |  |  | 30000
COVID19/CS/INDV-03 / Procurement Specialist | Procurement specialist |  | Direct |  | Nino Gvenetadze | Covid19/CS/INDV-03 | 16.06.2020 | 16.06.2021 |  |  | 26400
Translator | Interpreter |  | Direct |  | lela Dzidzikuri | Covid19/CS/INDV-07 | 27.07.2020 | 3 working month |  |  | 1000
|  |  |  | 0 | [6 empty] | 160800

## signed contracts
Component 1. Emergency COVID-19 Response | Activity Reference No. / Description: | Type of procurement | Singed contract/Suppliers Name | Contract | Contrac signed dated | Manufacturer’s Authorization /country of Origin | Applicable Incoterms / Consignee | Delivery Date as defined by Incoterms | Quantity required Quantity and physical unit | Delivered Quantity | Unit price | Actual Total Price per Line item (Col. 7+8)
1 | Project Management |  | Nino Kvernadze | Covid19/CS/INDV-01 | 16.06.2020 | Georgia |  | 16.06.2021 |  |  |  | 36000
2 | Enviromental Standards Consultant |  | Giorgi Kobaladze | Covid19/CS/INDV-06 | 16.06.2020 | Georgia |  | 110 working days |  |  |  | 19200
3 | Financial manager |  | Natalie Godziashvili | Covid19/CS/INDV-02 | 24.06.2020 | Georgia |  | 24.06.2021 |  |  |  | 30000
4 | Social Standarts Specialist/Consultamt |  | Nino patarashvili | Covid19/CS/INDV-05 | 25.06.2020 | Georgia |  | 150 working days |  |  |  | 19200
5 | Health specialist |  | Lia tavadze | Covid19/CS/INDV-04 | 16.06.2020 | Georgia |  | 16.06.2021 |  |  |  | 30000
6 | Procurement specialist |  | Nino Gvenetadze | Covid19/CS/INDV-03 | 16.06.2020 | Georgia |  | 16.06.2021 |  |  |  | 26400
7 | Interpreter |  | lela Dzidzikuri | Covid19/CS/INDV-07 | 27.07.2020 | Georgia |  | 3 working month |  |  |  | 1000
1 | Goggles, protective | Direct | Commander Health Supply | Commander -001 | 10.07.2020 | China | CIP | within 30 days from date of issues of Preproduction Inspection Report | 54000 |  | 3.33 | 179820
2 | COVID19/G/DC-02 / Procurement of Critical Care Ventilators and Related Services | Direct | MTECH LLC | COVID19/G/DC-02 | 21.05.2020 | CHINA/Mindray | DDP | 30th of August, 2020 | 30 |  | 13447.92 | 403437.6
3 | Rapid COVID-19 Test Cassette | Direct | JV Biogene LTD and Green Lab LTD | COVID19/G/DC-01 | 17.05.2020 | CHINA | CIP | Delivered/ Until August 5, 2020 | 197000 | Delivered | 5, 20 USD | 1024400
4 | Procurement of Standard COVID-19 Antigen Tests | Direct | SD BIOSENSOR | COVID19/G/DC-04 | 18.06.2020 | Republic of Korea | CIP | Delivered | 50000 | Delivered |  | 612200
5 | COVID19/G/DC-09 / Procurement of Qiagen RNA Mini Kit (250) | Direct | Prima Medi LTD | COVID19/G/DC-09 | 01.07.2020 | QIAGEN/Germany | DDP | Delivered | 250 Packs | Delivered | 4 200, 00 GEL | 338708
6 | Thermos Scientifics COVID-19 tests | Direct | ABM LTD | COVID19/G/DC-10 | 01.07.2020 | USA | DDP | 1st delivery 21.07 2020 2nd delivery 21.08.2020 3rd delivery 21.09.2020 4th delivery 21.10.2020 | 250000 | 1st delivery is delaying |  | 5685100
7 | Standard COVID-19 AG Test | Direct | SD BIOSENSOR | COVID19/G/DC-13 | 03.08.2020 | Republic of Korea | CIP | Within 1 week after payment of 40% on shipment , but not exceeding four (4) weeks of order placement. | 100000 |  | 9.1875 | 918750
8 | Xpert Xpress SARS-CoV-2 kit/10 tests | Direct | UNICEF | COVID19/G/UN-01 | 03.07.2020 | USA | CIP | October | 2000 packs | 2020-10-30 |  | 478240.4
9 | Nucleic Acid Diagnostic Kit 124 test | Direct | SANSURE BIOTECH INC | COVID19GDC-14 | 22.07.2020 | CHINA | CIP | within 30 business days after receiving the advance payment | 400000 |  |  | 4200000
10 | GeneMATRIX Viral RNA/DNA Purification Kit (100 detection | Direct | Bio Medi LLC | COVID19GDC-16 | 20.08.2020 | EURX, Poland | CIP | 100 kits can supply immediately . 400 kits in August. 500 kits in September. | 100000 |  | 298 | 356000
11 | COVID19/G/DC-08 / Procurement of In Vitro Diagnostic Medical Device (cobas) | Direct | Roche Diagnostics Turkey A.Ş. | COVID19/G/DC - 08 | 02.09.2020 | Switzerland / CH | CIP | 2021 March | 1 |  |  | 493980
12 | MATRIX Viral RNA/DNA Purification Kit | Direct | Prima Medi LTD | COVID19/G/DC-15/ | 07.09.2020 | Germany | CIP | DDP Within one month after contract signature | 500 Packs, 125 000 extraction |  | 3 200 GEL | 1600000 | 500000
13 | Procurement of Mobile Emergency Ventilators and Related Services | Direct | MDS LTD | COVID19/G/DC-03 / | 20.05.2020 | Hamilton Medical AG Switzerlan | DDP | Period-1: From 16.06.2020 to 03.07.2020; Period-2: From 30.06.2020 to 17.07.2020; Period-3: From 12.08.2020 - to 30.08.2020.” | 20 |  |  | 313476
14 | Furniture for Primary Healthcare Facilities | Direct | LLC Geo + | COVID19/G/DC-22 | 16.09.2020 | LLC Geo + | DDP | 25 days |  |  |  | 60000
15 | Disposable Surgical Masks | Direct | Sinoventure International Business and Managemnet company | COVID-G-DC-24 | 02.10.2020 | Sinoventure International Business and Managemnet company | CIP | within 60 days from date of issues of Preproduction Inspection Report | 3000000 |  | 0.203 | 618000
16 | FACE SHIELD, clear plastic, disp. | Direct | ERTUNC OZCAN SAGLIK TESİSLERİ VE TIBBI CIHAZLAR INSAAT AS. | Ertunc Ozcan-001 02/10/2020 | 02.10.2020 | Ertunc Ozcan/turckey | CIP | Within 60 days from the date of issue of a pre-production test report | 40000 |  | 1.18 | 48400
17 | Second hand good (CT scanner) | Direct | LTD Ivermedi. | COVID19/G/DC-20 | 08.10.2020 | Simens | DDP | Within one month after contract signature | 1 |  | 103980 | 103980
18 | Omni Gene oral from microbial DNA and RNA | Direct | DNA Genetic | COVID19/G/DC-18 September 29, 2020 | 18.09.2020 | Canada/DNA Genetic | CIP | One month after contract signature | 50000 |  |  | 363000
19 | AG/AB rapid tests | Direct | Biosensor | COVID19/G/DC-20 September 16, 2020 | 20.09.2020 | Biosensor/korea | CIP | Within two weeks after contract signature | 200000 |  |  | 2068500
20 | 15 motor Motor Vehicles for Infectious Control Monitoring Center | RFQ | JV LLC KIA motors Georgia and LLC GI TI Motors | COVID19/G/RFQ-04 | 30.09.2020 | South Korea/South aftica Kia /Ford | DDP | within 100 days | 15 Unit |  |  | 379240
21 | Equipment for Primary Healthcare Facilities | Direct | Tbilisi medic | COVID19/G/DC-23/ | 28.09.2020 | Various | DDP | 90 days from contact signature | 36 types |  | Various | 328020
29 | Technical Assistance for post crises COVID-19 strategy for Health Sector - Assistant Consultant | Direct | Tinatin Manjavidze | COVID19/CS/CDS-02 / | 02.07.2020 | Georgia |  | 25 working days |  |  |  | 6250
30 | COVID19/CS/CDS-01 / Technical Assistance for post-crises COVID-19 strategy for Health Sector - Lead Consultant | Direct | Natia Skhvitaridze | COVID19/CS/CDS-01 / | 02.07.2020 | Georgia |  | 25 working days |  |  |  | 3125