| “Emergency Covid-19 Response Project” (IBRD WB 9113-GE, AIIB LO388A) Signature Date – May 1, 2020 Effectiveness date May 28, 2020 Document: On Project Dated Covenants |  |  |
| --- | --- | --- |
| Type of the Document | Original Dates | Proposed revised timelines and deadlines |
| POM | Project Operations Manual (POM) to be adopted within 30 days after the signing date. Deadline: May 31, 2020 | Proposed revised timeline: No later than hundred and twenty (120) days after the Signature Date Proposed revised deadline: August 31, 2020 |
| Global budget reimbursement manual | The Borrower, through MoILHSA and the Ministry of Finance, shall prepare and adopt no later than thirty (30) days after the Signature Date, a manual for budget and reimbursements (“Global Budget and Reimbursements Manual”) Deadline: May 31, 2020 | Proposed revised timeline: No later than hundred and twenty (120) days after the Signature Date Proposed revised deadline: August 31, 2020 |
| Environmental and Social Commitment Plan (ESCP) | Deadline: June 28, 2020 | Proposed revised timeline: No later than hundred and twenty (120) days after the Signature Date Proposed revised deadline: August 31, 2020 |
| Stakeholder Engagement Plan (SEP) | Deadline: June 28, 2020 | Proposed revised timeline: No later than hundred and twenty (120) days after the Signature Date Proposed revised deadline: August 31, 2020 |
| Environmental and Social Management Framework (ESMF) and the Labor management Procedures (LMP) | Deadline: June 28, 2020 | Proposed revised timeline: No later than hundred and twenty (120) days after the Signature Date Proposed revised deadline: August 31, 2020 |
| Covenant on data protection | The Borrower shall no later than sixty (60) days after the Signature Date, provide the Bank a proposed plan (“Plan of Action”) Deadline: June 30, 2020 | Proposed revised timelines: - Action Plan - no later than hundred and twenty (120) days after the Signature Date - Adoption of the Action Plan - no later than hundred and fifty (150) days after the Signature Date adopt the Plan of Action Proposed revised deadlines: - Action Plan - no later than August 31, 2020 - Adoption of the Action Plan – September 30 |