## TOTAL
| PP 15.01.2021 | Cost estimate (USD) | Outstanding amount (USD) | ACTUALS (USD)
| Component 1. Emergency COVID-19 Response and Component 3. Project Management and Monitoring | 65650000 | 19862170.4635 | 45787829.5365
Component 1. Emergency COVID-19 Response | საქონელი | სავარაუდო ხარჯი (USD) | გაფორმებული კონტრაქტები | რესურსი | დარჩენილი თანხა მომავალი / სავარაუდო კონტრაქტები | უკვე დაგეგმილი კონტრაქტები | თანმდევი მომსახურება
საქონელი | GOODS | Cost estimate (USD) | ACTUALS (contracted) | Remaining funds after contracting | UNCOMITTED | Planned | CIP Contract related services (customs clearence, tranposrtation)
1. პერსონალური დაცვის საშუალებები COVID19/G/DC-05 | 1. Procurement of Personal Protective Equipment | 5000000 | 1649120 | 3350880 | 630880 | 2720000
2. კოვიდ-19 საპასუხო ღონისძიებებში ჩართული ჰოსპიტლებისთვის აღჭურვილობის შეძენა (რუხი, ბათუმი, თბ. ინფექციური, თბ. საუნივერსიტეტო, ქუთ. რეგიონული, LG, და საჩხერის რეგ. დაწესებულებები) | 2. Procurement of Hospital Equipment for dedicated COVID-19 clinics: Rukhi, Batumi, Tbilisi Infectious, Tbilisi University, Kutaisi Regional, and Sachkhere Regional | 11363500 | 9913136.6 | 1450363.4 | 1450363.4 | 0
3. პირველადი გადაუდებელი საპასუხო ღონისძიებებისთვის მოტოციკლები (სრული კომპლექტაცია) | 3. Procurement of Motorcycle for ambulance first responders with helmets | 1000000 | 0 | 1000000 | 0 | 1000000
4. ცე და ბე ტიპის (ინტენსიური დახმარების) მობილური ჯგუფებისთვის მნქანები და აღჭურვილობა (სრული კომპლექტაცია) 38 ცალი | 4. Procurement of fully equipped Ambulance car C and B type - Intensive Care Mobile Unit (38 Units) | 2650000 | 2605314.6 | 44685.4 | 44685.4 | 0
5. სადიაგნოსტიკო მასალები | 5. Procurement of Diagnostic Supplies | 37250000 | 27820634.6795 | 9429365.3205 | 4367365.3205 | 5062000
6. სასწრაფო-გადაუდებელი დახმარების ცენტრის აღჭურვილობა | 6. Procurement of Equipment for Emergency Control Center | 4620000 | 2365476 | 2254524 | 254524 | 2000000 | 254524
7. ინტერნეტ-საკომუნიკაციო აღჭურვილობა / კომპიუტერული ტექნიკა საზ. ჯანდაცვის დაწესებულებებისთვის | 7. Procurement of ICT goods for public health facilities | 800000 | 254231.8223 | 545768.1777 | 26768.1777 | 519000
8. ავტოსატრანსპორტო საშუალებები სამინისტროს შესაბამისი სააგენტოებისთვის | 8. Procurement of motor vehicles for Ministry | 780000 | 379240 | 400760 | 760 | 400000
9. პირველადი ჯანდაცვის აღჭურვილობა | 9. Equipment for Primary Care Facilities | 386500 | 386496 | 4 | 4 | 0
ჯამი | SUM | 63850000 | 45373649.7018 | 18476350.2982 | 6775350.2982 | 11701000
| WORKS | Cost estimate (USD) | ACTUALS (contracted) | Remaining funds after contracting | UNCOMITTED | Planned
| COVID19/CW/RFB-01 / Repair works of public health facilities | 1000000 | 0 | 1000000 | 704628 | 295372
| SUM | 1000000 | 0 | 1000000 | 704628 | 295372
| CONSULTANCY SERVICES | Cost estimate (USD) | ACTUALS (contracted) | Remaining funds | UNCOMITTED | Planned
|  | 500000 | 246575 | 253425 | 253425 | 0
|  | 500000 | 246575 | 253425 | 253425 | 0
| Quarantine, Preparedness, Cost of case | 5500000
Component 3. Project Management and Monitoring
| CONSULTANCY SERVICE Component III | Cost estimate (USD) | ACTUALS (contracted) | Remaining funds | UNCOMITTED | Planned
|  | 300000 | 167604.8347 | 132395.1653 | 132395.1653 | 0
|  | 300000 | 167604.8347 | 132395.1653 | 132395.1653 | 0
| SUM | 71150000 | 45787829.5365 | 19862170.4635

## GOODS I
Component 1. Emergency COVID-19 Response | Activity Reference No. / Description: | Estimate supplier | Type of procurement | Estimated Quantity /planned | Estimated Amount (US$)/planned/ | Singed contract/Suppliers Name | Contract N/ signed dated | Manufacturer’s Authorization /country of Origin | Applicable Incoterms / Consignee | Amendments | Delivery Date as defined by Incoterms | Quantity required Quantity and physical unit | Delivered Quantity | Unit price | Actual Total Price per Line item (Col. 7+8)
| 1.COVID19/G/DC-05 Procurement of Personal Protective Equipment |  |  |  | 5000000
1 | Goggles, protective |  | Direct |  |  | Commander Health Supply | Commander -001/ 10.07.2020 | China | CIP |  | within 30 days from date of issues of Preproduction Inspection Report | 54000 |  | 3.33 | 179820
2 | Disposable Surgical Masks |  | Direct |  |  | Sinoventure International Business and Managemnet company | COVID-G-DC-24, 02/10/2020 | China | CIP |  | within 60 days from date of issues of Preproduction Inspection Report | 3000000 |  | 0.203 | 618000
4 | Gloves, examination, non-sterile/Mask, respirator, KN95 |  | Direct |  |  | Commander Health Supply | Commander-007/05.11,2020 | Malayzia/China | CIP |  | 45 days from the date of issue of a pre-production test | 4 300 000gloves /230,000 mask |  | US $ 0.12 /US $ 1.13 mask | 802900
5 | FACE SHIELD, clear plastic, disp. |  | Direct |  |  | ERTUNC OZCAN SAGLIK TESİSLERİ VE TIBBI CIHAZLAR INSAAT AS. | Ertunc Ozcan-001 02/10/2020 | turckey | CIP |  | Within 60 days from the date of issue of a pre-production test report | 40000 |  | 1.18 | 48400
3 | GOWN Disposable |  | RFQ | 1600000 | 2400000 | ongoing
6 | Boot covers with bio protection |  | RFQ | 100000 | 120000 | ongoing
7 | Boot covers |  | RFQ | 1000000 | 100000 | ongoing
8 | medical coveralls |  | RFQ | 1000000 | 100000 | ongoing
TOTAL |  |  |  |  | 2720000 | [9 empty] | 1649120
| 2. COVID19/G/DC-06 / Procurement of Hospital Equipment for four dedicated COVID-19 clinics: Rukhi Hospital, Batumi Hospital, Lisi Hospital and Infectious Disease Hospital |  |  |  | 11363500
1 | Second hand good (CT scanner) |  | Direct |  |  | LTD Ivermedi. | COVID19/G/DC-20 October 08, 2020 | Simens | DDP |  | Within one month after contract signature | 1 |  | 103980 | 103980 |  | 3.6372
2 | COVID19/G/DC-02 / Procurement of Critical Care Ventilators and Related Services |  | Direct |  |  | MTECH LLC | 43972 | CHINA/Mindray | DDP | Ammendment N1 | 30th of August, 2020 | 30 |  | 13447.92 | 403437.6
3 | AGREEMENT FOR DELIVERY OF OUTPUTS (medical equipment and supplies) |  | Direct |  |  | UNOPS | August, 2020 |  |  |  | delivery schedules of the items/supplies will be determined in consultation with the parties |  |  |  | 6185998
4 | Oxygen concentrators |  | Direct |  |  | LTD KPI-Georgia (ID 400010796 ) | COVID19/G/DC-31/ 24.11.2020 | People’s republic of China | DDP |  | Estimate Delivery date 2 December, 2020. Maximum delivery date no later than 20 December, 2020 | 1000 |  |  | 710000
5 | Dialysis equipment for Georgian hospitals |  | Direct |  |  | Hospimed Georgia” LLC (ID 206335704) | COVID19-G-DC-27 /23.10.2020 | Germany Hungury | DDP |  | 50-51 weeks from contract signature | 36 |  |  | 585748.8
6 | CPAP Masks, BPAP and HFNC devices |  | Direct |  |  | LTD KPI-Georgia (ID 400010796 ) | COVID19/G/DC-33 |  | DDP |  | Within 10 days after contract signature | CPAP - 18000 BPAP 500+300 HFNC -50 |  |  | 1702803
7 | Laboratory equipment for Batumi and Rukhi Hospitals |  | Direct |  |  | MTECH LLC (ID 202443230 ) | COVID19/G/DC-30/07.12.2020 | various | DDP |  | Within 30 days after contract signature |  |  |  | 221169.2
TOTAL |  |  |  |  | 0 | [9 empty] | 9913136.6
| 3. COVID19/G/RFQ-03 / Procurement of Motorcycle for ambulance first responders with helmets |  | Limited |  | 1000000
1 | Motorcycle for ambulance first responders with helmets |  |  | 40 | 1000000 | ongoing | [8 empty] | 0
TOTAL |  |  |  |  | 1000000 | [9 empty] | 0
| 4. COVID19/G/RFQ-01 / Procurement of fully equipped Ambulance car C and B type - Intensive Care Mobile Unit (38 Units) |  | Limited |  | 2650000
1 | COVID19/G/RFQ-01 / Procurement of fully equipped Ambulance car C and B type - Intensive Care Mobile Unit (38 Units) |  | RFQ |  |  | AKA LLC (204875082) | COVID19-G-RFB-01 | Mercedes-Benz AG /Emergency mobile systems A.S | DDP |  | 180 days from contract signature | 38 |  |  | 2605314.6 | 2189340
TOTAL |  |  |  |  | 0 | [9 empty] | 2605314.6
| 5. COVID19/G/DC-07 / Procurement of Diagnostic Supplies |  | Direct |  | 37250000
1 | Rapid COVID-19 Test Cassette |  | Direct |  |  | JV Biogene LTD and Green Lab LTD | COVID19/G/DC-01 17/05/2020 | CHINA | CIP | Amendment N1 | Delivered | 97000 | Delivered | 5, 20 USD | 504400
|  |  | Direct |  |  |  |  | CHINA | CIP | Amendment N2 | Until August 5, 2020 | 100 000 | Delivered | 5, 20 USD | 520000
2 | Procurement of Standard COVID-19 Antigen Tests |  | Direct |  |  | SD BIOSENSOR | COVID19/G/DC-04 | Republic of Korea | CIP |  | Delivered | 50000 | Delivered |  | 612200
3 | COVID19/G/DC-09 / Procurement of Qiagen RNA Mini Kit |  | Direct |  |  | Prima Medi LTD | COVID19/G/DC-09 01/07/2020 | QIAGEN/Germany | DDP/ (NCDC) |  | Delivered | 250 Packs | Delivered | 4 200, 00 GEL | 338708
4 | Thermos Scientifics COVID-19 tests |  | Direct |  |  | ABM LTD | COVID19/G/DC-10 01/07/2020 | USA | DDP/ (NCDC) |  | 1st delivery 21.07 2020 2nd delivery 21.08.2020 3rd delivery 21.09.2020 4th delivery 21.10.2020 | 1800 | 1st delivery is delaying |  | 5685100
5 | Standard COVID-19 AG Test |  | Direct |  |  | SD BIOSENSOR | COVID19/G/DC-13 | Republic of Korea | CIP / (NCDC) |  | Within 1 week after payment of 40% on shipment , but not exceeding four (4) weeks of order placement. | 100000 |  | 9.1875 | 918750
6 | Xpert Xpress SARS-CoV-2 kit/10 tests |  | Direct |  |  | UNICEF | COVID19/G/UN-01 03/07/2020 | USA | CIP |  | October | 2000 packs | 44134 |  | 478240.4
7 | Nucleic Acid Diagnostic Kit 124 test |  | Direct |  |  | SANSURE BIOTECH INC | COVID19GDC-14 | CHINA | CIP / (NCDC) |  | within 30 business days after receiving the advance payment | 400000 |  |  | 4200000
8 | GeneMATRIX Viral RNA/DNA Purification Kit (100 detection |  | Direct |  |  | Bio Medi LLC | COVID19GDC-16 | EURX, Poland | CIP / (NCDC) | Amendment N1 |  | 200000 |  | 2.89 | 705160
9 | COVID19/G/DC-08 / Procurement of In Vitro Diagnostic Medical Device (cobas) |  | Direct |  |  | Roche Diagnostics Turkey A.Ş. | COVID19/G/DC - 08 | Switzerland / CH | CIP |  |  | 1 |  |  | 536800
10 | PCR tests for Procleix Panther System for Automated NAT (Grifols) device (10000 kit) |  | Direct |  |  | Lux Med LTD (ID 400130050) | COVID19/G/DC-17 | GRIFOLS | DDP / (NCDC) |  | within 45 days | 240000 |  |  | 654896
11 | MATRIX Viral RNA/DNA Purification Kit |  | Direct |  |  | Prima Medi LTD | COVID19/G/DC-15/ 07/09/2020 | Germany |  |  | DDP Within one month after contract signature | 125 000 |  |  | 519480.5195 | 1600000
12 | KIT COBAS 6800/8800 SARS-COV-2 192T (with consumables for 150 000 tests) |  | Direct |  |  | MIRKO LLC (ID 204996772) | COVID19/G/DC-1221.10.2020 | USA | DDP |  | 3000 tests per week | 150000 |  |  | 4391399.76
13 | Omni Gene oral from microbial DNA and RNA |  | Direct |  |  | DNA Genetic | COVID19/G/DC-18 September 29, 2020 |  | CIP |  | One month after contract signature | 50000 |  |  | 363000
14 | AG/AB rapid tests |  | Direct |  |  | SD BIOSENSOR | COVID19/G/DC-20 September 16, 2020 | korea | CIP |  | Within two weeks after contract signature | 200000 |  |  | 2068500
15 | STANDARD Q COVID-19 Ag test |  | Direct |  |  | SD BIOSENSOR | COVID19/G/DC-28 | korea | CIP |  | two weeks from contract signature | 500000 |  |  | 2662000
16 | STANDARD Q COVID-19 Ag test |  | Direct |  |  | SD BIOSENSOR | COVID19/G/DC-32 | korea | CIP |  | One month after contract signature | 500000 |  |  | 2662000
17 | TaqPath™ COVID-19 CE-IVD RT-PCR tests and KingFisher FLEX extraction kits |  | Direct | 150000 | 1800000 | ongoing
18 | STANDARD Q COVID-19 Ag test |  | Direct | 500000 | 2662000 | ongoing
19 | COVID19/G/DC-09 / Procurement of Qiagen RNA Mini Kit |  | Direct | 200000 | 600000 | ongoing
TOTAL |  |  |  |  | 5062000 | [9 empty] | 27820634.6795
| 6. COVID19/G/RFQ-02 / Procurement of Equipment for Emergency Control Center |  | Open - National |  | 4620000
1 | COVID19/G/DC-03 / Procurement of Mobile Emergency Ventilators and Related Services |  | Direct |  |  | MDS LTD | 43971 | Hamilton Medical AG Switzerlan | Emergency situations coordination and urgent assistance center”. | Ammendment N1 July 16, 2020 | Period-1: From 16.06.2020 to 03.07.2020; Period-2: From 30.06.2020 to 17.07.2020; Period-3: From 12.08.2020 - to 30.08.2020.” | 20 |  |  | 313476
2 | Tetra equipment with related services |  | Direct |  |  | Motorola Solutions Germany | COVID19/G/DC-26/06.10.2020 | Motorola Solutions Germany | CIP |  | 24 weeks - 44 weeks from contract signature |  |  |  | 2052000 | 1900000
3 | Medical Equipment for Emergency Services |  | RFQ |  | 2000000 | ongoing | [8 empty] | 0
TOTAL |  |  |  |  | 2000000 | [9 empty] | 2365476
| 7. COVID19/G/RFQ-07 / Procurement of ICT goods for public health facilities |  | Open - National |  | 800000
1 | Supply and Installation of Network Infrastructure |  |  | 1 |  | Green Systems LLC, (ID 404862190) | COVID19/G/RFQ-09 | Cisco International Limited | DDP |  | 90 day from contract signature | 1 |  |  | 81769.3946
2 | Supply and Installation of Server Infrastructure |  |  | 1 |  | UGT LLC, (ID 204892964) | COVID19-G-RFQ-11 | Georgia | DDP |  | 90 day from contract signature | 1 |  |  | 172462.4277
3 | Computers |  |  | 10 | 30000 | ongoing
4 | Headphone |  |  | 100 | 15000 | ongoing
5 | Recording camera for ambulance patient cabinet |  |  | 360 | 108000 | ongoing
6 | Body worn camera for ambulance group |  |  | 100 | 56000 | ongoing
7 | Tablet for Ambulance Emergency Medical Care Car |  |  | 350 | 280000 | ongoing
8 | Computers |  |  | 21 | 30000 | ongoing
TOTAL |  |  |  |  | 519000 | [9 empty] | 254231.8223
| 8. Procurement of motor vehicles for Infectious Control Monitoring Center |  | Open - National |  | 780000
1 | 15 motor Motor Vehicles for Agency for Regulation of Medical and Pharmaceutical Activities |  | RFQ |  |  | JV LLC KIA motors Georgia and LLC GI TI Motors | 30.09.2020 COVID19/G/RFQ-04 | South Korea/South aftica Kia /Ford | DDP |  | within 100 days | 15 Unit |  |  | 379240
2 | 15 motor Motor Vehicles GES |  | RFQ | 15 | 400000 | ongoing
TOTAL |  |  |  |  | 400000 | [9 empty] | 379240
| 9. Equipment for Primary Care Facilities |  |  |  | 386500
1 | Furniture for Primary Healthcare Facilities |  | Direct |  |  | LLC Geo + | COVID19/G/DC-22 | LLC Geo + | DDP |  | 25 days from contact signature |  |  |  | 58476
2 | Equipment for Primary Healthcare Facilities |  | Direct |  |  | Tbilisi medic | COVID19/G/DC-23/ 28.09.2020 | various | DDP |  | 90 days from contact signature |  |  |  | 328020
[5 empty] | 0 | [9 empty] | 386496

## WORKS I
| Activity Reference No. / Description: | Estimate supplier | Type of procurement | Estimated Quantity /pland | Estimated Amount (US$)/pland/ | Contractors name | Contract N/ signed dated | Manufacturer’s Authorization /country of Origin | Applicable Incoterms / Consignee | Ammendments | Delivery Date as defined by Incoterms | Quantity required Quantity and physical unit | Unit price | Actual Total Price per Line item (Col. 7+8)
| COVID19/CW/RFB-01 / Repair works of public health facilities |  |  |  | 1000000
1 | Kutaisi Emergency Coordination and Emergency Assistance Center |  | RFB |  | 230000 | [8 empty] | 0
2 | O.Chkhobadze Disabled and Elderly Medical Rehabilitation Clinical Center |  | RFB |  | 65372 | [8 empty] | 0
3 | Tbilisi |  | RFB | [10 empty] | 0
[5 empty] | 295372 | [8 empty] | 0

## CS I
| Component 1. Emergency COVID-19 Response | Activity Reference No. / Description: | Type of procurement | Estimated Amount (US$)/pland/ | Consultant name | Contract N | signed dated | Manufacturer’s Authorization /country of Origin | Ammendments | Delivery Date as defined by Incoterms | Actual Total Price per Line item (Col. 7+8)
500000
1 | COVID19/CS/CDS-02 / Technical Assistance for post crises COVID-19 strategy for Health Sector - Assistant Consultant | Consultant Services | Direct | 0 | Tinatin Manjavidze | COVID19/CS/CDS-02 / | 02.07.2020 |  |  | 25 working days | 6250
2 | COVID19/CS/CDS-01 / Technical Assistance for post-crises COVID-19 strategy for Health Sector - Lead Consultant | Consultant Services | Direct | 0 | Natia Skhvitaridze | COVID19/CS/CDS-01 / | 02.07.2020 |  |  | 25 working days | 3125
3 | STOP COVID MOBILE APPLICATION | Consultant Services | Direct | 0 | Grabner & Gretzmacher MDL GmbH | COVID19-CS-RFP-01 | 28.10.2020 |  |  | 3 month | 90000 | `
4 | DEVELOP COVID-19 SELF-ISOLATION IT PLATFORM | Consultant Services | Direct | 0 | LLC Business Process Management Group | COVID19-CS-RFP-02 | 10.11.2020 |  |  | Time one month from the contact signature. | 47200
5 | Design review and supervision | Consultant Services | QBS |  | ongoing | COVID19-CS-RFP-03 |  |  |  |  | 50000
6 | AUDIT | Consultant Services | LCS |  | ongoing | COVID19-CS-RFP-04 |  |  |  |  | 50000
| TOTAL |  |  | 0 | [6 empty] | 246575

## CS COMP.III
| Activity Reference No. / Description: | Estimate supplier | Type of procurement | Estimated Amount (US$)/pland/ | Conultant name | Contract N | signed dated | initial Duration monthe/day | Ammendments | Time extention | Actual Total Price per Line item (Col. 7+8)
PIU |  |  |  | 300000
COVID19/CS/INDV-01 / Procurement Manager | Project Management |  | Direct |  | Nino Kvernadze | Covid19/CS/INDV-01 | 16.06.2020 | 16.06.2021 |  |  | 36000
COVID19/CS/INDV-05 / Social Standards Specialist | Enviromental Standards Consultant |  | Direct |  | Giorgi Kobaladze | Covid19/CS/INDV-06 | 16.06.2020 | 110 working days |  |  | 19200
COVID19/CS/INDV-02 / Financial Manager | Financial manager |  | Direct |  | Natalie Godziashvili | Covid19/CS/INDV-02 | 24.06.2020 | 24.06.2021 |  |  | 30000
COVID19/CS/INDV-06 / Environmental Standards Specialist | Social Standarts Specialist/Consultamt |  | Direct |  | Nino patarashvili | Covid19/CS/INDV-05 | 25.06.2020 | 150 working days |  |  | 19200
COVID19/CS/INDV-04 / Health Specialist | Health specialist |  | Direct |  | Lia tavadze | Covid19/CS/INDV-04 | 16.06.2020 | 16.06.2021 |  |  | 30000
COVID19/CS/INDV-03 / Procurement Specialist | Procurement specialist |  | Direct |  | Nino Gvenetadze | Covid19/CS/INDV-03 | 16.06.2020 | 16.06.2021 |  |  | 26400
Translator | Interpreter |  | Direct |  | lela Dzidzikuri | Covid19/CS/INDV-07 | 27.07.2020 | 3 working month | Ammendment N1 time extention | 3working month | 1000
| Oris-Accounting Software |  | Direct |  | ORIS LLC | COVID19/G/DC-29 | 18.11.2020 | one week from contract siganture |  |  | 1217.5385
| Terminal services |  | Direct |  | lazare LLC | COVID19/G/DC-34 | 28.12.2020 | 31.12.2021 |  |  | 4587.2962
|  |  |  | 0 | [6 empty] | 167604.8347

## signed contracts
Component 1. Emergency COVID-19 Response | Activity Reference No. / Description: | Type of procurement | Singed contract/Suppliers Name | Contract | Contrac signed dated | Contract Award Notice Bank/MOH | Manufacturer’s Authorization /country of Origin | Applicable Incoterms / Consignee | Delivery Date as defined by Incoterms | Quantity required Quantity and physical unit | Delivered Quantity | Unit price | Actual Total Price according the the contract | Actual Total Price in USD
1 | Project Management |  | Nino Kvernadze | Covid19/CS/INDV-01 | 16.06.2020 |  | Georgia | N/A | 16.06.2021 | consultancy service |  |  | 36000
2 | Enviromental Standards Consultant |  | Giorgi Kobaladze | Covid19/CS/INDV-06 | 16.06.2020 |  | Georgia | N/A | 110 working days | consultancy service |  |  | 19200
3 | Financial manager |  | Natalie Godziashvili | Covid19/CS/INDV-02 | 24.06.2020 |  | Georgia | N/A | 24.06.2021 | consultancy service |  |  | 30000
4 | Social Standarts Specialist/Consultamt |  | Nino patarashvili | Covid19/CS/INDV-05 | 25.06.2020 |  | Georgia | N/A | 150 working days | consultancy service |  |  | 19200
5 | Health specialist |  | Lia tavadze | Covid19/CS/INDV-04 | 16.06.2020 |  | Georgia | N/A | 16.06.2021 | consultancy service |  |  | 30000
6 | Procurement specialist |  | Nino Gvenetadze | Covid19/CS/INDV-03 | 16.06.2020 |  | Georgia | N/A | 16.06.2021 | consultancy service |  |  | 26400
7 | Interpreter |  | lela Dzidziguri | Covid19/CS/INDV-07 | 27.07.2020 |  | Georgia | N/A | 6 working month | consultancy service |  |  | 1000
8 | Goggles, protective | Direct /BFP | Commander Health Supply | Commander -001 | 10.07.2020 |  | China | CIP | within 30 days from date of issues of Preproduction Inspection Report | 54000 | Delivered | 3.33 | 179820
9 | Rapid COVID-19 Test Cassette | Direct | Bio Gene LTD - (ID 422724412) / Green Lab LTD- (ID 416345832) | COVID19/G/DC-01 | 17.05.2020 |  | CHINA | CIP | Delivered/ Until August 5, 2020 | 197000 | Delivered | 5.2 | 1024400
10 | COVID19/G/DC-02 / Procurement of Critical Care Ventilators and Related Services | Direct | MTECH LLC (ID 202443230 ) | COVID19/G/DC-02 | 21.05.2020 |  | CHINA/Mindray | DDP | 30th of August, 2020 | 30 | Delivered | 13447.92 | 403437.6
11 | Procurement of Mobile Emergency Ventilators and Related Services | Direct | MDS LTD (ID 400096999) | COVID19/G/DC-03 | 20.05.2020 |  | Hamilton Medical AG Switzerlan | DDP | Period-1: From 16.06.2020 to 03.07.2020; Period-2: From 30.06.2020 to 17.07.2020; Period-3: From 12.08.2020 - to 30.08.2020.” | 20 | Delivered |  | 313476
12 | Procurement of Standard COVID-19 Antigen Tests | Direct | SD BIOSENSOR | COVID19/G/DC-04 | 18.06.2020 |  | Republic of Korea | CIP | Delivered | 50000 | Delivered | 12.244 | 612200
13 | COVID19/G/DC-08 / Procurement of In Vitro Diagnostic Medical Device (cobas 6800) | Direct | Roche Diagnostics Turkey A.Ş. | COVID19/G/DC - 08 | 02.09.2020 |  | Switzerland / CH | CIP | 2021 March | 1 |  |  | 440000 | 536800
14 | COVID19/G/DC-09 / Procurement of Qiagen RNA Mini Kit (250) | Direct | Prima Medi LTD (ID 204963851) | COVID19/G/DC-09 | 01.07.2020 |  | QIAGEN/Germany | DDP | Delivered | 62500 | Delivered |  | 1050000 | 342566.3111
15 | Thermos Scientifics COVID-19 tests with consurambales | Direct | ABM LTD (ID 404917328 ) | COVID19/G/DC-10 | 01.07.2020 |  | USA | DDP | 1st delivery 21.07 2020 2nd delivery 21.08.2020 3rd delivery 21.09.2020 4th delivery 21.10.2020 | 250000 | Delivered |  | 5685100
16 | KIT COBAS 6800/8800 SARS-COV-2 192T (with consumables for 150 000 tests) | Direct | MIRKO LLC (ID 204996772) | COVID19/G/DC-12 | 21.10.2020 |  | USA | DDP | 3000 tests per week | 150000 |  |  | 3599508 | 4391399.76
17 | Standard COVID-19 AG Test | Direct | SD BIOSENSOR | COVID19/G/DC-13 | 03.08.2020 |  | Republic of Korea | CIP | Within 1 week after payment of 40% on shipment , but not exceeding four (4) weeks of order placement. | 100000 | Delivered | 9.1875 | 918750
18 | Xpert Xpress SARS-CoV-2 kit/10 tests (2000 pack) | Direct | UNICEF | COVID19/G/UN-01 | 03.07.2020 |  | USA | CIP | October | 20000 | Parshall delivery 10/30/2020 (5000 tests ) |  | 478240.4
19 | Nucleic Acid Diagnostic Kit 124 test | Direct | SANSURE BIOTECH INC | COVID19GDC-14 | 22.07.2020 |  | CHINA | CIP | within 30 business days after receiving the advance payment | 400000 | Delivered | 10.5 | 4200000
20 | MATRIX Viral RNA/DNA Purification Kit (500 Packs, extraction) | Direct | Prima Medi LTD (ID 204963851) | COVID19/G/DC-15 | 07.09.2020 |  | Germany | DDP | DDP Within one month after contract signature | 125000 | Delivered | 12.8 | 1600000 | 519480.5195
21 | GeneMATRIX Viral RNA/DNA Purification Kit (100 detection | Direct | Bio Medi LLC (204992393) | COVID19GDC-16 | 20.08.2020 |  | EURX, Poland | CIP | 100 kits can supply immediately . 400 kits in August. 500 kits in September. | 200000 |  | 2.89 | 578000 | 705160
22 | PCR tests for Procleix Panther System for Automated NAT (Grifols) device (10000 kit) | Direct | Lux Med LTD (ID 400130050) | COVID19/G/DC-17 | 28.10.2020 |  | USA | DDP | Within 60 days after contract signature | 240000 |  |  | 253500 | 309270
23 | Omni Gene oral from microbial DNA and RNA | Direct | DNA Genetic | COVID19/G/DC-18 | 29.09.2020 |  | Canada/DNA Genetic | CIP | One month after contract signature | 50000 | Delivered |  | 363000
24 | CT scanner (Second hand good) | Direct | LTD Ivermedi. (ID 211357841 ) | COVID19/G/DC-20 | 08.10.2020 |  | Simens | DDP | Within one month after contract signature | 1 | Delivered |  | 88000 | 107360
25 | AG/AB combined package rapid tests | Direct | SD BIOSENSOR | COVID19/G/DC-21 | 16.09.2020 |  | Biosensor/korea | CIP | Within two weeks after contract signature (AG200000/AB200000) | 400000 | Delivered |  | 2068500
26 | Furniture for 100 Primary Healthcare Facilities | Direct | LLC Geo + (ID 423099774 ) | COVID19/G/DC-22 | 16.09.2020 |  | LLC Geo + | DDP | 35 days |  | Delivered |  | 184470 | 58476.5105
27 | Equipment for 100 Primary Healthcare Facilities | Direct | Tbilisi medic LLC (ID 404865286) | COVID19/G/DC-23 | 28.09.2020 |  | Various | DDP | 90 days from contact signature | 36 types |  | Various | 328020
28 | Disposable Surgical Masks | Direct/BFP | Sinoventure International Business and Managemnet company | COVID19-G-DC-24 | 02.10.2020 |  | Sinoventure International Business and Managemnet company | CIP | within 60 days from date of issues of Preproduction Inspection Report | 3000000 |  | 0.203 | 618000
29 | Procurement of medical equipment and supplies for hospitals | Direct | UNOPS | COVID19-G-DC-25 | 15.10.2020 |  |  | DDP | 31 July 2022. |  |  |  | 6185998
30 | FACE SHIELD, clear plastic, disp. | Direct/BFP | ERTUNC OZCAN SAGLIK TESİSLERİ VE TIBBI CIHAZLAR INSAAT AS. | Ertunc Ozcan-001 | 02.10.2020 |  | Ertunc Ozcan/turckey | CIP | Within 60 days from the date of issue of a pre-production test report | 40000 |  | 1.18 | 48400
31 | 15 motor Motor Vehicles for Infectious Control Monitoring Center | RFQ | JV LLC KIA motors Georgia (ID 236096675) and LLC GI TI Motors (ID 206276340) | COVID19/G/RFQ-04 | 30.09.2020 |  | South Korea/South aftica Kia /Ford | DDP | within 100 days | 15 Unit |  |  | 379240
32 | Technical Assistance for post crises COVID-19 strategy for Health Sector - Assistant Consultant | Direct | Tinatin Manjavidze | COVID19/CS/CDS-02 | 02.07.2020 |  | Georgia | N/A | 25 working days | consultancy service | Delivered |  | 6250
33 | Technical Assistance for post-crises COVID-19 strategy for Health Sector - Lead Consultant | Direct | Natia Skhvitaridze | COVID19/CS/CDS-01 | 02.07.2020 |  | Georgia | N/A | 25 working days | consultancy service | Delivered |  | 3125
34 | Tetra equipment with related services | Direct | Motorola Solutions Germany | COVID19/G/DC-26 | 06.10.2020 |  | USA/Malaysia | CIP | 24 weeks - 44 weeks from contract signature |  |  |  | 1900000 | 2261000
35 | Dialysis equipment for Georgian hospitals | Direct | Hospimed Georgia” LLC (ID 206335704) | COVID19-G-DC-27 | 23.10.2020 |  | Germany Hungury | DDP | 50-51 weeks of the year from contract signature | 36 Unit |  |  | 522990 | 585748.8 | 523314 | 586111.68
36 | STANDARD Q COVID-19 Ag test | Direct | SD BIOSENSOR | COVID19/G/DC-28 | 29.10.2020 |  | Korea | CIP | two weeks from contract signature | 500000 | Delivered | 5.324 | 2662000
37 | Gloves, examination, non-sterile/Mask, respirator, KN95 | Direct /BFP | Commander Health Supply | Commander-007 | 05.11.2020 |  | Malaysia/china | CIP | 45 days from the date of issue of a pre-production test | 4300000gloves 230000 mask |  | US $ 0.12/US $ 1.13 mask | 802900
38 | DEVELOP COVID-19 SELF-ISOLATION IT PLATFORM | Direct RFP | LLC Business Process Management Group (ID 405250053 ) | COVID19-CS-RFP-02 | 10.11.2020 |  |  | N/A | Time one month from the contact signature. | consultancy service |  |  | 47200
39 | STOP COVID MOBILE APPLICATION | Direct RFP | Grabner & Gretzmacher MDL GmbH | COVID19-CS-RFP-01 | 28.10.2020 |  |  | N/A | 3 month | consultancy service |  |  | 75000 | 89250
40 | Oris-Accounting Software | Direct | ORIS LLC | COVID19/G/DC-29 | 18.11.2020 | N/A |  | N/A | one week from contract signature |  |  |  | 3957 | 1217.5385
41 | Laboratory equipment for Hospitals | Direct | MTECH LLC (ID 202443230 ) | COVID19/G/DC-30 | 07.12.2020 | yes/yes | various | DDP | Within 30 days after contract signature |  |  |  | 221169.2
42 | Oxygen concentrators | Direct | LTD KPI-Georgia (ID 400010796 ) | COVID19/G/DC-31 | 24.11.2020 | yes /yes | People’s republic of China | DDP | Estimate Delivery date 2 December, 2020. Maximum delivery date no later than 20 December, 2020 | 1000 |  |  | 710000
43 | STANDARD Q COVID-19 Ag test | Direct | SD BIOSENSOR | COVID19/G/DC-32 | 10.12.2020 |  | Korea | CIP | Within 30 days after contract signature | 500000 |  | 5.324 | 2662000 |  | 9947850 | 1747000
44 | CPAP Masks, BPAP and HFNC devices | Direct | LTD KPI-Georgia (ID 400010796 ) | COVID19/G/DC-33 | 14.12.2020 |  | China /Germany | DDP | Within 10 days after contract signature | CPAP - 18000 BPAP 500+300 HFNC -50 |  |  | 842,100 Euro and 681,600 USD | 1702803 |  |  | 11153289.1105
45 | Terminal services | Direct | LAZARE LLC | COVID19/G/DC-34 | 28.12.2020 | N/A |  |  | 31.12.2021 |  |  |  |  | 4587.2962 | 3.2699
46 | Ambulance C and B type | RFB | AKA LLC (204875082) | COVID19-G-RFB-01 | 28.12.2020 |  | Mercedes-Benz AG /Emergency mobile systems A.S | DDP | 180 day from contract signature | 38 |  |  | 2189340 | 2605314.6
47 | Supply and Installation of Network Infrastructure | RFQ | Green Systems LLC, (ID 404862190) | COVID19/G/RFQ-09 | 12.01.2021 |  | Cisco International Limited | DDP | 90 day from contract signature | 1 |  |  | 268776 | 81769.3946 | 3.287
48 | Supply and Installation of Server Infrastructure | RFQ | UGT LLC, (ID 204892964) | COVID19-G-RFQ-11 | 12.01.2021 |  | Georgia | DDP | 90 day from contract signature | 1 |  |  | 566884 | 172462.4277 | 3.287
49 | TaqPath™ COVID-19 CE-IVD RT-PCR tests and KingFisher FLEX extraction kits | Direct |  | COVID19/G/DC-35
[9 empty] | 1350000 |  | 397000
437500
1060000